## Meeting at CERN
Components | Cern drawings LHCMB- | Meas. unit | Quantity necessary per CM | Total quantity arrivred at 1/7/05 | Total quantity scrapped | Quantity necessary to complete the work | Delivered by CERN Pre-series included | Comments | Comments
Superc. Cable for inner |  | nr. | 4 | 904 | 5 | 645 | 258 | manque 2 aimants | devrait manquer 640 car déjà remplacé les 5 rebus, soit 632
Superc. Cable for outer |  | nr. | 4 | 904 | 5 | 645 | 258 | manque 2 aimants | devrait manquer 640 car déjà remplacé les 5 rebus, soit 632
Apical for cable insulation A1 |  | Kg | 15.9 | 3750 | 66 | 2453.4 | 4322 | CERN pense 15 kg et pas 15.9
Apical for cable insulation P1 |  | Kg | 28 | 6600 | 113 | 4321 | 7560 | 28 kg ok
Copper wedges |  | set | 1 | 270 | 13 | 129 | 302 | manque 2 aimants
Collars |  | set | 1 | 227 | 2 | 161 | 264 | manque 7 aimants
Apical for ground insulation |  | Kg | 17 | 3853 | 221 | 2930 | 4297 | 17 kg non car CERN 15 kg
Apical for midplane shim |  | Kg | 0.3376 | 115 | 2.1 | 17.4136 | 266 aimants | en plus
Cold bore tube |  | nr. | 2 | 536 | 33 | 269 | 584 | 292 aimants
Yoke |  | set | 1 | 199 | 0 | 187 | 226 | 226 pour 229 ASG et 236 pour les extremités
Bus bars |  | set | 1 | 220 | 19 | 185 | 245 | dont 125 A et 120 B
Upper half shells |  | nr. | 1 | 204 | 9 | 191 | 237.5 paires
Lower half shells |  | nr. | 1 | 204 | 9 | 191 | 237.5
Temp. sensor |  | nr. | 1 | 270 | 9 | 125 | 342
Sextupole corrector |  | nr. | 2 | 358 | 14 | 428 | 550 dont 108 aujourd'hui
Decapole/octupole correct. |  | nr. | 2 | 175 | 8 | 605 | 223 dont 24 aujourd'hui
Cryoheater |  | nr. | 1 | 220 | 3 | 169 | A voir
End Cover CS | S008 | nr. | 1 | 223 | 9 | 172 | 239 | A voir ce qui est revenue comme rebus
End Cover NCS | S007 | nr. | 1 | 228 | 10 | 168 | 244
Bellow for M1-M2-M3 | S0084 | nr. | 3 | 650 | 21 | 529 | 312 jeux masses froides
Heat exchanger tube |  | nr. | 1 | 224 | 7 | 169 | 250
N-line tube |  | nr. | 1 | 300 | 9 | 95 | 336
Flexible pipe for N-line | MA0040 | nr. | 1 | 200 | 9 | 195 | Voir bellow
Extern. bellow for X -line | S0090 | nr. | 1 | 273 | 9 | 122 | Voir bellow
Inter. bellow for X-line | S0087 | nr. | 1 | 226 | 9 | 169 | Voir bellow
Diode R type |  | nr. | 1 | 175 | 18 | 229 | 205
Diode L type |  | nr. | 1 | 173 | 0 | 213 | 173
S.s. protections on lyra side |  | nr. | 3 | 650 | 0 | 508 | Voir bellow
Wiring set

## Meeting at ASG
Component | Remarks
Superc. Cable for inner | OK
Superc. Cable for outer | OK
Apical for cable insulation A1 | OK - 16Kg shipped per magnet; answer H. Kummer
Apical for cable insulation P1 | OK
Copper wedges | Discrepancies- Annick shall provide shipping details - Jurgen recorded 304 Outer and 291 Inner - 1 batch (10 magnets) scrapped shall be deducted - 4 CM scrapped - ASG says 300 Inner and 302 Outer
Collars | 264 shipped -4 sent back to Malvestiti -3 batches scrapped
Apical for ground insulation | OK
Apical for midplane shim | OK
Cold bore tube | 1 missing - it was destroyed by CERN personnel during inner diameter check
Yoke | OK
Bus bars | OK - 5 old type scrapped
Upper half shells | 1/2 half shell missing?????
Lower half shells | 1/2 half shell missing?????
Temp. sensor | 42 missing - certificates shipped but TT sensors never arrived - Annick to check
Sextupole corrector | 26 Missing - to check the shipping details
Decapole/octupole correct. | ASG says 232 pieces, CERN says 223 pieces….maybe a mistake? 8 too much at ASG
Cryoheater
End Cover CS | OK
End Cover NCS | OK
Bellow for M1-M2-M3 | OK
Heat exchanger tube | 7 Scrapped: can we repair them? - 4 were installed at CERN
N-line tube | 9 Scrapped - CERN personnel told them to repair after the 9 were already scrapped
Flexible pipe for N-line | OK
Extern. bellow for X -line | OK
Inter. bellow for X-line | Some were shipped back to CERN and 54 were not sent back - Missing 54!
Diode R type | OK - Still needed 3 if ASG has to produce 219
Diode L type | OK - Still needed 17 if ASG has to produce 197
S.s. protections on lyra side | OK
Wiring set | OK but now ASG shall produce 196A type and 220B type - CERN shipped 208A type and 208B type