## Weekly report 34/05

22.08.05

CC 2243, 2244, 2246 assembly

CC 2242 collaring

CM 2234 preparing to weld

CM 2217 final electrical measurements

23.08.05

CC 2243, 2244,2246 assembly

CC 2236 electrical measurements

CM 2234 welding start

CM 2237 yoke assembly

CM 2229 geometrical measurements

CM 2215 shipment

24.08.05

During leak testing of CM 2214 aleak was detected during pressurising

CC 2243, 2244 , 2246 assembly

CM 2237 yoke assembly

CM 2234 welding finished

CM 2233 magnetic measurements

25.08.05

The leak on CM 2214 was detected on the x-line bellow

CC 2244, 2245, 2246 assembly

CM 2237 preparing to weld

CM 2227 electrical measurements without end covers

CM 2218 shipment

26.08.05

Cutting of defective x-line bellow and welding a new one

CC 2234, 2245, 2246 assembly

CC 2243 collaring

CM 2235 yoke assembly

## Production until 26.08.05

# Winding inner layers for magnet 2253 and 2254

# Winding outer layers for magnet 2255 and 2256

# Poles assembled until magnet  2250

Collared coils ready: 243, 3 on assembly,  2049, 2069 de-collared

Cold masses welded: 230, 2 on assembly, 2 cut  (2049, 2069)

Cold masses delivered: 207, 4 back from CERN (2049, 2069, 2098, 2124), 1 cold mass ready for shipment