## Weekly report 48/05

28.11.05

Electrical measurements on poles for CM 2289, 2290, 2291

CC 2287, 2288, 2289 assembly

CC 2283 magnetic measurements

CC 2283, 2284 electrical measurements

CM 2282 yoke assembly

CM 2268 preparing to weld

CM 2280 welding

CM 2274 magnetic measurements

CM 2266 leak test

CM 2266 final electrical measurements

CM 2252 shipment

29.11.05

Travel to Cicorel to follow up quench heater production

CC 2288, 2289, 2290 assembly

CC 2287 collaring

CC 2285 magnetic measurements

CC 2285 electrical measurements

CM 2282 yoke assembly

CM 2268 welding

CM 2221 electrical measurements without end covers

CM 2258 geometrical measurements

CM 2237 leak test

CM 2237 final electrical measurements

30.11.05

Visit to Cicorel to follow up quench heater production, travel back to Genova

CC 2288, 2289, 2290 assembly

CC 2286 magnetic measurements

CC 2286 electrical measurements

CM 2267 yoke assembly

CM 2282 preparing to weld

CM 2280 magnetic measurements

CM 2263 electrical measurements without end covers

CM 2221 geometrical measurements

CM 2266 shipment

01.12.05

Electrical measurements on poles for CM 2292, 2293

CC 2290, 2291 assembly

CC 2278 preparing to de-collar

CC 2288, 2289 collaring

CC 2287 magnetic measurements

CC 2287 electrical measurements

CM 2270 yoke assembly

CM 2267 preparing to weld

CM 2282 welding

CM 2254 electrical measurements without end covers

CM 2265 leak test

CM 2265 final electrical measurements

CM 2240 shipment

02.12.05

Visit to Malvestittti to follow up collar production

# General strike

CM 2270 yoke assembly

CM 2267 preparing to weld

## Production until 02.12.05

# Winding inner layers for magnet 2300 and 2301

# Winding outer layers for magnet 2298 and 2299

# Poles assembled until magnet  2296

Collared coils ready: 289, 2 on assembly, 2278 to de-collar, 2069 de-collared

Cold masses welded: 270, 2 on assembly, 2 cut  (2049, 2069)

Cold masses delivered: 248, 4 back from CERN (2049, 2069, 2098, 2124), 2 cold masses ready for leak test, 3 cold masses ready for shipment