## production
cold mass | type | diode | cern ID | collaring | extra shim | mag meas. collared | mod. ferr.mag. length | q.h. el. test | long. welding | geo. meas. | reshaping | x-ray | mag.meas. cm | end covers | geo. meas. | leak test | sent | remarks
2001_B |  |  | HCMBBRA001-02000001 | 2001-02-06 |  | 2000-12-31 |  | ok | CERN |  |  | ok | 2001-07-06 | ok | nd | nd | nd | not accepted
2002_B | AR | MDB0207 | HCMBBRA001-02000002 | 2003-04-11 |  | 2003-04-17 |  | ok | 22/03 |  |  | ok | 2003-06-17 | ok | 2003-06-30 | 2003-07-04 | 2003-07-15 | first assembled at CERN, totally diassembled,recollared
2003_B | AR |  | HCMBBRA001-02000003 | 2001-06-26 |  | 2001-07-17 |  | ok | CERN |  |  | ok | 2001-08-01 | ok | nd | nd | nd
2004_B | AR | MDB0350 | HCMBBRA001-02000004 | 2001-12-12 |  | 2001-12-20 |  | ok | 26/02 | 2002-07-03 |  | ok | 2002-11-05 | ok | 2002-11-27 | 2002-11-26 | 2002-11-28
2005_A | AR | MDB0196 | HCMBARA001-02000005 | 2003-05-19 |  | 2003-06-03 |  | ok | 30/03 | 2003-09-08 |  | ok | 2003-08-19 | ok | 2003-10-10 | 2003-10-20 | 2003-10-27 | first assembled at CERN, totally diassembled,recollared
2006_B | AR | MDB0323 | HCMBBRA001-02000006 | 2002-03-19 |  | 2002-04-03 |  | ok | 37/02 | 2002-09-24 |  | ok | 2002-11-13 | ok | 2003-01-16 | 2003-01-27 | 2003-01-30
2007_B | AR | MDB0131 | HCMBBRA001-02000007 | 2002-01-15 |  | 2002-03-07 |  | ok | 51/02 |  |  | ok | 2003-02-26 | ok | 2003-04-10 | 2003-04-17 | 2003-04-22
2008_B | AR | MDB0368 | HCMBBRA001-02000008 | 2002-02-20 |  | 2002-03-06 |  | ok | 50/02 | 2002-12-28 |  | ok | 2002-12-19 | ok | 2003-03-20 | 2003-03-20 | 2003-03-25
2009_B | AR | MDB0327 | HCMBBRA001-02000009 | 2002-04-12 |  | 2002-05-23 |  | ok | 48/02 | 2002-12-19 |  | ok | 2003-02-27 | ok | 2003-05-06 | 2003-05-17 | 2003-05-20
2010_B | AR | MDB0363 | HCMBBRA001-02000010 | 2002-05-09 |  | 2002-05-22 |  | ok | 46/02 | 2002-11-19 |  | ok | 2002-12-05 | ok | 2003-04-23 | 2003-04-28 | 2003-04-29
2011_A | AR | / / / | HCMBARA001-02000011 | 2002-10-24 |  | 2002-10-29 |  | ok | 17.09.03 |  |  | ok | 2003-11-25 | ok | 2003-12-11 | 2003-12-16 | 2003-12-19 | recollared
2012_B | AR | MDB0316 | HCMBBRA001-02000012 | 2002-05-23 |  | 2002-06-27 | + 2x50mm | ok | 41/02 | 2002-10-22 |  | ok | 2002-10-30 | ok | 2003-03-27 | 01.04.03 | 2003-04-03
2013_A | AR | MDB0372 | HCMBARA001-02000013 | 2002-07-31 |  | 2002-08-27 | + 2x50mm | ok | 28/03 | 2003-07-31 |  | ok | 2003-07-29 | ok | 2003-08-25 | 2003-08-26 | 2003-09-02 | recollared, back from Cern
2014_B | AR | MDB0344 | HCMBBRA001-02000014 | 2002-06-24 |  | 2002-07-24 | + 2x50mm | ok | 09/03 |  |  | ok | 2003-03-27 | ok | 2003-05-27 | 2003-06-03 | 2003-06-10
2015_A | AR | MDB0267 | HCMBARA001-02000015 | 2002-11-29 |  | 2002-12-03 |  | ok | 05.09.03 | 2003-09-09 |  | ok | 2003-09-17 | ok | 2003-10-07 | 2003-10-09 | 2003-10-06
2016_A | AR | MDB0287 | HCMBARA001-02000016 | 2002-08-22 |  | 2002-09-19 | + 2x50mm | ok | 28/03 | 2003-07-17 |  | ok | 2003-07-30 | ok | 2003-08-06 | 2003-08-19 | 2003-08-29
2017_A | AR | MDB0218 | HCMBARA001-02000017 | 2002-10-02 |  | 2002-10-16 | + 2x50mm | ok | 24/03 | 2003-06-13 |  | ok | 2003-07-11 | ok | 2003-07-23 | 2003-07-30 | 2003-08-07
2018_A | AR | MDB0361 | HCMBARA001-02000018 | 2002-10-03 |  | 2002-10-17 | + 2x50mm | ok | 25/03 | 2003-06-26 |  | ok | 2003-07-03 | ok | 2003-07-22 | 2003-07-25 | 2003-07-31
2019_A | AR | MDB0204 | HCMBARA001-02000019 | 2002-11-07 |  | 2002-11-14 |  | ok | 38/03 | 2003-10-09 |  | ok | 2003-10-04 | ok | 2003-10-16 | 2003-10-22 | 2003-10-30
2020_A | AR | MDB0282 | HCMBARA001-02000020 | 2002-11-19 |  | 2002-12-04 |  | ok | 23/03 | 2003-06-13 |  | ok | 2003-06-18 | ok | 2003-07-11 | 2003-07-22 | 2003-07-28 | half shells cut and disassembled
2021_B | AR | MDB0351 | HCMBBRA001-02000021 | 2002-12-10 |  | 2002-12-19 |  | ok | 11/03 | 2003-04-04 |  | ok | 2003-03-28 | ok | 2003-05-19 | 2003-05-23 | 2003-06-03
2022_B | AR | MDB0127 | HCMBBRA001-02000022 | 2002-12-19 |  | 2002-12-27 |  | ok | 21/03 |  |  | ok | 2003-06-04 | ok | 2003-06-10 | 2003-06-17 | 2003-06-23
2523_A | AR | MDB0713 | HCMBARA001-02000023 | 1/15/03/decollared/4/28/04 |  | 2/19/03/4/28/04 |  | ok | 13/03/week 20/04(120504) | 24.04.03/24.05.04 |  | ok | 5/27/03/5/14/04 | ok | 7/1/03/5/28/04 | 7/8/03/6/4/04 | 7/17/2003/6/10/04 | recollared, dismantled, decollared,recollared
2024_A | AR | MDB0200 | HCMBARA001-02000024 | 2003-06-23 |  | 2003-07-07 |  | ok | 29.07.03 | 2003-08-28 |  | ok | 2003-08-21 | ok | 2003-09-12 | 2003-09-17 | 2003-09-22 | recollared, will be back from Cern
2025_B | AR | MDB0194 | HCMBBRA001-02000025 | 2003-02-11 |  | 2003-02-18 |  | ok | 20/03 | 2003-05-15 |  | ok | 2003-05-26 | ok | 2003-06-18 | 2003-06-23 | 2003-07-01 | back from CERN
2026_A | AR | MDB0221 | HCMBARA001-02000026 | 2003-02-25 |  | 2003-03-20 | + 2x50mm | ok | 28.08.03 | 2003-09-09 |  | ok | 2003-09-11 | ok | 2003-09-24 | 2003-10-07 | 2003-10-13
2027_A | AR | MDB0417 | HCMBARA001-02000027 | 2003-03-06 |  | 2003-03-21 |  | ok | 27/03 | 2003-07-08 |  | ok | 2003-07-10 | ok | 2003-10-24 | 2003-11-04 | 2003-11-06
2028_A | AR | MDB0281 | HCMBARA001-02000028 | 2003-03-14 |  | 2003-04-02 |  | ok | 29/03 | 2003-08-06 |  | ok | 2003-07-30 | ok | 2003-09-04 | 2003-09-13 | 2003-09-17
2029_A | AR | MDB0230 | HCMBARA001-02000029 | 2003-03-25 |  | 2003-04-03 |  | ok | 34/03 | 2003-09-09 |  | ok | 2003-09-10 | ok | 2003-09-22 | 2003-09-30 | 2003-10-22
2030_A | AR | MDB0199 | HCMBARA001-02000030 | 2003-03-31 |  | 2003-04-16 |  | ok | 06.09.03 | 2003-09-16 |  | ok | 2003-09-19 | ok | 2003-10-10 | 2003-10-13 | 2003-10-20
2031_A | AR | MDB0394 | HCMBARA001-02000031 | 2003-04-16 |  | 2003-04-29 |  | ok | week 18/04(290404) | 2004-05-08 |  | ok | 2004-05-03 | ok | 2004-05-21 | 2004-05-20 | 2004-05-27
2032_B | AL | / / / | HCMBBLA001-02000032 | 5/12/03/decollared 11/18/03/1/30/04/ | Supplementary Mid-plane shim | 5/22/03/9/24/03/2/3/04 |  | ok | week 6/'04(060204)/cut/ | 2004-02-17 |  | ok | 2004-02-10 | ok | 2004-02-25 | 2004-03-02 | 2004-03-12 | recollared, back from CERN
2033_A | AR | MDB0508 | HCMBARA001-02000033 | 2003-06-04 | NO Mid-plane shim | 2003-07-15 |  | ok | week 39/'03 | 2003-10-17 |  | ok | 2003-10-06 | ok | 2003-10-30 | 2003-11-05 | 2003-11-13
2034_A | AR | MDB0376 | HCMBARA001-02000034 | 2003-05-30 | NO Mid-plane shim | 2003-06-20 |  | ok | week 41/'03 | 2003-10-24 |  | ok | 2003-10-20 | ok | 2003-10-31 | 2003-11-13 | 2003-11-17
2035_B | AL | MDA0880 | HCMBBLA001-02000035 | 6/28/2003/decollared/6/7/04 | Supplementary Mid-plane shim | 7/14/03 / 9/24/03/6/8/04 |  | ok | week 25/04(190604) | 2004-06-30 |  | ok | 2004-06-22 | ok | 2004-07-02 | 2004-07-09 | 2004-07-15 | hold after magnetic measurement, decollared 27.04.04
2036_A | AR | MDB0505 | HCMBARA001-02000036 | 2003-06-11 | NO Mid-plane shim | 2003-06-19 |  | ok | week 40/'03 | 2003-11-13 |  | ok | 2003-10-31 | ok | 2003-10-31 | 2003-11-20 | 2003-11-25
2037_A | AR | MDB0393 | HCMBARA001-02000037 | 2003-06-16 | NO Mid-plane shim | 2003-07-02 |  | ok | week 17/04(210404) | 2004-04-28 |  | ok | 2004-04-23 | ok | 2004-05-06 | 2004-05-11 | 2004-05-17
2038_A | AR | / / / | HCMBARA001-02000038 | 2003-07-15 | NO Mid-plane shim | 2003-07-21 |  | ok | week 49/'03 | 2003-12-17 |  | ok | 2003-12-13 | ok | 2004-01-15 | 2004-01-16 | 2004-01-22 | no diode installed
2039_A | AR | MDB0487 | HCMBARA001-02000039 | 2003-07-18 | NO Mid-plane shim | 2003-07-28 |  | ok | week 43/'03 | 2003-11-17 |  | ok | 2003-11-07 | ok | 2003-11-17 | 2003-11-24 | 2003-11-27
2040_B | AL | / / / | HCMBBLA001- 02000040 | 2003-07-30 | Supplementary Mid-plane shim | 2003-08-02 |  | ok | week 45/'03 | 2003-12-01 |  | ok | 2003-11-15 | ok | 2003-12-01 | 2003-12-03 | 2003-12-09 | no diode installed
2041_B | AR | / / / | HCMBBRA001-02000041 | 2003-07-04 | Supplementary Mid-plane shim | 2003-07-23 |  | ok | week 44/'03 | 2003-11-25 |  | ok | 2003-11-17 | ok | 2003-11-25 | 2003-12-02 | 2003-12-04 | no diode installed
2042_A | AR | MDB0479 | HCMBARA001- 02000042 | 2003-07-14 | NO Mid-plane shim | 2003-07-18 |  | ok | week 17/04(220404) | 2004-05-03 |  | ok | 2004-04-26 | ok | 2004-05-18 | 2004-05-13 | 2004-05-19 | electrical connections disassammbled
2043_B | AL | / / / | HCMBBLA001-02000043 | 2003-07-29 | Supplementary Mid-plane shim | 2003-08-07 |  | ok | week 46/'03(101103) | 2003-11-24 |  | ok | 2003-11-29 | ok | 2003-12-02 | 2004-02-05 | 2004-02-16 | no diode installed, x-line bellow changed
2044_B | AR | / / / | HCMBBRA001-02000044 | 2003-07-30 | NO Mid-plane shim | 2003-08-26 |  | ok | week 46/'03(131103) | 2003-11-28 |  | ok | 2003-12-03 | ok | 2003-12-11 | 2003-12-11 | 2003-12-15 | no diode installed
2045_B | AL | MDA0440 | HCMBBLA001-02000045 | 2003-10-07 | Supplementary Mid-plane shim | 2003-10-15 |  | ok | week 11/04(080304) | 2004-03-22 |  | ok | 2004-03-17 | ok | 2004-03-24 | 2004-03-27 | 2004-04-02
2046_A | AL | / / / | HCMBALA001- 02000046 | 2003-11-28 | Supplementary Mid-plane shim | 2003-12-03 |  | ok | week 51/'03 | 2004-01-09 |  | ok | 2004-01-08 | ok | 2004-01-27 | 2004-02-02 | 2004-02-11 | recollared, x-line bellow changed, no diode installed
2047_A | AL | / / / | HCMBALA001-02000047 | 2003-11-11 | Supplementary Mid-plane shim | 11/14/03/1/7/04 |  | ok | week 4/'04(200104) | 2004-01-28 |  | ok | 2004-01-23 | ok | 2004-02-05 | 2004-02-11 | 2004-02-26 | no diode installed, recollared
2048_B | AR | / / / | HCMBBRA001- 02000048 | 2003-08-08 | NO Mid-plane shim | 2003-08-29 |  | ok | week 47/'03(201103) | 2003-12-10 |  | ok | 2003-11-29 | ok | 2003-12-23 | 2004-02-20 | 2004-03-08 | no diode installed
2049_B | AL | MDA0506 | HCMBBLA001-02000049 | 2003-09-26 | Supplementary Mid-plane shim | 2003-10-08 |  | ok | week 13/04(230304) | 2004-04-07 |  | ok | 2004-03-25 | ok | 2004-04-07 | 2004-04-09 | 2004-04-19 | back from CERN
2050_B | AR | / / / | HCMBBRA001-02000050 | 2003-08-27 | NO Mid-plane shim | 2003-09-18 |  | ok | week 44/'03 | 2003-11-13 |  | ok | 2003-11-10 | ok | 2003-11-20 | 2003-11-28 | 2003-12-02 | no diode installed
2051_A | AL | / / / | HCMBALA001-02000051 | 11/18/2003/decollared/1/23/04 | Supplementary Mid-plane shim | 12/1/03/1/27/04 |  | ok | week 6/'04(020204) | 2004-02-07 |  | ok | 2004-02-04 | ok | 2004-02-17 | 2004-02-21 | 2004-03-10 | recollared
2052_B | AR | / / / | HCMBBRA001-02000052 | 2003-08-20 | NO Mid-plane shim | 2003-09-02 |  | ok | week 47/'03(181103) | 2003-12-09 |  | ok | 2003-12-06 | ok | 2003-12-23 | 2003-12-22 | 2004-02-23 | no diode installed
2053_B | AL | MDA0403 | HCMBBLA001-02000053 | 2003-09-05 | Supplementary Mid-plane shim | 9/22/03 / 9/26/03/10/7/03 |  | ok | week 13/04(260304) | 2004-04-02 |  | ok | 2004-03-30 | ok | 2004-04-15 | 2004-04-14 | 2004-04-21
2054_A | AL | MDA0121 | HCMBALA001-02000054 | 2003-09-10 | Supplementary Mid-plane shim | 2003-09-16 |  | ok | week 43/'03 | 2003-10-28 |  | ok | 2003-10-31 | ok | 2003-11-13 | 2003-11-17 | 2003-11-20
2055_B | AL | MDA0592 | HCMBBLA001-02000055 | 2003-09-12 | Supplementary Mid-plane shim | 2003-10-07 |  | ok | week 8/'04(160204) | 2004-02-23 |  | ok | 2004-02-18 | ok | 2004-03-02 | 2004-03-06 | 2004-03-16
2056_A | AR | MDB0325 | HCMBARA001-02000056 | 2003-10-16 | NO Mid-plane shim | 2003-10-22 |  | ok | week 16/'04(160404) | 2004-04-26 |  | ok | 2004-04-20 | ok | 2004-05-06 | 2004-05-07 | 2004-05-12
2057_A | AL | MDA0859 | HCMBALA001-02000057 | 2003-09-23 | Supplementary Mid-plane shim | 2003-10-08 |  | ok | week 20/04(140504) | 2004-05-26 |  | ok | 2004-05-18 | ok | 2004-05-31 | 2004-06-08 | 2004-06-14
2058_B | AL | MDA0562 | HCMBBLA001-02000058 | 2003-09-29 | Supplementary Mid-plane shim | 2003-10-13 |  | ok | week 10/'04(010304) | 2004-03-10 |  | ok | 2004-03-04 | ok | 2004-03-15 | 2004-03-19 | 2004-03-29
2059_A | AL | MDA0921 | HCMBALA001-02000059 | 2003-11-03 | Supplementary Mid-plane shim | 2003-11-14 |  | ok | week 19/04(050504) | 2004-05-14 |  | ok | 2004-05-10 | ok | 2004-05-20 | 2004-05-26 | 2004-06-03
2060_A | AL | / / / | HCMBALA001-02000060 | 2003-12-03 | Supplementary Mid-plane shim | 2003-12-09 |  | ok | week 52/'03 | 2004-01-12 |  | ok | 2004-01-12 | ok | 2004-01-23 | 2004-01-28 | 2004-02-05 | no diode installed
2061_B | AL | MDA0460 | HCMBBLA001-02000061 | 2003-10-09 | Supplementary Mid-plane shim | 2003-10-17 |  | ok | week 14/04(310304) | 2004-04-06 |  | ok | 2004-04-01 | ok | 2004-04-15 | 2004-04-20 | 2004-04-26
2062_B | AL | MDA0405 | HCMBBLA001-02000062 | 2003-10-30 | Supplementary Mid-plane shim | 2003-11-13 |  | ok | week 14/04(020404 | 2004-04-08 |  | ok | 2004-04-05 | ok | 2004-04-26 | 2004-04-23 | 2004-04-28
2063_B | AL | MDA0565 | HCMBBLA001-02000063 | 11/24/2003/decollared/2/5/04 | Supplementary Mid-plane shim | 1/19/04/2/10/04 |  | ok | week 8/'04(180204) | 2004-02-26 |  | ok | 2004-02-23 | ok | 2004-03-03 | 2004-03-10 | 2004-03-18 | recollared
2064_A | AL | / / / | HCMBALA001-02000064 | 2003-12-10 | Supplementary Mid-plane shim | 2003-12-15 |  | ok | week 2/'04(080104) | 2004-01-16 |  | ok | 2004-01-15 | ok | 2004-01-28 | 2004-01-30 | 2004-02-09 | no diode installed
2065_B | AR | MDB0706 | HCMBBRA001-02000065 | 3/11/2004/decollared4/29/04/5/6/04 | NO Mid-plane shim | 3/15/04/3/17/04/5/11/04 |  | ok | week 21/04(210504) | 2004-06-03 |  | ok | 2004-05-24 | ok | 2004-06-09 | 2004-06-16 | 2004-06-18 | decollared 28.04.04, recollared 07.05.04, magnetic measurement short mole after welding
2066_A | AL | / / / | HCMBALA001-02000066 | 2003-12-15 | Supplementary Mid-plane shim | 2003-12-23 |  | ok | week 3/'04(150104) | 2004-01-23 |  | ok | 2004-01-20 | ok | 2004-02-02 | 2004-02-06 | 2004-02-18 | no diode installed, x-line bellow changed
2067_B | AL | MDA0599 | HCMBBLA001-02000067 | 2004-02-25 | Supplementary Mid-plane shim | 2004-03-02 |  | ok | week 12/04(160304) | 2004-03-23 |  | ok | 2004-03-17 | ok | 2004-04-01 | 2004-04-05 | 2004-04-13
2068_B | AL | MDA0372 | HCMBBLA001-02000068 | 2004-03-29 | Supplementary Mid-plane shim | 2004-04-02 |  | ok | week 16/'04(150404) | 2004-04-22 |  | ok | 2004-04-19 | ok | 2004-04-30 | 2004-04-05 | 2004-05-10
2069_A | AL | / / / | HCMBALA001-02000069 | 2004-01-12 | Supplementary Mid-plane shim | 2004-01-16 |  | ok | week 5/'04(270104) | 2004-02-05 |  | ok | 2004-01-30 | ok | 2004-02-12 | 2004-02-17 | 2004-03-03 | will be back from Cern accepted by CERN on 7/7/04!!!!
2070_B | AL | MDA0559 | HCMBBLA001-02000070 | 2004-02-14 | Supplementary Mid-plane shim | 2004-02-23 |  | ok | week 10/04(060304) | 2004-03-17 |  | ok | 2004-03-05 | ok | 2004-03-17 | 2004-03-23 | 2004-03-31
2071_B | AL | MDA0521 | HCMBBLA001-02000071 | 2004-02-14 | Supplementary Mid-plane shim | 2004-02-19 |  | ok | week 9/'04(270204) | 2004-03-10 |  | ok | 2004-03-01 | ok | 2004-03-10 | 2004-03-17 | 2004-03-24
2072_A | AL | / / / | HCMBALA001-02000072 | 2003-12-29 | Supplementary Mid-plane shim | 2004-01-09 |  | ok | week 4/'04(230104) | 2004-01-31 |  | ok | 2004-01-26 | ok | 2004-02-11 | 2004-02-12 | 2004-03-01 | no diode installed
2073_B | AL | MDA0871 | HCMBBLA001-02000073 | 1/26/2004decollared/5/7/04/decollared/5/15/04/ 5/27/04 | Supplementary Mid-plane shim | 1/29/04/5/27/04 |  | ok | week 6/04/cut/week24/04 | 2004-06-17 |  | ok | 2/9/04/6/10/04 | ok | 2004-06-22 | 2004-06-29 |  | problem with quench heater, short circuit qh to pole, half shells cut, decollared, recollared, decollared, recollared
2074_B | AL | MDA0628 | HCMBBLA001-02000074 | 2004-02-23 | NO Mid-plane shim | 2004-02-27 |  | ok | week 11/04(110304) | 2004-03-22 |  | ok | 2004-03-16 | ok | 2004-04-29 | 2004-04-01 | 2004-04-07
2075_B | AL | MDA0939 | HCMBBLA001-02000075 | 2004-03-26 | Supplementary Mid-plane shim | 2004-03-31 |  | ok | week 25/04(180604) | 2004-06-28 |  |  | 2004-06-19 | ok | 2004-07-06 | 2004-07-15 | 2004-07-28 | hold after magnetic measurement, assembly under responsibility of Ansaldo
2076_B | AL | MDA0500 | HCMBBLA001-02000076 | 2004-03-19 | Supplementary Mid-plane shim | 2004-03-24 |  | ok | week 15/'04(090404) | 2004-04-13 |  | ok | 2004-04-13 | ok | 2004-04-26 | 2004-04-30 | 2004-05-06
2077_B | AL | MDA0923 | HCMBBLA001-02000077 | 2004-03-04 | Supplementary Mid-plane shim | 3/5/04/3/18/04 |  | ok | week 21/04(190504) | 2004-05-24 |  | ok | 2004-05-21 | ok | 2004-06-04 | 2004-06-09 | 2004-06-16 | (to decollar?), assembling for welding under the responsibility of Ansaldo
2078_B | AL | MDA0382 | HCMBBLA001-02000078 | 2004-03-08 | Supplementary Mid-plane shim | 2004-03-10 |  | ok | week 12/04(190304) | 2004-04-07 |  | ok | 2004-03-23 | ok | 2004-04-07 | 2004-04-07 | 2004-04-15
2079_A | AL | MDA0922 | HCMBALA001-02000079 | 2004-04-09 | Supplementary Mid-plane shim | 2004-04-14 |  | ok | week 17/04(240404) | 2004-05-05 |  | ok | 2004-04-29 | ok | 2004-05-18 | 2004-05-18 | 2004-05-25
2080_A | AL | MDA0887 | HCMBALA001-02000080 | 2004-04-07 | Supplementary Mid-plane shim | 2004-04-09 |  | ok | week 19/04(070504) | 2004-05-18 |  | ok | 2004-05-13 | ok | 2004-05-24 | 2004-05-31 | 2004-06-07
2081_B | AL | MDA0513 | HCMBBLA001-02000081 | 2004-02-10 | Supplementary Mid-plane shim | 2004-02-13 |  | ok | week 9/'04(240204) | 2004-03-02 |  | ok | 2004-02-26 | ok | 2004-03-08 | 2004-03-15 | 2004-03-22
2082_B | AL | MDA0448 | HCMBBLA001-02000082 | 2004-03-16 | Supplementary Mid-plane shim | 2004-03-23 |  | ok | week 15/'04(060404) | 2004-04-19 |  | ok | 2004-04-08 | ok | 2004-04-26 | 2004-04-27 | 2004-05-03
2083_A | AL | MDA0945 | HCMBALA001-02000083 | 2004-04-13 | Supplementary Mid-plane shim | 2004-04-16 |  | ok | week 18/04(300404) | 2004-05-11 |  | ok | 2004-05-05 | ok | 2004-05-21 | 2004-05-25 | 2004-06-01
2084_B | AL |  | HCMBBLA001-02000084 | 4/23/2004/decollared/6/15/04 | Supplementary Mid-plane shim | 4/30/04/5/27/04/6/16/04 |  | ok | week 27/04(010704) | 2004-07-13 |  | ok | 2004-07-02 | ok | 2004-07-17 | 2004-08-05 | 2004-08-11 | hold after magnetic measurement, assembly under responsibility of Ansaldo
2085_B | AL | MDA0869 | HCMBBLA001-02000085 | 2004-05-14 | Supplementary Mid-plane shim | 5/17/04/5/25/04 |  | ok | week 23/04 | 2004-06-11 |  | ok | 2004-06-07 | ok | 2004-06-16 | 6/22/2004/7/5/04 | 2004-07-12 | hold after magnetic measurement, assembly under responsibility of Ansaldo
2086_B | AL |  | HCMBBLA001-02000086 | 2004-04-22 | Supplementary Mid-plane shim | 2004-05-13 |  | ok | week 29/04(170704) | 2004-08-02 |  | ok | 2004-07-20 | ok | 2004-08-10 | 2004-08-19 | 2004-08-30 | hold after magnetic measurement, assembly under responsibility of Ansaldo
2087_B | AL |  | HCMBBLA001-02000087 | 2004-05-05 | Supplementary Mid-plane shim | 5/14/04/5/28/04 |  | ok | week 29/04(150704)/cut |  |  |  | 2004-07-16 |  |  |  |  | hold after magnetic measurement, assembly under responsibility of Ansaldo, electrical fault (Interturn)
2088_B | AL |  | HCMBBLA001-02000088 | 2004-05-04 | Supplementary Mid-plane shim | 5/5/04/5/26/04 |  | ok | week 30/04(240704) |  |  |  | 2004-07-27 | ok | 2004-08-23 |  |  | hold after magnetic measurement, assembly under responsibility of Ansaldo
2089_B | AL | MDA0895 | HCMBBLA001-02000089 | 5/14/2004/decollared/6/8/04 | Supplementary Mid-plane shim | 5/18/04/6/9/04 |  | ok | week 27/04(290604) | 2004-07-07 |  | ok | 2004-06-30 | ok | 2004-07-12 | 2004-07-20 | 2004-07-26 | hold after magnetic measurement, decollared
2090_B | AL | MDA0942 | HCMBBLA001-02000090 | 2004-05-21 | Supplementary Mid-plane shim | 2004-05-21 |  | ok | week 25/'04(160604) | 2004-06-22 |  | ok | 2004-06-17 | ok | 2004-06-29 | 2004-07-07 | 2004-07-19 | collaring position in collaring press inverted, hold after magnetic measurement, assembly under responsibility of Ansaldo
2091_B | AL | MDA0898 | HCMBBLA001-02000091 | 2004-05-22 | Supplementary Mid-plane shim | 2004-05-24 |  | ok | week 25/'04(140604) | 2004-06-21 |  | ok | 2004-06-15 | ok | 2004-06-25 | 2004-07-01 | 2004-07-07 | collaring position in collaring press inverted, hold after magnetic measurement, assembly under responsibility of Ansaldo
2092_A | AL |  | HCMBALA001-02000092 | 7/1/2004/decollared/7/21/04 | Supplementary Mid-plane shim | 7/5/04/7/26/04 |  | ok | week 35/04(250804) | [8 empty] | hold after magnetic measurement, decollared
2093_B | AL |  | HCMBBLA001-02000093 | 2004-07-02 | Supplementary Mid-plane shim | 2004-07-02 |  | ok | week 30/04(200704) | 2004-07-29 |  | ok | 2004-07-21 | ok | 2004-08-04 | 2004-08-11 | 2004-08-18 | hold after magnetic measurement
2094_A | AL |  | HCMBALA001-02000094 | 2004-07-09 | Supplementary Mid-plane shim | 2004-07-12 |  | ok | week 31/04(270704) |  |  |  | 2004-07-30 | okCC 2110, 2111assembly | 2004-08-25
2095_A | AL |  | HCMBALA001-02000095 | 2004-07-08 | Supplementary Mid-plane shim | 2004-07-10 |  | ok | week 31/04(310704) |  |  |  | 2004-08-04 |  |  |  |  | hold after magnetic measurement
2096_A | AL |  | HCMBALA001-02000096 | 2004-07-15 |  | 2004-07-16 |  | ok | week 31/04(290704) |  |  |  | 2004-08-02
2097_A | AL |  | HCMBALA001-02000097 | 2004-07-23 |  | 2004-07-26
2098_A | AL |  | HCMBALA001-02000098 | 7/23/2004/decollared/assembly
2099_A | AL |  | HCMBALA001-02000099 | 2004-07-29 |  | 2004-08-03 |  | ok
2100_A | AL |  | HCMBALA001-02000100 | 2004-07-30 |  | 2004-08-02 |  | ok
2101_B | AL |  | HCMBBLA001-02000101 | 6/3/2004/decollared | Supplementary Mid-plane shim | 6/4/04/6/9/04/
2102_A | AL |  | HCMBALA001-02000102 | 2004-07-16 |  | 2004-07-23 |  |  | week 32/04(050804)
2103_B | AL |  | HCMBBLA001-02000103 | 2004-07-06 | Supplementary Mid-plane shim | 2004-07-07 |  | ok | week 30/04(220704) | 2004-08-03 |  | ok | 2004-07-26 | ok | 2004-08-13 | 2004-08-24 | 2004-09-01
2104_B | AL |  | HCMBBLA001-02000104 | 2004-06-23 | Supplementary Mid-plane shim | 2004-06-25 |  | ok | week 28/04(090704) | 2004-07-19 |  | ok | 2004-07-13 | ok | 2004-07-23 | 2004-07-30 | 2004-08-04
2105_B | AL |  | HCMBBLA001-02000105 | 2004-06-18 | Supplementary Mid-plane shim | 2004-06-19 |  | ok | week 28/04(070704) | 2004-07-14 |  | ok | 2004-07-09 | ok | 2004-07-20 | 2004-08-02 | 2004-08-09
2106_B | AL | MDA0937 | HCMBBLA001-02000106 | 2004-06-16 | Supplementary Mid-plane shim | 2004-06-17 |  | ok | week 27/04(020704) | 2004-07-10 |  | ok | 2004-07-06 | ok | 2004-07-14 | 2004-07-29 | 2004-08-02
2107_B | AL |  | HCMBBLA001-02000107 | 2004-06-23 | Supplementary Mid-plane shim | 2004-06-28 |  | ok | week 29/04(130704) | 2004-07-22 |  | ok | 2004-07-14 | ok | 2004-07-28 | 2004-08-09 | 2004-08-16
2108_B | AL | MDA0920 | HCMBBLA001-02000108 | 2004-06-09 | Supplementary Mid-plane shim | 2004-06-10 |  | ok | week 26/04(230604) | 2004-07-02 |  | ok | 2004-06-25 | ok | 2004-07-07 | 2004-07-16 | 2004-07-22
2109_A | AL |  | HCMBALA001-02000109 | 2004-07-30 |  | 2004-08-04 |  | ok
2110_B | AL |  | HCMBBLA001-02000110 | assembly
2111_B | AL |  | HCMBBLA001-02000111 | assembly
2112_B | AL |  | HCMBBLA001-02000112
2113_B | AL |  | HCMBBLA001-02000113
2114_B | AL |  | HCMBBLA001-02000114
2115_B | AL |  | HCMBBLA001-02000115
2116_B | AL |  | HCMBBLA001-02000116
2117_B | AL |  | HCMBBLA001-02000117
2118_B | AL |  | HCMBBLA001-02000118
2119_A | AL |  | HCMBBLA001-02000119
2120_A | AL |  | HCMBBLA001-02000120
2121_A | AL |  | HCMBBLA001-02000121
2122_A | AL |  | HCMBBLA001-02000122
2123_A | AL |  | HCMBBLA001-02000123
2124_A | AL |  | HCMBBLA001-02000124
2125_A | AL |  | HCMBBLA001-02000125
2126_A | AL |  | HCMBBLA001-02000126
2127_A | AL |  | HCMBBLA001-02000127
2128_A | AL |  | HCMBBLA001-02000128
2129_B | AL |  | HCMBBLA001-02000129
2130_B | AL |  | HCMBBLA001-02000130
2131_B | AL |  | HCMBBLA001-02000131
2132_B | AL |  | HCMBBLA001-02000132
2133_B | AL |  | HCMBBLA001-02000133
2134_A | AL |  | HCMBBLA001-02000134
2135_A | AL |  | HCMBBLA001-02000135
2136_A | AL |  | HCMBBLA001-02000136
2137_A | AL |  | HCMBBLA001-02000137
2138_A | AL |  | HCMBBLA001-02000138
2139_A | AL |  | HCMBBLA001-02000139
2140_A | AL |  | HCMBBLA001-02000140
2141_A | AL |  | HCMBBLA001-02000141
2142_A | AL |  | HCMBBLA001-02000142
2143_a | AL |  | HCMBBLA001-02000143
2144_A | AL |  | HCMBBLA001-02000144
2145_A | AL |  | HCMBBLA001-02000145
2146_A | AL |  | HCMBBLA001-02000146
2147_A | AL |  | HCMBBLA001-02000147
2148_A | AL |  | HCMBBLA001-02000148
2149_A | AL |  | HCMBBLA001-02000149
2150_B | AL |  | HCMBBLA001-02000150
2151_B | AL |  | HCMBBLA001-02000151
2152_B | AL |  | HCMBBLA001-02000152
2153_B | AL |  | HCMBBLA001-02000153
2154_B | AL |  | HCMBBLA001-02000154
2155_B | AL |  | HCMBBLA001-02000155
2156_B | AL |  | HCMBBLA001-02000156
2157_B | AL |  | HCMBBLA001-02000157
2158_B | AL |  | HCMBBLA001-02000158
2159_B | AL |  | HCMBBLA001-02000159
2160_A | AL |  | HCMBBLA001-02000160
2161_A | AL |  | HCMBBLA001-02000161
2162_A | AL |  | HCMBBLA001-02000162
2163_A | AL |  | HCMBBLA001-02000163
2164_A | AL |  | HCMBBLA001-02000164
2165_A | AL |  | HCMBBLA001-02000165
2166_A | AL |  | HCMBBLA001-02000166
2167_A | AL |  | HCMBBLA001-02000167
2168_A | AL |  | HCMBBLA001-02000168
2169_A | AL |  | HCMBBLA001-02000169
2170_A | AL |  | HCMBBLA001-02000170
2171_A | AL |  | HCMBBLA001-02000171
2172_A | AL |  | HCMBBLA001-02000172
2173_B | AL |  | HCMBBLA001-02000173
2174_B | AL |  | HCMBBLA001-02000174
2175_B | AL |  | HCMBBLA001-02000175
2176_B | AL |  | HCMBBLA001-02000176
2177_B | AL |  | HCMBBLA001-02000177
2178_B | AL |  | HCMBBLA001-02000178
2179_B | AL |  | HCMBBLA001-02000179
2180_B | AL |  | HCMBBLA001-02000180
2181_B | AL |  | HCMBBLA001-02000181
2182_B | AL |  | HCMBBLA001-02000182
2183_B | AL |  | HCMBBLA001-02000183
2184_B | AL |  | HCMBBLA001-02000184
2185_B | AL |  | HCMBBLA001-02000185
2186_B | AL |  | HCMBBLA001-02000186
2187_B | AL |  | HCMBBLA001-02000187

## collaring sequence
Magnet | collaring date | remarks | collar batch | quenches to 9T
2001_B | 2001-02-06 |  | MAL002
2003_B | 2001-06-26 |  | MAL10014
2004_B | 2001-12-12 |  | MAL10016 | 2
2007_B | 2002-01-15 |  | MAL10017 | 3
2008_B | 2002-02-20 |  | MAL10032 | 2
2006_B | 2002-03-19 |  | MAL10018 | 4
2009_B | 2002-04-12 |  | MAL10033 | 1
2010_B | 2002-05-09 |  | MAL10034
2012_B | 2002-05-23 |  | MAL10051
2014_B | 2002-06-24 |  | MAL20061 | 2, new criteria
2013_A | 2002-07-31 | back, bad quench performance | MAL10052 | 9+2, did not reach
2016_A | 2002-08-22 |  | MA000063 | 3
2017_A | 2002-10-02 |  | MA000064 | 3
2018_A | 2002-10-03 |  | MA000068 | 4
2011_A | 2002-10-24 |  | MA000062 | 3
2019_A | 2002-11-07 |  | MA000069 | 8
2020_A | 2002-11-19 |  | MAL10050 | 2
2015_A | 2002-11-29 |  | MAL20060 | 4
2021_B | 2002-12-10 |  | MAL20059 | 5
2022_B | 2002-12-19 |  | MA000070 | 7+4
2023_B | 2003-01-15 | back, bad quench performance | MA00083 | 8+2, did not reach
2025_B | 2003-02-11 | back, bad quench performance | MA000082 | 6+4, detraining
2026_A | 2003-02-25 |  | MA000081 | 7+2, detraining
2027_A | 2003-03-06 |  | MA000084 | 5+2, new criteria
2028_A | 2003-03-14 |  | MA000080 | 4
2029_A | 2003-03-25 |  | MAL10015 | 5
2030_A | 2003-03-31 |  | MA000092 | 8
2002_B | 2003-04-11 |  | MAL009 | 4
2031_A | 2003-04-16 |  | MA000094 | 8
2032_B | 2003-05-12 | decollared, mag. Meas., detachment | MA00098 | electrical problem
2005_A | 2003-05-19 |  | MA000085 | 2, new criteria
2034_A | 2003-05-30 |  | MA000100 | 5
2033_A | 2003-06-04 |  | MA000099
2036_A | 2003-06-11 |  | MA200046
2037_A | 2003-06-16 |  | MA00122
2024_A | 2003-06-23 | bad quench performance | MA000093 | 7+2, detraining
2035_B | 2003-06-28 | decollared, mag. Meas., detachment | MA00285
2041_B | 2003-07-04 |  | MA200045 | 3
2042_A | 2003-07-14 |  | MA000107 | 2, new criteria
2038_A | 2003-07-15 |  | MA200043
2039_A | 2003-07-18 |  | MA000106
2043_B | 2003-07-29 |  | MA000132
2040_B | 2003-07-30 |  | MA000128 | 2, new criteria
2044_B | 2003-07-30 |  | MA000129 | 8+2
2048_B | 2003-08-08 |  | MA00123 | 2+1, new criteria
2052_B | 2003-08-20 |  | MA000104 | 2, new criteria
2050_B | 2003-08-27 |  | MA000105 | 2, new criteria
2053_B | 2003-09-05 |  | MA00127 | 8
2054_A | 2003-09-10 |  | MA00120 | 7+2
2055_B | 2003-09-12 |  | MA000134
2057_A | 2003-09-23 |  | MA000133
2049_B | 2003-09-26 | back, insulation fault to ground | MA00124
2058_B | 2003-09-29 |  | MA00126
2045_B | 2003-10-07 |  | MA000130
2061_B | 2003-10-09 |  | MA20056
2056_A | 2003-10-16 |  | MA00121 | 2, new criteria
2062_B | 2003-10-30 |  | MA000131
2059_A | 2003-11-03 |  | MA00152 | 5
2047_A | 2003-11-11 | bad quench performance | MA00125
2051_A | 2003-11-18 | decollared, quench heater | MA20053
2063_B | 2003-11-24 | decollared, quench heater | MA20054 | 2, new criteria
2046_A | 2003-11-28 |  | MA00145 | 2, new criteria
2060_A | 2003-12-03 |  | MA000098 | 2, new criteria
2064_A | 2003-12-10 |  | MA000135
2066_A | 2003-12-15 |  | MA00144 | 2, new criteria
2072_A | 2003-12-29 |  | MA00154
2069_A | 2004-01-12 | bad quench performance | MA00167 | 9+6, did not reach
2051_A | 2004-01-23 |  | MA20053
2073_B | 2004-01-26 | decollared, quench heater | MA00155
2032_B | 2004-01-30 | back, strange voltage tap signals | MA00083
2063_B | 2004-02-05 |  | MA20054
2081_B | 2004-02-10 |  | MA00202 | 5
2070_B | 2004-02-14 |  | MA00175
2071_B | 2004-02-14 |  | MA00182
2074_B | 2004-02-23 |  | MA00169 | 3
2067_B | 2004-02-25 |  | MA20057
2077_B | 2004-03-04 |  | MA20055 | 4
2078_B | 2004-03-08 |  | MA00216
2065_B | 2004-03-11 | decollared, mag. Meas., detachment not seen | MA200042 scrapped | 2, new criteria
2082_B | 2004-03-16 |  | MA00168 | 2, new criteria
2076_B | 2004-03-19 |  | MA00170
2075_B | 2004-03-26 |  | MA00218
2068_B | 2004-03-29 |  | MA00238
2080_A | 2004-04-07 |  | MA00211
2079_A | 2004-04-09 |  | MA00188
2083_A | 2004-04-13 |  | MA00236 | 2, new criteria
2086_B | 2004-04-22 |  | MA00191
2084_B | 2004-04-23 | decollared, mag. Meas., detachment not seen | MA000263
2523_A | 2004-04-28 |  | MA00146 | 4, new criteria
2088_B | 2004-05-04 |  | MA00208
2087_B | 2004-05-05 | suspected detachment, interturn discharge, to decollar | MA00262
2065_B | 2004-05-06 |  | MA00219
2085_B | 2004-05-14 |  | MA00201
2089_B | 2004-05-14 | decollared, mag. Meas., detachment not seen | MA00166
2090_B | 2004-05-21 |  | MA00171
2091_B | 2004-05-22 |  | MA00153
2101_B | 2004-06-03 | decollared, discharge between layer | MA00252
2035_B | 2004-06-07 |  | MA00285
2089_B | 2004-06-08 |  | MA00166
2108_B | 2004-06-09 |  | MA00209
2084_B | 2004-06-15 |  | MA000263
2106_B | 2004-06-16 |  | MA00278
2105_B | 2004-06-18 |  | MA00190
2104_B | 2004-06-23 |  | MA00254
2107_B | 2004-06-23 |  | MA00287
2092_A | 2004-07-01 | decollared, quench heater and mag. Meas., no detachment seen | MA00253
2093_B | 2004-07-02 |  | MA00279
2103_B | 2004-07-06 |  | MA00284
2095_A | 2004-07-08 |  | MA00276
2094_A | 2004-07-09 |  | MA00165
2096_A | 2004-07-15 |  | MA00247
2102_A | 2004-07-16 |  | MA00217
2092_A | 2004-07-21 |  | MA00253
2097_A | 2004-07-23 |  | MA000298
2098_A | 2004-07-23 | decollared, quench heater | MA000297
2099_A | 2004-07-29 |  | MA000313
2100_A | 2004-07-30 |  | MA000312
2109_A | 2004-07-30 |  | MA000315
2073_B | 5/27/04 | quench heater, to decollar | MA00155
2098_A | pre collared |  | MA00297
2110_B | assembly
2111_B | assembly
2101_B | decollared |  | MA00252

## mag. meas. cc
2001_B | 2001-06-06 |  | 1
2003_B | 2001-07-17 |  | 1
2004_B | 2001-12-20 |  | 1
2008_B | 2002-03-06 |  | 1
2007_B | 2002-03-07 |  | 1
2006_B | 2002-04-03 |  | 1
2010_B | 2002-05-22 |  | 1
2009_B | 2002-05-23 |  | 1
2012_B | 2002-06-27 |  | 1
2014_B | 2002-07-24 |  | 1
2013_A | 2002-08-27 |  | 1
2016_A | 2002-09-19 |  | 1
2017_A | 2002-10-16 |  | 1
2018_A | 2002-10-17 |  | 1
2011_A | 2002-10-29 |  | 1
2019_A | 2002-11-14 |  | 1
2015_A | 2002-12-03 |  | 1
2020_A | 2002-12-04 |  | 1
2021_B | 2002-12-19 |  | 1
2022_B | 2002-12-27 |  | 1
2025_B | 2003-02-18 |  | 1
2023_B | 2003-02-19 |  | 1
2026_A | 2003-03-20 |  | 1
2027_A | 2003-03-21 |  | 1
2028_A | 2003-04-02 |  | 1
2029_A | 2003-04-03 |  | 1
2030_A | 2003-04-16 |  | 1
2002_B | 2003-04-17 | 2nd collaring | 1
2031_A | 2003-04-29 |  | 1
2032_B | 2003-05-22 | suspected detachment | 1
2005_A | 2003-06-03 | 2nd collaring | 1
2036_A | 2003-06-19 |  | 1
2034_A | 2003-06-20 |  | 1
2037_A | 2003-07-02 |  | 1
2024_A | 2003-07-07 |  | 1
2035_B | 2003-07-14 | suspected detachment | 2
2033_A | 2003-07-15 |  | 1
2042_A | 2003-07-18 |  | 1
2038_A | 2003-07-21 |  | 1
2041_B | 2003-07-23 |  | 1
2039_A | 2003-07-28 |  | 1
2040_B | 2003-08-02 |  | 1
2043_B | 2003-08-07 |  | 1
2044_B | 2003-08-26 |  | 1
2048_B | 2003-08-29 |  | 1
2052_B | 2003-09-02 |  | 1
2054_A | 2003-09-16 |  | 1
2050_B | 2003-09-18 |  | 1
2053_B | 2003-09-22 |  | 1
2032_B | 2003-09-24 | short mole, suspected detachment | 1
2035_B | 2003-09-24 | short mole, suspected detachment | 2
2053_B | 2003-09-26 |  | 1
2055_B | 2003-10-07 |  | 1
2053_B | 2003-10-07 | 2nd collaring | 1
2049_B | 2003-10-08 |  | 1
2057_A | 2003-10-08 |  | 1
2058_B | 2003-10-13 |  | 1
2045_B | 2003-10-15 |  | 1
2061_B | 2003-10-17 |  | 1
2056_A | 2003-10-22 |  | 1
2062_B | 2003-11-13 |  | 1
2047_A | 2003-11-14 |  | 1
2059_A | 2003-11-14 |  | 2
2051_A | 2003-12-01 |  | 1
2046_A | 2003-12-03 |  | 2
2060_A | 2003-12-09 |  | 1
2064_A | 2003-12-15 |  | 1
2066_A | 2003-12-23 |  | 2
2047_A | 2004-01-07 | 2nd collaring | 1
2072_A | 2004-01-09 |  | 2
2069_A | 2004-01-16 |  | 2
2063_B | 2004-01-19 |  | 1
2051_A | 2004-01-27 | 2nd collaring | 1
2073_B | 2004-01-29 |  | 2
2032_B | 2004-02-03 |  | 1
2063_B | 2004-02-10 | 2nd collaring | 1
2081_B | 2004-02-13 |  | 2
2071_B | 2004-02-19 |  | 2
2070_B | 2004-02-23 |  | 2
2074_B | 2004-02-27 |  | 2
2067_B | 2004-03-02 |  | 2
2077_B | 2004-03-05 | suspected detachment, or movement of block 6 | 1
2078_B | 2004-03-10 |  | 2
2065_B | 2004-03-15 | suspected detachment, or movement of block 6 | 2
2065_B | 2004-03-17 | remeasurement, suspected detachment, or movement of block 6 | 2
2077_B | 2004-03-18 | remeasurement, suspected detachment, or movement of block 6 | 1
2082_B | 2004-03-23 |  | 2
2076_B | 2004-03-24 |  | 2
2075_B | 2004-03-31 | suspected detachment, or movement of block 6 | 2
2068_B | 2004-04-02 |  | 2
2080_A | 2004-04-09 |  | 2
2079_A | 2004-04-14 |  | 2
2083_A | 2004-04-16 |  | 2
2523_A | 2004-04-28 | 2nd collaring | 2
2084_B | 2004-04-30 | suspected detachment, or movement of block 6 | 2
2088_B | 2004-05-05 | suspected detachment, or movement of block 6 | 2
2065_B | 2004-05-11 | 2nd collaring | 2
2086_B | 2004-05-13 | suspected detachment, or movement of block 6 | 2
2087_B | 2004-05-14 | suspected detachment, or movement of block 6 | 2
2085_B | 2004-05-17 | suspected detachment, or movement of block 6 | 2
2089_B | 2004-05-18 | suspected detachment, or movement of block 6 | 2
2090_B | 2004-05-21 | suspected detachment, or movement of block 6 | 2
2091_B | 2004-05-24 | suspected detachment, or movement of block 6 | 3
2085_B | 2004-05-25 | short mole, suspected detachment, or movement of block 6 | 2
2088_B | 2004-05-26 | short mole, suspected detachment, or movement of block 6 | 2
2073_B | 2004-05-27 | 2nd collaring | 2
2084_B | 2004-05-27 | short mole, suspected detachment, or movement of block 6 | 2
2087_B | 2004-05-28 | short mole, suspected detachment, or movement of block 6 | 2
2101_B | 2004-06-04 |  | 3
2035_B | 2004-06-08 | 2nd collaring | 1
2089_B | 2004-06-09 | 2nd collaring | 2
2101_B | 2004-06-09 | remeasurement | 3
2108_B | 2004-06-10 |  | 3
2084_B | 2004-06-16 | 2nd collaring | 2
2106_B | 2004-06-17 |  | 3
2105_B | 2004-06-19 |  | 3
2104_B | 2004-06-25 |  | 3
2107_B | 2004-06-28 |  | 3
2093_B | 2004-07-02 | suspected detachment, or movement of block 6 | 3
2092_A | 2004-07-05 | suspected detachment, or movement of block 6 | 3
2103_B | 2004-07-07 |  | 3
2095_A | 2004-07-10 | suspected detachment, or movement of block 6 | 3
2094_A | 2004-07-12 | suspected detachment, or movement of block 6 | 3
2096_A | 2004-07-16 | suspected detachment, or movement of block 6 | 3
2102_A | 2004-07-23 |  | 3
2097_A | 2004-07-26 | suspected detachment, or movement of block 6 | 3
2092_A | 2004-07-26 | 2nd collaring | 3
2100_A | 2004-08-02 |  | 3
2099_A | 2004-08-03 | suspected detachment, or movement of block 6 | 3
2109_A | 2004-08-04 | suspected detachment, or movement of block 6 | 3
2098_A | pre collared
2110_B
2111_B

## delivery
| 2001_B | 2002-01-01
| 2003_B | 2002-08-30
| 2004_B | 2002-11-28
| 2006_B | 2003-01-30
| 2008_B | 2003-03-25
| 2012_B | 2003-04-03
| 2007_B | 2003-04-22
| 2010_B | 2003-04-29
| 2009_B | 2003-05-20
| 2021_B | 2003-06-03
| 2014_B | 2003-06-10
| 2022_B | 2003-06-23
| 2025_B | 2003-07-01 | back, bad quench performance | at AS, to open
| 2002_B | 2003-07-15
| 2023_B | 2003-07-17 | back, bad quench performance | repaired
| 2020_A | 2003-07-28
| 2018_A | 2003-07-31
| 2017_A | 2003-08-07
| 2016_A | 2003-08-29
| 2013_A | 2003-09-02 | back, bad quench performance | at AS, to open
| 2028_A | 2003-09-17
| 2024_A | 2003-09-22 | bad quench performance | ?????
| 2015_A | 2003-10-06
| 2026_A | 2003-10-13
| 2030_A | 2003-10-20
| 2029_A | 2003-10-22
| 2005_A | 2003-10-27
| 2019_A | 2003-10-30
| 2027_A | 2003-11-06
| 2033_A | 2003-11-13
| 2034_A | 2003-11-17
| 2054_A | 2003-11-20
| 2036_A | 2003-11-25
| 2039_A | 2003-11-27
| 2050_B | 2003-12-02
| 2041_B | 2003-12-04
| 2040_B | 2003-12-09
| 2044_B | 2003-12-15
| 2011_A | 2003-12-19
| 2038_A | 2004-01-22
| 2060_A | 2004-02-05
| 2064_A | 2004-02-09
| 2046_A | 2004-02-11
| 2043_B | 2004-02-16
| 2066_A | 2004-02-18
| 2052_B | 2004-02-23
| 2047_A | 2004-02-26 | bad quench performance, TC | at CERN
| 2072_A | 2004-03-01
| 2069_A | 2004-03-03 | bad quench performance | at CERN
| 2048_B | 2004-03-08
| 2051_A | 2004-03-10
| 2032_B | 2004-03-12 | back, strange voltage tap signals | at AS, dismounted, to decollar
| 2055_B | 2004-03-16
| 2063_B | 2004-03-18
| 2081_B | 2004-03-22
| 2071_B | 2004-03-24
| 2058_B | 2004-03-29
| 2070_B | 2004-03-31
| 2045_B | 2004-04-02
| 2074_B | 2004-04-07
| 2067_B | 2004-04-13
| 2078_B | 2004-04-15
| 2049_B | 2004-04-19 | back, insulation fault to ground | at AS, to open
| 2053_B | 2004-04-21
| 2061_B | 2004-04-26
| 2062_B | 2004-04-28
| 2082_B | 2004-05-03
| 2076_B | 2004-05-06
| 2068_B | 2004-05-10
| 2056_A | 2004-05-12
| 2037_A | 2004-05-17
| 2042_A | 2004-05-19
| 2079_A | 2004-05-25
| 2031_A | 2004-05-27
| 2083_A | 2004-06-01
| 2059_A | 2004-06-03
| 2080_A | 2004-06-07
| 2523_A | 2004-06-10
| 2057_A | 2004-06-14
| 2077_B | 2004-06-16
| 2065_B | 2004-06-18
| 2091_B | 2004-07-07
| 2085_B | 2004-07-12
| 2035_B | 2004-07-15
| 2090_B | 2004-07-19
| 2108_B | 2004-07-22
| 2089_B | 2004-07-26
| 2075_B | 2004-07-28
| 2106_B | 2004-08-02
| 2104_B | 2004-08-04
| 2105_B | 2004-08-09
| 2084_B | 2004-08-11
| 2107_B | 2004-08-16
| 2093_B | 2004-08-18
1 | 2086_B | 2004-08-30
2 | 2103_B | 2004-09-01
3 | 2088_B | welded, final assembly
4 | 2094_A | welded, final assembly
5 | 2102_A | welded, final assembly
6 | 2095_A | welded, final assembly
7 | 2096_A | welded, final assembly
8 | 2092_A | in welding press
| 2097_A | collared
| 2099_A | collared
| 2100_A | collared
| 2109_A | collared
| 2098_A | pre-collaring
| 2110_B | pre-collaring
| 2111_B | pre-collaring
| 2101_B | decollared
| 2073_B | CM finished | at AS, quench heater | to open
| 2087_B | dismounted | at AS, interturn discharge | collared coil to decollar