## Sheet1
cold mass | type | diode | cern ID | collaring | extra shim | mag meas. collared | mod. ferr.mag. length | q.h. el. test | long. welding | geo. meas. | reshaping | x-ray | mag.meas. cm | end covers | geo. meas. | leak test | sent | remarks
2001 |  |  | HCMBBRA001-02000001 | 06.02.01 |  | nd |  | ok | CERN |  |  | ok | 06.07.01 | ok | nd | nd | nd
2002_B | AR | MDB0207 | HCMBBRA001-02000002 | 11.04.03 |  | 17.04.03 |  | ok | 22/03 |  |  | ok | done | ok | 30.06.03 | 04.07.03 | 15.07.03 | first assembled at CERN, totally diassembled,recollared
2003_B | AR |  | HCMBBRA001-02000003 | 26.06.01 |  | 17.07.01 |  | ok | CERN |  |  | ok | 01.08.01 | ok | nd | nd | nd
2004_B | AR | MDB0350 | HCMBBRA001-02000004 | 12.12.01 |  | 20.12.01 |  | ok | 26/02 | 03.07.02 |  | ok | 05.11.02 | ok | 27.11.02 | 26.11.02 | 28.11.02
2005_A | AR |  | HCMBARA001-02000005 | 19.05.03 |  | 03.06.03 |  | ok | 30/03 | 08.09.03 |  | ok | 19.08.03 |  |  |  |  | first assembled at CERN, totally diassembled,recollared
2006_B | AR | MDB0323 | HCMBBRA001-02000006 | 19.03.02 |  | 03.04.02 |  | ok | 37/02 | 24.09.02 |  | ok | 13.11.02 | ok | 16.01.03 | 27.01.03 | 30.01.03
2007_B | AR | MDB0131 | HCMBBRA001-02000007 | 15.01.02 |  | 07.03.02 |  | ok | 51/02 |  |  | ok | 26.02.03 | ok | 10.04.03 | 17.04.03 | 22.04.03
2008_B | AR | MDB0368 | HCMBBRA001-02000008 | 20.02.02 |  | 06.03.02 |  | ok | 50/02 | 28.12.02 |  | ok | 19.12.02 | ok | 20.03.03 | 20.03.03 | 25.03.03
2009_B | AR | MDB0327 | HCMBBRA001-02000009 | 12.04.02 |  | 23.05.02 |  | ok | 48/02 | 19.12.02 |  | ok | 27.02.03 | ok | 06.05.03 | 17.05.03 | 20.05.03
2010_B | AR | MDB0363 | HCMBBRA001-02000010 | 09.05.02 |  | 22.05.02 |  | ok | 46/02 | 19.11.02 |  | ok | 05.12.02 | ok | 23.04.03 | 28.04.03 | 29.04.03
2011_A | AR |  | HCMB__A001-02000011 | 24.10.02 |  | 29.10.02 |  | ok | 17.09.03 | [8 empty] | recollared
2012_B | AR | MDB0368 | HCMBBRA001-02000012 | 23.05.02 |  | 27.06.02 | + 2x50mm | ok | 41/02 | 22.10.02 |  | ok | 30.10.02 | ok | 27.03.03 | 01.04.03 | 03.04.03
2013_A | AR | MDB0372 | HCMBARA001-02000013 | 31.07.02 |  | 27.08.02 | + 2x50mm | ok | 28/03 | 31.07.03 |  | ok | 29.07.03 | ok | 25.08.03 | 26.08.03 | 02.09.03 | recollared
2014_B | AR | MDB0344 | HCMBBRA001-02000014 | 24.06.02 |  | 24.07.02 | + 2x50mm | ok | 09/03 |  |  | ok | 27.03.03 | ok | 27.05.03 | 03.06.03 | 10.06.03
2015_A | AR | MDB267 | HCMB__A001-02000015 | 29.11.02 |  | 03.12.02 |  | ok | 05.09.03 | 09.09.03 |  | ok | 17.09.03 | ok
2016_A | AR | MDB0287 | HCMBARA001-02000016 | 22.08.02 |  | 19.09.02 | + 2x50mm | ok | 28/03 | 17.07.03 |  | ok | 30.07.03 | ok | 06.08.03 | 19.08.03 | 29.08.03
2017_A | AR | MDB0218 | HCMBARA001-02000017 | 02.10.02 |  | 16.10.02 | + 2x50mm | ok | 24/03 | 13.06.03 |  | ok | 11.07.03 | ok | 23.07.03 | 30.07.03 | 07.08.03
2018_A | AR | MDB0361 | HCMBARA001-02000018 | 03.10.02 |  | 17.10.02 | + 2x50mm | ok | 25/03 | 26.06.03 |  | ok | 03.07.03 | ok | 22.07.03 | 25.07.03 | 31.07.03
2019_A | AR |  | HCMB__A001-02000019 | 07.11.02 |  | 14.11.02 |  | ok | 38/03
2020_A | AR | MDB0282 | HCMBARA001-02000020 | 19.11.02 |  | 04.12.02 |  | ok | 23/03 | 13.06.03 |  | ok | 18.06.03 | ok | 11.07.03 | 22.07.03 | 28.07.03 | half shells cut and disassembled
2021_B | AR | MDB0351 | HCMBBRA001-02000021 | 10.12.02 |  | 19.12.02 |  | ok | 11/03 | 04.04.03 |  | ok | 28.03.03 | ok | 19.05.03 | 23.05.03 | 03.06.03
2022_B | AR | MDB0127 | HCMBBRA001-02000022 | 19.12.02 |  | 27.12.02 |  | ok | 21/03 |  |  | ok | 04.06.03 | ok | 10.06.03 | 17.06.03 | 23.06.03
2023_B | AR | MDB0325 | HCMBBRA001-02000023 | 15.01.03 |  | 19.02.03 |  | ok | 13/03 | 24.04.03 |  | ok | 27.05.03 | ok | 01.07.03 | 08.07.03 | 17.07.03 | recollared
2024_A | AR | MDB0200 | HCMBARA001-02000024 | 23.06.03 |  | 07.07.03 |  | ok | 29.07.03 | 28.08.03 |  | ok | 21.08.03 | ok | 12.09.03 | 17.09.03 | 22.09.03 | recollared
2025_B | AR | MDB0194 | HCMBBRA001-02000025 | 11.02.03 |  | 18.02.03 |  | ok | 20/03 | 15.05.03 |  | ok | 26.05.03 | ok | 18.06.03 | 23.06.03 | 01.07.03
2026_A | AR | MDB0221 | HCMBARA001-02000026 | 25.02.03 |  | 20.03.03 | + 2x50mm | ok | 28.08.03 | 09.09.03 |  | ok | 11.09.03 | ok | 24.09.03 | in vessel
2027_A | AR |  | HCMBARA001-02000027 | 06.03.03 |  | 21.03.03 |  | ok | 27/03 | 08.07.03 |  | ok | 10.07.03
2028_A | AR | MDB0281 | HCMBARA001-02000028 | 14.03.03 |  | 02.04.03 |  | ok | 29/03 | 06.08.03 |  | ok | 30.07.03 | ok | 04.09.03 | 13.09.03 | 17.09.03
2029_A | AR | MDB0230 | HCMBARA001-02000029 | 25.03.03 |  | 03.04.03 |  | ok | 34/03 | 09.09.03 |  | ok | 10.09.03 | ok | 22.09.03 | 30.09.03
2030_A | AR |  | HCMBARA001-02000030 | 31.03.03 |  | 16.04.03 |  | ok | 06.09.03 | 16.09.03 |  | ok | 19.09.03
2031_A | AR |  | HCMB__A001-02000031 | 16.04.03 |  | 29.04.03 |  | ok
2032_A | AR |  | HCMB__A001-02000032 | 12.05.03 |  | 22.05.03 / 24.09.03 |  | ok | [9 empty] | hold after magnetic measurement
2033_A | AR |  | HCMB__A001-02000033 | 04.06.03 |  | 15.07.03 |  | ok | 39/03
2034_A | AR |  | HCMB__A001-02000034 | 30.05.03 |  | 20.06.03 |  | ok | preparing to weld
2035_A | AL |  | HCMB__A001-02000035 | 28.06.03 | yes | 14.07.03 / 24.09.03 |  | ok | [9 empty] | extra shim in mid plane, hold after magnetic measurement
2036_A | AR |  | HCMB__A001-02000036 | 11.06.03 |  | 19.06.03 |  | ok | 03.10.03
2037_A | AR |  | HCMB__A001-02000037 | 16.06.03 |  | 02.07.03 |  | ok
2038_B | AR |  | HCMB__A001-02000038 | 15.07.03 |  | 21.07.03 |  | ok
2039_A | AR |  | HCMB__A001-02000039 | 18.07.03 |  | 28.07.03 |  | ok
2040_B | AL |  | HCMB__A001-02000040 | 25.07.03 | yes | 02.08.03 |  | ok | [9 empty] | extra shim in mid plane
2041_A | AR |  | HCMB__A001-02000041 | 04.07.03 |  | 23.07.03 |  | ok
2042_B | AR |  | HCMB__A001-02000042 | 14.07.03 |  | 18.07.03 |  | ok
2043_A | AL |  | HCMB__A001-02000043 | 29.07.03 | yes | 07.08.03 |  | ok | [9 empty] | extra shim in mid plane
2044 |  |  | HCMB__A001-02000044 | 30.07.03 |  | 26.08.03 |  | ok
2045 |  |  | HCMB__A001-02000045 | assembly | yes
2046 |  |  | HCMB__A001-02000046
2047 |  |  | HCMB__A001-02000047
2048 |  |  | HCMB__A001-02000048 | 08.08.03 |  | 29.08.03 |  | ok
2049 |  |  | HCMB__A001-02000049 | assembly | yes
2050 |  |  | HCMB__A001-02000050 | 27.08.03 |  | 18.09.03 |  | ok
2051 |  |  | HCMB__A001-02000051
2052 |  |  | HCMB__A001-02000052 | 22.08.03 |  | 02.09.03 |  | ok
2053 |  |  | HCMB__A001-02000053 | 05.09.03 | yes | 22.09.03 / 26.09.03 |  | ok
2054 |  |  | HCMB__A001-02000054 | 11.09.03 | yes | 16.09.03 |  | ok | yoke assembly
2055 |  |  | HCMB__A001-02000055 | 12.09.03 | yes
2056 |  |  | HCMB__A001-02000056
2057 |  |  | HCMB__A001-02000057 | 23.09.03 | yes |  |  | ok
2058 |  |  | HCMB__A001-02000058 | in collaring press | yes
2059 |  |  | HCMB__A001-02000059
2060 |  |  | HCMB__A001-02000060
2061 |  |  | HCMB__A001-02000061 | assembly
2062 |  |  | HCMB__A001-02000062
2063 |  |  | HCMB__A001-02000063
2064 |  |  | HCMB__A001-02000064
2065 |  |  | HCMB__A001-02000065
2066 |  |  | HCMB__A001-02000066
2067 |  |  | HCMB__A001-02000067
2068 |  |  | HCMB__A001-02000068
2069 |  |  | HCMB__A001-02000069
2070 |  |  | HCMB__A001-02000070