## Sheet1
cold mass | type | diode | cern ID | collaring | extra shim | mag meas. collared | mod. ferr.mag. length | q.h. el. test | long. welding | geo. meas. | reshaping | x-ray | mag.meas. cm | end covers | geo. meas. | leak test | sent | remarks
2001_B |  |  | HCMBBRA001-02000001 | 06.02.01 |  | nd |  | ok | CERN |  |  | ok | 06.07.01 | ok | nd | nd | nd
2002_B | AR | MDB0207 | HCMBBRA001-02000002 | 11.04.03 |  | 17.04.03 |  | ok | 22/03 |  |  | ok | done | ok | 30.06.03 | 04.07.03 | 15.07.03 | first assembled at CERN, totally diassembled,recollared
2003_B | AR |  | HCMBBRA001-02000003 | 26.06.01 |  | 17.07.01 |  | ok | CERN |  |  | ok | 01.08.01 | ok | nd | nd | nd
2004_B | AR | MDB0350 | HCMBBRA001-02000004 | 12.12.01 |  | 20.12.01 |  | ok | 26/02 | 03.07.02 |  | ok | 05.11.02 | ok | 27.11.02 | 26.11.02 | 28.11.02
2005_A | AR |  | HCMBARA001-02000005 | 19.05.03 |  | 03.06.03 |  | ok | 30/03 | 08.09.03 |  | ok | 19.08.03 | ok | 10.10.03 | 20.10.03 | 27.10.03 | first assembled at CERN, totally diassembled,recollared
2006_B | AR | MDB0323 | HCMBBRA001-02000006 | 19.03.02 |  | 03.04.02 |  | ok | 37/02 | 24.09.02 |  | ok | 13.11.02 | ok | 16.01.03 | 27.01.03 | 30.01.03
2007_B | AR | MDB0131 | HCMBBRA001-02000007 | 15.01.02 |  | 07.03.02 |  | ok | 51/02 |  |  | ok | 26.02.03 | ok | 10.04.03 | 17.04.03 | 22.04.03
2008_B | AR | MDB0368 | HCMBBRA001-02000008 | 20.02.02 |  | 06.03.02 |  | ok | 50/02 | 28.12.02 |  | ok | 19.12.02 | ok | 20.03.03 | 20.03.03 | 25.03.03
2009_B | AR | MDB0327 | HCMBBRA001-02000009 | 12.04.02 |  | 23.05.02 |  | ok | 48/02 | 19.12.02 |  | ok | 27.02.03 | ok | 06.05.03 | 17.05.03 | 20.05.03
2010_B | AR | MDB0363 | HCMBBRA001-02000010 | 09.05.02 |  | 22.05.02 |  | ok | 46/02 | 19.11.02 |  | ok | 05.12.02 | ok | 23.04.03 | 28.04.03 | 29.04.03
2011_A | AR |  | HCMBARA001-02000011 | 24.10.02 |  | 29.10.02 |  | ok | 17.09.03 | [7 empty] | Prev. 27/11 | recollared
2012_B | AR | MDB0368 | HCMBBRA001-02000012 | 23.05.02 |  | 27.06.02 | + 2x50mm | ok | 41/02 | 22.10.02 |  | ok | 30.10.02 | ok | 27.03.03 | 01.04.03 | 03.04.03
2013_A | AR | MDB0372 | HCMBARA001-02000013 | 31.07.02 |  | 27.08.02 | + 2x50mm | ok | 28/03 | 31.07.03 |  | ok | 29.07.03 | ok | 25.08.03 | 26.08.03 | 02.09.03 | recollared
2014_B | AR | MDB0344 | HCMBBRA001-02000014 | 24.06.02 |  | 24.07.02 | + 2x50mm | ok | 09/03 |  |  | ok | 27.03.03 | ok | 27.05.03 | 03.06.03 | 10.06.03
2015_A | AR | MDB267 | HCMBARA001-02000015 | 29.11.02 |  | 03.12.02 |  | ok | 05.09.03 | 09.09.03 |  | ok | 17.09.03 | ok | 07.10.03 | 09.10.03 | 06.10.03
2016_A | AR | MDB0287 | HCMBARA001-02000016 | 22.08.02 |  | 19.09.02 | + 2x50mm | ok | 28/03 | 17.07.03 |  | ok | 30.07.03 | ok | 06.08.03 | 19.08.03 | 29.08.03
2017_A | AR | MDB0218 | HCMBARA001-02000017 | 02.10.02 |  | 16.10.02 | + 2x50mm | ok | 24/03 | 13.06.03 |  | ok | 11.07.03 | ok | 23.07.03 | 30.07.03 | 07.08.03
2018_A | AR | MDB0361 | HCMBARA001-02000018 | 03.10.02 |  | 17.10.02 | + 2x50mm | ok | 25/03 | 26.06.03 |  | ok | 03.07.03 | ok | 22.07.03 | 25.07.03 | 31.07.03
2019_A | AR |  | HCMBARA001-02000019 | 07.11.02 |  | 14.11.02 |  | ok | 38/03 | 09.10.03 |  | ok | 04.10.03 | ok | 16.10.03 | 22.10.03 | 30.10.03
2020_A | AR | MDB0282 | HCMBARA001-02000020 | 19.11.02 |  | 04.12.02 |  | ok | 23/03 | 13.06.03 |  | ok | 18.06.03 | ok | 11.07.03 | 22.07.03 | 28.07.03 | half shells cut and disassembled
2021_B | AR | MDB0351 | HCMBBRA001-02000021 | 10.12.02 |  | 19.12.02 |  | ok | 11/03 | 04.04.03 |  | ok | 28.03.03 | ok | 19.05.03 | 23.05.03 | 03.06.03
2022_B | AR | MDB0127 | HCMBBRA001-02000022 | 19.12.02 |  | 27.12.02 |  | ok | 21/03 |  |  | ok | 04.06.03 | ok | 10.06.03 | 17.06.03 | 23.06.03
2023_B | AR | MDB0325 | HCMBBRA001-02000023 | 15.01.03 |  | 19.02.03 |  | ok | 13/03 | 24.04.03 |  | ok | 27.05.03 | ok | 01.07.03 | 08.07.03 | 17.07.03 | recollared
2024_A | AR | MDB0200 | HCMBARA001-02000024 | 23.06.03 |  | 07.07.03 |  | ok | 29.07.03 | 28.08.03 |  | ok | 21.08.03 | ok | 12.09.03 | 17.09.03 | 22.09.03 | recollared
2025_B | AR | MDB0194 | HCMBBRA001-02000025 | 11.02.03 |  | 18.02.03 |  | ok | 20/03 | 15.05.03 |  | ok | 26.05.03 | ok | 18.06.03 | 23.06.03 | 01.07.03
2026_A | AR | MDB0221 | HCMBARA001-02000026 | 25.02.03 |  | 20.03.03 | + 2x50mm | ok | 28.08.03 | 09.09.03 |  | ok | 11.09.03 | ok | 24.09.03 | 07.10.03 | 13.10.03
2027_A | AR |  | HCMBARA001-02000027 | 06.03.03 |  | 21.03.03 |  | ok | 27/03 | 08.07.03 |  | ok | 10.07.03 | ok | 24.10.03 | 04.11.03 | 06.11.03
2028_A | AR | MDB0281 | HCMBARA001-02000028 | 14.03.03 |  | 02.04.03 |  | ok | 29/03 | 06.08.03 |  | ok | 30.07.03 | ok | 04.09.03 | 13.09.03 | 17.09.03
2029_A | AR | MDB0230 | HCMBARA001-02000029 | 25.03.03 |  | 03.04.03 |  | ok | 34/03 | 09.09.03 |  | ok | 10.09.03 | ok | 22.09.03 | 30.09.03 | 22.10.03
2030_A | AR |  | HCMBARA001-02000030 | 31.03.03 |  | 16.04.03 |  | ok | 06.09.03 | 16.09.03 |  | ok | 19.09.03 | ok | 10.10.03 | 13.10.03 | 20.10.03
2031_A | AR |  | HCMBARA001-02000031 | 16.04.03 |  | 29.04.03 |  | ok
2032_A | AR |  | HCMBARA001-02000032 | 12.05.03/decollared 18.11.03 |  | 22.05.03 / 24.09.03 |  | ok | [9 empty] | hold after magnetic measurement
2033_A | AR |  | HCMBARA001-02000033 | 04.06.03 |  | 15.07.03 |  | ok | week 39/'03 |  |  | ok | 06.10.03 | OK | 30.10.03 | 05.11.03 | 13.11.03
2034_A | AR |  | HCMBARA001-02000034 | 30.05.03 |  | 20.06.03 |  | ok | week 41/'03 |  |  | ok | 20.10.03 | OK | 31.10.03 | 13.11.03 | 17.11.03
2035_A | AL |  | HCMBALA001-02000035 | 28.06.03 | Supplementary Mid-plane shim | 14.07.03 / 24.09.03 |  | ok | [9 empty] | extra shim in mid plane, hold after magnetic measurement
2036_A | AR |  | HCMBARA001-02000036 | 11.06.03 |  | 19.06.03 |  | ok | week 40/'03 |  |  | ok | 31.10.03 | OK | 31.10.03 | 20.11.03 | Prev. 24/11
2037_A | AR |  | HCMBARA001-02000037 | 16.06.03 |  | 02.07.03 |  | ok
2038_B | AR |  | HCMBBRA001-02000038 | 15.07.03 |  | 21.07.03 |  | ok
2039_A | AR |  | HCMBARA001-02000039 | 18.07.03 |  | 28.07.03 |  | ok | week 43/'03 |  |  | ok | 07.11.03 | OK | 17.11.03 |  | Prev. 1/12
2040_B | AL |  | HCMBBLA001-02000040 | 25.07.03 | Supplementary Mid-plane shim | 02.08.03 |  | ok | week 45/'03 | [7 empty] | Prev. 11/12 | extra shim in mid plane
2041_B | AR |  | HCMBBRA001-02000041 | 04.07.03 |  | 23.07.03 |  | ok | week 44/'03 |  |  | done |  |  |  |  | Prev. 9/12
2042_B | AR |  | HCMBBRA001-02000042 | 14.07.03 |  | 18.07.03 |  | ok
2043_B | AL |  | HCMBBLA001-02000043 | 29.07.03 | Supplementary Mid-plane shim | 07.08.03 |  | ok | week 46/'03 | [7 empty] | Prev. 18/12 | extra shim in mid plane
2044_B | AR |  | HCMBBRA001-02000044 | 30.07.03 |  | 26.08.03 |  | ok | week 46/'03 | [7 empty] | Prev. 15/12
2045_A | AR |  | HCMBARA001-02000045 | 09.10.03 | Supplementary Mid-plane shim | 15.10.03
2046_B | AR |  | HCMBBRA001-02000046 | decollared | Supplementary Mid-plane shim
2047_A | AR |  | HCMBARA001-02000047 | assembly | Supplementary Mid-plane shim
2048_B | AR |  | HCMBBRA001-02000048 | 08.08.03 |  | 29.08.03 |  | ok | week 47/03
2049_A | AL |  | HCMBALA001-02000049 | 26.09.03 | Supplementary Mid-plane shim | 08.10.03
2050_B | AR |  | HCMBBRA001-02000050 | 27.08.03 |  | 18.09.03 |  | ok | week 44/'03 |  |  | done | 10.11.03 |  |  |  | Prev. 4/12
2051_A | AL |  | HCMBALA001-02000051 | assembly | Supplementary Mid-plane shim
2052_B | AR |  | HCMBBRA001-02000052 | 20.08.03 |  | 02.09.03 |  | ok | in press
2053_A | AL |  | HCMBALA001-02000053 | 05.09.03 | Supplementary Mid-plane shim | 22.09.03 / 26.09.03/07.10.03 |  | ok
2054_A | AL |  | HCMBALA001-02000054 | 10.09.03 | Supplementary Mid-plane shim | 16.09.03 |  | ok | week 43/'03 |  |  | ok | 31.10.03 | OK | 13.11.03 | 17.11.03 | 20.11.03
2055_A | AL |  | HCMBALA001-02000055 | 12.09.03 | Supplementary Mid-plane shim | 07.10.03 |  | ok
2056_A | AR |  | HCMBARA001-02000056 | 16.10.03 | NO Mid-plane shim | 22.10.03
2057_A | AL |  | HCMBALA001-02000057 | 23.09.03 | Supplementary Mid-plane shim | 08.10.03 |  | ok
2058_A | AL |  | HCMBALA001-02000058 | 29.09.03 | Supplementary Mid-plane shim | 13.10.03
2059_B | AL |  | HCMBBLA001-02000059 | 03.11.03 | Supplementary Mid-plane shim
2060_B | AL |  | HCMBBLA001-02000060
2061_B | AL |  | HCMBBLA001-02000061 | 09.10.03 | Supplementary Mid-plane shim | 17.10.03
2062_B | AL |  | HCMBBLA001-02000062 | 30.10.03 | Supplementary Mid-plane shim
2063 |  |  | HCMB__A001-02000063 | decollared | Supplementary Mid-plane shim
2064 |  |  | HCMB__A001-02000064
2065 |  |  | HCMB__A001-02000065
2066 |  |  | HCMB__A001-02000066
2067 |  |  | HCMB__A001-02000067
2068 |  |  | HCMB__A001-02000068
2069 |  |  | HCMB__A001-02000069
2070 |  |  | HCMB__A001-02000070
2071
2072
2073
2074
2075
2076
2077
2078
2079
2080
2081
2082
2083
2084
2085
2086
2087
2088
2089
2090
2091
2092
2093
2094
2095
2096
2097
2098
2099
2100

## Sheet2
17.04.03 | 2001-07-17 | 1
17.07.01 | 2001-12-20 | 2
20.12.01 | 2002-03-06 | 3
03.06.03 | 2002-03-07 | 4
03.04.02 | 2002-04-03 | 5
07.03.02 | 2002-05-23 | 6
06.03.02 | 2002-06-27 | 7
23.05.02 | 2002-07-24 | 8
22.05.02 | 2002-08-27 | 9
29.10.02 | 2002-09-19 | 10
27.06.02 | 2002-10-16 | 11
27.08.02 | 2002-10-17 | 12
24.07.02 | 2002-11-14 | 13
03.12.02 | 2002-12-03 | 14
19.09.02 | 2002-12-04 | 15
16.10.02 | 2002-12-19 | 16
17.10.02 | 2002-12-27 | 17
14.11.02 | 2003-02-18 | 18
04.12.02 | 2003-02-19 | 19
19.12.02 | 2003-03-20 | 20
27.12.02 | 2003-03-21 | 21
19.02.03 | 2003-04-02 | 22
07.07.03 | 2003-04-03 | 23
18.02.03 | 2003-04-16 | 24
20.03.03 | 2003-04-17 | 25
21.03.03 | 2003-04-29 | 26
02.04.03 | 2003-05-22 | 27
03.04.03 | 2003-06-03 | 28
16.04.03 | 2003-06-19 | 29
29.04.03 | 2003-06-20 | 30
22.05.03 / 24.09.03 | 2003-07-02 | 31
15.07.03 | 2003-07-07 | 32
20.06.03 | 2003-07-15 | 33
14.07.03 / 24.09.03 | 2003-07-18 | 34
19.06.03 | 2003-07-21 | 35
02.07.03 | 2003-07-23 | 36
21.07.03 | 2003-07-28 | 37
28.07.03 | 2003-08-02 | 38
02.08.03 | 2003-08-07 | 39
23.07.03 | 2003-08-09 | 40
18.07.03 | 2003-08-26 | 41
07.08.03 | 2003-09-02 | 42
26.08.03 | 2003-09-16 | 43
15.10.03 | 2003-09-18 | 44
| 2003-09-24 | 45
| 2003-09-24 | 46
29.08.03 | 2003-10-07 | 47
08.10.03 | 2003-10-07 | 48
18.09.03 | 2003-10-08 | 49
| 2003-10-08 | 50
02.09.03 | 2003-10-13 | 51
22.09.03 / 26.09.03/07.10.03 | 2003-10-15 | 52
16.09.03 | 2003-10-17 | 53
07.10.03 | 2003-10-22 | 54
22.10.03 | 2003-10-29 | 55
08.10.03
13.10.03
17.10.03

## Sheet3
COLLARING | WELDING | DELIVERY
2001-02-06 | 2002-06-30 | 2002-11-28 | 1
2001-06-26 | 2002-09-10 | 2003-01-30 | 2
2001-12-12 | 2002-10-15 | 2003-03-25 | 3
2002-01-15 | 2002-11-15 | 2003-04-03 | 4
2002-02-20 | 2002-11-30 | 2003-04-22 | 5
2002-03-19 | 2002-12-14 | 2003-04-29 | 6
2002-04-12 | 2002-12-21 | 2003-05-20 | 7
2002-05-19 | 2003-02-27 | 2003-06-03 | 8
2002-05-23 | 2003-03-14 | 2003-06-10 | 9
2002-06-24 | 2003-03-28 | 2003-06-23 | 10
2002-07-31 | 2003-05-16 | 2003-07-01 | 11
2002-08-22 | 2003-05-23 | 2003-07-15 | 12
2002-10-02 | 2003-05-31 | 2003-07-17 | 13
2002-10-03 | 2003-06-06 | 2003-07-28 | 14
2002-10-24 | 2003-06-13 | 2003-07-31 | 15
2002-11-07 | 2003-06-20 | 2003-08-07 | 16
2002-11-19 | 2003-07-04 | 2003-08-29 | 17
2002-11-29 | 2003-07-11 | 2003-09-02 | 18
2002-12-10 | 2003-07-11 | 2003-09-17 | 19
2002-12-19 | 2003-07-18 | 2003-09-22 | 20
2003-01-15 | 2003-07-25 | 2003-10-06 | 21
2003-02-11 | 2003-07-29 | 2003-10-13 | 22
2003-02-25 | 2003-08-22 | 2003-10-20 | 23
2003-03-06 | 2003-08-28 | 2003-10-22 | 24
2003-03-14 | 2003-09-05 | 2003-10-27 | 25
2003-03-25 | 2003-09-06 | 2003-10-30 | 26
2003-03-31 | 2003-09-17 | 2003-11-06 | 27
2003-04-11 | 2003-09-19 | 2003-11-13 | 28
2003-04-16 | 2003-09-26 | 2003-11-17 | 29
2003-05-12 | 2003-10-03 | 2003-11-20 | 30
2003-05-19 | 2003-10-10 | 2003-11-24 | 31
2003-05-30 | 2003-10-21 | 2003-11-27 | 32
2003-06-04 | 2003-10-24 | 2003-12-01 | 33
2003-06-11 | 2003-10-28 | 2003-12-04 | 34
2003-06-16 | 2003-10-31 | 2003-12-11 | 35
2003-06-23 | 2003-11-07 | 2003-12-15 | 36
2003-06-28 | 2003-11-11 | 2003-12-18 | 37
2003-07-04 |  |  | 38
2003-07-14 |  |  | 39
2003-07-15 |  |  | 40
2003-07-18 |  |  | 41
2003-07-25 |  |  | 42
2003-07-29 |  |  | 43
2003-07-30 |  |  | 44
2003-08-08 |  |  | 45
2003-08-20 |  |  | 46
2003-08-27 |  |  | 47
2003-09-05 |  |  | 48
2003-09-10 |  |  | 49
2003-09-12 |  |  | 50
2003-09-23 |  |  | 51
2003-09-26 |  |  | 52
2003-09-29 |  |  | 53
2003-10-09 |  |  | 54
2003-10-09 |  |  | 55
2003-10-16 |  |  | 56
2003-10-30 |  |  | 57
2003-11-03 |  |  | 58