## Cold Mass
ANSALDO
[5 empty] | ITP10b | [5 empty] | ITP14 |  |  | ITP16 |  | ITP17 | ITP18 | ITP19 |  |  | ITP21 |  |  | ITP20 | ITP23,24 | ITP25
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
|  | holding point 1 | month | magnet produced | Perform inspection collared coil incl. cold bore tube inner diameter | Install collar/insert shims, insert/yoke shims | Preparation lower half-yoke | Preparation upper half-yoke | Assembly cold mass | Welding | Perform X-ray examinations | Weld end plates on shrinking cylinder | Solder remaining electric connections | Perform horizontal curvature and vertical straightness measurements | Machine chamfers at ends of shrinking cylinder | Install and allign spool pieces and heat exchanger tube | Perform electrical test on Cold Mass Assembly | Install, allign and weld end covers | Install, allign and weld support bases and external busbar pipe supports | Allign and weld cold bore and heat exchanger tubes on end covers | Perform warm magnetic measurements | Realize temporary short circuits | Install and weld interconnect bellows and diode container, close cold mass | Perform final geometric test | Perform pressure and leak tests | Perform final electrical test | Prepare cold mass for transportation | Collared Coil Traveler Completed | travelers filled out
1
| traveler |  | 2
| measurement file to CERN |  | 3
| HCMBB_A001-02000002 |  | 4 |  | ITP10b 6: 2003-05-29
| traveler |  | 5
| measurement file to CERN |  | 6
7
| traveler |  | 8
| measurement file to CERN |  | 9
| HCMBB_A001-02000004 |  | 10 |  |  |  | 2001-11-30 | 2001-11-30 | 2002-08-01 | 2002-09-09 | 2002-09-09 |  | 2002-09-20 | 2002-09-24 | 2002-09-24 | 2002-09-24 | 2002-10-16 | 2002-10-23 |  |  | 2002-11-06 |  |  | 2002-11-05 | 2002-11-26 | 2002-11-27 | 2002-11-27
| traveler |  | 11
| measurement file to CERN |  | 12
13
| traveler |  | 14
| measurement file to CERN |  | 15
| HCMBB_A001-02000006 |  | 16 |  |  |  | 2002-05-10 | 2002-05-10 | 2009-09-12 | 2002-09-20 | 2002-10-04 |  | 2002-10-14 | 2002-10-20 | 2002-11-05 | 2002-11-05 | 2002-11-29 | 2002-12-06 |  |  | 2002-11-13 |  |  | 2003-01-16 | 2003-01-27 | 2003-01-29 | 2003-01-29
| traveler |  | 17
| measurement file to CERN |  | 18
| HCMBB_A001-02000007 |  | 19 |  |  |  | 2002-12-12 | 2002-12-12 | 2002-12-17 | 2002-12-20 | 2003-02-03 |  | 2003-02-10 | 2003-03-31 | 2003-04-03 | 2003-04-05 | 2003-04-07 | 2003-04-08 |  |  | 2003-02-26 |  |  | 2003-04-10 | 2003-04-17 | 2003-04-18 | 2003-04-18
| traveler |  | 20
| measurement file to CERN |  | 21 | [17 empty] | 2003-02-26
| HCMBB_A001-02000008 |  | 22 |  |  |  | 2002-12-02 | 2002-12-02 | 2002-12-06 | 2002-12-10 | 2002-12-13 |  | 2003-01-13 | 2003-02-22 | 2003-02-22 | 2003-02-22 | 2003-02-26 | 2003-03-04 |  |  | 2002-12-19 |  |  | 2003-03-20 | 2003-03-20 | 2003-03-21 | 2003-03-21
| traveler |  | 23 | [17 empty] | 2003-01-17 |  |  | 2003-03-20 | 2003-03-20 | 2003-03-21
| measurement file to CERN |  | 24 | [17 empty] | 2002-12-19 |  |  | 2003-03-20 | 2003-03-20 | 2003-03-21
| HCMBB_A001-02000009 |  | 25 |  |  |  | 2002-11-10 | 2002-11-10 | 2002-11-25 | 2002-12-04 | 2003-02-10 | 2003-02-18 | 2003-03-03 | 2003-02-25 | 2003-04-30 | 2003-04-30 | 2003-05-02 | 2003-05-02 |  |  | 2003-02-27 |  |  | 2003-05-06 | 2003-05-17 | 2003-05-19 | 2003-05-19
| traveler |  | 26
| measurement file to CERN |  | 27 | [17 empty] | 2003-02-27
| HCMBB_A001-02000010 |  | 28 |  |  |  | 2002-11-30 | 2002-11-30 | 2002-11-04 | 2002-11-18 | 2002-12-16 |  |  | 2003-03-30 | 2003-04-15 | 2003-04-15 | 2003-04-16 | 2003-04-17 |  |  | 2002-12-05 |  |  | 2003-04-23 | 2003-04-27 | 2003-04-28 | 2003-04-28
| traveler |  | 29
| measurement file to CERN |  | 30 | [17 empty] | 2002-12-05
31
| traveler |  | 32
| measurement file to CERN |  | 33
| HCMBB_A001-02000012 |  | 34 |  |  |  | 2002-08-05 | 2002-08-05 | 2002-10-09 | 2002-10-12 | 2002-10-20 |  | 2003-01-20 | 2003-01-25 | 2003-01-25 | 2003-01-25 | 2003-02-04 | 2003-02-10 |  |  | 2002-10-31 |  |  | 2003-03-27 | 2003-04-01 | 2003-04-02 | 2003-04-02
| traveler |  | 35 | [20 empty] | 2003-03-27 | 2003-04-01 | 2003-04-02
| measurement file to CERN |  | 36 | [20 empty] | 2003-03-27 | 2003-04-01 | 2003-04-02
37
| traveler |  | 38
| measurement file to CERN |  | 39
| HCMBB_A001-02000014 |  | 40 |  |  |  | 2003-01-20 | 2003-01-20 | 2003-02-25 | 2003-02-28 | 2003-03-21 |  |  | 2003-05-20 | 2003-05-21 | 2003-05-21 | 2003-05-22 | 2003-05-23 |  |  | 2003-03-27 |  |  | 2003-05-27 | 2003-05-29 | 2003-06-03
| traveler |  | 41
| measurement file to CERN |  | 42 | [17 empty] | 2003-03-27
43
| traveler |  | 44
| measurement file to CERN |  | 45
46
| traveler |  | 47
| measurement file to CERN |  | 48
49
| traveler |  | 50
| measurement file to CERN |  | 51
52
| traveler |  | 53
| measurement file to CERN |  | 54
55
| traveler |  | 56
| measurement file to CERN |  | 57
Bis | HCMBB_A001-02000020 |  | 58 |  | 2002-12-01 |  | 2002-12-23 | 2002-12-23 | 2003-01-13
| traveler |  | 59
| measurement file to CERN |  | 60
| HCMBB_A001-02000021 |  | 61 |  |  |  | 2003-02-20 | 2003-02-20 | 2003-03-12 | 2003-03-13 | 2003-03-19 | 2003-04-20 | 2003-04-24 | 2003-05-07 | 2003-05-09 | 2003-05-10 | 2003-05-12 | 2003-05-12 |  |  | 2003-03-28 |  |  | 2003-05-19 | 2003-05-22 | 2003-05-23 | 2003-06-03
| traveler |  | 62
| measurement file to CERN |  | 63 | [17 empty] | 2003-03-28
| HCMBB_A001-02000022 |  | 64 |  | 2002-12-23 |  | 2003-05-06 | 2003-05-16 | 2003-05-20 | 2003-05-22 |  |  | 2003-03-31: 2003-06-05; 2003-04-03: 2003-06-05; 2003-04-05: 2003-06-06 |  |  | 2003-06-04
| traveler |  | 65
| measurement file to CERN |  | 66
| HCMBB_A001-02000023 |  | 67 |  |  |  | 2003-03-10 | 2003-03-10 | 2003-03-21 | 2003-03-27 | 2003-04-04 | 2003-04-26
| traveler |  | 68
| measurement file to CERN |  | 69
70
| traveler |  | 71
| measurement file to CERN |  | 72
| HCMBB_A001-02000025 | [8 empty] | 2003-05-13 | 2003-05-20 | 2003-05-31 | 2003-03-31: 2003-05-26
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
[5 empty] | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS | MAGNET ASSEMBLY ERRORS
| HCMBB_A001-02000020 |  | 1 |  | 2002-12-01 |  | 2002-12-23 | 2002-12-23 | 2003-01-13 | 2003-01-18 | 2003-01-23 | [9 empty] | 2003-02-26
| traveler |  | 2
| measurement file to CERN |  | 3 | [17 empty] | 2003-02-26
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
MAINTENANCE
Don't fill the cells below
Process | Last Magnet
25 | 25
Row index for RW magnet
1
CLOSE
Add Process
Remove Process
Resume Process
CLOSE
NEW MAGNET
HIDE MAGNET
HELP
UNHIDE MAGNET
Check TIME
Incomplete Magnets
UPDATE MAGNET
Rework MAGNET
See RW Magnets
MAINTENANCE
Search Process
Delete
OUTPUT
UPDATE DATA
DELIVERY
Data Analysis
SEARCH

## Table Process
PHASE NUMBER | OPERATIONAL PHASES - COLD MASS
1 | Perform inspection collared coil incl. cold bore tube inner diameter ITP10b ITP10b
2 | Install collar/insert shims, insert/yoke shims
3 | Preparation lower half-yoke
4 | Preparation upper half-yoke
5 | Assembly cold mass
6 | Welding
7 | Perform X-ray examinations ITP14
8 | Weld end plates on shrinking cylinder
9 | Solder remaining electric connections
10 | Perform horizontal curvature and vertical straightness measurements ITP16
11 | Machine chamfers at ends of shrinking cylinder
12 | Install and allign spool pieces and heat exchanger tube ITP17
13 | Perform electrical test on Cold Mass Assembly ITP18
14 | Install, allign and weld end covers ITP19
15 | Install, allign and weld support bases and external busbar pipe supports
16 | Allign and weld cold bore and heat exchanger tubes on end covers
17 | Perform warm magnetic measurements ITP21
18 | Realize temporary short circuits
19 | Install and weld interconnect bellows and diode container, close cold mass
20 | Perform final geometric test ITP20
21 | Perform pressure and leak tests ITP23,24
22 | Perform final electrical test ITP25
23 | Prepare cold mass for transportation
24 | Collared Coil Traveler Completed

## Time
| 37635.6364 |  | 4216.2222 |  | 85.75 |  | 37706.75 |  | TOT. AVERAGE (days)
| #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | AVERAGE last | 5 | magnets
| Time between Collared Coil Receipt and X-ray examinations (days) |  | Time between X-ray examinations and warm magnetic measurements (days) |  | Time between warm magnetic measurements and preparation cold mass for transportation (days) |  | Total Assembly Time (days) |  | Delay alarm: with this cell is possible to set for which deviation of time, from the average value of the last magnets, we have a delay alarm. For example 0.1 means 10% more than the average |  |  | 0.1
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
HCMBB_A001-02000002 | 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
HCMBB_A001-02000004 | 37508 | 37508 | 58 | 58 | 21 | 21 | 37587 | 37587
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
HCMBB_A001-02000006 | 37533 | 37533 | 40 | 40 | 77 | 77 | 37650 | 37650
traveler
measurement file to CERN
HCMBB_A001-02000007 | 37655 | 37655 | 23 | 23 | 51 | 51 | 37729 | 37729
traveler
measurement file to CERN
HCMBB_A001-02000008 | 37603 | 37603 | 6 | 6 | 92 | 92 | 37701 | 37701
traveler
measurement file to CERN
HCMBB_A001-02000009 | 37662 | 37662 | 17 | 17 | 81 | 81 | 37760 | 37760
traveler
measurement file to CERN
HCMBB_A001-02000010 | 37606 | 37606 | -11 | undone | 144 | 144 | 37739 | 37739
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
HCMBB_A001-02000012 | 37549 | 37549 | 11 | 11 | 153 | 153 | 37713 | 37713
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
HCMBB_A001-02000014 | 37701 | 37701 | 6 | 6 | -37707 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
HCMBB_A001-02000020 | -37591 | undone | 0 | undone | 0 | undone | -37591 | undone
traveler
measurement file to CERN
HCMBB_A001-02000021 | 37699 | 37699 | 9 | 9 | 67 | 67 | 37775 | 37775
traveler
measurement file to CERN
HCMBB_A001-02000022 | -37613 | undone | 37776 | 37776 | -37776 | undone | -37613 | undone
traveler
measurement file to CERN
HCMBB_A001-02000023 | 37715 | 37715 | -37715 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
HCMBB_A001-02000025 | 37761 | 37761 | -37761 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
| 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
HCMBB__A001-03000450 | 0 | undone | 0 | undone | 0 | undone | 0 | undone
traveler
measurement file to CERN
Note on R2: Insert integer number between 1 and 20
CLOSE TIME
HIDE MAGNET
HELP
UNHIDE MAGNET
Main Window

## Report
ANSALDO
Magnet | Last Process done | Date
CLOSE

## Time Table
Date | Cold Mass | Process
Close

## Removed
TOT. REMOVED PROCESSES
0
Removed Processes
traveler
measurement file to CERN
HCMBB_A001-02000002
traveler
measurement file to CERN
traveler
measurement file to CERN
HCMBB_A001-02000004
traveler
measurement file to CERN
traveler
measurement file to CERN
HCMBB_A001-02000006
traveler
measurement file to CERN
HCMBB_A001-02000007
traveler
measurement file to CERN
HCMBB_A001-02000008
traveler
measurement file to CERN
HCMBB_A001-02000009
traveler
measurement file to CERN
HCMBB_A001-02000010
traveler
measurement file to CERN
traveler
measurement file to CERN
HCMBB_A001-02000012
traveler
measurement file to CERN
traveler
measurement file to CERN
HCMBB_A001-02000014
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
HCMBB_A001-02000020
traveler
measurement file to CERN
HCMBB_A001-02000021
traveler
measurement file to CERN
HCMBB_A001-02000022
traveler
measurement file to CERN
HCMBB_A001-02000023
traveler
measurement file to CERN
traveler
measurement file to CERN
HCMBB_A001-02000025
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN
traveler
measurement file to CERN

## DELIVERY
update graph
go back

## readme
NEW MAGNET | allows to insert new magnets and the dates in which a certain process is done over a certain magnet. |  | Rework Magnet | allows to insert dates relative to a reworked magnet
>Insert the type of the magnet (A/B) and the serial number (1-450) of the magnet that you want to rework
> Insert the letter (A or B) that defines the type of the dipole
>Insert the first process that you want to repeat to rework the magnet (1-26)
>Insert the numbers that define the cold mass name. Example for HCMBB_A001-03000003 you have to insert 3
>Push the button UPDATE MAGNET to insert new dates
| >Insert the number (1-26) of the process chosen from a list. For example if you are interested in process "Assembly cold mass" you have to digit 6 |  | See RW Magnets | shows magnets with assembly errors before reworking
|  |  | Incomplete Magnets | print a report about status of pending processes (name of the magnet, last process and date in which it was done, date of holding point if done)
| 6 | Assembly cold mass
| >Insert the date in which the process is done paying attention that the program requires the date or in form dd/mm or dd/mm/yy. Example: 24 October 2002 insert 24/10/02 or 24/10 |  | To see the update report push Incomplete Magnets button
|  |  | Check TIME | shows the gap of time between processes and total time for collaring each magnet
|  |  | Time Table | It shows all the processes done between two dates specified by the user.
UPDATE MAGNET | allows to insert new dates in which certain processes are done over a certain magnet already inserted.
It shows the graph in which it is compared the expected delivery of cold masses and the real production
User has not to insert the date directly in the cells but he has to use the INPUT buttons
This program was done by Alberto Schiappapietra mailto:Alberto.Schiappapietra@cern.ch
it opens the menu dedicated to the excel sheet maintenance
Add Process | It allows to add a process to the sheet
Removed Process | It allows to delete a process from the sheet (deleted
processes are stored in the sheet "Removed")
Resume Process | It allows to add a process previously removed and
stored in the sheet "Removed". All the dates stored
in the process before deleting are kept
See RW Magnets | shows magnets with assembly errors before reworking
It allows to delete a data erroneously inserted
UPDATE DATA | it allows to read the output file sent weekly by email from the inspectors and update the MACRO with the new data.
OUTPUT | it creates an output file.txt easy to send by email.
This program was done by Alberto Schiappapietra mailto:Alberto.Schiappapietra@cern.ch
Close
NEW MAGNET
UPDATE MAGNET
Rework MAGNET
See RW Magnets
Close
MAINTENANCE
Add Process
Remove Process
Resume Process
>>
Incomplete Magnets
Check TIMES
See RW Magnets
Search Process
Delete
Delivery
UPDATE DATA
OUTPUT
USER'S GUIDE

## delivery data
| serial number | month | expected delivery | magnet assembled
2002 | 1 | 2002-01-01 | 2 | 0
| 2 | 2002-02-01 | 2 | 0
| 3 | 2002-03-01 | 3 | 0
| 4 | 2002-04-01 | 3 | 0
| 5 | 2002-05-01 | 3 | 0
| 6 | 2002-06-01 | 3 | 0
| 7 | 2002-07-01 | 3 | 0
| 8 | 2002-08-01 | 3 | 0
| 9 | 2002-09-01 | 4 | 0
| 10 | 2002-10-01 | 5 | 0
| 11 | 2002-11-01 | 7 | 0
| 12 | 2002-12-01 | 9 | 0
2003 | 13 | 2003-01-01 | 11 | 0
| 14 | 2003-02-01 | 13 | 0
| 15 | 2003-03-01 | 16 | 0
| 16 | 2003-04-01 | 18 | 0
| 17 | 2003-05-01 | 21 | 0
| 18 | 2003-06-01 | 24 | 0
| 19 | 2003-07-01 | 28 | 0
| 20 | 2003-08-01 | 32 | 0
| 21 | 2003-09-01 | 36 | 0
| 22 | 2003-10-01 | 40 | 0
| 23 | 2003-11-01 | 46 | 0
| 24 | 2003-12-01 | 52 | 0
2004 | 25 | 2004-01-01 | 60 | 0
| 26 | 2004-02-01 | 68 | 0
| 27 | 2004-03-01 | 76 | 0
| 28 | 2004-04-01 | 85 | 0
| 29 | 2004-05-01 | 98 | 0
| 30 | 2004-06-01 | 109 | 0
| 31 | 2004-07-01 | 120 | 0
| 32 | 2004-08-01 | 133 | 0
| 33 | 2004-09-01 | 145 | 0
| 34 | 2004-10-01 | 155 | 0
| 35 | 2004-11-01 | 165 | 0
| 36 | 2004-12-01 | 175 | 0
2005 | 37 | 2005-01-01 | 186 | 0
| 38 | 2005-02-01 | 198 | 0
| 39 | 2005-03-01 | 210 | 0
| 40 | 2005-04-01 | 222 | 0
| 41 | 2005-05-01 | 237 | 0
| 42 | 2005-06-01 | 249 | 0
| 43 | 2005-07-01 | 261 | 0
| 44 | 2005-08-01 | 273 | 0
| 45 | 2005-09-01 | 282 | 0
| 46 | 2005-10-01 | 294 | 0
| 47 | 2005-11-01 | 305 | 0
| 48 | 2005-12-01 | 317 | 0
2006 | 49 | 2006-01-01 | 329 | 0
| 50 | 2006-02-01 | 339 | 0
| 51 | 2006-03-01 | 350 | 0
| 52 | 2006-04-01 | 365 | 0
| 53 | 2006-05-01 | 377 | 0
| 54 | 2006-06-01 | 387 | 0
| 55 | 2006-07-01 | 401 | 0
| 56 | 2006-08-01 | 413 | 0
| 57 | 2006-09-01 | 416 | 0
| 58 | 2006-10-01 | 416 | 0
| 59 | 2006-11-01 | 416 | 0
| 60 | 2006-12-01 | 416 | 0
2007 | 61 | 2007-01-01 | 416 | 0
| 62 | 2007-02-01 | 416 | 0
| 63 | 2007-03-01 | 416 | 0
| 64 | 2007-04-01 | 416 | 0
| 65 | 2007-05-01 | 416 | 0
| 66 | 2007-06-01 | 416 | 0
| 67 | 2007-07-01 | 416 | 0
| 68 | 2007-08-01 | 416 | 0
| 69 | 2007-09-01 | 416 | 0
| 70 | 2007-10-01 | 416 | 0
| 71 | 2007-11-01 | 416 | 0
| 72 | 2007-12-01 | 416 | 0
0