Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 35 and 36 - 2004

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | 2128 inner and 2127 outer |
| Pole assembled |  | Up to 2124 |
| Collared coils finished |  | 109 items |
| Cold masses welded | 3 welded | 103 items |
| Cold masses in course of finishing | 6 | - |
| Ready for pressure and leak test | - | - |
| Cold masses ready for delivery | 2 | - |
| Cold masses delivered |  | 95 items |

Short summary (tooling, NCRs, outstanding problems): Problem on Servorobot system ( substituted one component) 1 week lost One cold mass welded has been opened (2087)