## Tabelle1
SERIES Summary and Status of NC Reports (NCR)
BNN Order-No. N.911004
| Scope of application | BG | BNN Serial No. | CERN Serial No. | Kind of Document | Reason / Remarks | Decision of Dispositon | Date of NCR | BNN Status | CERN approval | NCR work status | Remarks
NCR3003_0 | CM3033 | I | N-3009I | HCMB__A010-03003009 | NC Report | Damage insulation of inner layer coil N-3009I during crane handling | repair | 2003-04-01 | signed | signed | completed | WÜ
NCR3005_0 | CM3031-CM3033 | I | N-3001I up to N-3010 | HCMB__A010-03003001 up to HCMB__A010-03003010 | NC Report | Spacer for inner layer coil N-03001I up to N-3010I, lamination damagec | reject and replace | 2003-04-10 | signed | signed | completed | covers NCR3001_0, NCR3002_0 no replacement so far WÜ
NCR3008_0 | CM3031 | E | N-3001E N-3002E N-3003E N-3004E | HCMB__A001-03000031 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3009_0 | CM3032 | E | N-3005E N-3006E N-3006E N-3008E | HCMB__A001-03000032 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3010_0 | CM3033 | E | N-3009E N-3010E N-3011E N-3012E | HCMB__A001-03000033 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3011_0 | CM3034 | E | N-3013E N-3014E N-3015E N-3016E | HCMB__A001-03000034 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3012_0 | CM3035 | E | N-3018E N-3019E N-3020E | HCMB__A001-03000035 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3013_0 | CM3036 | E | N-3021E N-3022E N-3023E N-3024E | HCMB__A001-03000036 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3014_0 | CM3037 | E | N-3025E N-3026E N-3027E N-3028E | HCMB__A001-03000037 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3015_0 | CM3038 | E | N-3029E N-3030E N-3031E N-3032E | HCMB__A001-03000038 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3016_0 | CM3039 | E | N-3033E N-3034E N-3035E N-3036E | HCMB__A001-03000039 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3017_0 | CM3040 | E | N-3037E N-3038E N-3039E N-3040E | HCMB__A001-03000040 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3018_0 | CM3041 | E | N-3041E N-3042E N-3043E N-3044E | HCMB__A001-03000041 | NC Report | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | use-as-is | 2003-04-23 | signed | signed | completed | WÜ
NCR3019_0 | CM3041 | I | N-3041I | HCMB__A001-03000041 | NC Report | Rest of carton glued on the cable 01B10199E for inner layer coil | repair | 2003-04-29 | signed | signed | completed | WÜ
NCR3021_0 | CM3032 | E | N-3006E | HCMB__A001-03000032 | NC Report | Cutting layer end from winding machine too short | use-as-is | 2003-05-12 | signed | signed | completed | completed when Dipole assembly WÜ
NCR3025_0 | CM3040 | P | N-3037P | HCMB__A001-03000040 | NC Report | Damage of inner layer coil N-3037I during curing of pole N-3037P | repair | 2003-05-22 | signed | signed | completed | WÜ
NCR3030_0 | CM3034 | U | NB3034 | HCMBB_A001_03000034 | NC Report | Locking device for pressure bolt | use-as-is | 2003-06-30 | signed | signed | completed | Zz
NCR3038_0 | CM3038 | T | NB3038M | HCMBB_A001_03000038 | NC Report | Sextupol, insulation resistance | repair | 2003-07-14 | signed | signed | completed | no replacement so far Zz
NCR3040-0 | CM3040 | P | N-3040P | HCMB__A001-03000040 | NC Report | Damage of inner layer coil N-3040I during curing of pole N-3040P | repair | 2003-06-23 | signed | signed | completed | WÜ
NCR3041_0 | CM3037 | R | NB3037M | HCMBBRA001-03000037 | NC Report | Spacer into the CS Endplate according to drawing 227545b and 227546b | accept as is | 2003-06-26 | signed | signed | completed | Zz
NCR3042_0 | CM3038 | R | NB3038M | HCMBBRA001-03000038 | NC Report | Spacer into the CS Endplate according to drawing 227545b and 227546b | accept as is | 2003-06-26 | signed | signed | completed | Zz
NCR3043_0 | CM3039 | R | NB3039M | HCMBBRA001-03000039 | NC Report | Spacer into the CS Endplate according to drawing 227545b and 227546b | accept as is | 2003-06-26 | signed | signed | completed | Zz
NCR3044_0 | CM3041 | R | NB3041M | HCMBBRA001-03000041 | NC Report | Spacer into the CS Endplate according to drawing 227545b and 227546b | accept as is | 2003-06-26 | signed | signed | completed | Zz
NCR3045_0 | CM3036 | T | NB3036M | HCMBBRA001-03000036 | NC Report | Diode - cracked wires | repair | 2003-06-27 | signed | signed | completed | Zz
NCR3045_0 | CM3036 | T | NB3036M | HCMBBRA001-03000036 | NC Report | Diode - cracked wires | repair | 2003-06-27 | signed | signed | completed | Zz
NCR3051_0 | CM3039 | T | NB3039M | HCMBBRA001-03000039 | NC Report | Shape out of tolerance | repair | 2003-07-08 | signed | signed | completed | Zz
NCR3052_0 | CM3042 | T | NB3042M | HCMBBRA001-03000042 | NC Report | Shape out of tolerance | repair | 2003-07-10 | signed | signed | completed | Zz
NCR3053_0 | CM3044 | T | NA3044M | HCMBALA001-03000044 | NC Report | Shape out of tolerance | repair | 2003-07-10 | signed | signed | completed | Zz no replacement so far
NCR3055_0 | CM3045 | S | NA3045M | HCMBALA001-03000045 | NC Report | Twist under the press | repair | 2003-07-14 | signed | signed | completed | Zz no replacement so far
NCR3057_A | CM3044 | T | NA3044M | HCMBALA001-03000044 | NC Report | Shape out of tolerance (again) | repair | 2003-09-16 | signed | signed | completed | Zz
NCR3058_0 | CM3048 | R | NA3048M | HCMBALA001-03000048 | NC Report | Busbar M1 - electrical defekt | repair | 2003-07-23 | signed | signed | completed | Zz
NCR3060_A | CM3046 | M | NA3046M | HCMBALA001-03000046 | NC Report | Shape out of tolerance | repair | 2003-08-06 | signed | signed | completed | ok acc. e-mail Mr. Miles 06.08.03 Zz
NCR3061_A | CM3043 | T | NA3043M | HCMBARA001-03000043 | NC Report | X-line - leckage on NCS-side | repair | 2003-08-20 | signed | see CERN e-mail from 01.09.2003 | completed | e-mail Miles 1.9.03 Zz
NCR3062_0 | CM3067 | E | N-3045E | HCMB__A001-03000067 | NC Report | Damage of outer layer coil N-3145E, cable ID 02K15001A | repair | 2003-06-30 | signed | signed | completed | WÜ
NCR3063_A | CM3039 | T | NB3039M | HCMBBRA001-03000039 | NC Report | Shape out of tolerance (again) | repair | 2003-09-12 | signed | signed | completed | Zz
NCR3064_0 | CM3060 | P | N-3119P | HCMB__A001-03000060 | NC Report | Dipol 2 upper pol, colour changing of quench heater wires | use-as-is | 2003-08-11 | signed | signed | completed | ok acc. e-mail Mr. Miles 11.08.03 WÜ
NCR3068_A | CM3076 | I | N-3183I | HCMB__AI76-01B10268B | NC Report | Damage of inner layer coil N-3183I, cable ID 01B10268B | repair | 2003-08-20 | signed | signed | completed | Elektrische Nachmessung in Zeitz o.k. WÜ
NCR3075_0 | CM3068 | C | N-3068C | HCMB__A001-03000068 | NC Report | Lower insulation resistance between 2 QH's in aperture 1 | repair | 2003-09-04 | signed | signed | completed | WÜ
NCR3076_0 | CM3071 | C | N-3071C | HCMB__A001-03000071 | NC Report | Weakness of insulation QH YT111- against upper pole in aperture 1 | repair | 2003-09-15 | signed | signed | completed | WÜ
NCR3077_0 | CM3068 | P | N-3149P | HCMB__A001-03000068 | NC Report | Dipol 1 upper pol, colour changing of quench heater wires | use-as-is | 2003-09-05 | signed | signed | completed | ok like e-mail Mr. Miles 11.08.03 WÜ
NCR3078_0 | CM3047 | T | NA3047M | HCMBALA001-03000047 | NC Report | Shape out of tolerance | repair | 2003-09-11 | signed | signed | completed | Zz
NCR3079_0 | CM3053 | T | NA3053M | HCMBA_A001-03000053 | NC Report | Shape out of tolerance | repair | 2003-09-12 | signed | signed | completed | Zz
NCR3080_0 | CM3063 | T | NA3063M | HCMBA_A001-03000063 | NC Report | Stacking factor for laminations Stacking factor for inserts | use-as-is | 2003-09-09 | signed | signed | completed | mail Mr. Miles 09.09.03 Zz
NCR3083_0 | CM3055 | T | NA3055M | HCMBA_A001-03000055 | NC Report | Shape out of tolerance | repair | 2003-10-07 | signed | signed | completed | Zz
NCR3085_0 | CM3056 | T | NA3056M | HCMBA_A001-03000056 | NC Report | Shape out of tolerance | repair | 2003-12-11 | signed | signed | completed | Fax from Mr. Miles / 18.12.03 Zz
NCR3086_0 | CM3058 | T | NA3058M | HCMBA_A001-03000058 | NC Report | Tube ends out of tolerance | repair | 2003-10-09 | signed | signed | completed | Zz
NCR3087_0 | CM3055 | M | NA3055M | HCMBA_A001-03000055 | NC Report | Final shape measurement of lower quality | use-as-is | 2003-10-07 | signed | signed | completed | Zz
NCR3088_A | CM3085 | T | N_3085M | HCMB__A001-03000085 | NC Report | Shape out of tolerance | repair | 2004-02-27 | signed | signed | completed | Zz
NCR3089_0 | CM3035 | P | N-3019P | Damage of the pole N-3019P (coil outer layer N-3019E and coil innerlayer N-3019I) during a handling operation | NC Report | Accident on pole N-3019P | reject and replace | reserved by Weinhard | signed | signed | completed | compensation delivery by CERN WÜ
NCR3090_0 | CM3075 | P | N-3079P | HCMB__A001-03000075 | NC Report | Voltage breakdown in the outer layer N-3179E of the upper pole N-3179P | repair | 2003-11-06 | signed | signed | completed | WÜ
NCR3091_0 | CM3087 | I | N-3225I | HCMBA_A001-03000087 | NC Report | Inner layer N-3225I - excess end | use as is | 2003-09-26 | signed | signed | completed | WÜ
NCR3092_0 | CM3090 | I | N-3237I | HCMBA_A001-03000090 | NC Report | Inner layer N-3237I - excess end | use as is | 2003-09-26 | signed | signed | completed | WÜ
NCR3093_0 | CM3091 | I | N-3242I | HCMBA_A001-03000091 | NC Report | Inner layer N-3242I - excess end | use as is | 2003-09-26 | signed | signed | completed | WÜ
NCR3095_A | CM3060 | S | NA3060M | HCMBA_A001-03000060 | NC Report | Shape out of tolerance | repair | 2003-11-13 | signed | signed | completed | Zz
NCR3096_0 | CM3092 | I | N-3247I | HCMBA_A001-03000092 | NC Report | Inner layer N-3247I - excess end | use as is | 2003-09-26 | signed | signed | completed | WÜ
NCR3097_0 | CM3077 | I | N-3185I | HCMBA_A001-03000077 | NC Report | Inner layer N-3185I - short circuit between two threads of the 9th layer | repair | 2003-09-29 | signed | signed | completed | WÜ
NCR3099_0 | CM3053 | T | NA3053M | HCMBA_A001-03000053 | NC Report | X-line - leckage on NCS-side | repair | 2003-10-16 | signed | signed | completed | Zz
NCR3102_0 | CM3056 | T | NA3056M | HCMBALA001-03000056 | NC Report | Leck im IFS-Deckel | repair | 2003-10-09 | signed | not required | completed | Zz
NCR3103_0 | CM3102 | E | N-3286E | HCMB__A001-03000102 | NC Report | Damage of cable | reject and replace | 2003-10-17 | signed | signed | completed | WÜ
NCR3104_0 | CM3071 | T | NB3071M | HCMBB_A001-03000071 | NC Report | YT111+ too short | repair | 2003-10-15 | signed | signed | completed | Zz
NCR3106_0 | CM3056 | V | NA3056M | HCMBALA001-03000056 | NC Report | X-type internal equiped bellow - leakage on NCS-side | repair | 2003-10-23 | signed | signed | completed | Zz
NCR3114_0 | CM3081 | T | N_3081M | HCMB__A001-03000081 | NC Report | Shape out of tolerance | repair | 2003-11-17 | signed | signed | completed | Zz
NCR3116_0 | CM3040 | V | NB3040M | HCMBBLA001-03000040 | NC Report | Diode cable | repair | 2003-11-17 | signed | signed | completed | Zz
NCR3119_0 | CM3088 |  | NB3088M | HCMBB_A001-03000088 | Receiving Inspection and Testing | Sextupol, protection cap | repair | 2003-12-08 | signed | signed | completed | Zz
NCR3120_0 | CM3031 | T | NB3031M | HCMBB_A001-03000031 | NC Report | No diode assembled | repair | 2003-11-27 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3122_0 | CM3032 | V | NB3032M | HCMBB_A001-03000032 | NC Report | X-type internal equiped bellow - leakage on NCS-side | repair | 2003-12-02 | signed | signed | completed | Zz
NCR3123_0 | CM3032 | T | NB3032M | HCMBB_A001-03000032 | NC Report | No diode assembled | repair | 2003-12-01 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3124_0 | CM3033 | T | NB3033M | HCMBB_A001-03000033 | NC Report | No diode assembled | repair | 2003-12-01 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3126_0 | CM3087 | T | NB3087M | HCMBB_A001-03000087 | NC Report | No diode assembled | repair | 2003-12-02 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3127_0 | CM3088 | T | NB3088M | HCMBB_A001-03000088 | NC Report | No diode assembled | repair | 2003-12-02 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3128_0 | CM3089 | T | NB3089M | HCMBB_A001-03000089 | NC Report | No diode assembled | repair | 2003-12-02 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3129_0 | CM3082 | T | NB3082M | HCMBB_A001-03000082 | NC Report | No diode assembled | repair | 2003-12-02 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3130_0 | CM3090 | T | NB3090M | HCMBB_A001-03000090 | NC Report | No diode assembled | repair | 2003-12-02 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3131_A | CM3097 | M | N_3097M | HCMB__A001-03000097 | NC Report | Shape out of tolerance | repair | 2004-02-19 | signed | signed | completed | Zz
NCR3132_0 | CM3098 | T | N_3098M | HCMB__A001-03000098 | NC Report | Shape out of tolerance | repair | 2004-01-15 | signed | signed | completed | Zz
NCR3134_0 | CM3091 | T | NB3091M | HCMBB_A001-03000091 | NC Report | No diode assembled | repair | 2003-12-11 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3135_0 | CM3092 | T | NB3092M | HCMBB_A001-03000092 | NC Report | No diode assembled | repair | 2003-12-11 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3136_0 | CM3093 | T | NB3093M | HCMBB_A001-03000093 | NC Report | No diode assembled | repair | 2003-12-11 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3138_0 | CM3094 | T | NB3094M | HCMBB_A001-03000094 | NC Report | No diode assembled | repair | 2003-12-11 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3139_0 | CM3092 | T | N_3092M | HCMB__A001-03000092 | NC Report | Shape out of tolerance | repair | 2003-12-12 | signed | signed | completed | Zz
NCR3140_0 | CM3095 | T | N_3095M | HCMB__A001-03000095 | NC Report | Shape out of tolerance | repair | 2004-01-12 | signed | signed | completed | Zz
NCR3141_0 | CM3168 | S | NA3168M | HCMBA_A001-03000168 | NC Report | Measurement of inner gap | use as is | 2004-04-30 | signed | signed | completed | Zz
NCR3142_0 | CM3099 | T | N_3099M | HCMB__A001-03000099 | NC Report | Shape out of tolerance | repair | 2004-01-14 | signed | signed | completed | Zz
NCR3143_0 | CM3093 | V | NB3093M | HCMBB_A001-03000093 | NC Report | X-type internal equiped bellow - leakage on NCS-side | repair | 2004-01-13 | signed | signed | completed | Zz
NCR3145_0 | CM3106 | T | NA3106M | HCMBALA001-03000106 | NC Report | No diode assembled | repair | 2004-02-20 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3147_0 | CM3095 | T | NB3095M | HCMBB_A001-03000095 | NC Report | No diode assembled | repair | 2003-12-11 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3148_0 | CM3096 | T | NB3096M | HCMBB_A001-03000096 | NC Report | No diode assembled | repair | 2003-12-11 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3149_0 | CM3100 | T | NB3100M | HCMBB_A001-03000100 | NC Report | No diode assembled | repair | 2003-12-11 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3150_0 | CM3079 | T | NA3079M | HCMBA_A001-03000079 | NC Report | Busbar "Half-Moon" connections | repair | 2004-01-12 | signed | signed | completed | Zz
NCR3152_0 | CM3101 | T | NA3101M | HCMBA_A001-03000101 | NC Report | No diode assembled | repair | 2004-01-16 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3153_0 | CM3103 | T | NA3103M | HCMBA_A001-03000103 | NC Report | No diode assembled | repair | 2004-01-16 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3154_0 | CM3109 | T | N_3109M | HCMB__A001-03000109 | NC Report | Shape out of tolerance | use as is | 2004-01-20 | signed | signed | completed | Zz
NCR3155_0 | CM3111 | T | NA3111M | HCMBALA001-03000111 | NC Report | Shape out of tolerance | use as is | 2004-01-20 | signed | signed | completed | Zz
NCR3156_0 | CM3104 | T | NA3104M | HCMBA_A001-03000104 | NC Report | No diode assembled | repair | 2004-01-20 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3157_0 | CM3105 | T | NA3105M | HCMBA_A001-03000105 | NC Report | No diode assembled | repair | 2004-01-20 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3159_0 | CM3146 | E | N-3462E | HCMB__A001-03000146 | NC Report | Damage of outerlayer N-3462E | compensition delivery by CERN | 2004-01-29 | signed | signed | completed | WÜ
NCR3160_0 | CM3049 | V | NB4049M | HCMBARA001-03000049 | NC Report | Tube N-Line pushed in | repair | 2004-01-26 | signed | signed | completed | Zz
NCR3162_0 | CM3107 | T | NA3107M | HCMBA_A001-03000107 | NC Report | No diode assembled | repair | 2004-01-28 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3163_0 | CM3109 | T | NA3109M | HCMBA_A001-03000109 | NC Report | No diode assembled | repair | 2004-01-28 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3164_0 | CM3075 | S | NB3075M | HCMBB_A001-03000075 | NC Report | Busbar M1 - electrical defekt | reject and replace | 2004-01-29 | signed | signed | completed | Zz
NCR3165_0 | CM3149 | E | N-3474E | HCMB__A001-03000149 | NC Report | wrong endspacer on CS | repair | 2004-01-30 | signed | signed | completed | WÜ
NCR3166_0 | CM3097 | T | NB3097M | HCMBB_A001-03000097 | NC Report | No diode assembled | repair | 2004-02-02 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3167_0 | CM3098 | T | NB3098M | HCMBB_A001-03000098 | NC Report | No diode assembled | repair | 2004-02-02 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3168_0 | CM3099 | T | NB3099M | HCMBB_A001-03000099 | NC Report | No diode assembled | repair | 2004-02-02 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3169_0 | CM3102 | P | N-3102C | HCMB__A001-03000102 | NC Report | Permuted cables (colours) on pole N-3285P (connection side) of collared coil N-3102C | rework | 2004-02-09 | signed | signed | completed | WÜ
NCR3170_0 | CM3108 | T | NA3108M | HCMBA_A001-03000108 | NC Report | No diode assembled | repair | 2004-02-05 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3171_0 | CM3110 | T | NA3110M | HCMBA_A001-03000110 | NC Report | No diode assembled | repair | 2004-02-05 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3172_0 | CM3111 | T | NA3111M | HCMBA_A001-03000111 | NC Report | No diode assembled | repair | 2004-02-05 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3175_0 | CM3075 | T | NB3075M | HCMBBLA001-03000075 | NC Report | No diode assembled | repair | 2004-02-13 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3176_0 | CM3110 | T | NB3085M | HCMBBLA001-03000085 | NC Report | No diode assembled | repair | 2004-02-13 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3177_0 | CM3112 | T | NA3112M | HCMBA_A001-03000112 | NC Report | No diode assembled | repair | 2004-02-13 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3178_0 | CM3113 | T | NA3113M | HCMBA_A001-03000113 | NC Report | No diode assembled | repair | 2004-02-13 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3179_0 | CM3114 | T | NA3114M | HCMBA_A001-03000114 | NC Report | No diode assembled | repair | 2004-02-13 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3182_0 | CM3124 | S | NB3124M | HCMBB_A001-03000124 | NC Report | Busbar M2 - electrical defekt | reject and replace | 2004-03-10 | signed | signed | completed | Zz
NCR3183_0 | CM3135 | P | N-3420P | HCMB__A001-03000135 | NC Report | Red alarm during the magnetic measurements | repair | 2004-02-18 | signed | signed | completed | WÜ
NCR3184_0 | CM3159 | I | N-3515i | HCMB__A001-03000159 | NC Report | Damage of the inner layer N-3515i | reject and replace | 2004-02-20 | signed | signed | completed | WÜ
NCR3185_0 | CM3126 | T | NB3126M | HCMBB_A001-03000126 | NC Report | No diode assembled | repair | 2004-02-19 | signed | not required | completed | NCR ohne CERN-Unterschrift in Enddoku geben (Hr.Miles 20.11.03) Zz
NCR3186_0 | CM3118 | T | NB3118M | HCMBBLA001-03000118 | NC Report | Shape out of tolerance | use as is | 2004-02-26 | signed | signed | completed | Zz
NCR3189_0 | CM3126 | M | NB3126M | HCMBBLA001-03000085 | NC Report | Shape out of tolerance | use as is | 2004-02-19 | signed | signed | completed | Zz
NCR3191_A | CM3147 | P | N-3466P | HCMB__A001-03000147 | NC Report | Electrical breakthrough in the collared coil N-3147C | repair | 2004-02-20 | signed | signed | completed | WÜ
NCR3192_0 | CM3035 | E | N-3019EA | HCMB__A001-03000035 | NC Report | Modification of the spacer for the outer layer N-3019EA | use as is | reserved for Mr. Weinhard | signed | signed | completed | WÜ
NCR3195_0 | CM3005_CM3006_CM3007_CM3008_CM3009_CM3010_CM3011_CM3012_CM3013_CM3014_CM3015_CM3016_CM3017_CM3018_CM3019_CM3020_CM3021_CM3022_CM3023_CM3024_CM3025_CM3029_CM3030_CM3031_CM3032_CM3033_CM3039_CM3040_CM3043_CM3044_CM3045_CM3046_CM3047_CM3048_CM3049_CM3050_CM3051_CM3052_CM3053_CM3054_CM3055_CM3056_CM3057_CM3058_CM3059_CM3060_CM3061_CM3062_CM3063_CM3064_CM3065_CM3066_CM3068_CM3069_CM3070_CM3071_CM3072_CM3073_CM3074_CM3075_CM3076_CM3077_CM3078_CM3079_CM3080_CM3081_CM3082_CM3083_CM3084_CM3085_CM3086_CM3087_CM3088_CM3089_CM3090_CM3091_CM3092_CM3093_CM3094_CM3095_CM3096_CM3097_CM3098_CM3099_CM3100_CM3101_CM3103_CM3104_CM3105_CM3106_CM3107_CM3108_CM3109_CM3110_CM3111_CM3112_CM3113_CM3114_CM3116_CM3117_CM3118_CM3119_CM3120_CM3121_CM3122_CM3123_CM3124_CM3125_CM3126_CM3127_CM3129 | T | see list | see list | NC Report | Sextupoles | use as is | 2004-03-17 | signed | sigmed | completed | Zz
NCR3196_0 | CM3150 | M | NA3150M | HCMB__A001-03000150 | NC Report | Wire YT221+ insulation damaged | repair | 2004-03-18 | signed | sigmed | completed | Zz
NCR3198_0 | CM3155 | V | NB3155M | HCMBBLA001-03000155 | NC Report | Measurement of the magnetic field | use as is | 2004-03-26 | signed | signed | completed | Zz
NCR3200_0 | CM3169 | I | N-3556I | HCMB__A001-03000169 | NC Report | Damage of the inner layer N-3556i during cutting the layer jump | reject and replace | 2004-03-11 | signed | signed | completed | WÜ
NCR3201_0 | CM3171 | E | N-3562E | HCMB__A001-03000171 | NC Report | Outer layer with shifted layer and not kept curing times | use as is | 2004-03-12 | signed | signed | completed | WÜ
NCR3202_0 | CM3156 | C | N-3156C | HCMB__A001-03000156 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-29 | signed | signed | completed | WÜ
NCR3203_0 | CM3152 | C | N-3152C | HCMB__A001-03000152 | NC Report | Installation of CPS in stainless steel | repair | 2004-04-07 | signed | signed | completed | WÜ
NCR3204_0 | CM3154 | C | N-3154C | HCMB__A001-03000154 | NC Report | Installation of CPS in stainless steel | repair | 2004-04-07 | signed | signed | completed | WÜ
NCR3205_0 | CM3160 | C | N-3160C | HCMB__A001-03000160 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-31 | signed | signed | completed | WÜ
NCR3207_0 | CM3148 | C | N-3148C | HCMB__A001-03000148 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-31 | signed | signed | completed | WÜ
NCR3208_0 | CM3140 | C | N-3140C | HCMB__A001-03000140 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-31 | signed | signed | completed | WÜ
NCR3209_0 | CM3151 | C | N-3151C | HCMB__A001-03000151 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-31 | signed | signed | completed | WÜ
NCR3210_0 | CM3150 | C | N-3150C | HCMB__A001-03000150 | NC Report | Installation of CPS in stainless steel | repair | 2004-04-02 | signed | signed | completed | WÜ
NCR3211_0 | CM3067 | C | N-3067C | HCMB__A001-03000067 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-31 | signed | signed | completed | WÜ
NCR3212_0 | CM3153 | C | N-3153C | HCMB__A001-03000153 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-31 | signed | signed | completed | WÜ
NCR3213_0 | CM3144 | C | N-3144C | HCMB__A001-03000144 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-31 | signed | signed | completed | WÜ
NCR3214_0 | CM3147 | C | N-3147C | HCMB__A001-03000147 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-17 | signed | signed | completed | WÜ
NCR3215_0 | CM3102 | C | N-3102C | HCMB__A001-03000102 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-22 | signed | signed | completed | WÜ
NCR3216_0 | CM3128 | C | N-3128C | HCMB__A001-03000128 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-22 | signed | signed | completed | WÜ
NCR3217_0 | CM3134 | C | N-3134C | HCMB__A001-03000134 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-23 | signed | signed | completed | WÜ
NCR3218_0 | CM3149 | C | N-3149C | HCMB__A001-03000149 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-23 | signed | signed | completed | WÜ
NCR3219_0 | CM3139 | C | N-3139C | HCMB__A001-03000139 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-23 | signed | signed | completed | WÜ
NCR3220_0 | CM3143 | C | N-3143C | HCMB__A001-03000143 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-23 | signed | signed | completed | WÜ
NCR3221_0 | CM3141 | C | N-3141C | HCMB__A001-03000141 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-29 | signed | signed | completed | WÜ
NCR3222_0 | CM3142 | C | N-3142C | HCMB__A001-03000142 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-29 | signed | signed | completed | WÜ
NCR3223_0 | CM3145 | C | N-3145C | HCMB__A001-03000145 | NC Report | Installation of CPS in stainless steel | repair | 2004-03-29 | signed | signed | completed | WÜ
NCR3224_0 | CM3138 | C | N-3138C | HCMB__A001-03000138 | NC Report | Installation of CPS in stainless steel | repair | 2004-04-02 | signed | signed | completed | WÜ
NCR3225_0 | CM3137 | C | N-3137C | HCMB__A001-03000137 | NC Report | Installation of CPS in stainless steel | repair | 2004-04-07 | signed | signed | completed | WÜ
NCR3230_0 | CM3031__M3032__CM3033__CM3034__CM3035__CM3036__CM3037__CM3038__CM3039__CM3040__CM3041__CM3042__CM3043__CM3044__CM3045__CM3046__CM3047__CM3048__CM3049__CM3050__CM3051__CM3052__CM3053__CM3054__CM3055__CM3056__CM3057__CM3058__CM3059__CM3060__CM3061__CM3062__CM3063__CM3064__CM3065__CM3066__CM3067__CM3068__CM3069__CM3070__CM3071__CM3072__CM3073__CM3074__CM3075__CM3076__CM3077__CM3078__CM3079__CM3080__CM3081__CM3082__CM3083__CM3084__CM3085__CM3086__CM3087__CM3088__CM3089__CM3090__CM3091__CM3092__CM3093__CM3094__CM3095__CM3096__CM3097__CM3098__CM3099__CM3100__CM3101__CM3102__CM3103__CM3104__CM3105__CM3106__CM3107__CM3108__CM3109__CM3110__CM3111__CM3112__CM3113__CM3114__CM3115__CM3116__CM3117__CM3118__CM3119__CM3120__CM3121__CM3122__CM3123__CM3124__CM3125__CM3126__CM3127__CM3128__CM3129__CM3130__CM3131__CM3132__CM3133__CM3134__CM3135__CM3136__CM3137__CM3138__CM3139__CM3140__CM3141__CM3142__CM3143__CM3144__CM3145__CM3146__CM3147__CM3148__CM3149__CM3150__CM3151__CM3152__CM3153__CM3154__CM3155__CM3156__CM3157__CM3158__CM3159__CM3160__CM3161__CM3162__CM3163__CM3164__CM3165__CM3166__CM3167__CM3168__ | C | diverse | diverse | NC Report | Not kept curing times in different collared coils | use as is | 2004-04-20 | signed | signed | completed | WÜ
NCR3231_0 | CM3130 | C | N-3130C | HCMB__A001-03000130 | NC Report | Damage of the insulation N-3397I and N-3399E and installation of CPS in stainless steel - CS and NCS | repair | 2004-04-21 | signed | signed | completed | WÜ
NCR3232_0 | CM3132 | C | N-3132C | HCMB__A001-03000132 | NC Report | Damage of the insulation N-3406I and N-3405E and installation of CPS in stainless steel - CS and NCS | repair | 2004-04-21 | signed | signed | completed | WÜ
NCR3233_0 | CM3185 | E | N-3619E | HCMB__A001-03000185 | NC Report | Resin entered into the outer layer N-3619E | repair | 2004-04-21 | signed | signed | completed | WÜ
NCR3234_0 | CM3186 | E | N-3621E; N-3622E; N-3623E; N-3624E | HCMB__A001-03000186 | NC Report | Resin entered into the outer layers N-3621E; N-3622E; N-3623E; N-3624E | repair | 2004-04-21 | signed | signed | completed | WÜ
NCR3235_0 | CM3187 | E | N-3626E | HCMB__A001-03000187 | NC Report | Resin entered into the outer layer N-3626E | repair | 2004-04-21 | signed | signed | completed | WÜ
NCR3236_0 |  |  | ohne | ohne Magnetnr. | NC Report | Modification of Headspacers | use as is | 2004-04-22 | signed | signed | completed | WÜ
NCR3237_0 | CM3188 | E | N-3629E | HCMB__A001-03000188 | NC Report | Damage of the outer layer N-3629E during curing | repair | 2004-04-22 | signed | signed | completed | WÜ
NCR3238_0 | CM3131 | C | N-3131C | HCMB__A001-03000131 | NC Report | Installation of CPS in stainless steel | repair | 2004-04-28 | signed | signed | completed | WÜ
NCR3239_0 | CM3133 | C | N-3133C | HCMB__A001-03000133 | NC Report | Installation of CPS in stainless steel | repair | 2004-04-28 | signed | signed | completed | WÜ
NCR3240_0 | CM3192 | E | N-3647E; N-3648E | HCMB__A001-03000192 | NC Report | Resin entered into the outer layers N-3647E and N-3648E | repair | 2004-04-28 | signed | signed | completed | WÜ
NCR3241_0 | CM3191 | E | N-3642E | HCMB__A001-03000191 | NC Report | Resin entered into the outer layer N-3642E | repair | 2004-04-28 | signed | signed | completed | WÜ
NCR3242_0 | CM3136 | C | N-3136CE | HCMB__A001-03000136 | NC Report | Installation of CPS in stainless steel | repair | 2004-05-07 | signed | signed | completed | WÜ
NCR3244_0 | CM3175 | E | N-3680E | HCMB__A001-03000200 | NC Report | Damage of the coil outerlayer N-3680E during the winding | compensition delivery by CERN | 2004-05-17 | signed | signed | completed | WÜ
NCR3245_0 | CM3204 | E | N-3693E | HCMB__A001-03000204 | NC Report | Damage of the coil outerlayer N-3693E during the winding | compensition delivery by CERN | 2004-05-18 | signed | signed | completed | WÜ
NCR3247_0 | CM3102 | R | N-3102C | HCMB__A001-03000102 | NC Report | D2 - electrical defekt | repair | 2004-04-13 | signed | signed | completed | Zz
NCR3249_0 | CM3167 | S | NA3167M | HCMBA_A001-03000167 | NC Report | Busbar M1 - electrical defekt | reject and replace | 2004-04-23 | signed | signed | completed | Zz
NCR3252_0 | CM3140 | T | NA3140M | HCMBA_A001-03000140 | NC Report | End cover NCS out of tolerance | repair | 2004-05-11 | signed | signed | completed | Zz
NCR3253_0 | CM3158 | C | N-3158C | HCMBA_A001-03000158 | NC Report | Using material AISI 304 instead of AISI 304L | use as is | 2004-05-10 | signed | signed | completed | WÜ
NCR3254_0 | CM3165 | C | N-3165C | HCMBA_A001-03000165 | NC Report | Using material AISI 304 instead of AISI 304L | use as is | 2004-05-10 | signed | signed | completed | WÜ
NCR3255_0 | CM3166 | C | N-3166C | HCMBA_A001-03000166 | NC Report | Using material AISI 304 instead of AISI 304L | use as is | 2004-05-10 | signed | signed | completed | WÜ
NCR3256_0 | CM3167 | C | N-3167C | HCMBA_A001-03000167 | NC Report | Using material AISI 304 instead of AISI 304L | use as is | 2004-05-10 | signed | signed | completed | WÜ
NCR3257_0 | CM3171 | C | N-3171C | HCMBA_A001-03000171 | NC Report | Using material AISI 304 instead of AISI 304L | use as is | 2004-05-10 | signed | signed | completed | WÜ
NCR3258_0 | CM3172 | C | N-3172C | HCMBA_A001-03000172 | NC Report | Using material AISI 304 instead of AISI 304L | use as is | 2004-05-10 | signed | signed | completed | WÜ
NCR3259_0 | CM3173 | C | N-3173C | HCMBA_A001-03000173 | NC Report | Using material AISI 304 instead of AISI 304L | use as is | 2004-05-10 | signed | signed | completed | WÜ
NCR3260_0 | CM3174 | C | N-3174C | HCMBA_A001-03000174 | NC Report | Using material AISI 304 instead of AISI 304L | use as is | 2004-05-10 | signed | signed | completed | WÜ
NCR3261_0 | CM3170 | T | NA3170M | HCMBA_A001-03000170 | NC Report | Shape out of tolerance | repair | 2004-05-13 | signed | Mail Mr. Miles 09.06.04 | completed | Zz
NCR3264_0 | CM3174 | C | NA3174M | HCMBA_A001-03000174 | NC Report | Temperature sensor | repair | 2004-05-17 | signed | signed | completed | Zz
NCR3268_0 | CM3175 | C | N-3175C | HCMB__A001-03000175 | NC Report | Electrical disruptive discharge at the outer layer N-3580E | reject and replace | 2004-05-25 | signed | signed | completed | WÜ
NCR3269_A | CM3102 | C | N-3102C | HCMB___A001-03000102 | NC Report | Disruptive discharge between the inner layer N-3287i and the outer layer N-3287e | repair | 2004-06-24 | signed | signed | completed | WÜ
NCR3270_0 | CM3170__CM3171__CM3172__CM3173__CM3174__CM3175__CM3176__CM3177__CM3178__CM3179__CM3180__CM3181__CM3182__CM3183__CM3184__CM3185__CM3186__CM3187__CM3188__CM3189__CM3190__CM3191__CM3192__CM3193__CM3194__CM3195__CM3196__CM3197__CM3198__CM3199__CM3200__CM3201__CM3202__CM3203__CM3204__CM3205__CM3206__CM3207__CM3208__CM3209__CM3210 | C |  | HCMB__A001-3000170__A001-3000171__A001-3000172__A001-3000173__A001-3000174__A001-3000175__A001-3000176__A001-3000177__A001-3000178__A001-3000179__A001-3000180__A001-3000181__A001-3000182__A001-3000183__A001-3000184__A001-3000185__A001-3000186__A001-3000187__A001-3000188__A001-3000189__A001-3000190__A001-3000191__A001-3000192__A001-3000193__A001-3000194__A001-3000195__A001-3000196__A001-3000197__A001-3000198__A001-3000199__A001-3000200__A001-3000201__A001-3000202__A001-3000203__A001-3000204__A001-3000205__A001-3000206__A001-3000207__A001-3000208__A001-3000209 | NC Report | Not kept curing temperatures | use as is | 2004-06-03 | signed | signed | completed | WÜ
NCR3272_0 | CM3215 | E | N-3737E | HCMB__A001-03000215 | NC Report | Damage of the outer layer N-3737E during a handling operation | reject and replace | 2004-06-22 | signed | signed | completed | WÜ
NCR3273_0 | CM3175 | I | N-3578I | HCMB__A001-03000175 | NC Report | Collared coil N-3175C Loose spices on the inner layer N-3578i | repair | 2004-06-16 | signed | signed | completed | WÜ
NCR3274_0 | CM3214 | E | N-3736E | HCMB__A001-03000214 | NC Report | Not kept curing times in different collared coils | use as is | 2004-07-13 | signed | signed | completed | WÜ
NCR3275_A | CM3226 | E | N-3226C | HCMB__A001-03000226 | NC Report | Collared coil N-3226C Loose spices on the outer layer N-3781E | repair | 2004-07-06 | signed | signed | completed | WÜ
NCR3276_A | CM3231 | E | N-3803E | HCMB__A001-03000231 | NC Report | Collared coil N-3231C Gaps and easily detachable splices on the outer layer N-3803E | rework | 2004-07-13 | signed | signed | completed | WÜ
NCR3277_A | CM3233 | E | N-3810E | HCMB__A001-03000233 | NC Report | Collared coil N-3233C Gaps and easily detachable splices on the outer layer N-3810E | rework | 2004-07-13 | signed | signed | completed | WÜ
NCR3278_0 | CM3216 | E | N-3742E | HCMB__A001-03000216 | NC Report | Not kept curing time | use as is | 2004-07-13 | signed | signed | completed | WÜ
NCR3279_A | CM3222 | E | N-3768E | HCMB__A001-03000222 | NC Report | Disruptive discharge in the lower pole of D2 | repair | 2004-08-09 | signed | signed | completed | WÜ
NCR3280_A | CM3233 | E | N-3812E | HCMB__A001-03000233 | NC Report | Preparation of copper wedges with VANTICO | rework | 2004-07-14 | signed | signed | completed | WÜ
NCR3281_0 | CM3173 | M | NA3173M | HCMBA_A001-03000173 | NC Report | Shape out of tolerance | use as is | 2004-05-25 | signed | Mail Mr. Miles 15.06.04 | completed | Zz
NCR3283_0 | CM3183 | M | NA3183M | HCMBALA001-03000183 | NC Report | Diode damaged | repair | 2004-06-16 | signed | signed | completed | Zz
NCR3291_0 | CM3206 | S | NA3206M | HCMBA_A001-03000206 | NC Report | Measurement of inner gap | use as is | 2004-07-14 | signed | signed | completed | Zz
NCR3293_0 | CM3207 | S | NA3207M | HCMBA_A001-03000207 | NC Report | Measurement of inner gap | use as is | 2004-07-14 | signed | signed | completed | Zz
NCR3294_0 | CM3212 | I | N-3212C | HCMB__A001-03000212 | NC Report | Gaps at innter layer N-3728I | rework | 2004-08-06 | signed | signed | completed | WÜ
NCR3295_0 | CM3234 | E | N-3234C | HCMB__A001-03000234 | NC Report | Gaps and easily detachable splices at outer layer N-3815E | rework | 2004-07-20 | signed | signed | completed | WÜ
NCR3303_0 | CM3235 | S | NB3235 | HCMBB_A001-03000235 | NC Report | Busbar M3 damaged | repair | 2004-08-28 | signed | signed | completed | CoC von Hr. Perinet (Besuch 20.-22.07.2004 zu NCR3282_0)
NCR3305_0 | CM3253 | I | N-3891i | HCMB__A001-03000253 | NC Report | During winding of inner layer N-3891i - damage on winding machine 1 | use as is | 2004-09-09 | signed | signed | completed | WÜ
NCR3308_0 | CM3254 | P | N-3896P | HCMB__A001-03000254 | NC Report | Red and yellow alarms during the magnetic measurements of collared coil N-3254 | repair | 2004-09-15 | signed | signed | completed | WÜ
NCR3309_0 | CM3242 | E | N-3846E | HCMB__A001-03000242 | NC Report | Electrical disruptive discharge at the outer layer N-3846E | reject and replace | 2004-09-15 | signed | signed | completed | WÜ
NCR3310_A | CM3208 CM3708 | I | N-3709i N-3710i | HCMBALA001-03000208 HCMBALA001-03000708 HCMB__A001-03000708 | NC Report | Cold mass 3208 / Collared Coil N-3208C; Bad quench performance, CC/CM have to be rebuild; new magnet no. = N-3708M | repair | 2005-06-06 | signed | signed | completed | WÜ
NCR3311_0 | CM3218 | C | N-3218C | HCMB__A001-03000218 | NC Report | loss of datas mech. measurement | use as is | 2004-09-15 | signed | signed | completed | WÜ
NCR3312_0 | CM3240 | R | NB3240M | HCMBB_A001-03000240 | NC Report | casing to short | repair | 2004-09-15 | signed | signed | completed | Zz
NCR3320_0 | CM3175 | T | NA3175M | LHCMBALA001-03000175 | NC Report | Halterung für Decapole / Octupole CS Zg. 227556 / e | use as is | 2004-11-01 | signed | signed | completed | Zz
NCR3322_0 | CM3249 | S | NA3249M | HCMBARA001-03000249 | NC Report | Busbar M3 - broken supraconductor | repair | 2004-11-03 | signed | signed | completed | Zz
NCR3324_0 | CM3258 | I | N-3912i | HCMB__A001-03000258 | NC Report | Inner layer N-3912i (Cable id number 01B10591B - cycled too late during curing | use as is | 2004-10-15 | signed | signed | completed | WÜ
NCR3326_0 | CM3276 | C | N-3276C | HCMB__A001-03000276 | NC Report | Overstepping of tolerance on the gap between endplate and NCS head | use as is | 2004-10-19 | signed | signed | completed | WÜ
NCR3328_A | CM3253 | U | NA3253M | HCMBARA001-03000253 | NC Report | M type bellows assembly onto M1 | repair | 2004-11-15 | signed | signed | completed | Zz
NCR3330_0 | CM3270 | S | NB3270M | LHCMBBRA001-03000270 | NC Report | Busbar M1 - electrical fault | reject and replace | 2004-11-03 | signed | signed | completed | Zz
NCR3334_0 | CM3292 | P | N-4047P | HCMB__A001-03000292 | NC Report | Short circuit on Collared coil N-3292C | repair | 2004-11-17 | signed | signed | completed | WÜ
NCR3335_0 | CM3278 | I | N-3992I | HCMB__A001-03000278 | NC Report | Inner layer N-3992i (Cable id number 01B10623D - cycled too late during curing | use as is | 2004-11-22 | signed | signed | completed | WÜ
NCR3336_0 | CM3250 (hence) | T | NA3250M | HCMBARA001-03000250 | NC Report | Support Decapole / Octupole | use as is | 2004-11-15 | signed | by CERN e-mail of 22nd Nov.2004 | completed | Zz
NCR3338_A | CM3136 CM3636 | M I | N-3636M N-3423I | HCMBBLA001-03000136 HCMBBLA001-03000636 HCMB__A001-03000636 | NC Report | Cold mass 3136 / Collared Coil N-3136C; Bad quench performance, no memory; CC/CM have to be rebuild; new magnet no. = N-3636M | repair | 2005-02-02 | signed | signed | completed | WÜ
NCR3339_A | CM3224 CM3724 | M I | N-3224M N-3775I | HCMBBLA001-03000224 HCMBBLA001-03000724 HCMB__A001-03000724 | NC Report | Cold mass 3224 / Collared Coil N-3224C; Not fullfilling the acceptance criteria; CC/CM have to be rebuild; new magnet no. = N-3724M | repair | 2005-05-09 | signed | signed | completed | WÜ
NCR3342_0 | CM3317 | E | N-4147E | HCMB__A001-03000317 | NC Report | Not kept curing temperatures on the outer layers N-4147E and N-4148E | use as is | 2004-12-07 | signed | signed | completed | WÜ
NCR3346_0 | CM3323 | E | N-4172E | HCMB__A001-03000323 | NC Report | Damage of the outer layer N-4172E during the winding | compensation delivery by CERN | 2004-12-15 | signed | signed | completed | WÜ
NCR3347_A | CM3342 | E | N-4247E | HCMB__A001-03000342 | NC Report | Short-circuit at the outer layer N-4247E | reject and replace | 2005-02-09 | signed | signed | completed | WÜ
NCR3348_0 | CM3273 | V | NB3273M | HCMBBRA001-03000273 | NC Report | Tube N-Line pushed in | repair | 2004-12-22 | signed | 27.01.05 signed at Würzburg | completed | Zz
NCR3351_0 | CM3254 | S | NA3254M | HCMBARA001-03000254 | NC Report | Busbar M3 - broken supraconductor | repair | 2005-01-19 | signed | 03.02.05 signed at Zeitz | completed | Zz
NCR3359_0 | CM3300 | M | NA3300M | HCMBA_A001-03000300 | NC Report | Sextupoles support | use as is | 2005-02-07 | signed | 03.02.05 signed at Zeitz | completed | Zz
NCR3361_0 | CM3294 | T | NB3294M | HCMBBRA001-03000294 | NC Report | Diode Container Tee | use as is | 2005-02-07 | signed | 03.02.05 signed at Zeitz | completed | Zz
NCR3362_0 | CM3292 | T | NB3292M | HCMBB_A001-03000292 | NC Report | Temperature sensor | repair | 2005-02-10 | signed | 03.02.05 signed at Zeitz | completed | Zz
NCR3365_0 | CM3321 | S | NA3321M | HCMBA_A001-03000321 | NC Report | V2 Line - insulation fault | repair | 2005-02-28 | signed | 03.02.05 signed at Zeitz | completed | Zz
NCR3366_0 | CM3299 | V | NA3299M | HCMBARA001-03000299 | NC Report | Diode container - Leck | repair | 2005-03-01 | signed | 03.02.05 signed at Zeitz | completed | Zz
NCR3367_B | CM3319 | V | NA3319M | HCMBARA001-03000319 | NC Report | Electrical fault | repair | 2005-05-03 | signed | signed | completed | Zz
NCR3373_0 | CM3321 | V | NA3321M | HCMBARA001-03000321 | NC Report | Temperature sensor | repair | 2005-03-18 | signed | signed | completed | Zz
NCR3374_A | CM3234 CM3734 | M E | N-3224M N-3814E | HCMBBLA001-03000234 HCMBBLA001-03000734 HCMB__A001-03000734 | NC Report | Cold mass 3234 / Collared Coil N-3234C; Short circuit between QH and coil during quench training at CERN; CC/CM have to be rebuild; new magnet no. = N-3734M | repair | 2005-05-11 | signed | signed | completed | WÜ
NCR3375_A | CM3143 CM3643 | M E | N-3143M N-3449E | HCMBBLA001-03000143 HCMBBLA001-03000643 HCMB__A001-03000643 | NC Report | Cold mass 3143 / Collared Coil N-3143C; Short circuit between QH and coil during the warm acceptance testat CERN; CC/CM have to be rebuild; new magnet no. = N-3643M | repair | 2005-05-11 | signed | signed | completed | WÜ
NCR3379_A | CM3332 | T | NB3332M | HCMBB_A001-03000332 | NC Report | Busbar 405B/M3 | use as is | 2005-04-26 | signed | signed | completed | Zz
NCR3382_0 | CM3346 | T | NB3346M | HCMBA_A001-03000346 | NC Report | End cover NCS | use as is | 2005-05-12 | signed | signed | completed | Zz
NCR3385_0 | CM3372 | I | N-4367I | HCMB__A001-03000372 | NC Report | Not kept specified cycling time of 30 min. | use as is | 2003-05-19 | signed | signed | completed | WÜ
NCR3387_0 | CM3404 | I | N-4493I | HCMB__A001-03000404 | NC Report | Not kept specified cycling time of 30 min. | use as is | 2005-06-08 | signed | signed | completed | WÜ
NCR3388_0 | CM3405 | I | N-4500I | HCMB__A001-03000405 | NC Report | Not kept specified cycling time of 30 min. | use as is | 2005-06-08 | signed | signed | completed | WÜ
NCR3391_0 | CM3353 | V | NA3353M | HCMBARA001-03000353 | NC Report | X-line - leckage on NCS-side | repair | 2005-06-13 | signed | signed | completed | Zz
NCR3393_0 | CM3153 CM3653 | C E | N-3153C N-3653C N-3490E | HCMBARA001-03000153 HCMBARA001-03000653 HCMB__A001-03000653 | NC Report | Rebuilt of collared coil and cold mass because of a short circuit between coil, QH and CPS during quench training at CERN The new magnet no. = N-3653C | repair | 2005-06-22 | signed | signed | completed | WÜ
NCR3394_0 | CM3406 | C I | N-3406C N-4501I N-4502I N-4503I N-4504I | HCMB__A001-03000406 | NC Report | Collared coil N-3406C - Inner layers with noticeable problems | use as is | 2005-06-21 | signed | signed | completed | WÜ
NCR3395_0 | CM3407 | C I | N-3407C N-4505I N-4506I N-4507I N-4508I | HCMB__A001-03000407 | NC Report | Collared coil N-3407C - Inner layers with noticeable problems | use as is | 2005-06-21 | signed | signed | completed | WÜ
NCR3396_0 | CM3409 | C I | N-3409C N-4513I | HCMB__A001-03000409 | NC Report | Collared coil N-3409C - Inner layer N-4513I with noticeable problems | use as is | 2005-06-21 | signed | signed | completed | WÜ
NCR3397_0 | CM3363 | V | NB3363M | HCMBBRA001-03000363 | NC Report | X-line - leckage on NCS-side | repair | 2005-07-28 | signed | signed | completed | Zz
NCR3398_0 | CM3388 | T | NB3388M | HCMBBRA001-03000388 | NC Report | Temperature sensor | repair | 2005-07-05 | signed | signed | completed | Zz
NCR3399_0 | CM3395 | T | NA3395M | HCMBALA001-03000395 | NC Report | M-line bellow | repair | 2005-07-13 | signed | signed | completed | Zz
NCR3402_0 | CM3382 | T | NB3382M | HCMBBRA001-03000382 | NC Report | Leakage on CS-side | repair | 2005-07-27 | signed | signed | completed | Zz
NCR3405_A | CM3376 | T | NA3376M | HCMBARA001-03000376 | NC Report | Insulation fault | repair | 2005-09-27 | signed | signed | completed | Zz
NCR3406_0 | CM3392 | T | NA3392M | HCMBB_A001-03000392 | Receiving Inspection | Octupole/Decapole MCDO MA-I 698 | repair | 2005-07-15 | signed | signed | completed | Zz
NCR3410_0 | CM3643 | T | NA3643M | HCMBALA001-03000643 | NC Report | Temperature sensor | repair | 2005-08-24 | signed | signed | completed | Zz
NCR3411_0 | CM3408 | T | NB3408M | HCMBBLA001-03000408 | NC Report | Busbar M1 | repair | 2005-08-24 | signed | signed | completed | Zz
NCR3413_0 | CM3406 | S | NB3406M | HCMBBLA001-03000406 | NC Report | V1 Line - insulation fault | repair | 2005-08-26 | signed | signed | completed | Zz
NCR3414_0 | CM3405 | S | NB3405M | HCMBBLA001-03000405 | NC Report | V2 Line - diameter | repair | 2005-09-01 | signed | signed | completed | Zz freigegeben
NCR3415_0 | CM3408 | U | NB3408M | HCMBBLA001-03000408 | NC Report | V2 Line - diameter | repair | 2005-09-01 | signed | signed | completed | Zz freigegeben
NCR3416_0 | CM3400 | T | NA3400M | HCMBALA001-03000400 | NC Report | Diode | repair | 2005-08-31 | signed | signed | completed | Zz
NCR3417_0 | CM3724 | V | NA3724M | HCMBALA001-03000724 | NC Report | Diode container | use as is | 2005-09-02 | signed | approval by phone and signed by Mr. Barbio | completed | Zz freigegeben
NCR3419_0 | CM3734 | V | NA3734M | HCMBALA001-03000734 | NC Report | Temperature sensor | repair | 2005-09-08 | signed | signed | completed | Zz
NCR3420_A | CM3406 | C | NA3406M | HCMBBLA001-03000406 | NC Report | Damaged isolation on the cold bore tube of Aperture D1 | repair | 2005-09-19 | signed | signed | completed | WÜ
NCR3421_0 | CM3341 | T | NB3341M | HCMBBRA001-03000341 | NC Report | End cover NCS | use as is | 2005-10-25 | signed | signed | completed | Zz
NCR3423_0 | CM3341 | V | NB3341M | HCMBBRA001-03000341 | NC Report | Leakage on internal X-Line-bellow | repair | 2005-10-25 | signed | signed | completed | Zz
NCR3425_0 | CM3388 | Z | NB3388M | HCMBBRA001-03000388 | NC Report | Electrical fault | repair | 2005-11-08 | signed | signed | completed | Zz