|  | NON CONFORMITY REPORT | Nr. NC CERN 69 (CERN NC id. num.) |
| --- | --- | --- |
| Ansaldo Superconduttori S.p.A. |  |  |

| CUSTOMER CERN |  | JOB 0209EM |  | PROJECT NAME LHC 30 cold masses |  |  | Nr. RNC 020802C (ANSALDO NC id. num.) Date: 02/08/2002 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRODUCT IDENTIFICATION Cold mass M004: longitudinal welds |  |  |  |  |  |  |  MAJOR  minor |  |
| REFERENCE DOCUMENTS |  |  |  |  |  |  |  |  |
| NON CONFORMITY DESCRIPTION |  |  |  |  |  |  |  |  |
| X-ray test of longitudinal welds on M004 shrinking cylinders, showed defects on WA (nr.20 films) and WB welds (nr.2 films) as described on test reports Ansaldo-SIGE nr. 02052-1 & 02052-2 Both report and films have been submitted to CERN analysis. |  |  |  |  |  |  |  |  |
| RESOLUTION |  |  |  |  |  |  |  |  |
| With reference to Ansaldo-CERN meeting of 25/07/02 and 01/08/02, Ansaldo will proceed with identification of the defects on both welds, grinding of damaged parts, restoring of welds by manual TIG welding procedure. Dye penetrant test and X-ray test will follow. |  |  |  |  |  |  |  |  |
| INTERNAL APPROVAL |  |  |  |  |  |  |  |  |
|  | PREPARED |  | CHECKED |  |  |  |  | APPROVED |
| Dept. | PRC |  | TEC |  |  |  |  | TEC |
| Name | B. Caserza |  | G. Drago |  |  |  |  | F. Terzi |
| Signature |  |  |  |  |  |  |  |  |
| Date | 02/08/2002 |  | 02/08/2002 |  |  |  |  | 05/08/2002 |

| CORRECTIVE ACTIONS |  |  |  |
| --- | --- | --- | --- |
| CUSTOMER APPROVAL |  |  |  |
|  ACCEPTED by F.Savary on 13th of August 2002 |  |  NOT ACCEPTED |  |
| REMARKS |  |  |  |
| Ansaldo shall repair the welds on both sides, WA and WB, according to conclusions of the inspection reports of the company Sige (see above) and of the company AJC international (PV N° 2793 dated 22 July 2002). We also reviewed together with the inspector of Sige at Ansaldo premises both reports and agreed on a common interpretation of the indications observed on the X-ray films. The weld repairs shall be then inspected according to the Technical Specification. |  |  |  |
| CORRECTIVE ACTION EXECUTED |  |  | REPORTS ISSUED |
| Date 29/08/02 | Signature F. Terzi |  | SIGE 02025-3-DM |
| REMARKS |  |  |  |
| Repairs executed on 26-27/08/02. After repairing, X-rays examination shows some defects on repairs of WA weld: please refer to SIGE test report nr. 02052-3 for details (29/08/02) A Non Conformity Report will be issued. |  |  |  |

MOD NC-CERN_2