## legend
Nomenclature to be used
assemblies
CC | up to collared coil warm magnetic measurement approved
CM | from collared coil magnetic measurement up to shipment
sub-assemblies
coil | from SC cable to surfaced layers
pole | from surfaced coil to connected pole
dipole | from pole to dipoles ready with coil protection sheet
collared coil | from coil protection sheet to warm magnetic measurement
cold mass main body | from yoking till end of longitudinal welding
cold mass | from longitudinal welding till shipment
typology
electrical | affecting electrical properties
mechanical | damage affecting mechanical (and electrical) properties
irriversible damage | i.e. layer with cut strand
traceability | CoC not avaialable
raw material | raw material not conform to tech spec
component | component received or used not conform to tech spec
action
use as is
repair
reject | sub-assembly rejected, no repair possible (layer)
dismantle | repairing needs de-collaring or cutting of long weld
replace | the component non according to spec will be replaced (stock not magnet)
in green NCR in process or managed internal by the firm
in red NCR where the file is not available at CERN

## layers-poles
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011 | JI38
1012
1013
1014
1015
1016 | JI62 | JI63 | JI64 | JI65
1017 | JI66 | JI67 | JI68 | JI69
1018 | JI70 | JI71 | JI72 | JI73
1019 | JI74 | JI75 | JI76 | JI77
1020 | JI78 | JI79 | JI80 | JI81
1021 | JI82 | JI83 | JI84 | JI85
1022 | JI86 | JI87 | JI88 | JI89
JO89
1023 | JI91 | JI92 | JI93 | JI94
JO93
1024 | JI99 | JI100 | JI101 | JI102
JO100
1025 | JI107 | JI109 | JI108 | JI110
| JO106 |  |  | JO109
1026 | JI103 | JI104 | JI105 | JI106
| JO102 | JO103 | JO104 | JO105
1027 | JI111 | JI112 | JI113 | JI114
| JO110 | JO111 | JO112 | JO113
1028 | JI120 | JI121 | JI122 | JI119
| JO119 | JO120 | JO121 | JO118
1029 | JI97 | JI98 | JI156 | JI155
| JO96 | JO97 | JO95 | JO94
1030 | JI132 | JI133 | JI134 | JI131
| JO131 |  | JO133
1037

## topology occurence
NCR topology Occurrence
Count of typology | typology
magnet | electrical | mechanical | raw material | alignment | irriversible damage | blank | Grand Total
1001 |  |  |  | 1 |  |  | 1
1002 |  | 1 | 1 |  |  |  | 2
1003 | [5 empty] | 4 | 4
1004 | 1 | 4 |  | 3 |  |  | 8
1005 | 2 |  |  |  |  | 2 | 4
1006 |  | 1 |  | 1 |  | 4 | 6
1007 | 1 | 1 |  | 2 |  | 1 | 5
1008 |  | 1 |  |  |  | 1 | 2
1009 |  | 2 |  | 1 |  |  | 3
1010 |  |  |  | 1 |  | 1 | 2
1011 | 1 | [5 empty] | 1
1012 |  | 1 |  | 2 |  |  | 3
1013 |  | 2 |  | 1 |  |  | 3
1014 |  | 1 |  |  |  |  | 1
1015 |  | 2 |  |  |  |  | 2
1016 |  | 2 |  | 1 |  |  | 3
1017 |  | 2 |  | 1 |  |  | 3
1018 | 1 | 2 |  | 1 |  |  | 4
1019 | 1 | 1 |  | 1 |  |  | 3
1020 | 1 |  |  |  |  | 1 | 2
1021 |  |  |  | 2 |  |  | 2
1022 |  | 1 |  | 1 |  |  | 2
1023 | 1 | 2 |  | 2 |  |  | 5
1024 |  | 4 |  | 1 | 2 |  | 7
1025 |  | 2 |  |  |  |  | 2
1026 | 1 | 2 |  |  |  |  | 3
1027 |  | 1 |  | 1 |  |  | 2
1028 | 2 | [5 empty] | 2
1029 | 1 | 1 |  |  |  |  | 2
1031 |  | 1 |  |  | 1 |  | 2
1032 | 1 | [5 empty] | 1
1033 | 1 | 4 |  | 1 |  |  | 6
1034 |  |  |  | 1 |  |  | 1
1035 | 1 | 1 |  | 1 |  |  | 3
1037 |  |  |  | 1 |  |  | 1
1038 |  |  |  | 1 |  |  | 1
1039 |  |  |  | 1 |  |  | 1
1040 | 1 |  |  | 1 |  |  | 2
1041 | 1 |  |  | 1 |  |  | 2
1042 | 2 | 1 |  | 1 |  |  | 4
1043 |  |  |  |  | 1 |  | 1
1045 |  | 1 |  | 1 |  |  | 2
1046 |  | 1 |  |  |  |  | 1
1047 |  | 1 |  |  |  |  | 1
1050 |  | 1 |  |  |  |  | 1
1051 |  | 1 |  | 1 |  |  | 2
1052 |  | 1 |  |  |  |  | 1
1053 |  | 1 |  | 1 |  |  | 2
1054 | 1 | 1 |  |  |  |  | 2
1055 | 2 | 1 |  |  |  |  | 3
1056 | 2 | 2 |  |  |  |  | 4
1057 | 1 | 1 |  |  |  |  | 2
1058 | 1 | 2 |  |  |  |  | 3
1059 |  | 2 |  | 1 |  |  | 3
1060 |  | 2 |  |  |  |  | 2
1062 | 1 | 3 |  |  | 1 |  | 5
1063 |  | 1 |  |  |  |  | 1
1065 |  | 1 |  |  |  |  | 1
1067 | 4 | [5 empty] | 4
1069 |  | 1 |  |  |  |  | 1
1072 |  | 1 |  |  |  |  | 1
1073 |  | 1 |  |  |  |  | 1
1075 | 1 | 2 |  |  |  |  | 3
1076 |  | 3 |  |  |  |  | 3
1082 | 1 | [5 empty] | 1
Grand Total | 34 | 74 | 1 | 36 | 5 | 14 | 164

## sub-assembly occurence
Count of sub-assembly | sub-assembly
magnet | coil | cold mass | cold mass main body | collared coil | pole | blank | Grand Total
1001 |  | 1 |  |  |  |  | 1
1002 |  | 1 | 1 |  |  |  | 2
1003 | [5 empty] | 4 | 4
1004 |  | 3 | 5 |  |  |  | 8
1005 |  | 1 |  | 1 |  | 2 | 4
1006 |  | 1 | 1 |  |  | 4 | 6
1007 |  | 1 | 3 |  |  | 1 | 5
1008 |  |  | 1 |  |  | 1 | 2
1009 |  | 1 | 2 |  |  |  | 3
1010 |  |  | 1 |  |  | 1 | 2
1011 |  | 1 |  |  |  |  | 1
1012 |  | 2 | 1 |  |  |  | 3
1013 |  | 2 | 1 |  |  |  | 3
1014 |  |  | 1 |  |  |  | 1
1015 |  |  | 2 |  |  |  | 2
1016 |  |  | 3 |  |  |  | 3
1017 |  |  | 3 |  |  |  | 3
1018 |  | 1 | 3 |  |  |  | 4
1019 |  | 2 | 1 |  |  |  | 3
1020 |  |  |  | 1 |  | 1 | 2
1021 |  |  | 2 |  |  |  | 2
1022 |  |  | 2 |  |  |  | 2
1023 | 1 | 3 | 1 |  |  |  | 5
1024 | 5 | 1 | 1 |  |  |  | 7
1025 |  | 1 | 1 |  |  |  | 2
1026 | 2 |  |  |  | 1 |  | 3
1027 | 1 |  | 1 |  |  |  | 2
1028 | 1 | 1 |  |  |  |  | 2
1029 | 1 | 1 |  |  |  |  | 2
1031 | 2 | [5 empty] | 2
1032 |  |  | 1 |  |  |  | 1
1033 | 5 | 1 |  |  |  |  | 6
1034 |  | 1 |  |  |  |  | 1
1035 |  | 2 |  | 1 |  |  | 3
1037 |  | 1 |  |  |  |  | 1
1038 |  | 1 |  |  |  |  | 1
1039 |  | 1 |  |  |  |  | 1
1040 |  | 2 |  |  |  |  | 2
1041 |  | 2 |  |  |  |  | 2
1042 | 1 | 1 |  |  | 2 |  | 4
1043 |  |  |  |  | 1 |  | 1
1045 |  | 2 |  |  |  |  | 2
1046 |  |  |  |  | 1 |  | 1
1047 |  |  |  |  | 1 |  | 1
1050 |  |  |  |  | 1 |  | 1
1051 |  | 1 |  |  | 1 |  | 2
1052 |  |  |  |  | 1 |  | 1
1053 | 1 | 1 |  |  |  |  | 2
1054 | 2 | [5 empty] | 2
1055 | 1 | 1 |  |  | 1 |  | 3
1056 | 2 |  |  |  | 2 |  | 4
1057 | 1 |  |  |  | 1 |  | 2
1058 | 1 |  |  |  | 2 |  | 3
1059 | 1 | 1 |  |  | 1 |  | 3
1060 | 1 |  |  |  | 1 |  | 2
1062 | 1 |  |  |  | 4 |  | 5
1063 |  |  |  |  | 1 |  | 1
1065 |  |  |  |  | 1 |  | 1
1067 | 1 |  |  |  | 3 |  | 4
1069 | 1 | [5 empty] | 1
1072 |  |  |  |  | 1 |  | 1
1073 |  |  |  |  | 1 |  | 1
1075 |  |  |  |  | 3 |  | 3
1076 |  |  |  |  | 3 |  | 3
1082 | 1 | [5 empty] | 1
Grand Total | 33 | 42 | 38 | 3 | 34 | 14 | 164

## NCR list
code | N | type | magnet | date | typology | Assembly | sub-assembly | action | Affected object and explication | Cable amount to be replaced
NCR | NCF088 |  | 1001 | 2001-04-10 | alignment | CM | cold mass | use as is | twist out of tolerance | 0
NCR | NCF092 |  | 1002 | 2001-04-10 | raw material | CM | cold mass main body | use as is | some steel sheets in extreneties instead of stainless | 0
NCR | NCF080 |  | 1002 | 2001-04-10 | mechanical | CM | cold mass | repair | shrinking cylinder cut too short, add ring | 0
NCR | 01LHCA006 |  | 1003 | 2001-08-21 | blank | blank | blank | blank
NCR | 01LHCA007 |  | 1003 | 2001-08-21 | blank | blank | blank | blank
NCR | 01LHCA008 |  | 1003 | 2001-08-21 | blank | blank | blank | blank
NCR | 01LHCA009 |  | 1003 | 2001-11-06 | blank | blank | blank | blank
NCR | 01LHCA004 |  | 1004 | 2001-07-06 | mechanical | CM | cold mass main body | use as is | stacking factor of some packs outside tolerance | 0
NCR | 01LHCA005 |  | 1004 | 2001-07-06 | electrical | CM | cold mass main body | use as is | Temperature sensor displaced | 0
NCR | 02LHCA012 |  | 1004 | 2002-01-03 | mechanical | CM | cold mass main body | repair | longitudinal welding faults | 0
NCR | 02LHCA014 |  | 1004 | 2002-01-14 | alignment | CM | cold mass main body | use as is | H and V shape out of tolerance | 0
NCR | 02LHCA016 |  | 1004 | 2002-02-02 | mechanical | CM | cold mass | use as is | thickness end cover welding too small | 0
NCR | 02LHCA017 |  | 1004 | 2002-02-15 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCA028 |  | 1004 | 2002-03-28 | alignment | CM | cold mass | repair | H shape and end positions V1 and V2 out of tolerance | 0
NCR | 02LHCA032 |  | 1004 | 2002-04-19 | alignment | CM | cold mass | use as is | end cover position out of tolerance | 0
NCR | 02LHCA010 |  | 1005 | 2002-01-15 | blank | blank | blank | blank
NCR | 02LHCA013 |  | 1005 | 2002-02-04 | blank | blank | blank | blank
NCR | 02LHCA015 |  | 1005 | 2002-01-14 | electrical | CM | cold mass | repair | bus bar cables M2 damaged | 0
NCR | 02LHCA022 |  | 1005 | 2002-03-06 | electrical | CC | collared coil | use as is | quench heater wires inversion | 0
NCR | 01LHCA011 |  | 1006 | 2001-12-21 | blank | blank | blank | blank
NCR | 02LHCA018 |  | 1006 | 2002-02-18 | blank | blank | blank | blank
NCR | 02LHCA021 |  | 1006 | 2002-02-27 | blank | blank | blank | blank
NCR | 02LHCA023 |  | 1006 | 2002-03-05 | mechanical | CM | cold mass | repair | CM length out of tolerance (small) | 0
NCR | 02LHCA029 |  | 1006 | 2002-04-12 | alignment | CM | cold mass main body | use as is | H and V shape out of tolerance | 0
NCR | 02LHCA033 |  | 1006 | 2002-04-29 | blank | blank | blank | blank
NCR | 02LHCA020 |  | 1007 | 2002-02-27 | blank | blank | blank | blank
NCR | 02LHCA024 |  | 1007 | 2002-03-25 | alignment | CM | cold mass main body | repair | shape out of tolerance | 0
NCR | 02LHCA027 |  | 1007 | 2002-03-27 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform
NCR | 02LHCA034 |  | 1007 | 2002-05-28 | alignment | CM | cold mass main body | use as is | twist out of tolerance | 0
NCR | 02LHCA036 |  | 1007 | 2002-06-06 | electrical | CM | cold mass | repair | Temperature sensor contact cut | 0
NCR | 02LHCA019 |  | 1008 | 2002-02-27 | blank | blank | blank | blank
NCR | 02LHCA026 |  | 1008 | 2002-03-13 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCA025 |  | 1009 | 2002-09-06 | mechanical | CM | cold mass main body | repair | longitudinal welding faults (porosity) | 0
NCR | 02LHCA047 |  | 1009 | 2002-09-06 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCA048 |  | 1009 | 2002-09-17 | alignment | CM | cold mass | repair | V shape out of tolerance, repair with shims under feet | 0
NCR | 02LHCA030 |  | 1010 | 2002-04-15 | alignment | CM | cold mass main body | repair | shape out of tolerance | 0
NCR | 02LHCA031 |  | 1010 | 2002-04-16 | blank | blank | blank | blank
NCR | 02LHCA035 |  | 1011 | 2002-05-30 | electrical | CM | cold mass | repair | cable cut for type B instead of type A | 0
NCR | 02LHCA038 |  | 1012 | 2002-07-10 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCA041 |  | 1012 | 2002-07-24 | alignment | CM | cold mass | use as is | twist out of tolerance | 0
NCR | 02LHCA042 |  | 1012 | 2002-07-25 | alignment | CM | cold mass | use as is | end cover position out of tolerance | 0
NCR | 02LHCA039 |  | 1013 | 2002-09-06 | alignment | CM | cold mass | use as is | twist out of tolerance | 0
NCR | 02LHCA040 |  | 1013 | 2002-07-16 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCA043 |  | 1013 | 2002-08-13 | mechanical | CM | cold mass | repair | CM length out of tolerance (small) | 0
NCR | 02LHCA044 |  | 1014 | 2002-08-23 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCA045 |  | 1015 | 2002-08-23 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCA046 |  | 1015 | 2002-08-30 | mechanical | CM | cold mass main body | use as is | stacking factor too high | 0
NCR | 02LHCA046 |  | 1016 | 2002-08-30 | mechanical | CM | cold mass main body | use as is | stacking factor too high | 0
NCR | 02LHCA051 |  | 1016 | 2002-10-03 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCA054 |  | 1016 | 2002-10-22 | alignment | CM | cold mass main body | use as is | twist out of tolerance | 0
NCR | 02LHCA046 |  | 1017 | 2002-08-30 | mechanical | CM | cold mass main body | use as is | stacking factor too high | 0
NCR | 02LHCA050 |  | 1017 | 2002-10-03 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCA053 |  | 1017 | 2002-10-14 | alignment | CM | cold mass main body | use as is | twist out of tolerance | 0
NCR | 02LHCA046 |  | 1018 | 2002-08-30 | mechanical | CM | cold mass main body | use as is | stacking factor too high | 0
NCR | 02LHCA059 |  | 1018 | 2002-12-05 | electrical | CM | cold mass | use as is | bus bar 14 and 15 inversed | 0
NCR | 02LHCA060 |  | 1018 | 2002-12-09 | alignment | CM | cold mass main body | use as is | twist out of tolerance | 0
NCR | 02LHCA061 |  | 1018 | 2002-12-10 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCA056 |  | 1019 | 2002-11-07 | mechanical | CM | cold mass | repair | end cover position out of tolerance, repair by welding | 0
NCR | 02LHCA057 |  | 1019 | 2002-11-15 | alignment | CM | cold mass main body | use as is | twist out of tolerance | 0
NCR | 02LHCA058 |  | 1019 | 2002-11-22 | electrical | CM | cold mass | repair | bus bar cables M1 damaged | 0
NCR | 02LHCA037 |  | 1020 | 2002-07-02 | blank | blank | blank | blank
NCR | 02LHCA052 |  | 1020 | 2002-10-14 | electrical | CM | collared coil | repair | short between spires, repair coil | 0
NCR | 02LHCA055 |  | 1021 | 2002-11-07 | alignment | CM | cold mass main body | repair | shape out of tolerance, new shells
NCR | 03LHCA073 |  | 1021 | 2003-03-10 | alignment | CM | cold mass main body | use as is | twist out of tolerance | 0
NCR | 03LHCA063 |  | 1022 | 2003-01-10 | alignment | CM | cold mass main body | use as is | twist out of tolerance | 0
NCR | 03LHCA064 |  | 1022 | 2003-01-13 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 03LHCA062 |  | 1023 | 2003-01-09 | alignment | CM | cold mass | use as is | twist out of tolerance | 0
NCR | 03LHCA065 |  | 1023 | 2003-01-13 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 02LHCJ005B |  | 1023 | 2003-02-26 | mechanical | CC | coil | use as is | disalignment 2 spires block 6 and 1 spire block 5 | 0
NCR | 03LHCA067 |  | 1023 | 2003-01-24 | electrical | CM | cold mass | repair | bus bars conductors damaged | 0
NCR | 03LHCA071 |  | 1023 | 2003-01-24 | alignment | CM | cold mass | use as is | M1, M2, M3 flanges out of tolerance | 0
NCR | 02LHCJ006A |  | 1024 | 2002-04-25 | irriversible damage | CC | coil | reject | glueing fault between spires | 1
NCR | 02LHCJ007A |  | 1024 | 2002-04-26 | irriversible damage | CC | coil | reject | glueing fault between spires | 1
NCR | 02LHCJ009B |  | 1024 | 2002-05-06 | mechanical | CC | coil | use as is | disalignment between spires | 0
NCR | 02LHCJ010B |  | 1024 | 2002-05-03 | mechanical | CC | coil | use as is | disalignment between spires | 0
NCR | 02LHCJ011B |  | 1024 | 2002-05-06 | mechanical | CC | coil | use as is | disalignment between spires | 0
NCR | 03LHCA068 |  | 1024 | 2003-01-21 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 03LHCA069 |  | 1024 | 2003-01-21 | alignment | CM | cold mass | use as is | twist and central foot out of tolerance | 0
NCR | 03LHCA070 |  | 1025 | 2003-01-21 | mechanical | CM | cold mass main body | use as is | longitudinal welding coupons non-conform | 0
NCR | 03LHCA072 |  | 1025 | 2003-02-06 | mechanical | CM | cold mass | use as is | stacking factor too high | 0
NCR | 02LHCJ012B |  | 1026 | 2002-05-15 | mechanical | CC | coil | use as is | disalignment between spires | 0
NCR | 02LHCJ013B |  | 1026 | 2002-05-24 | mechanical | CC | coil | use as is | disalignment between spires | 0
NCR | 03LHCA049 |  | 1026 | 2002-09-23 | electrical | CC | pole | repair | cable too short from layer 1 in pole | 0
NCR | 02LHCJ014B |  | 1027 | 2002-06-05 | mechanical | CC | coil | use as is | disalignment between spires | 0
NCR | 03LHCA077 |  | 1027 | 2003-04-14 | alignment | CM | cold mass main body | use as is | flanges lyre side out of tolerance | 0
NCR | 02LHCJ017B |  | 1028 | 2002-06-27 | electrical | CC | coil | repair | strand damaged | 0
NCR | 03LHCA075 |  | 1028 | 2003-03-21 | electrical | CM | cold mass | repair | cold bore tube insulation not far enough | 0
NCR | 02LHCJ008B |  | 1029 | 2002-04-29 | mechanical | CC | coil | use as is | disalignment between spires | 0
NCR | 03LHCA066 |  | 1029 | 2003-01-15 | electrical | CM | cold mass | repair | Temperature sensor contact cut | 0
NCR | 02LHCJ016B |  | 1031 | 2002-06-26 | irriversible damage | CC | coil | reject | strand damaged in press | 1
NCR | 02LHCJ015B |  | 1031 | 2002-06-21 | mechanical | CC | coil | repair | disalignment between spires | 0
NCR | 03LHCA078 |  | 1032 | 2003-05-05 | electrical | CM | cold mass main body | repair | Temperature sensor damaged
NCR | 02LHCJ018 |  | 1033 | 2002-07-30 | mechanical | CC | coil | use as is | disalignment between spires | 0
NCR | 02LHCJ019 |  | 1033 | 2002-07-30 | mechanical | CC | coil | use as is | disalignment between spires | 0
NCR | 02LHCJ020 |  | 1033 | 2002-07-30 | mechanical | CC | coil | use as is | disalignment between spires | 0
NCR | 02LHCJ021 |  | 1033 | 2002-10-04 | mechanical | CC | coil | repair | disalignment between spires | 0
NCR | 02LHCJ022 |  | 1033 | 2002-10-15 | electrical | CC | coil | repair | insulation damaged on layer | 0
NCR | 03LHCA079 |  | 1033 | 2003-05-16 | alignment | CM | cold mass | use as is | twist out of tolerance | 0
NCR | 03LHCA080 |  | 1034 | 2003-06-03 | alignment | CM | cold mass | use as is | twist and end cover out of tolerance | 0
NCR | 03LHCA082 |  | 1035 | 2003-06-25 | alignment | CM | cold mass | use as is | shape out of tolerance | 0
NCR | 03LHCA074 |  | 1035 | 2003-03-17 | mechanical | CC | collared coil | repair | damage on cold bore tube after collision | 0
NCR | 03LHCA083 |  | 1035 | 2003-06-25 | electrical | CM | cold mass | use as is | three stands at M3 bus bar end sliced | 0
NCR | 03LHCA092 |  | 1037 | 2003-03-17 | alignment | CM | cold mass | use as is | shape out of tolerance | 0
NCR | 03LHCA081 |  | 1038 | 2003-06-19 | alignment | CM | cold mass | use as is | twist out of tolerance | 0
NCR | 03LHCA086 |  | 1039 | 2003-08-11 | alignment | CM | cold mass | use as is | shape out of tolerance | 0
NCR | 03LHCA088 |  | 1040 | 2003-09-25 | alignment | CM | cold mass | use as is | shape out of tolerance | 0
NCR | 03LHCA090 |  | 1040 | 2003-08-14 | electrical | CM | cold mass | repair | superconducting cable cut off too short | 0
NCR | 03LHCA087 |  | 1041 | 2003-07-11 | alignment | CM | cold mass | use as is | shape out of tolerance | 0
NCR | 03LHCA091 |  | 1041 | 2003-08-21 | electrical | CM | cold mass | repair | half moon bus bar connection scratched | 0
NCR | 03LHCJ048A |  | 1042 | 2003-06-18 | mechanical | CC | coil | repair | fill in holes in coil end spacers | 0
NCR | 03LHCJ056A |  | 1042 | 2003-07-28 | electrical | CC | pole | repair | insulation damaged on layer | 0
NCR | 03LHCJ057A |  | 1042 | 2003-07-28 | electrical | CC | pole | repair | insulation damaged on layer | 0
NCR | 03LHCA085 |  | 1042 | 2003-07-10 | alignment | CM | cold mass | use as is | shape out of tolerance | 0
NCR | 03LHCJ023A |  | 1043 | 2003-01-24 | irriversible damage | CC | pole | reject | inner layer size out of tolerance | 1
NCR | 03LHCA084 |  | 1045 | 2003-07-09 | alignment | CM | cold mass | use as is | shape (H) and feet (V) out of tolerance feet | 0
NCR | 03LHCA089 |  | 1045 | 2003-07-15 | mechanical | CM | cold mass | use as is | flanges damaged | 0
NCR | 03LHCJ024A |  | 1046 | 2003-02-17 | mechanical | CC | pole | repair | inner layer size out of tolerance, recombine | 0
NCR | 03LHCJ025A |  | 1047 | 2003-02-18 | mechanical | CC | pole | repair | inner layer size out of tolerance, recombine | 0
NCR | 03LHCJ30A |  | 1050 | 2003-03-24 | mechanical | CC | pole | use as is | inner layer size out of tolerance, recombine | 0
NCR | 03LHCJ31A |  | 1051 | 2003-03-24 | mechanical | CC | pole | use as is | inner layer size out of tolerance | 0
NCR | 03LHCA095 |  | 1051 | 2003-09-11 | alignment | CM | cold mass | use as is | shape out of tolerance | 0
NCR | 03LHCJ037A |  | 1052 | 2003-05-19 | mechanical | CC | pole | repair | inner layer size out of tolerance, re-measure | 0
NCR | 03LHCA094 |  | 1053 | 2003-09-11 | alignment | CM | cold mass | use as is | shape out of tolerance | 0
NCR | 03LHCJ029A |  | 1053 | 2003-03-14 | mechanical | CC | coil | repair | wrong wedge used | 0
NCR | 03LHCJ028A |  | 1054 | 2003-03-05 | electrical | CC | coil | use as is | cable insulation operation not done according to spec | 0
NCR | 03LHCJ038A |  | 1054 | 2003-06-11 | mechanical | CC | coil | repair | fill in holes in coil end spacers | 0
NCR | 03LHCJ33A |  | 1055 | 2003-04-25 | mechanical | CC | pole | use as is | inner layer size out of tolerance | 0
NCR | 03LHCA096 |  | 1055 | 2003-08-22 | electrical | CM | cold mass | repair | half moon bus bar connection not nickeled | 0
NCR | 03LHCJ028A |  | 1055 | 2003-03-05 | electrical | CC | coil | use as is | cable insulation operation not done according to spec | 0
NCR | 03LHCJ028A |  | 1056 | 2003-03-05 | electrical | CC | coil | use as is | cable insulation operation not done according to spec | 0
NCR | 03LHCJ047A |  | 1056 | 2003-06-18 | mechanical | CC | coil | repair | fill in holes in coil end spacers | 0
NCR | 03LHCJ036A |  | 1056 | 2003-05-19 | electrical | CC | pole | repair | insulation on an inner layer damaged, strand misaligned | 0
NCR | 03LHCJ049A |  | 1056 | 2003-06-24 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ032A |  | 1057 | 2003-04-07 | electrical | CC | pole | repair | strand damaged during layer jump box mounting | 0
NCR | 03LHCJ039A |  | 1057 | 2003-06-12 | mechanical | CC | coil | repair | fill in holes in coil end spacers | 0
NCR | 03LHCJ035A |  | 1058 | 2003-05-14 | electrical | CC | pole | repair | insulation on an inner layer damaged | 0
NCR | 03LHCJ040A |  | 1058 | 2003-06-12 | mechanical | CC | coil | repair | fill in holes in coil end spacers | 0
NCR | 03LHCJ043A |  | 1058 | 2003-06-13 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCA093 |  | 1059 | 2003-09-03 | alignment | CM | cold mass | use as is | shape out of tolerance | 0
NCR | 03LHCJ041A |  | 1059 | 2003-06-12 | mechanical | CC | coil | repair | fill in holes in coil end spacers | 0
NCR | 03LHCJ044A |  | 1059 | 2003-06-13 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ046A |  | 1060 | 2003-06-13 | mechanical | CC | coil | repair | fill in holes in coil end spacers | 0
NCR | 03LHCJ045A |  | 1060 | 2003-06-13 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ042A |  | 1062 | 2003-06-13 | irriversible damage | CC | coil | reject | inner layer saturated with oil from curing press | 1
NCR | 03LHCJ052A |  | 1062 | 2003-07-08 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ050A |  | 1062 | 2003-06-30 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ054A |  | 1062 | 2003-07-11 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ058A |  | 1062 | 2003-07-28 | electrical | CC | pole | repair | insulation on an outer layer damaged | 0
NCR | 03LHCJ053A |  | 1063 | 2003-07-09 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ055A |  | 1065 | 2003-07-24 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ034B |  | 1067 | 2003-04-25 | electrical | CC | coil | use as is | cable insulation checks not done according to spec | 0
NCR | 03LHCJ064A |  | 1067 | 2003-09-18 | electrical | CC | pole | repair | layer jump box mounting, cable squeezed | 0
NCR | 03LHCJ065A |  | 1067 | 2003-09-19 | electrical | CC | pole | repair | insulation on an inner layer damaged | 0
NCR | 03LHCJ059A |  | 1067 | 2003-08-29 | electrical | CC | pole | use as is | insulation on an inner layer damaged | 0
NCR | 03LHCJ051A |  | 1069 | 2003-07-04 | mechanical | CC | coil | use as is | cable insulation external aspect is different | 0
NCR | 03LHCJ062A |  | 1072 | 2003-09-18 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ063A |  | 1073 | 2003-09-18 | mechanical | CC | pole | use as is | coil end curing mould overheated | 0
NCR | 03LHCJ061A |  | 1075 | 2003-09-17 | electrical | CC | pole | repair | insulation on a wedge damaged | 0
NCR | 03LHCJ066A |  | 1075 | 2003-09-24 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ070A |  | 1075 | 2003-09-30 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ067A |  | 1076 | 2003-09-26 | mechanical | CC | pole | repair | layer jump box badly aligned | 0
NCR | 03LHCJ068A |  | 1076 | 2003-09-29 | mechanical | CC | pole | repair | layer jump box badly aligned | 0
NCR | 03LHCJ072A |  | 1076 | 2003-10-02 | mechanical | CC | pole | repair | layer jump box fissured | 0
NCR | 03LHCJ069A |  | 1082 | 2003-09-29 | electrical | CC | coil | use as is | discoloured spot on cable end | 0

## TEMP
Numéro NCR |  | Numéro PV |  |  | Envoi électronique | Décision CERN | Clôture ALSTOM
| N° de série de l'aimant |  | Descriptif succinct | Solution proposée
01LHCA001 | HCMBB_A001 01 000001 | F088 | Mesure finale de twist hors tolérance | accepter en l'état | 2001-05-28 | 2001-08-01 | 2002-06-10
01LHCA002 | HCMBB_A001 01 000002 | F092 | Tôles en acier dans les paquets livrés par CERN | accepter en l'état | 2001-05-28 | 2001-08-01 | 2002-06-10
01LHCA003 | HCMBB_A001 01 000002 | F080 | Usinage de la frette coté CNC réalisé à l'envers | ajouter une bague, souder et contrôler | 2001-05-28 | 2001-08-01 | 2002-06-10
01LHCA004 | HCMBBRA001 01 000004 | F109-F110 | Paquets d'inserts standards et paquets d'extrémité | accepter en l'état | 2001-07-06 | 2002-03-22 | 2002-03-27
01LHCA005 | HCMBB_A001 01 000004 | F114 | Sonde de température déplacée | accepter en l'état | 2001-07-06 | 2001-08-01 | 2002-03-27
01LHCA006 | HCMBB_A001 01 000003 | F117 | Pied côté connexion hors tolérance | accepter en l'état | 2001-08-21 | 2002-02-06 | 2002-02-06
01LHCA007 | HCMBB_A001 01 000003 | F117 | Mesure de courbure hors tolérance | accepter en l'état | 2001-08-21 | 2002-02-06 | 2002-02-06
01LHCA008 | HCMBB_A001 01 000003 | / | Coupons témoins soudure longitudinale | accepter en l'état | 2001-08-21 | 2002-02-06 | 2002-02-06
01LHCA009 | HCMBB_A001 01 000003 | F139 | Position des tubes faisceaux | accepter en l'état | 2001-11-06 | 2002-02-06 | 2002-02-06
02LHCA010 | HCMBB_A001 01 000005 | F165 | Essais sur coupons des frettes non conformes | concevoir un outillage de maintien | 2002-01-15 | 2002-02-06 | 2002-04-30
01LHCA011 | HCMBBRA001 01 000006 | F163 | Soudure longitudinale des frettes défectueuse coté R | réparer selon indications CERN | 2001-12-21 | 2002-02-06 | 2002-05-23
02LHCA012 | HCMBBRA001 01 000004 | 02-473 | Soudures longitudinales des frettes défectueuses | réparer selon indications ARISI | 2002-01-03 | 2002-02-06 | 2002-03-27
02LHCA013 | HCMBB_A001 01 000005 | F173 | Sonde de température coupée après soudage fonds | accepter en l'état | 2002-02-04 | 2002-02-06 | 2002-02-06
02LHCA014 | HCMBBRA001 01 000004 | F172 | Courbure de la masse froide non conforme | accepter en l'état | 2002-01-15 | 2002-02-06 | 2002-03-27
02LHCA015 | HCMBBRA001 01 000005 | F168 | Deux câbles des bus bars auxiliaires endommagés | réparer selon indications PV F168 | 2002-01-15 | 2002-02-06 | 2002-03-27
02LHCA016 | HCMBBRA001 01 000004 | F177 | Cote minimale d'épaisseur des frettes non respectée | décentrer le fond selon indications | 2002-02-04 | 2002-02-06 | 2002-03-27
02LHCA017 | HCMBBRA001 01 000004 | / | Essais sur coupons des frettes non conformes | accepter en l'état | 2002-02-18 | 2002-02-28 | 2002-03-27
02LHCA018 | HCMBBRA001 01 000006 | / | Essais sur coupons des frettes S1 non conformes | accepter en l'état | 2002-02-18 | 2002-02-28 | 2002-05-23
02LHCA019 | HCMBBRA001 01 000008 | F187 | Défauts sur soudures longitudinales (vus en radio) | réparer en TIG et radiographier | 2002-02-27 | 2002-03-04 | 2002-04-24
02LHCA020 | HCMBBRA001 01 000007 | F194 | Défauts sur soudures longitudinales (vus en radio) | réparer en TIG et radiographier | 2002-02-27 | 2002-03-04 | 2002-06-10
02LHCA021 | HCMBBRA001 01 000006 | F195 | Manque de fusion au nœud de soudure S2 / S58 | accepter en l'état | 2002-02-27 | 2002-03-04 | 2002-05-23
02LHCA022 | HCMBB_A001 01 000005 | F203 | Mesure géométrique des collerettes hors spécification | CERN : réparer avant Cold tests | 2002-03-06 | 2002-03-22 | 2002-06-10
02LHCA023 | HCMBBRA001 01 000006 | F197 | Longueur de la masse froide hors spécification. | réparer selon procédure jointe | 2002-03-05 | 2002-03-22 | 2002-05-23
02LHCA024 | HCMBBRA001 01 000007 | F201 | Défaut de géométrie sur les tubes V1 et V2 | CERN:corriger la courbure de l'aimant | 2002-03-07 | mail 25/03 | 2002-06-10
02LHCA025 | HCMBBRA001 01 000009 | F209 | Défauts sur soudures longitudinales (vus en radio) | CERN : changer les 2 frettes | 2002-03-14 | 2002-03-22
|  | F209 revB |  | réparer sur presse au CERN | 2002-09-06 | 2002-09-17 | 2002-09-26
02LHCA026 | HCMBBRA001 01 000008 | / | Essais sur coupons des frettes non conformes | accepter en l'état | 2002-03-14 | 2002-03-22 | 2002-03-27
02LHCA027 | HCMBBRA001 01 000007 | / | Essais sur coupons des frettes non conformes | accepter en l'état | 2002-03-26 | 2002-04-02 | 2002-06-10
02LHCA028 | HCMBBRA001 01 000004 | F210 | Relevé géométrique des collerettes hors tolérances | réparer selon procédure proposée | 2002-03-28 | 2002-04-02 | 2002-04-23
02LHCA029 | HCMBBRA001 01 000006 | F226 | Mesure géométrique des tubes hors tolérance (3 pts) | accepter en l'état | 2002-04-12 | 2002-05-17 | 2002-05-25
02LHCA030 | HCMBBRA001 01 000010 | F227 | Mesure géométrique de l'aimant hors tolérances | réparer | 2002-04-15 | 2002-05-17 | 2002-06-10
02LHCA031 | HCMBBRA001 01 000010 | F229 | Défauts sur soudures longitudinales (vus en radio) | réparer en TIG et radiographier | 2002-04-16 | 2002-04-19 | 2002-06-10
02LHCA032 | HCMBBRA001 01 000004 | / | Centre fond bombé CC décalé | accepter en l'état | 2002-04-19 | 2002-04-23 | 2002-04-23
02LHCA033 | HCMBBRA001 01 000006 | F239 | Position verticale des pieds CC et CNC hors tolérance | accepter en l'état | 2002-04-29 | 2002-05-03 | 2002-05-23
02LHCA034 | HCMBBRA001 01 000007 | F238 | Un point de twist est hors tolérance | accepter en l'état | 2002-05-28 | 2002-06-05 | 2002-06-11
02LHCA035 | HCMBARA001 01 000011 | F248 | Câble D' coupé trop court | réparer selon procédure jointe | 2002-05-30 | 2002-06-05 | 2002-06-12
02LHCA036 | HCMBBRA001 01 000007 | F247 | Sonde de température coupée | accepter en l'état | 2002-06-06 | 2002-06-19 | 2002-06-25
02LHCA037 | HCMBBRA001 01 000020 | F269 | Inversion des fils orange/ vert clair de 2 chaufferettes | accepter en l'état | 2002-07-02 | 2002-07-15 | 2003-03-18
02LHCA038 | HCMBARA001 01 000012 | 09CT | Essais sur coupons des frettes non conformes | accepter en l'état | 2002-07-10 | 2002-07-26 | 2002-07-26
[6 empty] | (stand-by) | (stand-by)
02LHCA039 | HCMBARA001 01 000013 | F272 | Twist hors tolérance | accepter en l'état | 2002-09-06 | 2002-09-12 | 2002-09-03
02LHCA040 | HCMBARA001 01 000013 | / | Essais sur coupons des frettes non conformes | accepter en l'état | 2002-07-16 | 2002-09-12 | 2002-09-13
[6 empty] | (stand-by) | (stand-by)
02LHCA041 | HCMBARA001 01 000012 | F281 | Twist hors tolérance | accepter en l'état | 2002-07-24 | 2002-07-24 | 2002-07-25
02LHCA042 | HCMBARA001 01 000012 | F282 | Fond bombé côté Lyre hors tolérance | accepter en l'état | 2002-07-25 | 2002-07-26 | 2002-07-26
02LHCA043 | HCMBARA001 01 000013 | F283 | Longueur hors tolérance | accepter en l'état | 2002-08-13 | 2002-08-28 | 2002-09-13
02LHCA044 | HCMBARA001 01 000014 | I.S. 11CT | Essais sur coupons des frettes non conformes | accepter en l'état | 2002-08-23 | 2002-09-11 | 2002-09-11
[6 empty] | (stand-by) | (stand-by)
02LHCA045 | HCMBBRA001 01 000015 | I.S. 11CT | Essais sur coupons des frettes non conformes | accepter en l'état | 2002-08-23 | 2002-09-17 | 2002-09-26
(stand-by)
02LHCA046 | HCMBBRA001 01 000015 | F287 | Coefficient de foisonnement hors tolérances | accepter en l'état | 2002-08-30 | 2002-09-17 | 2002-09-26
0016 / 0017 / 0018 .
02LHCA047 | HCMBBRA001 01 000009 | F209 revB | Essais sur coupons S2 des frettes non réalisés | accepter en l'état | 2002-09-06 | 2002-09-25 | 2002-09-26
(stand-by)
02LHCA048 | HCMBBRA001 01 000009 | F295 | Défaut sur l'axe vertical de l'aimant | réparer selon proposition | 2002-09-17 | 2002-09-25 | 2002-09-26
02LHCA049 | HCMBBRA001 01 000026 | F308 | Câble 1ère couche du pôle JP 101 coupé trop court | réparer selon proposition | 2002-09-23 | 2002-12-03 | 2003-02-25
02LHCA050 | HCMBBRA001 01 000017 | / | Essais sur coupons des frettes non conformes | accepter en l'état | 2002-10-03 | 2002-10-08 | 2002-10-10
(stand-by)
02LHCA051 | HCMBBRA001 01 000016 | / | Essais sur coupons des frettes non conformes | accepter en l'état | 2002-10-03 | 2002-10-08 | 2002-10-10
(stand-by)
02LHCA052 | HCMBBRA001 01 000020 | F 275 | Proposition de réparation du pôle JP77 | réparer selon proposition | 2002-10-14 | 2002-10-17 | 2003-03-18
02LHCA053 | HCMBBRA001 01 000017 | F 337 | Twist hors tolérance | accepter en l'état | 2002-10-14 | 2002-10-16 | 2002-10-16
02LHCA054 | HCMBBRA001 01 000016 | F 347 | Twist hors tolérance | accepter en l'état | 2002-10-22 | 2002-10-24 | 2002-10-25
02LHCA055 | HCMBBRA001 01 000021 | / | Courbure non satisfaisante (conforme spec) en sortie de presse | annulation de la NCR | 2002-11-07 | 2002-11-15 | 2002-11-15
02LHCA056 | HCMBBRA001 01 000019 | F349 | Inclinaison fond bombé non conforme | réparer selon proposition | 2002-11-07 | 2002-11-15 | 2002-11-15
02LHCA057 | HCMBBRA001 01 000019 | F379 | Twist hors tolérance | accepter en l'état | 2002-11-15 | 2002-11-15 | 2002-11-18
02LHCA058 | HCMBBRA001 01 000019 | F387 | Conducteur bus bar aux. M1 coté CC endommagé | réparer selon proposition | 2002-11-22 | 2002-11-28 | 2002-12-03
02LHCA059 | HCMBBRA001 01 000018 | F397 | Bus bars auxiliaires 14 et 15 inversés coté CNC | accepter en l'état | 2002-12-05 | 2002-12-06 | 2002-12-12
02LHCA060 | HCMBBRA001 01 000018 | F369 | Twist hors tolérance | accepter en l'état | 2002-12-09 | 2002-12-12 | 2002-12-12
02LHCA061 | HCMBBRA001 01 000018 | I.S.16CT | Essais sur coupons des frettes non conformes | accepter en l'état | 2002-12-10 | 2002-12-10 | 2002-12-10
03LHCA062 | HCMBBRA001 01 000023 | F380 | Twist hors tolérance à une extrémité | accepter en l'état | 2003-01-09 | 2003-01-10 | 2003-01-10
03LHCA063 | HCMBBRA001 01 000022 | F377 | Twist hors tolérance aux deux extrémités | accepter en l'état | 2003-01-10 | 2003-01-10 | 2003-01-10
03LHCA064 | HCMBBRA001 01 000022 | / | Essais sur coupons témoins non réalisés | accepter en l'état | 2003-01-13 | 2003-01-14 | 2003-01-14
03LHCA065 | HCMBBRA001 01 000023 | / | Essais sur coupons témoins non réalisés | accepter en l'état | 2003-01-13 | 2003-01-14 | 2003-01-14
03LHCA066 | HCMBBRA001 01 000029 | / | Sonde de température endommagée | réparer selon proposition | 2003-01-15 | 2003-01-21 | 2003-03-10
03LHCA067 | HCMBBRA001 01 000023 | F414 | Trois conducteurs bus bars endommagés | réparer selon proposition | 2003-01-15 | 2003-01-21 | 00/00/00
révision B |  | F414 A | Demande client brasage câble lg. 100mm | réparation effectuée lg. 60mm | 2003-01-24 | 2003-01-27 | 2003-01-27
03LHCA068 | HCMBBRA001 01 000024 | / | Essais sur coupons témoins non réalisés | accepter en l'état | 2003-01-21 | 2003-01-22 | 2003-01-22
03LHCA069 | HCMBBRA001 01 000024 | / | Twist et semelle centrale hors tolérance | accepter en l'état | 2003-01-21 | 2003-01-22 | 2003-01-22
03LHCA070 | HCMBBRA001 01 000025 | / | Essais sur coupons témoins réalisés partiellement | accepter en l'état | 2003-01-21 | 2003-01-22 | 2003-01-22
03LHCA071 | HCMBBRA001 01 000023 | F429 | Position des anneaux à souder hors tolérance | réparer selon proposition | 2003-01-24 | 2003-01-27 | 2003-01-27
03LHCA072 | HCMBBRA001 01 000025 | / | Coefficient de foisonnement demi-c sup. hors tolérances | accepter en l'état | 2003-02-06 | 2003-02-06 | 2003-02-06
03LHCA073 | HCMBBRA001 01 000021 | F460 | Twist hors tolérance à une extrémité | accepter en l'état | 2003-03-10 | 2003-03-11 | 2003-03-11
03LHCA074 | HCMBBRA001 01 000037 | F462 | Tube faisceau UP2 endommagé en sortie de collaring | réparer selon proposition | 2003-03-17 | 2003-03-19 | 2003-03-31
03LHCA075 | HCMBBRA001 01 000028 | F472 | Isolation trop courte sur tube faisceau UP2 | réparer selon proposition | 2003-03-21 | 2003-04-02 | 2003-04-02
03LHCA076 | N-LINE 0072 + N-LINE 0074 | F478 | Lignes N trop courtes | réparer selon proposition | 2003-03-25 | 2003-04-02
03LHCA077 | HCMBBRA001 01 000027 | F503 | Positionnement des embouts coté lyre hors tolérance. | accepter en l'état | 2003-04-14 | 2003-04-15 | 2003-04-15
03LHCA078 | HCMBBRA001 01 000032 | F515 | Sonde de température endommagée | réparer selon proposition | 28/04/03 05/05/03 | 2003-04-28 | 00/00/00
révision B |  |  |  | isolation des fils endommagés pdt rép. |  | 2003-05-22 | 2003-05-22
03LHCA079 | HCMBBRA001 01 000033 | F525 | Twist hors tolérance à une extrémité | accepter en l'état | 2003-05-16 | 2003-05-21 | 2003-05-21
03LHCA080 | HCMBBRA001 01 000034 | F546 | Twist hors tolérance et position du fond CC hors tolér. | accepter en l'état | 2003-06-03 | 00/00/00 | 00/00/00
révision B |  |  | Ajout : courbure non conforme, acceptée par CERN | accepter en l'état | 2003-06-03

## done
done table | 1001 | done
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070