## legend
Nomenclature to be used
assemblies
CC | up to collared coil warm magnetic measurement approved
CM | from collared coil magnetic measurement up to shipment
sub-assemblies
coil | from SC cable to surfaced layers
pole | from surfaced coil to connected pole
dipole | from pole to dipoles ready with coil protection sheet
collared coil | from coil protection sheet to warm magnetic measurement
cold mass main body | from yoking till end of longitudinal welding
cold mass | from longitudinal welding till shipment
typology
electrical | affecting electrical properties
mechanical | damage affecting mechanical (and electrical) properties
irriversible damage | i.e. layer with cut strand
traceability | CoC not avaialable
raw material | raw material not conform to tech spec
component | component received or used not conform to tech spec
action
use as is
repair
reject | sub-assembly rejected, no repair possible (layer)
dismantle | repairing needs de-collaring or cutting of long weld
replace | the component non according to spec will be replaced (stock not magnet)
in green NCR in process or managed internal by the firm
in red NCR where the file is not available at CERN

## NCR list
code | N | type | magnet | date | typology | Assembly | sub-assembly | action | Affected object and explication | Cable amount to be replaced
QN | 1 |  | 3001 | 1999-11-08 | component | CC |  | repair | dirty copper wedges, no CoC
QN | 2 | internal | 3001 | 1999-11-08 | mechanical | CC | coil | repair | insualtion of copper wedge extremity not conform, change before use
QN | 3 |  | 3006 | 2000-01-25 | component | CC | coil | repair | dirty SC cable 2m
QN | 4 |  | 3003 | 2000-01-31 | component | CC | pole | use as is | missing CoC ground insulation
QN | 4 |  | 3004 | 2000-01-31 | component | CC | pole | use as is | missing CoC ground insulation
QN | 5 |  | 3002 | 2000-03-01 | component | CC | coil | use as is | missing CoC stabilisers
QN | 6 |  | 3004 | 2000-03-13 | component | CC | coil | use as is | missing CoC copper wedges
QN | 7 |  | 3003 | 2000-10-11 | component | CC | coil | repair | outer layer spacer cut of 6 mm
QN | 8 |  | 3001 | 2001-08-30 | mechanical | CM | cold mass | use as is | geometical measurements out of tolerance
QN | 9 |  | 3002 | 2001-08-30 | mechanical | CM | cold mass | use as is | geometical measurements out of tolerance
QN | 10 |  | 3001 | 2002-03-06 | traceability | CM | cold mass main body | use as is | long weld
QN | 10 |  | 3002 | 2002-03-06 | traceability | CM | cold mass main body | use as is | long weld
QN | 11 |  | 3003 | 2002-02-15 | traceability | CM | cold mass | use as is | sextupole
QN | 11 |  | 3004 | 2002-02-15 | traceability | CM | cold mass | use as is | sextupole
QN | 11 |  | 3005 | 2002-02-15 | traceability | CM | cold mass | use as is | sextupole
QN | 12 |  | 3006 | 2002-02-26 | irriversible damaged | CC | coil | rejected | outer layer | 1
QN | 13 |  | 3003 | 2002-02-28 | component | CM |  | use as is | collars
QN | 14 |  | 3003 | 2002-03-08 | electrical | CM | cold mass | repair | diode
QN | 15 | internal
QN | 16 |  | 3014 | 2003-03-04 | mechanical | CM | cold mass | repair | long weld
QN | 17 |  | 3003 | 2002-02-17 | electrical | CM | cold mass | repair | instrumentation wires
QN | 17 |  | 3003 | 2002-06-13 | electrical | CM | cold mass | repair | instrumentation wires
QN | 18 |  | 3004 | 2002-08-05 | mechanical | CM | cold mass | repair | extremities alignement
QN | 18 |  | 3004 | 2002-06-10 | mechanical | CM | cold mass | repair | extremities alignement
QN | 19 |  | 3003 | 2002-07-09 | mechanical | CM | cold mass | use as is | extremities alignement
QN | 19 |  | 3003 | 2002-06-20 | mechanical | CM | cold mass | use as is | extremities alignement
QN | 20 |  | 3005 | 2002-06-11 | mechanical | CM | cold mass main body | repair | curvature
QN | 21 |  | 3004 | 2002-06-20 | traceability | CM | cold mass main body | use as is | long weld
QN | 21 |  | 3005 | 2002-06-20 | traceability | CM | cold mass main body | use as is | long weld
QN | 22 |  | 3004 | 2002-06-10 | electrical | CM | cold mass | repair | diode
QN | 23 |  | 3012 | 2002-06-20 | mechanical | CC | coil | use as is | outer layer nor perfectly glued
QN | 23 |  | 3013 | 2002-06-20 | mechanical | CC | coil | use as is | outer layer nor perfectly glued
QN | 23 |  | 3010 | 2002-06-20 | mechanical | CC | coil | use as is | outer layer nor perfectly glued
QN | 23 |  | 3014 | 2002-06-20 | mechanical | CC | coil | use as is | outer layer nor perfectly glued
QN | 23 |  | 3015 | 2002-06-20 | mechanical | CC | coil | use as is | outer layer nor perfectly glued
QN | 24 |  | 3011 | 2002-07-10 | electrical | CC | pole | dismantle | short circuit between layers
QN | 25 |  | 3012 | 2002-07-03 | electrical | CC | dipole | dismantle | Q.H. failure
QN | 26 |  | 3013 | 2002-10-28 | mechanical | CC | dipole | repair | collaring problem on the heads
QN | 27 |  | 3004 | 2002-07-31 | raw material | CM | cold mass | use as is | extremities
QN | 27 |  | 3005 | 2002-07-31 | raw material | CM | cold mass | use as is | extremities
QN | 27 |  | 3006 | 2002-07-31 | raw material | CM | cold mass | use as is | extremities
QN | 27 |  | 3007 | 2002-07-31 | raw material | CM | cold mass | use as is | extremities
QN | 27 |  | 3008 | 2002-07-31 | raw material | CM | cold mass | use as is | extremities
QN | 28 |  | 3003 | 2002-12-04 | mechanical | CM | cold mass | repair | extremity. Welds fully penetrating, …
QN | 29 |  | 3004 | 2002-08-05 | mechanical | CM | cold mass main body | use as is | laminations assembly
QN | 30 |  | 3015 | 2002-08-19 | mechanical | CC | coil | repair | inner layer aaasembled with wrong copper wedges
QN | 31 |  | 3005 | 2003-02-20 | electrical | CM | cold mass main body | repair | temp sens
QN | 31 |  | 3005 | 2002-08-30 | electrical | CM | cold mass main body | repair | temp sens
QN | 32 |  | 3014 | 2002-08-26 | mechanical | CC | coil | use as is | curing accident
QN | 33 |  |  | 2002-08-28 | component | CM |  | substitute | bus bar
QN | 34 |  | 3005 | 2002-12-04 | mechanical | CM | cold mass | repair | length and other dimension of cold mass out of tolerance
QN | 35 |  | 3007 | 2002-12-04 | mechanical | CM | cold mass | repair | extr. Weld fully penetrating
QN | 36 |  | 3009 | 2002-09-10 | mechanical | CM | cold mass main body | repair | long weld
QN | 37 |  | 3007 | 2002-09-23 | traceability | CM |  | use as is | bus bar
QN | 37 |  | 3008 | 2002-09-23 | traceability | CM |  | use as is | bus bar
QN | 37 |  | 3009 | 2002-09-23 | traceability | CM |  | use as is | bus bar
QN | 37 |  | 3013 | 2002-09-23 | traceability | CM |  | use as is | bus bar
QN | 37 |  | 3007 | 2002-09-23 | traceability | CM |  | use as is | bus bar
QN | 37 |  | 3008 | 2002-09-23 | traceability | CM |  | use as is | bus bar
QN | 37 |  | 3009 | 2002-09-23 | traceability | CM |  | use as is | bus bar
QN | 37 |  | 3013 | 2002-09-23 | traceability | CM |  | use as is | bus bar
QN | 38 |  | 3017 | 2002-11-06 | electrical |  |  | repair | bus bar
QN | 39 |  | 3012 | 2002-10-15 | mechanical | CM | cold mass main body | repair | long weld
QN | 39 |  | 3012 | 2003-03-04 | mechanical | CM | cold mass main body | repair | long weld
QN | 40 |  | 3005 | 2003-02-14 | electrical | CM | cold mass | repair | sextupole | Sextupole
QN | 40 |  | 3003 | 2003-02-14 | electrical | CM | cold mass | repair | sextupole | Sextupole
QN | 40 |  | 3007 | 2003-02-14 | electrical | CM | cold mass | repair | sextupole | Sextupole
QN | 41 |  | 3006 | 2002-11-11 | mechanical | CM | cold mass main body | repair | long weld W1
QN | 42 |  | 3013 | 2002-11-07 | electrical | CM | cold mass | repair | diode
QN | 43 |  | 3011 | 2002-10-28 | mechanical | CC | collared coil | use as is | gap collars-colared coil end plate
QN | 43 |  | 3012 | 2002-10-28 | mechanical | CC | collared coil | use as is | gap collars-colared coil end plate
QN | 43 |  | 3013 | 2002-10-28 | mechanical | CC | collared coil | use as is | gap collars-colared coil end plate
QN | 44 |  | 3012 | 2002-11-20 | alignement | CM | cold mass main body | repair | curvature
QN | 45 |  | 3005 | 2002-11-20 | alignement | CM | cold mass main body | repair | curvature
QN | 46 | in process | [6 empty] | sextupole shunt ressitance
QN | 47 |  | 3003 | 2002-11-13 | traceability | CM |  | use as is | laminations assembly
QN | 48 |  | 3011 | 2002-11-14 | mechanical | CM | cold mass | repair | extremities
QN | 49 |  | 3009 | 2002-11-26 | electrical | CM | cold mass | repair | instrumentation wires damaged
QN | 50 |  | 3009 | 2003-12-12 | mechanical | CM | cold mass main body | repair | extremities, cold bore diameter
QN | 51 |  | 3006 | 2002-11-14 | mechanical | CM | cold mass | repair | end cover CS out of tolerance
QN | 52 |  | 3005 | 2003-02-26 | mechanical | CM | cold mass | use as is | extremities
QN | 52 |  | 3013 | 2003-02-26 | mechanical | CM | cold mass | use as is | extremities
QN | 53 |  | 3011 | 2003-01-20 | mechanical | CM | cold mass main body | repair | long weld
QN | 54 |  | 3006 | 2003-12-05 | mechanical | CM | cold mass main body | use as is | laminations assembly stacking factor
QN | 54 |  | 3008 | 2003-12-05 | mechanical | CM | cold mass main body | use as is | laminations assembly stacking factor
QN | 54 |  | 3009 | 2003-12-05 | mechanical | CM | cold mass main body | use as is | laminations assembly stacking factor
QN | 54 |  | 3011 | 2003-12-05 | mechanical | CM | cold mass main body | use as is | laminations assembly stacking factor
QN | 55 |  |  | 2003-12-18 | component | CM | cold mass | repair | bus bar | bus bar
QN | 56 |  | 3011 | 2002-12-05 | mechanical | CM | cold mass | use as is | extr. Weld to be rapaired
QN | 57 |  | 3011 | 2003-01-15 | mechanical | CM | cold mass main body | repair | long weld
QN | 58 |  | 3009 | 2003-12-12 | mechanical | CM | cold mass | repair | circ. Weld
QN | 59 |  | 3008 | 2003-03-04 | mechanical | CM | cold mass main body | repair | long weld
QN | 60 |  | 3009 | 2003-12-13 | mechanical | CM | cold mass main body | repair | long weld
QN | 61 | in process
QN | 62 |  | 3008 | 2003-01-21 | mechanical | CM | cold mass main body | repair | long weld
QN | 63 |  | 3003 | 2003-02-19 | mechanical | CC | collared coil | repair | CBT diameter
QN | 64 |  | 3009 | 2003-12-11 | electrical | CM | cold mass | repair | instrumentation wires
QN | 65 |  | 3006 | 2003-12-16 | mechanical | CM | cold mass | use as is | extremities
QN | 65 |  | 3012 | 2003-12-16 | mechanical | CM | cold mass | use as is | extremities
QN | 65 |  | 3013 | 2003-12-16 | mechanical | CM | cold mass | use as is | extremities
QN | 66 |  | 3020 | 2003-12-17 | electrical | CC | coil | repair | inner layer with metallic particle
QN | 67 |  | 3005 | 2003-03-04 | mechanical | CM | cold mass | repair | long weld
QN | 68 |  | 3018 | 2003-12-17 | mechanical | CC | coil | repair | outer layer not correclty glued
QN | 69 |  | 3013 | 2003-03-04 | mechanical | CM | cold mass main body | repair | long weld
QN | 70 |  | 3014 | 2003-03-04 | mechanical | CM | cold mass main body | repair | long weld
QN | 71 |  | 3007 | 2003-01-17 | mechanical | CM | cold mass main body | repair | long weld
QN | 72 |  |  | 2003-01-22 | component | CC |  | use as is | collars no clean | collars
QN | 73 | internal
QN | 74 | internal
QN | 75 |  | 3007 | 2003-02-07 | mechanical | CM | cold mass | repair | tightness
QN | 76 | internal
QN | 77 | internal
QN | 78 |  | 3005 | 2003-02-13 | alignement | CM | cold mass | use as is | extremities
QN | 79 |  | 3010 | 2003-02-06 | electrical | CC | collared coil | dismantle | Q.H. failure
QN | 80 |  | 3003 | 2003-02-18 | mechanical | CM | cold mass | use as is | feet alignement
QN | 81 |  | 3027 | 2003-02-07 | mechanical | CC | coil | repair | problem cable insulation
QN | 82 |  |  | 2003-02-14 | component | CC |  | replace | Q.H. | Q.H.
QN | 83 |  | 3005 | 2003-02-13 | electrical | CM | cold mass | repair | diode
QN | 84 |  |  | 2003-02-19 | component | CC |  | replace | Q.H. | Q.H.
QN | 84 |  |  | 2003-02-19 | component | CC |  | replace | Q.H. | Q.H.
QN | 85 |  | 3003 | 2003-02-20 | mechanical | CM | cold mass main body | use as is | laminations assembly
QN | 86 |  | 3005 | 2003-02-25 | traceability | CM | cold mass | use as is | warm magnetic measurements
QN | 86 |  | 3013 | 2003-02-25 | traceability | CM | cold mass | use as is | warm magnetic measurements
QN | 86 |  | 3014 | 2003-02-25 | traceability | CM | cold mass | use as is | warm magnetic measurements
QN | 86 |  | 3015 | 2003-02-25 | traceability | CM | cold mass | use as is | warm magnetic measurements
QN | 87 |  | 3013 | 2003-02-28 | mechanical | CM | cold mass | repair | extremities
QN | 88 |  |  | 2003-02-21 | component | CM |  | replace | N line provided by CERN not inspec
QN | 89 | internal
QN | 90 |  | 3005 | 2003-02-24 | mechanical | CM | cold mass main body | use as is | laminations assembly
QN | 91 |  | 3013 | 2003-03-03 | alignement | CM | cold mass | use as is | feet
QN | 92 |  | 3013 | 2003-03-04 | electrical | CM | cold mass | repair | M3-line
QN | 93 |  | 3013 | 2003-02-25 | electrical | CM | cold mass | repair | instrumentation wires
QN | 94 |  | 3012 | 2002-03-26 | alignement | CM | cold mass main body | repair | feet
QN | 95 |  | 3015 | 2003-03-03 | mechanical | CM | cold mass | repair | extremities
QN | 96 | internal
QN | 97 |  | 3008 | 2003-03-31 | alignement | CM | cold mass | use as is | feet alignement
QN | 98 |  | 3025 | 2003-03-05 | mechanical | CC | pole | repair | pole local daamge during measurements
QN | 99 |  | 3015 | 2003-03-07 | alignement | CM | cold mass | use as is | feet
QN | 100 |  | 3014 | 2003-03-12 | mechanical | CM | cold mass main body | use as is | laminations assembly
QN | 101 |  | 3013 | 2003-03-04 | mechanical | CM | cold mass main body | use as is | laminations assembly
QN | 102 | internal
QN | 103 |  | 3026 | 2003-03-10 | irriversible damaged | CC | coil | rejected | outer layer
QN | 104 |  |  | 2003-03-11 | component | CM |  | replace | N lines | N lines
QN | 105 |  |  | 2002-03-20 | component | CM |  | replace | bellows
QN | 106 |  | 3015 | 2003-03-04 | mechanical | CM | cold mass main body | repair | long weld
QN | 107 |  | 3014 | 2003-03-13 | alignement | CM | cold mass | repair | extremities
QN | 108 |  | 3015 | 2003-03-17 | mechanical | CM | cold mass main body | use as is | laminations assembly
QN | 109 |  | 3015 | 2003-03-17 | mechanical | CM | cold mass main body | use as is | long weld
QN | 110 |  |  | 2003-03-25 | component | CM |  | replace | bus bar
QN | 111 |  | 3027 | 2003-05-28 | alignement | CM | cold mass | use as is | extremities
QN | 112 | in process
QN | 113 |  | 3017 | 2003-05-23 | mechanical | CM | cold mass main body | repair | long weld
QN | 114 | in process
QN | 115 | in process
QN | 116 | in process
QN | 117 |  | 3022 | 2003-06-03 | mechanical | CM | cold mass main body | repair | long weld
QN | 118 | in process
QN | 119 | in process
QN | 120 |  | 3016 | 2003-04-23 | mechanical | CM | cold mass main body | use as is | long weld
QN | 121 |  | 3018 | 2003-05-09 | mechanical | CM | cold mass main body | repair | long weld
QN | 122 | in process
QN | 123 | in process
QN | 124 |  | 3008 | 2003-04-07 | electrical | CM | cold mass main body | use as is | Q.H.
QN | 125 | internal
QN | 126 |  | 3024 | 2003-06-11 | mechanical | CM | cold mass main body | repair | long weld
QN | 127 |  | 3012 | 2003-04-09 | mechanical | CM | cold mass main body | use as is | laminations assembly
QN | 128 | internal
QN | 129 |  | 3025 | 2003-06-03 | alignement | CM | cold mass | use as is | extremities
QN | 130 |  | 3025 | 2003-04-16 | mechanical | CM | cold mass main body | use as is | long weld
QN | 131 | in process
QN | 132 |  | 3030 | 2003-04-30 | mechanical | CM | cold mass | use as is | laminations assembly
QN | 133 |  | 3028 | 2003-05-14 | electrical | CC | collared coil | dismantle | Q.H. defect
QN | 134 |  | 3020 | 2003-05-07 | mechanical | CM | cold mass main body | use as is | curvature
QN | 135 |  | 3021 | 2003-05-19 | mechanical | CM | cold mass main body | use as is | curvature
QN | 136 |  |  | 2003-04-23 | mat non conf | CM |  | replace | extremities
QN | 137 |  | 3018 | 2003-05-09 | alignement | CM | cold mass main body | use as is | curvature
QN | 138 |  | 3018 | 2003-05-09 | alignement | CM | cold mass | use as is | feet
QN | 139 |  | 3023 | 2003-05-14 | mechanical | CM | cold mass main body | repair | curvature TIG welding
QN | 140 | internal
QN | 141 | in process
QN | 142 |  | 3024 | 2003-05-20 | alignement | CM | cold mass main body | use as is | curvature
QN | 143 | in process
QN | 144 | in process
QN | 145 | in process
QN | 146 | in process
QN | 147 | in process
QN | 148 | in process
QN | 149 | in process
QN | 150 |  | 3026 |  | mechanical | CM | cold mass | repair | leaking bellow
QN | 151 | in process
QN | 152 | in process
QN | 153 | in process
QN | 154 | in process
QN | 155 |  | 3026 | 2003-06-26 | component | CM | cold mass | use as is | spacer end plate not conform
QN | 156 |  | 3028 | 2003-06-26 | component | CM | cold mass | use as is | spacer end plate not conform
QN | 157 |  | 3028 | 2003-06-27 | electrical | CM | cold mass | repair | broken wires of temp sensor
QN | 158 |  | 3026 | 2003-07-24 | mechanical | CM | cold mass main body | repair | curvature
NCR | 3001 |  | 3031 | 2003-03-12 | irriversible damaged | CC | coil | rejected | inner layer | 4
NCR | 3002 |  | 3032 | 2003-03-18 | irriversible damaged | CC | coil | rejected | inner layer | 4
NCR | 3003 |  | 3009 | 2003-04-01 | mechanical | CC | coil | repair | inner layer
NCR | 3004 | internal
NCR | 3005 |  | 3033 | 2003-04-10 | mechanical | CC | coil | rejected | inner layer | 2
NCR | 3006 |  |  | 2003-04-15 | component | CC |  | use as is | collars | collars
NCR | 3007 |  |  | 2003-04-15 | component | CC |  | use as is | collars | collars
NCR | 3008 |  | 3031 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3009 |  | 3032 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3010 |  | 3033 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3011 |  | 3034 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3012 |  | 3035 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3013 |  | 3036 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3014 |  | 3037 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3015 |  | 3038 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3016 |  | 3039 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3017 |  | 3040 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3018 |  | 3041 | 2003-04-23 | mechanical | CC | coil | use as is | outer layer
NCR | 3019 |  | 3041 | 2003-04-29 | electrical | CC | coil | use as is | outer layer
NCR | 3020 | internal
NCR | 3021 |  | 3032 | 2003-05-12 | mechanical | CC | coil | use as is | outer layer
NCR | 3022 | internal
NCR | 3023 | internal
NCR | 3024 | internal
NCR | 3025 |  | 3040 | 2003-05-22 | irriversible damaged | CC | coil | rejected | inner layer | 1
NCR | 3026 | internal
NCR | 3027 | internal
NCR | 3028 | internal
NCR | 3029 | internal
NCR | 3030 |  | 3034 | 2003-07-02 | mechanical | CM | cold mass main body | use as is | point welding of washers instead of lockers
NCR | 3031 | internal
NCR | 3032 | internal
NCR | 3033 | internal
NCR | 3034 | internal
NCR | 3035 |  | 3037 | 2003-06-19 | electrical | CM | cold mass main body | use as is | low insualtion to ground
NCR | 3036 |  |  | 2003-07-16 | component | CM |  | replace | bus bar
NCR | 3037 |  |  | 2003-07-28 | component | CM |  | use as is | rusted laminations
NCR | 3038 |  |  | 2003-07-15 | electrical | CM |  | replace | insulation to ground of sextupole
NCR | 3039 |  |  | 2003-06-23 | component | CC |  | replace | 17 damaged CW on 3 batches
NCR | 3040 |  | 3040 | 2003-06-23 | irriversible damaged | CC | coil | rejected | inner layer | 1
NCR | 3041 |  | 3037 | 2003-06-26 | component | CM | cold mass | use as is | end plate spacer not conform
NCR | 3042 |  | 3038 | 2003-06-26 | component | CM | cold mass | use as is | end plate spacer not conform
NCR | 3043 |  | 3039 | 2003-06-26 | component | CM | cold mass | use as is | end plate spacer not conform
NCR | 3044 |  | 3041 | 2003-06-26 | component | CM | cold mass | use as is | end plate spacer not conform
NCR | 3045 |  | 3036 | 2003-06-27 | electrical | CM | cold mass | repair | brken wire diode
NCR | 3046 | internal
NCR | 3047 | in process
NCR | 3048 | internal
NCR | 3049 |  |  | 2003-07-08 | component | CC |  | use as is | collars embosses thicknesses
NCR | 3050 | internal
NCR | 3051 |  | 3039 | 2003-07-08 | mechanical | CM | cold mass main body | repair | curvature
NCR | 3052 |  | 3042 | 2003-07-10 | mechanical | CM | cold mass main body | repair | curvature
NCR | 3053 |  | 3044 | 2003-07-10 | mechanical | CM | cold mass main body | repair | curvature
NCR | 3054 |  |  | 2003-07-16 | component | CM |  | replace | tolerances half shells
NCR | 3055 |  |  | 2003-04-15 | mechanical | CM | cold mass main body | repair | twist out of tolerance
NCR | 3056 |  |  | 2003-06-18 | component | CM |  | replace | sextupole
NCR | 3057 |  | 3044 | 2003-07-23 | mechanical | CM | cold mass main body | repair | curvature, manget to be re-weld+correction with TIG
NCR | 3058 |  | 3048 | 2003-07-23 | component | CM |  | replace | bus bar
NCR | 3059 | internal
NCR | 3060 |  | 3046 | 2003-08-06 | mechanical | CM | cold mass main body | repair | curvature repaired with extra weld
NCR | 3061 |  | 3043 | 2003-07-30 | component | CM |  | replace | leaking bellow see 3061 A
NCR | 3062 |  | 3067 | 2003-06-30 | irriversible damaged | CC | coil | rejected | damaged outer layer | 1
NCR | 3063 |  | 3039 | 2003-07-31 | mechanical | CM | cold mass main body | repair | curvature, manget to be re-weld
NCR | 3064 |  | 3060 | 2003-08-11 | electrical | CC | collared coil | use as is | wrong wiring of Q.H.
NCR | 3065 | internal
NCR | 3066 | internal
NCR | 3067 | internal
NCR | 3068 |  | 3076 | 2003-08-20 | mechanical | CC | coil | repair | deformed cable repaired
NCR | 3069 | internal
NCR | 3070 | internal
NCR | 3071 | in process |  | 2003-09-24 | component | CM | cold mass | replace | leaking bellows
3072
3073
3074
3075
NCR | 3076 |  | 3071 | 2003-09-15 | electrical | CC | dipole | repair | Q.H. connection dirty
3077
3078
3079
NCR | 3080 |  | 3063 | 2003-09-10 | mechanical | CM | cold mass main body | use as is | compaction factor, resude pack 3004
3081
3082
3083
NCR | 3084 |  |  | 2003-09-11 | traceability | CM | cold mass | use as is | traceability of heat exchanger tube
3085
3086
3087
3088
3089
3090
NCR | 3091 |  | 3087 | 2003-09-29 | mechanical | CC | coil | use as is | imrpint of mandrel key on spacers
NCR | 3092 |  | 3090 | 2003-09-29 | mechanical | CC | coil | use as is | imrpint of mandrel key on spacers
NCR | 3093 |  | 3091 | 2003-09-29 | mechanical | CC | coil | use as is | imrpint of mandrel key on spacers
3094
3095
NCR | 3096 |  | 3092 | 2003-09-29 | mechanical | CC | coil | use as is | imrpint of mandrel key on spacers
NCR | 3097 |  | 3077 | 2003-09-30 | electrical | CC | pole | repair | short circuit between layers
3098
3099
3100
3101
3102
3103
3104

## sub-aasembly vs magnet
Count of sub-assembly | sub-assembly
magnet | coil | cold mass | cold mass main body | collared coil | dipole | pole | (blank) | Grand Total
3001 | 1 | 1 | 1 |  |  |  |  | 3
3002 | 1 | 1 | 1 |  |  |  |  | 3
3003 | 1 | 9 | 1 | 1 |  | 1 |  | 13
3004 | 1 | 5 | 2 |  |  | 1 |  | 9
3005 |  | 9 | 6 |  |  |  |  | 15
3006 | 2 | 3 | 2 |  |  |  |  | 7
3007 |  | 4 | 1 |  |  |  |  | 5
3008 |  | 2 | 4 |  |  |  |  | 6
3009 | 1 | 3 | 4 |  |  |  |  | 8
3010 | 1 |  |  | 1 |  |  |  | 2
3011 |  | 2 | 3 | 1 |  | 1 |  | 7
3012 | 1 | 1 | 5 | 1 | 1 |  |  | 9
3013 | 1 | 8 | 2 | 1 | 1 |  |  | 13
3014 | 2 | 3 | 2 |  |  |  |  | 7
3015 | 2 | 3 | 3 |  |  |  |  | 8
3016 |  |  | 1 |  |  |  |  | 1
3017 |  |  | 1 |  |  |  |  | 1
3018 | 1 | 1 | 2 |  |  |  |  | 4
3020 | 1 |  | 1 |  |  |  |  | 2
3021 |  |  | 1 |  |  |  |  | 1
3022 |  |  | 1 |  |  |  |  | 1
3023 |  |  | 1 |  |  |  |  | 1
3024 |  |  | 2 |  |  |  |  | 2
3025 |  | 1 | 1 |  |  | 1 |  | 3
3026 | 1 | 2 | 1 |  |  |  |  | 4
3027 | 1 | 1 | [5 empty] | 2
3028 |  | 2 |  | 1 |  |  |  | 3
3030 |  | 1 | [5 empty] | 1
3031 | 2 | [6 empty] | 2
3032 | 3 | [6 empty] | 3
3033 | 2 | [6 empty] | 2
3034 | 1 |  | 1 |  |  |  |  | 2
3035 | 1 | [6 empty] | 1
3036 | 1 | 1 | [5 empty] | 2
3037 | 1 | 1 | 1 |  |  |  |  | 3
3038 | 1 | 1 | [5 empty] | 2
3039 | 1 | 1 | 2 |  |  |  |  | 4
3040 | 3 | [6 empty] | 3
3041 | 2 | 1 | [5 empty] | 3
3042 |  |  | 1 |  |  |  |  | 1
3043
3044 |  |  | 2 |  |  |  |  | 2
3046 |  |  | 1 |  |  |  |  | 1
3048
3060 |  |  |  | 1 |  |  |  | 1
3063 |  |  | 1 |  |  |  |  | 1
3067 | 1 | [6 empty] | 1
3071 |  |  |  |  | 1 |  |  | 1
3076 | 1 | [6 empty] | 1
3077 | [5 empty] | 1 |  | 1
3087 | 1 | [6 empty] | 1
3090 | 1 | [6 empty] | 1
3091 | 1 | [6 empty] | 1
3092 | 1 | [6 empty] | 1
(blank) |  | 3 | 1 |  |  |  |  | 4
Grand Total | 42 | 70 | 59 | 7 | 3 | 5 |  | 186

## typology vs magnet
Count of typology | typology
magnet | alignement | component | electrical | irriversible damaged | mat non conf | mechanical | raw material | traceability | (blank) | Grand Total
3001 |  | 1 |  |  |  | 2 |  | 1 |  | 4
3002 |  | 1 |  |  |  | 1 |  | 1 |  | 3
3003 |  | 3 | 4 |  |  | 6 |  | 2 |  | 15
3004 |  | 2 | 1 |  |  | 3 | 1 | 2 |  | 9
3005 | 2 |  | 4 |  |  | 5 | 1 | 3 |  | 15
3006 |  | 1 |  | 1 |  | 4 | 1 |  |  | 7
3007 |  |  | 1 |  |  | 3 | 1 | 2 |  | 7
3008 | 1 |  | 1 |  |  | 3 | 1 | 2 |  | 8
3009 |  |  | 2 |  |  | 6 |  | 2 |  | 10
3010 |  |  | 1 |  |  | 1 |  |  |  | 2
3011 |  |  | 1 |  |  | 6 |  |  |  | 7
3012 | 2 |  | 1 |  |  | 6 |  |  |  | 9
3013 | 1 |  | 3 |  |  | 8 |  | 3 |  | 15
3014 | 1 |  |  |  |  | 5 |  | 1 |  | 7
3015 | 1 |  |  |  |  | 6 |  | 1 |  | 8
3016 | [5 empty] | 1 |  |  |  | 1
3017 |  |  | 1 |  |  | 1 |  |  |  | 2
3018 | 2 |  |  |  |  | 2 |  |  |  | 4
3020 |  |  | 1 |  |  | 1 |  |  |  | 2
3021 | [5 empty] | 1 |  |  |  | 1
3022 | [5 empty] | 1 |  |  |  | 1
3023 | [5 empty] | 1 |  |  |  | 1
3024 | 1 |  |  |  |  | 1 |  |  |  | 2
3025 | 1 |  |  |  |  | 2 |  |  |  | 3
3026 |  | 1 |  | 1 |  | 2 |  |  |  | 4
3027 | 1 |  |  |  |  | 1 |  |  |  | 2
3028 |  | 1 | 2 | [6 empty] | 3
3030 | [5 empty] | 1 |  |  |  | 1
3031 |  |  |  | 1 |  | 1 |  |  |  | 2
3032 |  |  |  | 1 |  | 2 |  |  |  | 3
3033 | [5 empty] | 2 |  |  |  | 2
3034 | [5 empty] | 2 |  |  |  | 2
3035 | [5 empty] | 1 |  |  |  | 1
3036 |  |  | 1 |  |  | 1 |  |  |  | 2
3037 |  | 1 | 1 |  |  | 1 |  |  |  | 3
3038 |  | 1 |  |  |  | 1 |  |  |  | 2
3039 |  | 1 |  |  |  | 3 |  |  |  | 4
3040 |  |  |  | 2 |  | 1 |  |  |  | 3
3041 |  | 1 | 1 |  |  | 1 |  |  |  | 3
3042 | [5 empty] | 1 |  |  |  | 1
3043 |  | 1 | [7 empty] | 1
3044 | [5 empty] | 2 |  |  |  | 2
3046 | [5 empty] | 1 |  |  |  | 1
3048 |  | 1 | [7 empty] | 1
3060 |  |  | 1 | [6 empty] | 1
3063 | [5 empty] | 1 |  |  |  | 1
3067 |  |  |  | 1 | [5 empty] | 1
3071 |  |  | 1 | [6 empty] | 1
3076 | [5 empty] | 1 |  |  |  | 1
3077 |  |  | 1 | [6 empty] | 1
3087 | [5 empty] | 1 |  |  |  | 1
3090 | [5 empty] | 1 |  |  |  | 1
3091 | [5 empty] | 1 |  |  |  | 1
3092 | [5 empty] | 1 |  |  |  | 1
(blank) |  | 19 | 1 |  | 1 | 1 |  | 1 |  | 23
Grand Total | 13 | 35 | 30 | 7 | 1 | 107 | 5 | 21 |  | 219