## legend
Nomenclature to be used
assemblies
CC | up to collared coil warm magnetic measurement approved
CM | from collared coil magnetic measurement up to shipment
sub-assemblies
coil | from SC cable to surfaced layers
pole | from surfaced coil to connected pole
dipole | from pole to dipoles ready with coil protection sheet
collared coil | from coil protection sheet to warm magnetic measurement
cold mass main body | from yoking till end of longitudinal welding
cold mass | from longitudinal welding till shipment
typology
electrical | affecting electrical properties
mechanical | damage affecting mechanical (and electrical) properties
irriversible damage | i.e. layer with cut strand
traceability | CoC not available
raw material | raw material not conform to tech spec
component | component received or used not conform to tech spec
alignment | out of tolerance on geometrical measurements
welding | welding defects
action
use as is
repair
rejected | sub-assembly rejected, no repair possible (layer)
dismantle | repairing needs de-collaring or cutting of long weld
replace | the component non according to spec will be replaced (stock not magnet)
in green NCR in process or managed internal by the firm
in red NCR where the file is not available at CERN

## NCR_Total
N | magnet | Description | date | action | Assembly | sub-assembly | typology
NCR3058_0 | CM3048 | Busbar M1 - electrical defekt | 2003-07-23 | dismantle | cm | cold mass | component
NCR3351_0 | CM3254 | Busbar M3 - broken supraconductor | 2005-01-19 | dismantle | cm | cold mass | electrical
NCR3338_A | CM3136 CM3636 | Cold mass 3136 / Collared Coil N-3136C; Bad quench performance, no memory; CC/CM have to be rebuild; new magnet no. = N-3636M | 2005-02-02 | dismantle | cm | cold mass | electrical
NCR3375_A | CM3143 CM3643 | Cold mass 3143 / Collared Coil N-3143C; Short circuit between QH and coil during the warm acceptance testat CERN; CC/CM have to be rebuild; new magnet no. = N-3643M | 2005-05-11 | dismantle | cm | cold mass | electrical
NCR3310_A | CM3208 CM3708 | Cold mass 3208 / Collared Coil N-3208C; Bad quench performance, CC/CM have to be rebuild; new magnet no. = N-3708M | 2005-06-06 | dismantle | cm | cold mass | electrical
NCR3339_A | CM3224 CM3724 | Cold mass 3224 / Collared Coil N-3224C; Not fullfilling the acceptance criteria; CC/CM have to be rebuild; new magnet no. = N-3724M | 2005-05-09 | dismantle | cm | cold mass | electrical
NCR3374_A | CM3234 CM3734 | Cold mass 3234 / Collared Coil N-3234C; Short circuit between QH and coil during quench training at CERN; CC/CM have to be rebuild; new magnet no. = N-3734M | 2005-05-11 | dismantle | cm | cold mass | electrical
NCR3273_0 | CM3175 | Collared coil N-3175C Loose spices on the inner layer N-3578i | 2004-06-16 | dismantle | cc | collared coil | mechanical
NCR3275_A | CM3226 | Collared coil N-3226C Loose spices on the outer layer N-3781E | 2004-07-06 | dismantle | cc | collared coil | mechanical
NCR3231_0 | CM3130 | Damage of the insulation N-3397I and N-3399E and installation of CPS in stainless steel - CS and NCS | 2004-04-21 | dismantle | cc | collared coil | electrical
NCR3232_0 | CM3132 | Damage of the insulation N-3406I and N-3405E and installation of CPS in stainless steel - CS and NCS | 2004-04-21 | dismantle | cc | collared coil | electrical
NCR3045_0 | CM3036 | Diode - cracked wires | 2003-06-27 | dismantle | cm | cold mass | electrical
NCR3283_0 | CM3183 | Diode damaged | 2004-06-16 | dismantle | cm | cold mass | electrical
NCR3279_A | CM3222 | Disruptive discharge in the lower pole of D2 | 2004-08-09 | dismantle | cc | pole | electrical
NCR3191_A | CM3147 | Electrical breakthrough in the collared coil N-3147C | 2004-02-20 | dismantle | cm | cold mass | electrical
NCR3367_B | CM3319 | Electrical fault | 2005-05-03 | dismantle | cm | cold mass | electrical
NCR3425_0 | CM3388 | Electrical fault | 2005-11-08 | dismantle | cc | collared coil | electrical
NCR3202_0 | CM3156 | Installation of CPS in stainless steel | 2004-03-29 | dismantle | cc | collared coil | mechanical
NCR3203_0 | CM3152 | Installation of CPS in stainless steel | 2004-04-07 | dismantle | cc | collared coil | mechanical
NCR3204_0 | CM3154 | Installation of CPS in stainless steel | 2004-04-07 | dismantle | cc | collared coil | mechanical
NCR3205_0 | CM3160 | Installation of CPS in stainless steel | 2004-03-31 | dismantle | cc | collared coil | mechanical
NCR3207_0 | CM3148 | Installation of CPS in stainless steel | 2004-03-31 | dismantle | cc | collared coil | mechanical
NCR3208_0 | CM3140 | Installation of CPS in stainless steel | 2004-03-31 | dismantle | cc | collared coil | mechanical
NCR3209_0 | CM3151 | Installation of CPS in stainless steel | 2004-03-31 | dismantle | cc | collared coil | mechanical
NCR3210_0 | CM3150 | Installation of CPS in stainless steel | 2004-04-02 | dismantle | cc | collared coil | mechanical
NCR3211_0 | CM3067 | Installation of CPS in stainless steel | 2004-03-31 | dismantle | cc | collared coil | mechanical
NCR3212_0 | CM3153 | Installation of CPS in stainless steel | 2004-03-31 | dismantle | cc | collared coil | mechanical
NCR3213_0 | CM3144 | Installation of CPS in stainless steel | 2004-03-31 | dismantle | cc | collared coil | mechanical
NCR3214_0 | CM3147 | Installation of CPS in stainless steel | 2004-03-17 | dismantle | cc | collared coil | mechanical
NCR3215_0 | CM3102 | Installation of CPS in stainless steel | 2004-03-22 | dismantle | cc | collared coil | mechanical
NCR3216_0 | CM3128 | Installation of CPS in stainless steel | 2004-03-22 | dismantle | cc | collared coil | mechanical
NCR3217_0 | CM3134 | Installation of CPS in stainless steel | 2004-03-23 | dismantle | cc | collared coil | mechanical
NCR3218_0 | CM3149 | Installation of CPS in stainless steel | 2004-03-23 | dismantle | cc | collared coil | mechanical
NCR3219_0 | CM3139 | Installation of CPS in stainless steel | 2004-03-23 | dismantle | cc | collared coil | mechanical
NCR3220_0 | CM3143 | Installation of CPS in stainless steel | 2004-03-23 | dismantle | cc | collared coil | mechanical
NCR3221_0 | CM3141 | Installation of CPS in stainless steel | 2004-03-29 | dismantle | cc | collared coil | mechanical
NCR3222_0 | CM3142 | Installation of CPS in stainless steel | 2004-03-29 | dismantle | cc | collared coil | mechanical
NCR3223_0 | CM3145 | Installation of CPS in stainless steel | 2004-03-29 | dismantle | cc | collared coil | mechanical
NCR3224_0 | CM3138 | Installation of CPS in stainless steel | 2004-04-02 | dismantle | cc | collared coil | mechanical
NCR3225_0 | CM3137 | Installation of CPS in stainless steel | 2004-04-07 | dismantle | cc | collared coil | mechanical
NCR3238_0 | CM3131 | Installation of CPS in stainless steel | 2004-04-28 | dismantle | cc | collared coil | mechanical
NCR3239_0 | CM3133 | Installation of CPS in stainless steel | 2004-04-28 | dismantle | cc | collared coil | mechanical
NCR3405_A | CM3376 | Insulation fault | 2005-09-27 | dismantle | cc | collared coil | electrical
NCR3102_0 | CM3056 | Leck im IFS-Deckel | 2003-10-09 | dismantle | cm | cold mass | mechanical
NCR3075_0 | CM3068 | Lower insulation resistance between 2 QH's in aperture 1 | 2003-09-04 | dismantle | cc | collared coil | electrical
NCR3406_0 | CM3392 | Octupole/Decapole MCDO MA-I 698 | 2005-07-15 | dismantle | cm | cold mass | electrical
NCR3393_0 | CM3153 CM3653 | Rebuilt of collared coil and cold mass because of a short circuit between coil, QH and CPS during quench training at CERN The new magnet no. = N-3653C | 2005-06-22 | dismantle | cm | cold mass | electrical
NCR3183_0 | CM3135 | Red alarm during the magnetic measurements | 2004-02-18 | dismantle | cm | cold mass | electrical
NCR3308_0 | CM3254 | Red and yellow alarms during the magnetic measurements of collared coil N-3254 | 2004-09-15 | dismantle | cc | collared coil | electrical
NCR3038_0 | CM3038 | Sextupol, insulation resistance | 2003-07-14 | dismantle | cm | cold mass | electrical
NCR3334_0 | CM3292 | Short circuit on Collared coil N-3292C | 2004-11-17 | dismantle | cc | collared coil | electrical
NCR3160_0 | CM3049 | Tube N-Line pushed in | 2004-01-26 | dismantle | cm | cold mass | mechanical
NCR3348_0 | CM3273 | Tube N-Line pushed in | 2004-12-22 | dismantle | cm | cold mass | mechanical
NCR3413_0 | CM3406 | V1 Line - insulation fault | 2005-08-26 | dismantle | cc | collared coil | electrical
NCR3365_0 | CM3321 | V2 Line - insulation fault | 2005-02-28 | dismantle | cc | collared coil | electrical
NCR3090_0 | CM3075 | Voltage breakdown in the outer layer N-3179E of the upper pole N-3179P | 2003-11-06 | dismantle | cc | layer | electrical
NCR3076_0 | CM3071 | Weakness of insulation QH YT111- against upper pole in aperture 1 | 2003-09-15 | dismantle | cc | collared coil | electrical
NCR3089_0 | CM3035 | Accident on pole N-3019P | reserved by Weinhard | rejected | cc | pole | irriversible damage
NCR3164_0 | CM3075 | Busbar M1 - electrical defekt | 2004-01-29 | rejected | cm | cold mass | irriversible damage
NCR3249_0 | CM3167 | Busbar M1 - electrical defekt | 2004-04-23 | rejected | cm | cold mass | irriversible damage
NCR3330_0 | CM3270 | Busbar M1 - electrical fault | 2004-11-03 | rejected | cm | cold mass | electrical
NCR3182_0 | CM3124 | Busbar M2 - electrical defekt | 2004-03-10 | rejected | cm | cold mass | irriversible damage
NCR3103_0 | CM3102 | Damage of cable | 2003-10-17 | rejected | cc | layer | irriversible damage
NCR3159_0 | CM3146 | Damage of outerlayer N-3462E | 2004-01-29 | rejected | cc | layer | irriversible damage
NCR3244_0 | CM3175 | Damage of the coil outerlayer N-3680E during the winding | 2004-05-17 | rejected | cc | layer | irriversible damage
NCR3245_0 | CM3204 | Damage of the coil outerlayer N-3693E during the winding | 2004-05-18 | rejected | cc | layer | irriversible damage
NCR3184_0 | CM3159 | Damage of the inner layer N-3515i | 2004-02-20 | rejected | cc | layer | irriversible damage
NCR3200_0 | CM3169 | Damage of the inner layer N-3556i during cutting the layer jump | 2004-03-11 | rejected | cc | layer | irriversible damage
NCR3272_0 | CM3215 | Damage of the outer layer N-3737E during a handling operation | 2004-06-22 | rejected | cc | layer | irriversible damage
NCR3346_0 | CM3323 | Damage of the outer layer N-4172E during the winding | 2004-12-15 | rejected | cc | layer | irriversible damage
NCR3268_0 | CM3175 | Electrical disruptive discharge at the outer layer N-3580E | 2004-05-25 | rejected | cc | layer | irriversible damage
NCR3309_0 | CM3242 | Electrical disruptive discharge at the outer layer N-3846E | 2004-09-15 | rejected | cc | layer | irriversible damage
NCR3347_A | CM3342 | Short-circuit at the outer layer N-4247E | 2005-02-09 | rejected | cc | layer | irriversible damage
NCR3005_0 | CM3031-CM3033 | Spacer for inner layer coil N-03001I up to N-3010I, lamination damagec | 2003-04-10 | rejected | cc | coil | irriversible damage
NCR3264_0 | CM3174 | Temperature sensor | 2004-05-17 | rejected | cm | cold mass | electrical
NCR3362_0 | CM3292 | Temperature sensor | 2005-02-10 | rejected | cm | cold mass | electrical
NCR3373_0 | CM3321 | Temperature sensor | 2005-03-18 | rejected | cm | cold mass | electrical
NCR3398_0 | CM3388 | Temperature sensor | 2005-07-05 | rejected | cm | cold mass | electrical
NCR3410_0 | CM3643 | Temperature sensor | 2005-08-24 | rejected | cm | cold mass | electrical
NCR3419_0 | CM3734 | Temperature sensor | 2005-09-08 | rejected | cc | collared coil | electrical
NCR3303_0 | CM3235 | Busbar M3 damaged | 2004-08-28 | repair | cm | cold mass | component
NCR3150_0 | CM3079 | Busbar "Half-Moon" connections | 2004-01-12 | repair | cm | cold mass | electrical
NCR3411_0 | CM3408 | Busbar M1 | 2005-08-24 | repair | cm | cold mass | electrical
NCR3322_0 | CM3249 | Busbar M3 - broken supraconductor | 2004-11-03 | repair | cm | cold mass | electrical
NCR3312_0 | CM3240 | casing to short | 2004-09-15 | repair | cm | cold mass | mechanical
NCR3276_A | CM3231 | Collared coil N-3231C Gaps and easily detachable splices on the outer layer N-3803E | 2004-07-13 | repair | cc | layer | mechanical
NCR3277_A | CM3233 | Collared coil N-3233C Gaps and easily detachable splices on the outer layer N-3810E | 2004-07-13 | repair | cc | layer | mechanical
NCR3247_0 | CM3102 | D2 - electrical defekt | 2004-04-13 | repair | cc | collared coil | electrical
NCR3003_0 | CM3033 | Damage insulation of inner layer coil N-3009I during crane handling | 2003-04-01 | repair | cc | coil | electrical
NCR3025_0 | CM3040 | Damage of inner layer coil N-3037I during curing of pole N-3037P | 2003-05-22 | repair | cc | pole | mechanical
NCR3040-0 | CM3040 | Damage of inner layer coil N-3040I during curing of pole N-3040P | 2003-06-23 | repair | cc | layer | mechanical
NCR3068_A | CM3076 | Damage of inner layer coil N-3183I, cable ID 01B10268B | 2003-08-20 | repair | cc | layer | mechanical
NCR3062_0 | CM3067 | Damage of outer layer coil N-3145E, cable ID 02K15001A | 2003-06-30 | repair | cc | layer | mechanical
NCR3237_0 | CM3188 | Damage of the outer layer N-3629E during curing | 2004-04-22 | repair | cc | layer | mechanical
NCR3420_A | CM3406 | Damaged isolation on the cold bore tube of Aperture D1 | 2005-09-19 | repair | cc | collared coil | electrical
NCR3416_0 | CM3400 | Diode | 2005-08-31 | repair | cm | cold mass | electrical
NCR3045_0 | CM3036 | Diode - cracked wires | 2003-06-27 | repair
NCR3116_0 | CM3040 | Diode cable | 2003-11-17 | repair | cm | cold mass | electrical
NCR3366_0 | CM3299 | Diode container - Leck | 2005-03-01 | repair | cm | cold mass | mechanical
NCR3269_A | CM3102 | Disruptive discharge between the inner layer N-3287i and the outer layer N-3287e | 2004-06-24 | repair | cc | layer | electrical
NCR3252_0 | CM3140 | End cover NCS out of tolerance | 2004-05-11 | repair | cm | cold mass | mechanical
NCR3294_0 | CM3212 | Gaps at innter layer N-3728I | 2004-08-06 | repair | cc | layer | mechanical
NCR3295_0 | CM3234 | Gaps and easily detachable splices at outer layer N-3815E | 2004-07-20 | repair | cc | layer | mechanical
NCR3097_0 | CM3077 | Inner layer N-3185I - short circuit between two threads of the 9th layer | 2003-09-29 | repair | cc | layer | electrical
NCR3242_0 | CM3136 | Installation of CPS in stainless steel | 2004-05-07 | repair | cc | collared coil | mechanical
NCR3402_0 | CM3382 | Leakage on CS-side | 2005-07-27 | repair | cm | cold mass | mechanical
NCR3423_0 | CM3341 | Leakage on internal X-Line-bellow | 2005-10-25 | repair | cm | cold mass | mechanical
NCR3328_A | CM3253 | M type bellows assembly onto M1 | 2004-11-15 | repair | cm | cold mass | mechanical
NCR3399_0 | CM3395 | M-line bellow | 2005-07-13 | repair | cm | cold mass | mechanical
NCR3120_0 | CM3031 | No diode assembled | 2003-11-27 | repair | cm | cold mass | electrical
NCR3123_0 | CM3032 | No diode assembled | 2003-12-01 | repair | cm | cold mass | electrical
NCR3124_0 | CM3033 | No diode assembled | 2003-12-01 | repair | cm | cold mass | electrical
NCR3126_0 | CM3087 | No diode assembled | 2003-12-02 | repair | cm | cold mass | electrical
NCR3127_0 | CM3088 | No diode assembled | 2003-12-02 | repair | cm | cold mass | electrical
NCR3128_0 | CM3089 | No diode assembled | 2003-12-02 | repair | cm | cold mass | electrical
NCR3129_0 | CM3082 | No diode assembled | 2003-12-02 | repair | cm | cold mass | electrical
NCR3130_0 | CM3090 | No diode assembled | 2003-12-02 | repair | cm | cold mass | electrical
NCR3134_0 | CM3091 | No diode assembled | 2003-12-11 | repair | cm | cold mass | electrical
NCR3135_0 | CM3092 | No diode assembled | 2003-12-11 | repair | cm | cold mass | electrical
NCR3136_0 | CM3093 | No diode assembled | 2003-12-11 | repair | cm | cold mass | electrical
NCR3138_0 | CM3094 | No diode assembled | 2003-12-11 | repair | cm | cold mass | electrical
NCR3145_0 | CM3106 | No diode assembled | 2004-02-20 | repair | cm | cold mass | electrical
NCR3147_0 | CM3095 | No diode assembled | 2003-12-11 | repair | cm | cold mass | electrical
NCR3148_0 | CM3096 | No diode assembled | 2003-12-11 | repair | cm | cold mass | electrical
NCR3149_0 | CM3100 | No diode assembled | 2003-12-11 | repair | cm | cold mass | electrical
NCR3152_0 | CM3101 | No diode assembled | 2004-01-16 | repair | cm | cold mass | electrical
NCR3153_0 | CM3103 | No diode assembled | 2004-01-16 | repair | cm | cold mass | electrical
NCR3156_0 | CM3104 | No diode assembled | 2004-01-20 | repair | cm | cold mass | electrical
NCR3157_0 | CM3105 | No diode assembled | 2004-01-20 | repair | cm | cold mass | electrical
NCR3162_0 | CM3107 | No diode assembled | 2004-01-28 | repair | cm | cold mass | electrical
NCR3163_0 | CM3109 | No diode assembled | 2004-01-28 | repair | cm | cold mass | electrical
NCR3166_0 | CM3097 | No diode assembled | 2004-02-02 | repair | cm | cold mass | electrical
NCR3167_0 | CM3098 | No diode assembled | 2004-02-02 | repair | cm | cold mass | electrical
NCR3168_0 | CM3099 | No diode assembled | 2004-02-02 | repair | cm | cold mass | electrical
NCR3170_0 | CM3108 | No diode assembled | 2004-02-05 | repair | cm | cold mass | electrical
NCR3171_0 | CM3110 | No diode assembled | 2004-02-05 | repair | cm | cold mass | electrical
NCR3172_0 | CM3111 | No diode assembled | 2004-02-05 | repair | cm | cold mass | electrical
NCR3175_0 | CM3075 | No diode assembled | 2004-02-13 | repair | cm | cold mass | electrical
NCR3176_0 | CM3110 | No diode assembled | 2004-02-13 | repair | cm | cold mass | electrical
NCR3177_0 | CM3112 | No diode assembled | 2004-02-13 | repair | cm | cold mass | electrical
NCR3178_0 | CM3113 | No diode assembled | 2004-02-13 | repair | cm | cold mass | electrical
NCR3179_0 | CM3114 | No diode assembled | 2004-02-13 | repair | cm | cold mass | electrical
NCR3185_0 | CM3126 | No diode assembled | 2004-02-19 | repair | cm | cold mass | electrical
NCR3169_0 | CM3102 | Permuted cables (colours) on pole N-3285P (connection side) of collared coil N-3102C | 2004-02-09 | repair | cc | collared coil | electrical
NCR3280_A | CM3233 | Preparation of copper wedges with VANTICO | 2004-07-14 | repair | cc | collared coil | component
NCR3233_0 | CM3185 | Resin entered into the outer layer N-3619E | 2004-04-21 | repair | cc | layer | mechanical
NCR3235_0 | CM3187 | Resin entered into the outer layer N-3626E | 2004-04-21 | repair | cc | layer | mechanical
NCR3241_0 | CM3191 | Resin entered into the outer layer N-3642E | 2004-04-28 | repair | cc | layer | mechanical
NCR3234_0 | CM3186 | Resin entered into the outer layers N-3621E; N-3622E; N-3623E; N-3624E | 2004-04-21 | repair | cc | layer | mechanical
NCR3240_0 | CM3192 | Resin entered into the outer layers N-3647E and N-3648E | 2004-04-28 | repair | cc | layer | mechanical
NCR3019_0 | CM3041 | Rest of carton glued on the cable 01B10199E for inner layer coil | 2003-04-29 | repair | cc | layer | electrical
NCR3119_0 | CM3088 | Sextupol, protection cap | 2003-12-08 | repair | cm | cold mass | electrical
NCR3051_0 | CM3039 | Shape out of tolerance | 2003-07-08 | repair | cm | cold mass | mechanical
NCR3052_0 | CM3042 | Shape out of tolerance | 2003-07-10 | repair | cm | cold mass | mechanical
NCR3053_0 | CM3044 | Shape out of tolerance | 2003-07-10 | repair | cm | cold mass | mechanical
NCR3060_A | CM3046 | Shape out of tolerance | 2003-08-06 | repair | cm | cold mass | mechanical
NCR3078_0 | CM3047 | Shape out of tolerance | 2003-09-11 | repair | cm | cold mass | mechanical
NCR3079_0 | CM3053 | Shape out of tolerance | 2003-09-12 | repair | cm | cold mass | mechanical
NCR3083_0 | CM3055 | Shape out of tolerance | 2003-10-07 | repair | cm | cold mass | mechanical
NCR3085_0 | CM3056 | Shape out of tolerance | 2003-12-11 | repair | cm | cold mass | mechanical
NCR3088_A | CM3085 | Shape out of tolerance | 2004-02-27 | repair | cm | cold mass | mechanical
NCR3095_A | CM3060 | Shape out of tolerance | 2003-11-13 | repair | cm | cold mass | mechanical
NCR3114_0 | CM3081 | Shape out of tolerance | 2003-11-17 | repair | cm | cold mass | mechanical
NCR3131_A | CM3097 | Shape out of tolerance | 2004-02-19 | repair | cm | cold mass | mechanical
NCR3132_0 | CM3098 | Shape out of tolerance | 2004-01-15 | repair | cm | cold mass | mechanical
NCR3139_0 | CM3092 | Shape out of tolerance | 2003-12-12 | repair | cm | cold mass | mechanical
NCR3140_0 | CM3095 | Shape out of tolerance | 2004-01-12 | repair | cm | cold mass | mechanical
NCR3142_0 | CM3099 | Shape out of tolerance | 2004-01-14 | repair | cm | cold mass | mechanical
NCR3261_0 | CM3170 | Shape out of tolerance | 2004-05-13 | repair | cm | cold mass | mechanical
NCR3057_A | CM3044 | Shape out of tolerance (again) | 2003-09-16 | repair | cm | cold mass | mechanical
NCR3063_A | CM3039 | Shape out of tolerance (again) | 2003-09-12 | repair | cm | cold mass | mechanical
NCR3086_0 | CM3058 | Tube ends out of tolerance | 2003-10-09 | repair | cm | cold mass | mechanical
NCR3055_0 | CM3045 | Twist under the press | 2003-07-14 | repair | cm | cold mass | mechanical
NCR3414_0 | CM3405 | V2 Line - diameter | 2005-09-01 | repair | cc | collared coil | mechanical
NCR3415_0 | CM3408 | V2 Line - diameter | 2005-09-01 | repair | cc | collared coil | mechanical
NCR3196_0 | CM3150 | Wire YT221+ insulation damaged | 2004-03-18 | repair | cc | collared coil | electrical
NCR3165_0 | CM3149 | wrong endspacer on CS | 2004-01-30 | repair | cc | layer | mechanical
NCR3061_A | CM3043 | X-line - leakage on NCS-side | 2003-08-20 | repair | cm | cold mass | mechanical
NCR3099_0 | CM3053 | X-line - leckage on NCS-side | 2003-10-16 | repair | cm | cold mass | mechanical
NCR3391_0 | CM3353 | X-line - leckage on NCS-side | 2005-06-13 | repair | cm | cold mass | mechanical
NCR3397_0 | CM3363 | X-line - leckage on NCS-side | 2005-07-28 | repair | cm | cold mass | mechanical
NCR3106_0 | CM3056 | X-type internal equiped bellow - leakage on NCS-side | 2003-10-23 | repair | cm | cold mass | mechanical
NCR3122_0 | CM3032 | X-type internal equiped bellow - leakage on NCS-side | 2003-12-02 | repair | cm | cold mass | mechanical
NCR3143_0 | CM3093 | X-type internal equiped bellow - leakage on NCS-side | 2004-01-13 | repair | cm | cold mass | mechanical
NCR3104_0 | CM3071 | YT111+ too short | 2003-10-15 | repair | cc | collared coil | electrical
NCR3379_A | CM3332 | Busbar 405B/M3 | 2005-04-26 | use as is | cm | cold mass | electrical
NCR3394_0 | CM3406 | Collared coil N-3406C - Inner layers with noticeable problems | 2005-06-21 | use as is | cc | layer | traceability
NCR3395_0 | CM3407 | Collared coil N-3407C - Inner layers with noticeable problems | 2005-06-21 | use as is | cc | layer | traceability
NCR3396_0 | CM3409 | Collared coil N-3409C - Inner layer N-4513I with noticeable problems | 2005-06-21 | use as is | cc | layer | traceability
NCR3417_0 | CM3724 | Diode container | 2005-09-02 | use as is | cm | cold mass | mechanical
NCR3361_0 | CM3294 | Diode Container Tee | 2005-02-07 | use as is | cm | cold mass | mechanical
NCR3305_0 | CM3253 | During winding of inner layer N-3891i - damage on winding machine 1 | 2004-09-09 | use as is | cc | layer | mechanical
NCR3382_0 | CM3346 | End cover NCS | 2005-05-12 | use as is | cm | cold mass | mechanical
NCR3421_0 | CM3341 | End cover NCS | 2005-10-25 | use as is | cm | cold mass | mechanical
NCR3320_0 | CM3175 | Halterung für Decapole / Octupole CS Zg. 227556 / e | 2004-11-01 | use as is | cm | cold mass | component
NCR3091_0 | CM3087 | Inner layer N-3225I - excess end | 2003-09-26 | use as is | cc | layer | mechanical
NCR3092_0 | CM3090 | Inner layer N-3237I - excess end | 2003-09-26 | use as is | cc | layer | mechanical
NCR3093_0 | CM3091 | Inner layer N-3242I - excess end | 2003-09-26 | use as is | cc | layer | mechanical
NCR3096_0 | CM3092 | Inner layer N-3247I - excess end | 2003-09-26 | use as is | cc | layer | mechanical
NCR3324_0 | CM3258 | Inner layer N-3912i (Cable id number 01B10591B - cycled too late during curing | 2004-10-15 | use as is | cc | layer | mechanical
NCR3335_0 | CM3278 | Inner layer N-3992i (Cable id number 01B10623D - cycled too late during curing | 2004-11-22 | use as is | cc | layer | mechanical
NCR3311_0 | CM3218 | loss of datas mech. measurement | 2004-09-15 | use as is | cm | cold mass | traceability
NCR3141_0 | CM3168 | Measurement of inner gap | 2004-04-30 | use as is | cm | cold mass | mechanical
NCR3291_0 | CM3206 | Measurement of inner gap | 2004-07-14 | use as is | cm | cold mass | mechanical
NCR3293_0 | CM3207 | Measurement of inner gap | 2004-07-14 | use as is | cm | cold mass | mechanical
NCR3198_0 | CM3155 | Measurement of the magnetic field | 2004-03-26 | use as is | cm | cold mass | electrical
NCR3236_0 |  | Modification of Headspacers | 2004-04-22 | use as is | cc | layer | mechanical
NCR3192_0 | CM3035 | Modification of the spacer for the outer layer N-3019EA | reserved for Mr. Weinhard | use as is | cc | layer | mechanical
NCR3270_0 | CM3170__CM3171__CM3172__CM3173__CM3174__CM3175__CM3176__CM3177__CM3178__CM3179__CM3180__CM3181__CM3182__CM3183__CM3184__CM3185__CM3186__CM3187__CM3188__CM3189__CM3190__CM3191__CM3192__CM3193__CM3194__CM3195__CM3196__CM3197__CM3198__CM3199__CM3200__CM3201__CM3202__CM3203__CM3204__CM3205__CM3206__CM3207__CM3208__CM3209__CM3210 | Not kept curing temperatures | 2004-06-03 | use as is | cc | layer | mechanical
NCR3342_0 | CM3317 | Not kept curing temperatures on the outer layers N-4147E and N-4148E | 2004-12-07 | use as is | cc | layer | mechanical
NCR3278_0 | CM3216 | Not kept curing time | 2004-07-13 | use as is | cc | collared coil | mechanical
NCR3230_0 | CM3031__M3032__CM3033__CM3034__CM3035__CM3036__CM3037__CM3038__CM3039__CM3040__CM3041__CM3042__CM3043__CM3044__CM3045__CM3046__CM3047__CM3048__CM3049__CM3050__CM3051__CM3052__CM3053__CM3054__CM3055__CM3056__CM3057__CM3058__CM3059__CM3060__CM3061__CM3062__CM3063__CM3064__CM3065__CM3066__CM3067__CM3068__CM3069__CM3070__CM3071__CM3072__CM3073__CM3074__CM3075__CM3076__CM3077__CM3078__CM3079__CM3080__CM3081__CM3082__CM3083__CM3084__CM3085__CM3086__CM3087__CM3088__CM3089__CM3090__CM3091__CM3092__CM3093__CM3094__CM3095__CM3096__CM3097__CM3098__CM3099__CM3100__CM3101__CM3102__CM3103__CM3104__CM3105__CM3106__CM3107__CM3108__CM3109__CM3110__CM3111__CM3112__CM3113__CM3114__CM3115__CM3116__CM3117__CM3118__CM3119__CM3120__CM3121__CM3122__CM3123__CM3124__CM3125__CM3126__CM3127__CM3128__CM3129__CM3130__CM3131__CM3132__CM3133__CM3134__CM3135__CM3136__CM3137__CM3138__CM3139__CM3140__CM3141__CM3142__CM3143__CM3144__CM3145__CM3146__CM3147__CM3148__CM3149__CM3150__CM3151__CM3152__CM3153__CM3154__CM3155__CM3156__CM3157__CM3158__CM3159__CM3160__CM3161__CM3162__CM3163__CM3164__CM3165__CM3166__CM3167__CM3168__ | Not kept curing times in different collared coils | 2004-04-20 | use as is | cc | layer | mechanical
NCR3274_0 | CM3214 | Not kept curing times in different collared coils | 2004-07-13 | use as is | cc | collared coil | mechanical
NCR3385_0 | CM3372 | Not kept specified cycling time of 30 min. | 2003-05-19 | use as is | cc | layer | mechanical
NCR3387_0 | CM3404 | Not kept specified cycling time of 30 min. | 2005-06-08 | use as is | cc | layer | mechanical
NCR3388_0 | CM3405 | Not kept specified cycling time of 30 min. | 2005-06-08 | use as is | cc | layer | mechanical
NCR3201_0 | CM3171 | Outer layer with shifted layer and not kept curing times | 2004-03-12 | use as is | cc | layer | mechanical
NCR3326_0 | CM3276 | Overstepping of tolerance on the gap between endplate and NCS head | 2004-10-19 | use as is | cm | collared coil | mechanical
NCR3195_0 | CM3005_CM3006_CM3007_CM3008_CM3009_CM3010_CM3011_CM3012_CM3013_CM3014_CM3015_CM3016_CM3017_CM3018_CM3019_CM3020_CM3021_CM3022_CM3023_CM3024_CM3025_CM3029_CM3030_CM3031_CM3032_CM3033_CM3039_CM3040_CM3043_CM3044_CM3045_CM3046_CM3047_CM3048_CM3049_CM3050_CM3051_CM3052_CM3053_CM3054_CM3055_CM3056_CM3057_CM3058_CM3059_CM3060_CM3061_CM3062_CM3063_CM3064_CM3065_CM3066_CM3068_CM3069_CM3070_CM3071_CM3072_CM3073_CM3074_CM3075_CM3076_CM3077_CM3078_CM3079_CM3080_CM3081_CM3082_CM3083_CM3084_CM3085_CM3086_CM3087_CM3088_CM3089_CM3090_CM3091_CM3092_CM3093_CM3094_CM3095_CM3096_CM3097_CM3098_CM3099_CM3100_CM3101_CM3103_CM3104_CM3105_CM3106_CM3107_CM3108_CM3109_CM3110_CM3111_CM3112_CM3113_CM3114_CM3116_CM3117_CM3118_CM3119_CM3120_CM3121_CM3122_CM3123_CM3124_CM3125_CM3126_CM3127_CM3129 | Sextupoles | 2004-03-17 | use as is | cm | cold mass | electrical
NCR3359_0 | CM3300 | Sextupoles support | 2005-02-07 | use as is | cm | cold mass | mechanical
NCR3154_0 | CM3109 | Shape out of tolerance | 2004-01-20 | use as is | cm | cold mass | mechanical
NCR3155_0 | CM3111 | Shape out of tolerance | 2004-01-20 | use as is | cm | cold mass | mechanical
NCR3186_0 | CM3118 | Shape out of tolerance | 2004-02-26 | use as is | cm | cold mass | mechanical
NCR3189_0 | CM3126 | Shape out of tolerance | 2004-02-19 | use as is | cm | cold mass | mechanical
NCR3281_0 | CM3173 | Shape out of tolerance | 2004-05-25 | use as is | cm | cold mass | mechanical
NCR3041_0 | CM3037 | Spacer into the CS Endplate according to drawing 227545b and 227546b | 2003-06-26 | use as is | cc | layer | mechanical
NCR3042_0 | CM3038 | Spacer into the CS Endplate according to drawing 227545b and 227546b | 2003-06-26 | use as is | cc | layer | mechanical
NCR3043_0 | CM3039 | Spacer into the CS Endplate according to drawing 227545b and 227546b | 2003-06-26 | use as is | cc | layer | mechanical
NCR3044_0 | CM3041 | Spacer into the CS Endplate according to drawing 227545b and 227546b | 2003-06-26 | use as is | cc | layer | mechanical
NCR3336_0 | CM3250 (hence) | Support Decapole / Octupole | 2004-11-15 | use as is | cm | cold mass | mechanical
NCR3253_0 | CM3158 | Using material AISI 304 instead of AISI 304L | 2004-05-10 | use as is | cm | cold mass | mechanical
NCR3254_0 | CM3165 | Using material AISI 304 instead of AISI 304L | 2004-05-10 | use as is | cm | cold mass | mechanical
NCR3255_0 | CM3166 | Using material AISI 304 instead of AISI 304L | 2004-05-10 | use as is | cm | cold mass | mechanical
NCR3256_0 | CM3167 | Using material AISI 304 instead of AISI 304L | 2004-05-10 | use as is | cm | cold mass | mechanical
NCR3257_0 | CM3171 | Using material AISI 304 instead of AISI 304L | 2004-05-10 | use as is | cm | cold mass | mechanical
NCR3258_0 | CM3172 | Using material AISI 304 instead of AISI 304L | 2004-05-10 | use as is | cm | cold mass | mechanical
NCR3259_0 | CM3173 | Using material AISI 304 instead of AISI 304L | 2004-05-10 | use as is | cm | cold mass | mechanical
NCR3260_0 | CM3174 | Using material AISI 304 instead of AISI 304L | 2004-05-10 | use as is | cm | cold mass | mechanical
NCR3021_0 | CM3032 | Cutting layer end from winding machine too short | 2003-05-12 | use-as-is | cc | layer | mechanical
NCR3077_0 | CM3068 | Dipol 1 upper pol, colour changing of quench heater wires | 2003-09-05 | use-as-is | cc | collared coil | electrical
NCR3064_0 | CM3060 | Dipol 2 upper pol, colour changing of quench heater wires | 2003-08-11 | use-as-is | cc | pole | electrical
NCR3087_0 | CM3055 | Final shape measurement of lower quality | 2003-10-07 | use-as-is | cm | cold mass | mechanical
NCR3030_0 | CM3034 | Locking device for pressure bolt | 2003-06-30 | use-as-is | cm | cold mass | mechanical
NCR3008_0 | CM3031 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3009_0 | CM3032 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3010_0 | CM3033 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3011_0 | CM3034 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3012_0 | CM3035 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3013_0 | CM3036 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3014_0 | CM3037 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3015_0 | CM3038 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3016_0 | CM3039 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3017_0 | CM3040 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3018_0 | CM3041 | Overlapping insulation polyimide tape layers 1 and 2 not according to specification | 2003-04-23 | use-as-is | cc | layer | electrical
NCR3080_0 | CM3063 | Stacking factor for laminations Stacking factor for inserts | 2003-09-09 | use-as-is | cm | cold mass | mechanical

## Data_Chart
Tipology
|  |  | component | 4
|  |  | electrical | 98
|  |  | irriversible damage | 16
|  |  | mechanical | 130
|  |  | traceability | 3
Dismantle
| Bus Bar | Short | CPS stainless steel | Diode | Corrector | Other | Quench performance | Leak
| 2 | 14 | 25 | 2 | 2 | 6 | 4 | 1
Rejected
| Bus Bar | Short | Accident | Other | TT
| 4 | 3 | 9 | 1 | 6
Repair
| Bus Bar | Short | CPS stainless steel | Diode | Corrector | Other | Leak | TT | Geometry
| 4 | 10 | 1 | 38 | 1 | 18 | 9 | 1 | 23
Use as is
| Bus Bar | Diode | Corrector | Accident | Other | Geometry | Layer
| 1 | 2 | 4 | 1 | 24 | 5 | 33
All
| Dismantle | Rejected | Repair | Use as is
| 56 | 23 | 105 | 70
Short | CPS stainless steel | Diode | Corrector | Accident | Other | Quench performance | Leak | TT | Geometry | Layer
2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12