## legend
Nomenclature to be used
assemblies
CC | up to collared coil warm magnetic measurement approved
CM | from collared coil magnetic measurement up to shipment
sub-assemblies
coil | from SC cable to surfaced layers
pole | from surfaced coil to connected pole
dipole | from pole to dipoles ready with coil protection sheet
collared coil | from coil protection sheet to warm magnetic measurement
cold mass main body | from yoking till end of longitudinal welding
cold mass | from longitudinal welding till shipment
typology
electrical | affecting electrical properties
mechanical | damage affecting mechanical (and electrical) properties
irriversible damage | i.e. layer with cut strand
traceability | CoC not available
raw material | raw material not conform to tech spec
component | component received or used not conform to tech spec
alignment | out of tolerance on geometrical measurements
welding | welding defects
action
use as is
repair
rejected | sub-assembly rejected, no repair possible (layer)
dismantle | repairing needs de-collaring or cutting of long weld
replace | the component non according to spec will be replaced (stock not magnet)
in green NCR in process or managed internal by the firm
in red NCR where the file is not available at CERN

## NCR total
N | magnet | Component | date | typology | Assembly | sub-assembly | action | Affected object and explication
1 |  | Batch 2 end spacers | 2000-02-04 | component | CC | coil | repair | End spacers out of tolerance
2 |  | Batch 2 end spacers | 2000-02-04 | component | CC | coil | repair | End spacers out of tolerance
3 |  |  |  | component | CC | coil | use as is | Polymide tape without serial number
4 | 2001 | Batch 02 copper wedges | 2000-04-13 | component | CC | coil | repair | Copper wedges end burrs
5 |  | Batch 03 copper wedges | 2000-04-13 | component | CC | coil | repair | Copper wedges end burrs
6 | 2002 |  | 2000-05-02 | component | CC | coil | use as is | Polymide tape without serial number
7 | 2002 | 01C00006A | 2000-05-02 | component | CC | coil | use as is | Cable without CERN documents as per tech. spec.
8 |  | Batch 8 copper wedges | 2000-06-29 | component | CC | coil | repair | Copper wedges end burrs
9 | 2001 | E005 | 2000-11-09 | mechanical | CC | coil | repair | Cracks on spacers after curing
10 | 2001 | E005 | 2000-11-10 | mechanical | CC | coil | repair | Damaged spacer after Emod measurements
11 | 2001 | E002 | 2000-10-19 | irriversible damage | CC | coil | rejected | Out of tolerance between blocks on layer
12 | 2002 | I005 | 2000-11-14 | mechanical | CC | coil | use as is | Out of tolerance of spacers by respect to dwg.
13 | 2002 | I006 | 2000-11-16 | mechanical | CC | coil | use as is | Out of tolerance of spacers by respect to dwg.
14 |  | I005 | 2001-01-11 | irriversible damage | CC | coil | rejected | Cracks on spacers after curing
15 |  | I006 | 2000-11-30 | irriversible damage | CC | coil | rejected | Cracks on spacers after curing
16 | 2001 | E006 | 2001-01-09 | mechanical | CC | coil | use as is | Surface cracks on spacers after curing
17 | 2002 | E007 | 2001-01-10 | mechanical | CC | coil | repair | Cable misaligned on three turns
18 | 2002 | I007 | 2001-01-11 | mechanical | CC | coil | use as is | Out of tolerance of spacers by respect to dwg.
19 | 2001 |  | 2000-11-13 | mechanical | CC | collared coil | use as is | Planarity out of tolerance on collars type 1 & 2
20 | 2001 |  | 2001-02-12 | mechanical | CC | collared coil | repair | Collared coil - total length out of tolerance
21 | 2003 | Quench Heater | 2001-07-11 | electrical | CC | collared coil | repair | Cut cable of QH wire YT221
22 |  | P013 | 2001-07-25 | irriversible damage | CC | pole | rejected | Burned during splice operations
23 | 2004 | E016 - E017 | 2001-07-26 | mechanical | CC | coil | repair | Strand on cable out of position
24 | 2004 - 2005 | E018 to E022 | 2001-07-26 | mechanical | CC | coil | repair | Strand on cable out of position
25 |  | E019 | 2001-07-26 | mechanical | CC | coil | rejected | Damaged end spacer
26 | 2005 | E020 | 2001-07-26 | mechanical | CC | coil | repair | Damaged end spacer
27 | 2005 | E021 | 2001-07-26 | mechanical | CC | coil | use as is | Strand on cable out of position
28 |  | I025 | 2001-08-07 | irriversible damage | CC | coil | rejected | Cut strand on head
29 | 2004 - 2005 | Batch 13 | 2001-04-11 | component | CC | coil | rejected | Interlayer spacers out of tolerance
30 | 2004 | I024 | 2001-09-18 | mechanical | CC | coil | repair | Gap between copper wedge and end spacer
31 | 2002 | Quench Heater | 2001-09-21 | electrical | CC | collared coil | repair | Cut cable of QH wire YT221
32 | 2005 |  | 2001-10-01 | mechanical | CC | collared coil | use as is | Gap of end plates out of tolerance
33 | 2004 | P014-P019-P020-P021 | 2001-11-16 | mechanical | CC | pole | use as is | Small marks on cable after Emod measurements
34 | 2009 | I039 | 2001-12-21 | mechanical | CC | coil | use as is | Defects on layer
35 | 2002 |  | 2001-07-13 | mechanical | CC | coil |  | Double protection sheet
36 | 2002 |  | 2001-07-13 | mechanical | CC | coil | dismantle | Double protection sheet
37 | 2008 | E029 | 2002-01-28 | mechanical | CC | coil | use as is | Mark on cable
38 | 2008 | P027 to P029 | 2002-01-28 | mechanical | CC | coil | use as is | Mark on cable
39 | 2007 |  | 2002-01-28 | mechanical | CC | coil | repair | Cold bore tube squeezed
40 | 2006 | E035 | 2002-01-29 | component | CC | coil | repair | Strand on cable out of position
41 | 2009 | E037 | 2002-01-29 | component | CC | coil | repair | Strand on cable out of position
42 | 2002 |  | 2002-03-15 | electrical | CM | cold mass | dismantle | Electrical problems on QH
43 |  | Shell 0084 | 2002-03-18 | component | CM | cold mass main body | use as is | Half shell out of tolerance
44 | 2012 | E049 | 2002-03-19 | mechanical | CC | coil | use as is | Gap in head
45 | 2012 | I050 | 2002-03-21 | mechanical | CC | coil | repair | Broken end spacer during winding
46 | 2006 |  | 2002-04-02 | mechanical | CC | collared coil | use as is | Gap of end plates out of tolerance
47 | 2002 |  | 2002-04-05 | mechanical | CC | collared coil | repair | QH damaged
48 |  | E046 | 2002-04-23 | irriversible damage | CC | coil | rejected | Cable damaged during splice operations
49 | 2012 | I051 | 2002-04-29 | mechanical | CC | coil | repair | Detached cable
50 | 2010 |  | 2002-05-03 | electrical | CC | collared coil | repair | Short circuit between layers
51 | 2005 |  | 2002-05-03 | electrical | CM | cold mass main body | dismantle | QH failure
52 | 2014 | I057 | 2002-05-22 | mechanical | CC | coil | repair | Detached cable
53 | 2014 | P055 | 2002-05-22 | mechanical | CC | coil | repair | Detached cable
54 | 2015 | I061 | 2002-05-24 | mechanical | CC | coil | use as is | Gap in head
55 |  | QH4528 | 2002-05-24 | irriversible damage | CC | collared coil | rejected | QH failure during test
56 |  | Cable 02K03501A | 2002-05-30 | irriversible damage | CC | coil | rejected | Defect cable
57 |  | QH4704 | 2002-06-11 | irriversible damage | CC | collared coil | rejected | QH failure during test
58 |  | QH4445 | 2002-06-28 | irriversible damage | CC | collared coil | rejected | QH failure during test
59 | 2013 |  | 2002-07-03 | mechanical | CC | collared coil | dismantle | QH failure
60 |  | Batch 23 copper wedges | 2002-07-09 | irriversible damage | CC | collared coil | rejected | Some c.w. damaged during transport
61 |  | QH4389 | 2002-07-15 | irriversible damage | CC | collared coil | rejected | QH failure during test
62 | 2018 | E076 | 2002-07-11 | mechanical | CC | coil | repair | End spacer damaged after curing
63 | 2011 | E045 to E048 | 2002-07-10 | mechanical | CC | collared coil | use as is | Small cracks on saddles
64 | 2011 |  | 2002-07-19 | electrical | CC | collared coil | dismantle | QH failure
65 | 2017 | E070 | 2002-07-22 | mechanical | CC | collared coil | repair | Detached cable
66 | 2011 |  | 2002-07-29 | electrical | CC | collared coil |  | QH failure
67 | 2012 |  | 2002-08-02 | mechanical | CC | collared coil | use as is | Magnetic measurements b1 out of tolerance
68 | 2014 |  | 2002-08-02 | mechanical | CC | collared coil | use as is | Magnetic measurements b1 out of tolerance
69 | 2004 |  | 2002-08-02 | welding | CM | cold mass | repair | Welding defects
70 | 2006 |  | 2002-08-04 | mechanical | CM | cold mass main body | dismantle | Misalignment between half shells before welding
71 | 2004 |  | 2002-10-11 | welding | CM | cold mass | repair | Welding defects
72 | 2004 |  | 2002-10-23 | alignment | CM | cold mass | repair | Geometry
73 | 2011 | QH4751 | 2002-10-25 | electrical | CC | collared coil | use as is | Wrong reference colour on cables
74 | 2006 |  | 2002-10-17 | welding | CM | cold mass | repair | Welding defects
75 | 2006 | TT821 | 2002-11-22 | electrical | CM | cold mass | repair | Temperature sensor broken
76 | 2004 |  | 2002-11-25 | alignment | CM | cold mass | use as is | Geometry
77 |  | I099 | 2002-01-13 | irriversible damage | CC | coil | rejected | Cut strand on head
78 | 2009 |  | 2002-12-10 | alignment | CM | cold mass | repair | Geometry
79 | 2006 |  | 2002-01-16 | alignment | CM | cold mass | repair | Geometry
80 |  | Support pads | 2002-01-10 | mechanical | CM | cold mass | use as is | Support pads out of tolerance
81 | 2023 | P092 | 2002-01-15 | electrical | CC | collared coil | repair | Inter turn discharge
82 | 2012 |  | 2002-10-18 | welding | CM | cold mass | use as is | Welding defects
83 | 2020 |  | 2002-01-24 | electrical | CM | cold mass main body | repair | Cable cut at wrong length
84 | 2010 |  | 2002-12-18 | welding | CM | cold mass | repair | Welding defects
85 | 2008 |  | 2003-01-15 | welding | CM | cold mass | repair | Welding defects
86 | 2007 |  | 2003-01-22 | welding | CM | cold mass | use as is | Welding defects
87 | 2009 |  | 2003-02-03 | welding | CM | cold mass | use as is | Welding defects
88 | 2012 |  | 2003-02-17 | alignment | CM | cold mass | repair | Geometry
89 | 2020 |  | 2003-01-23 | welding | CM | cold mass | repair | Welding defects
90 | 2008 |  | 2003-03-20 | alignment | CM | cold mass | repair | Geometry
91 | 2005 |  | 2003-03-21 | electrical | CM | cold mass main body | repair | Damaged cable during dismounting
92 | 2021 | TT821 | 2003-04-09 | electrical | CM | cold mass | repair | Temperature sensor broken
93 | 2012 |  | 2003-03-26 | alignment | CM | cold mass | use as is | Geometry
94 | 2020 |  | 2003-03-26 | alignment | CM | cold mass | repair | Geometry
95 | 2012 |  | 2003-03-27 | alignment | CM | cold mass | repair | Geometry
96 | 2012 |  | 2003-04-02 | electrical | CM | cold mass | repair | Voltage taps interchanged
97 | 2020 | QH YT112 | 2003-04-02 | electrical | CM | cold mass | dismantle | QH failure
98 | 2010 | Bus Bar 00000024 typeB | 2003-04-08 | component | CM | cold mass | use as is | Wrong length of cable
99 | 2007 |  | 2003-04-15 | alignment | CM | cold mass | use as is | Geometry
100 | 2010 |  | 2003-04-23 | alignment | CM | cold mass | use as is | Geometry
101 | 2021 |  | 2003-03-19 | welding | CM | cold mass | use as is | Welding defects
102 | 2014 |  | 2003-03-20 | welding | CM | cold mass | repair | Welding defects
103 | 2023 |  | 2003-04-04 | welding | CM | cold mass | repair | Welding defects
104 | 2009 |  | 2003-05-09 | alignment | CM | cold mass | repair | Geometry
105 | 2024 | P096 & P097 | 2003-05-12 | electrical | CC | collared coil | repair | Short circuit between two poles
106 | 2009 |  | 2003-05-13 | mechanical | CM | cold mass | repair | Leak
107 | 2021 |  | 2003-05-19 | alignment | CM | cold mass | repair | Geometry
108 | 2024 | P097 | 2003-05-21 | electrical | CC | collared coil | repair | Short circuit between quench heater and pole
109 | 2025 |  | 2003-05-25 | welding | CM | cold mass | repair | Welding defects
110 | 2014 |  | 2003-05-27 | alignment | CM | cold mass | use as is | Geometry
111 | 2002 |  | 2003-06-05 | welding | CM | cold mass | repair | Welding defects
112 | 2032 |  | 2003-06-10 | mechanical | CC | collared coil |  | Magnetic measurements out of tolerance
113 | 2022 |  | 2003-06-16 | alignment | CM | cold mass | use as is | Geometry
114 | 2017 |  | 2003-06-26 | welding | CM | cold mass | repair | Welding defects
115 | 2020 |  | 2003-06-26 | welding | CM | cold mass | repair | Welding defects
116 | 2027 | QH YT122 | 2003-05-27 | electrical | CM | cold mass main body | dismantle | QH failure
117 | 2018 |  | 2003-06-27 | welding | CM | cold mass | repair | Welding defects
118 | 2002 |  | 2003-06-30 | alignment | CM | cold mass | use as is | Geometry
119 | 2027 |  | 2003-07-15 | welding | CM | cold mass | repair | Welding defects
120 | 2013 |  | 2003-07-15 | welding | CM | cold mass | repair | Welding defects
121 | 2016 | TT821 | 2003-07-16 | electrical | CM | cold mass | repair | Temperature sensor broken
122 |  | EYA00044 | 2003-07-18 | mechanical | CM | cold mass main body | use as is | Shorter by 2mm by respect to tolerance
123 | 2016 |  | 2003-07-18 | welding | CM | cold mass | repair | Welding defects
124 |  | Lower shell L0270 | 2003-07-21 | mechanical | CM | cold mass main body | use as is | Lower shell with grindings on surface
125 | 2020 |  | 2003-07-18 | mechanical | CM | cold mass | repair | Leak
126 | 2017 |  | 2003-07-23 | alignment | CM | cold mass | use as is | Geometry
127 |  | Copper wedges batch 31 | 2003-07-31 | component | CC | coil | rejected | Transport accident
128 | 2005 |  | 2003-08-06 | welding | CM | cold mass | repair | Welding defects
129 | 2024 |  | 2003-08-06 | welding | CM | cold mass | repair | Welding defects
130 | 2016 |  | 2003-08-07 | alignment | CM | cold mass | use as is | Geometry
131 | 2013 |  | 2003-08-26 | alignment | CM | cold mass | repair | Geometry
132 | 2035 |  | 2003-07-17 | mechanical | CC | collared coil |  | Magnetic measurements out of tolerance
133 | 2029 |  | 2003-09-01 | welding | CM | cold mass | repair | Welding defects
134 | 2054 | E0217 | 2003-09-10 | electrical | CC | collared coil | repair | Short circuit between turns
135 |  | TT821 | 2003-09-15 | mechanical | CM | cold mass main body | repair | TT821 position change
136 | 2062 | E0250 | 2003-09-18 | mechanical | CC | collared coil | repair | Detachment of turn and compression in it
137 | 2036 | TT821 | 2003-09-15 | mechanical | CM | cold mass main body | use as is | TT821 position change
138 | 2062 | E0252 | 2003-09-18 | mechanical | CC | coil | repair | Small detachment of a turn
139 | 2011 |  | 2003-09-25 | welding | CM | cold mass | repair | Welding defects
140 | 2029 |  | 2003-10-02 | electrical | CM | cold mass |  | Wrong connection of voltage tap EE841
141 | 2068 | E0274 | 2003-10-02 | mechanical | CC | collared coil | repair | Detachment
142 | 2015 |  | 2003-10-09 | welding | CM | cold mass | repair | Welding defects
143 | 2033 |  | 2003-10-28 | welding | CM | cold mass | repair | Welding defects
144 | 2036 |  | 2003-10-10 | welding | CM | cold mass | repair | Welding defects
145 | 2071 | E0285 | 2003-10-15 | mechanical | CC | coil | use as is | Winding machine crash
146 | 2065 | P0259 | 2003-10-28 | electrical | CC | pole |  | damaged cable
147 | 2034 |  | 2003-10-28 | welding | CM | cold mass | repair | Welding defects
148 | 2054 |  | 2003-10-28 | welding | CM | cold mass | repair | Welding defects
149 | 2063 | QHYT212 - B0130 | 2003-11-07 | electrical | CC | collared coil | dismantle | Electrical discharge between QH and pole P0253
150 | 2054 |  | 2003-11-11 | electrical | CM | cold mass |  | Inversion between wires 1 & 2 of aux. Bus bar
151 | 2039 |  | 2003-11-11 | welding | CM | cold mass | repair | Welding defects
152 | 2050 |  | 2003-11-11 | welding | CM | cold mass | repair | Welding defects
153 | 2046 | QHYT111-121 B0163 B0131 | 2003-11-12 | electrical | CC | pole | dismantle | Elect. Disch. Betw. QH's and poles P0183 and P0184
154 | 2041 |  | 2003-11-17 | welding | CM | cold mass | repair | Welding defects
155 | 2040 |  | 2003-11-19 | welding | CM | cold mass | repair | Welding defects
156 | 2050 |  | 2003-11-21 | alignment | CM | cold mass | use as is | Geometry - twist
157 | 2048 |  | 2003-11-26 | welding | CM | cold mass | repair | Welding defects
158 | 2048 |  | 2003-11-26 | welding | CM | cold mass | repair | Welding defects
159 | 2048 |  | 2003-12-17 | alignment | CM | cold mass | use as is | Geometry - twist
160 | 2038 |  | 2004-01-08 | welding | CM | cold mass | repair | Welding defects
161 | 2066 | HCDCBHA055-BI000186 | 2004-01-23 | electrical | CM | cold mass main body | repair | Damaged bus bar
162 |  |  | 2004-01-16 | mechanical | CC | collared coil | repair | Rejlers press
163 | 2043 |  | 2004-01-12 | mechanical | CM | cold mass | repair | leak
164 | 2048 |  | 2004-01-12 | mechanical | CM | cold mass | repair | leak
165 | 2046 | TT821 | 2004-01-15 | electrical | CM | cold mass main body | repair | Temperature sensor broken
166 | 2043 |  | 2004-01-19 | welding | CM | cold mass | repair | Welding defects
167 | 2064 |  | 2004-01-19 | welding | CM | cold mass | repair | Welding defects
168 | 2047 |  | 2004-01-20 | mechanical | CC | collared coil | repair | shims
169 | 2051 |  | 2004-01-20 | mechanical | CC | collared coil | repair | shims
170 | 2051 | QHYT112 - CICOA0147 | 2004-01-20 | electrical | CC | collared coil | dismantle | QH failure
171 | 2046 |  | 2004-01-26 | mechanical | CM | cold mass | repair | leak
172 | 2063 |  | 2004-01-26 | mechanical | CC | collared coil | repair | Fish bones deplaced
173 | 2072 |  | 2004-01-28 | welding | CM | cold mass | repair | Welding defects
174 | 2064 |  | 2004-02-02 | alignment | CM | cold mass | use as is | Geometry - feet
175 |  | MAL00200-201-202 | 2004-02-02 | component | CC | collared coil | rejected | Collars out of tolerance
176 | 2069 |  | 2004-01-04 | welding | CM | cold mass | repair | Welding defects
177 |  | HCDCBHA055 | 2004-02-09 | component | CM | cold mass main body | repair | Bus bars
178 |  | MAL00208-217 | 2004-02-10 | component | CC | collared coil | rejected | Collars out of tolerance
179 | 2051 |  | 2004-02-10 | welding | CM | cold mass | repair | Welding defects
180 | 2072 |  | 2004-02-13 | alignment | CM | cold mass | use as is | Geometry - feet
181 | 2073 | QHYT211 - CICOA0120 | 2004-02-17 | electrical | CC | cold mass main body | dismantle | QH failure
182 | 2032 | EE012-EE013 | 2004-02-17 | electrical | CM | cold mass main body | use as is | Color inversion on wires
183 | 2063 |  | 2004-02-26 | welding | CM | cold mass | repair | Welding defects
184 | 2066 |  | 2004-02-27 | mechanical | CM | cold mass | repair | Leak on X-line
185 | 2070 | TT821 | 2004-03-05 | electrical | CM | cold mass main body | repair | Temperature sensor broken
186 | 2097 |  | 2004-03-17 | mechanical | CC | coil | use as is | Pop up of some strands
187 | 2095 |  | 2004-03-17 | mechanical | CC | coil | repair | Pop up of some strands
188 | 2096 |  | 2004-03-17 | mechanical | CC | coil | use as is | Pop up of some strands
189 | 2074 |  | 2004-03-19 | welding | CM | cold mass | repair | Welding defects
190 |  | MAL00164-165-166 | 2004-03-16 | component | CC | collared coil | repair | Burrs on upper slot of collars
191 |  | MAL00232-235-244-247-252-255 | 2004-03-30 | component | CC | collared coil | repair | Burrs on collars
192 | 2067 |  | 2004-03-31 | welding | CM | cold mass | repair | Welding defects
193 | 2078 |  | 2004-03-31 | welding | CM | cold mass | repair | Welding defects
194 | 2061 |  | 2004-04-07 | welding | CM | cold mass | repair | Welding defects
195 | 2082 |  | 2004-04-14 | welding | CM | cold mass | repair | Welding defects
196 | 2112 | 02B50250A | 2004-04-15 | mechanical | CC | coil | use as is | Transport accident
197 | 2062 |  | 2004-04-22 | welding | CM | cold mass | repair | Welding defects
198 | 2076 |  | 2004-04-22 | welding | CM | cold mass | repair | Welding defects
199 | 2059 | TT821 | 2004-05-07 | electrical | CM | cold mass main body | repair | Temperature sensor broken
200 |  | CW Batch 75 | 2004-06-29 | component | CC | coil | rejected | Transport accident
201 |  | EYA00100-101-102 | 2004-05-13 | component | CM | cold mass | use as is | Cleanliness problem
202 | 2073 | QHYT111 - ASGCICO-B0081 | 2004-05-19 | electrical | CC | collared coil | dismantle | QH failure
203 | 2104 | 02I00418 | 2004-05-24 | mechanical | CC | coil | use as is | Curing temp exceeded
204 | 2107 | 02I00430 | 2004-05-24 | mechanical | CC | coil | use as is | Curing temp exceeded
205 | 2079 |  | 2004-05-19 | welding | CM | cold mass | repair | Welding defects
206 | 2031 |  | 2004-05-24 | welding | CM | cold mass | repair | Welding defects
207 | 2523 |  | 2004-06-08 | alignment | CM | cold mass | use as is | Corrector reference holes out of tolerance
208 | 2101 | 02P00403 | 2004-06-10 | electrical | CC | pole | repair | Short circuit
209 | 2523 | P092 | 2002-01-15 | electrical | CC | collared coil | repair | Inter turn discharge - From NCR 081
210 | 2077 |  | 2004-06-10 | alignment | CM | cold mass | use as is | Corrector reference holes out of tolerance
211 | 2073 |  | 2004-06-11 | mechanical | CM | cold mass main body | repair | Extended cable to bus bar
212 | 2085 |  | 2004-06-17 | alignment | CM | cold mass | use as is | Corrector reference holes out of tolerance
213 | 2065 |  | 2004-06-11 | alignment | CM | cold mass | use as is | Corrector reference holes out of tolerance
214 | 2035 |  | 2004-06-29 | welding | CM | cold mass | repair | Welding defects
215 | 2108 |  | 2004-06-29 | welding | CM | cold mass | repair | Welding defects
216 |  | MCS-MA-E0156-AT000156 | 2004-06-28 | component | CM | cold mass | rejected | Sextupole not conforming
217 | 2112 |  | 2004-06-28 | mechanical | CC | coil | use as is | Curing temp exceeded
218 | 2085 |  | 2004-06-28 | electrical | CM | cold mass | repair | Low insulation resistance
219 | 2091 |  | 2004-07-12 | welding | CM | cold mass | repair | Welding defects
220 |  | MCDO-MA-I0186 | 2004-07-12 | irriversible damage | CM | cold mass | rejected | Decapole with wire cut
221 |  | MAL00296-297-298-299 | 2004-07-12 | component | CC | collared coil | use as is | Thickness higher than tolerance
222 | 2084 |  | 2004-07-12 | welding | CM | cold mass | repair | Welding defects
223 | 2090 |  | 2004-07-08 | electrical | CM | cold mass | use as is | Wrong connection of spool
224 | 2092 | YT121-ASG-CICOB0369 | 2004-07-05 | electrical | CC | collared coil | dismantle | QH failure
225 | 2073 | YT121 | 2004-07-05 | electrical | CC | collared coil | dismantle | QH failure
226 | 2096 | YT221-ASG-CICO-B0354 | 2004-07-31 | electrical | CC | collared coil | use as is | Wrong wires color
227 | 2087 |  | 2004-08-04 | component | CM | cold mass | use as is | Cable of bus bar too short
228 | 2075 |  | 2004-07-22 | mechanical | CM | cold mass | repair | N-Line damaged
229 | 2103 |  | 2004-08-04 | component | CM | cold mass | use as is | Cable of bus bar too short
230 | 2098 | 02E00396 | 2004-07-24 | electrical | CC | collared coil | dismantle | QH failure
231 | 2087 | 02P00348 | 2004-07-28 | electrical | CM | cold mass | dismantle | Short circuit
232 | 2094 |  | 2004-08-09 | mechanical | CM | cold mass | repair | Bus bar cable cut too short
233 | 2103 |  | 2004-08-23 | welding | CM | cold mass | repair | Welding defects
234 | 2088 |  | 2004-08-23 | welding | CM | cold mass | repair | Welding defects
235 | 2092 | MC-DO-MA-I0431 | 2004-09-08 | electrical | CM | cold mass | dismantle | Short circuit on decapole
236 | 2125 | 02E00502 | 2004-09-01 | mechanical | CC | coil | repair | Curing temp stopped at 140deg.
237 | 2096 |  | 2004-09-14 | welding | CM | cold mass | repair | Welding defects
238 | 2130 | 02I00524 | 2004-09-16 | mechanical | CC | coil | repair | Polyimide protection sheet glued
239 | 2032 | 02I00129 | 2004-09-17 | electrical | CC | coil | repair | Inter turn discharge
240 | 2114 |  | 2004-09-20 | mechanical | CC | collared coil | use as is | CC felt from wheels to bench
241 | Cold bore tubes |  | 2004-09-22 | mechanical | CC | collared coil | use as is | cbt out of tolerance - remeasured by CERN ok
242 | 2109 |  | 2004-09-27 | welding | CM | cold mass | repair | Welding defects
243 | 2119 | YT121-ASG-CICOA0423 | 2004-09-27 | electrical | CC | collared coil | dismantle | QH failure
244 | 2124 | YT111-ASG-CICOB0446 | 2004-09-27 | electrical | CC | collared coil | dismantle | QH failure
245 | 2111 |  | 2004-09-27 | welding | CM | cold mass | repair | Welding defects
246 | 2113 |  | 2004-10-04 | electrical | CM | cold mass main body | repair | Temperature sensor broken
247 | 2116 |  | 2004-10-04 | electrical | CM | cold mass | repair | Cable cut too short
248 | 2112 | MCS-MA-E0081 | 2004-10-05 | electrical | CM | cold mass | dismantle | Corrector with low resistance
249 | 2114 |  | 2004-10-11 | electrical | CM | cold mass | dismantle | Corrector with low resistance
250 | 2121 |  | 2004-10-09 | electrical | CM | cold mass | dismantle | QH failure
251 | S.s. collars MAL 00203 |  | 2004-10-14 | component | CC | collared coil | repair | Collars with burrs
252 | 2118 | MCS-MA-E0324 | 2004-10-18 | electrical | CM | cold mass | dismantle | Corrector with low resistance
253 | 2117 | MCS-MA-E0297; MCS-MA-E0298; MCDO-MA-E0028 | 2004-10-25 | electrical | CM | cold mass | dismantle | Corrector with low resistance
254 | 2124 | MCDO-MA-E0059 | 2004-10-25 | electrical | CM | cold mass | dismantle | Corrector with low resistance
255 | 2118 |  | 2004-10-28 | electrical | CM | cold mass | repair | Short in capillary
256 | 2134 | YT221-YT111 | 2004-11-05 | electrical | CC | collared coil | dismantle | QH failure
257 | 2136 | 02I00545 | 2004-11-16 | mechanical | CC | coil | repair | Pop up of some strands
258 | 2136 | 02I00546 | 2004-11-16 | mechanical | CC | coil | repair | Pop up of some strands
259 | 2136 | 02I00547 | 2004-11-16 | mechanical | CC | coil | repair | Pop up of some strands
260 | 2136 | 02I00548 | 2004-11-16 | mechanical | CC | coil | repair | Pop up of some strands
261 | 2137 | 02I00551 | 2004-11-16 | mechanical | CC | coil | repair | Pop up of some strands
262 | 2140 | 02I00562 | 2004-11-16 | mechanical | CC | coil | repair | Pop up of some strands
263 | 2143 | 02I00573 | 2004-11-16 | mechanical | CC | coil | repair | Pop up of some strands
264 | 2138 | 02I00555 | 2004-11-17 | mechanical | CC | coil | repair | Pop up of some strands
265 | 2125 |  | 2004-11-16 | electrical | CM | cold mass | dismantle | Low insulation-G11 piece changed
266 | 2130 |  | 2004-11-27 | welding | CM | cold mass | repair | Welding defects
267 | 2137 |  | 2004-11-27 | electrical | CM | cold mass main body | repair | Low resistance-High humidity
268 | bus-bars from nr. A-336 to A-345 and from nr. B-351 to B-360 |  | 2004-11-27 | component | CM | cold mass | repair | Low resistance-High humidity
269 | 2154 |  | 2004-12-02 | mechanical | CC | coil | repair | Pop up of some strands
270 | 2133 | YT111 | 2004-12-07 | electrical | CM | cold mass | repair | Wire too short
271 | 2148 | YT121-YT122 | 2004-12-09 | electrical | CM | cold mass | use as is | Inversion of wire's colors
272 | 2141 | TT821 | 2004-12-09 | electrical | CM | cold mass main body | repair | Temperature sensor broken
273 | 2158 | 02I00617 | 2004-12-14 | mechanical | CC | coil | repair | Low curing temperature
274 | 2148 | YT211-ASGCICO-B0572 | 2004-12-15 | electrical | CC | collared coil | dismantle | QH failure-short Vs. Outer
275 | 2140 | Bus Bar B-358 | 2004-12-20 | electrical | CM | cold mass | repair | Low resistance-High humidity
276 | 2150 | YT121 | 2004-12-22 | electrical | CM | cold mass | use as is | Inversion of wire's colors
277 | 2158 | 02P00630-02I00633 | 2005-10-03 | irriversible damage | CC | pole | rejected | short in head
278 | 2145 |  | 2005-01-11 | welding | CM | cold mass | repair | Welding defects
279 | 2156 | YT111-YT112 | 2005-01-12 | electrical | CM | cold mass | repair | Inversion of wire's colors
280 | 2182 | 02C0136A | 2005-02-24 | mechanical | CC | coil | repair | Pop up of some strands
281 | 2178 | YT221 | 2005-02-16 | mechanical | CC | coil | repair | Pop up of some strands
282 | 2153 | 02C00168E | 2005-03-07 | electrical | CM | cold mass | dismantle | Short QH to ground
283 | 2169 | TT821 | 2005-03-07 | electrical | CM | cold mass main body | repair | Temperature sensor broken
284 | 2184 | 02C00145A | 2005-02-03 | irriversible damage | CC | coil | rejected | cable buckled
285 | 2163 |  | 2005-03-16 | welding | CM | cold mass | repair | Welding of flare pass through
286 | 2159 |  | 2005-03-21 | welding | CM | cold mass | repair | Welding of flare pass through
287 | 2160 |  | 2005-03-21 | welding | CM | cold mass | repair | Leak on welding
288 | 2198 | 02I00796 | 2005-03-21 | mechanical | CC | coil | repair | Pop up of some strands
289 | 2167 | V-taps EE012 and EE013 | 2005-03-22 | electrical | CM | cold mass | use as is | Inversion on wire's colors
290 | 2186 | 02P00743 - 02I00746 | 2005-03-25 | irriversible damage | CC | pole | rejected | short in head
291 | MCS-MA-E0264 | Sextupole Corrector | 2005-03-29 | irriversible damage | CM | cold mass | rejected | Low insulation in corrector
292 | 2204 | 02E00820 | 2005-04-06 | mechanical | CC | coil | repair | Pop up of some strands
293 | 2196 | 02E00787 | 2005-04-06 | mechanical | CC | coil | repair | Pop up of some strands
294 | 2198 | 02I00794 | 2005-04-13 | irriversible damage | CC | coil | rejected | Cut of strand
295 | 2024 | cryo heater | 2005-04-19 | electrical | CM | cold mass | use as is | Wire EH821 open circuit
296 | 2206 | 02I00828 | 2005-04-26 | mechanical | CC | coil | repair | Accident during winding
297 | 2202 | 02P00809 | 2005-05-13 | electrical | CC | collared coil | repair | Short
298 | 2144 |  | 2005-05-20 | alignment | CM | cold mass | repair | cbt out of alignment
299 | 2024 | N-line NN0107 | 2005-05-20 | mechanical | CM | cold mass | dismantle | N-line damaged
300 | 2194 | 02P00777-02E00780 | 2005-05-27 | electrical | CC | pole | repair | Short
301 | 2191 |  | 2005-05-31 | welding | CM | cold mass | repair | scaled surface-flare weld
302 | 2186 | TT821 | 2005-06-13 | electrical | CM | cold mass main body | repair | Temperature sensor broken
303 | 2199 |  | 2005-06-16 | welding | CM | cold mass | repair | scaled surface-flare weld
304 | 2210 | TT821 | 2005-06-17 | electrical | CM | cold mass main body | repair | Temperature sensor broken
305 | 2197 | Bus bar | 2005-06-23 | electrical | CM | cold mass | dismantle | Low insulation-G11 piece changed
306 | 2236 |  | 2005-07-01 | irriversible damage | CC | coil | rejected | cable buckled
307 | 2170 |  | 2005-07-01 | welding | CM | cold mass | repair | scaled surface-flare weld
308 | 2177 |  | 2005-07-01 | welding | CM | cold mass | repair | scaled surface-flare weld
309 | 2231 | YT221-YT222 | 2005-07-20 | electrical | CM | cold mass | use as is | Inversion on wire's colors
310 | 2233 | YT222-02E00935 | 2005-07-20 | electrical | CC | pole | repair | Short
311 | 2182 |  | 2005-07-25 | welding | CM | cold mass | repair | scaled surface-flare weld
312 | 2240 |  | 2005-07-29 | electrical | CM | cold mass | use as is | Inversion on wire's colors
313 | 2205 | Bus bar A-426 | 2005-08-03 | electrical | CM | cold mass | use as is | Cable length
314 | 2208 |  | 2005-08-03 | welding | CM | cold mass | repair | scaled surface-flare weld
315 | 2200 |  | 2005-08-03 | mechanical | CM | cold mass | use as is | Leak test background\
316 | S.s. collars | MAL00311 MAL00448 MAL00449 | 2005-08-04 | component | CC | collared coil | rejected | Planarity out of tolerance on collars
317 | 2215 |  | 2005-08-11 | welding | CM | cold mass | repair | scaled surface-flare weld
318 | 2214 |  | 2005-08-12 | welding | CM | cold mass | repair | scaled surface-flare weld
319 | 2214 |  | 2005-08-25 | mechanical | CM | cold mass | repair | Leak on bellow
320 | 2237 | TT821 | 2005-09-01 | electrical | CM | cold mass main body | repair | Temperature sensor broken
321 | 2229 | Bus bar | 2005-09-05 | electrical | CM | cold mass | dismantle | Low insulation-G11 piece changed
322 | 2202 | TT821 | 2005-09-06 | electrical | CM | cold mass main body | repair | Temperature sensor broken
323 | 2243 | YT111-02E00974 | 2005-09-07 | electrical | CC | pole | repair | Short
324 | MCS-MA-E-0475 | (AT000475) | 2005-09-13 | irriversible damage | CM | cold mass | rejected | Damaged during installation
325 | 2207 | Bus Bar | 2005-09-15 | electrical | CM | cold mass | use as is | Short length of cable on Bus bar
326 | 2221 |  | 2005-09-21 | welding | CM | cold mass | repair | Welding defects
327 | 2229 |  | 2005-09-22 | welding | CM | cold mass | repair | Welding defects
328 | 2216 |  | 2005-09-22 | electrical | CM | cold mass | repair | Damaged wires in capillary
329 | 2211 | TT821 | 2005-09-27 | electrical | CM | cold mass main body | repair | Temperature sensor broken
330 | 2257 | YT111-02E01030 | 2005-10-01 | electrical | CC | pole | repair | Short
331 | 2256 | 02P01024 | 2005-10-03 | electrical | CC | pole | repair | Short
332 | 2211 | Bus Bar | 2005-10-03 | electrical | CM | cold mass | use as is | Short length of cable on Bus bar
333 | 2210 | Bus Bar | 2005-10-06 | electrical | CM | cold mass | use as is | Short length of cable on Bus bar
334 | MCS-MA-I0825 | Correctors | 2005-10-06 | component | CM | cold mass | rejected | Low insulation
335 | 2278 | 02D00190G | 2005-10-17 | irriversible damage | CC | coil | rejected | cable buckled
336 | 2240-2247-2252-2253-2256-2259-2264-2265-2276-2311 |  | 2005-10-18 | component | CM | cold mass | repair | Oxidation on laminations
337 | S.s. collars | MAL00423-00450-00708-00709-00712-00713 | 2005-11-04 | component | CC | collared coil | use as is | Planarity out of tolerance on collars
338 | MCS-MA-E0423 | Correctors | 2005-07-01 | component | CM | cold mass | rejected | Low insulation
339 | MA4577 |  | 2005-05-18 | component | CM | cold mass | rejected | Defect on bellow
340 | 2275 | YT121-02E01102 | 2005-11-11 | electrical | CC | pole | repair | Short
341 | 2223 | YT221-YT111 | 2005-11-14 | electrical | CM | cold mass | repair | Wires damaged
342 | 2265 | V-taps EE012 and EE013 | 2005-11-16 | electrical | CM | cold mass | use as is | Inversion on wire's colors
343 | 2264 | Bus bar B-184 | 2005-11-17 | electrical | CM | cold mass | repair | Damaged aux. Bus bar
344 | 2265 | Bus Bar B-193 | 2005-11-21 | electrical | CM | cold mass | use as is | Short length of cable on Bus bar
345 | 2253 | Bus bar A-508 | 2005-11-22 | electrical | CM | cold mass | use as is | Bus bar A type instead B type
346 | 2278 | 02P01110 | 2005-11-23 | electrical | CC | pole | repair | Short
347 | 2283 | YT112-02E01134 | 2005-11-25 | electrical | CC | pole | repair | Short
348 | 2263 | V-tap E-931 | 2005-12-05 | electrical | CM | cold mass | repair | open circuit
349 | 2264 | Bellow heat exchanger | 2005-12-07 | mechanical | CM | cold mass | repair | Leak
350 | 2221 | Diode | 2005-12-12 | electrical | CM | cold mass | dismantle | Non conforming screws on diode
351 | 2263 | Diode | 2005-12-12 | electrical | CM | cold mass | dismantle | Non conforming screws on diode
352 | 2278 | 02P01110 | 2005-12-19 | irriversible damage | CC | coil | rejected | Short
353 | 2253 | Bellow heat exchanger | 2005-12-19 | mechanical | CM | cold mass | repair | Leak
354 | 2304 | 02E01218 | 2005-12-09 | irriversible damage | CC | coil | rejected | Coil with one turn less
355 | 2274 | Bellow heat exchanger | 2005-12-20 | mechanical | CM | cold mass | repair | Leak
356 | 2282 | Corrector | 2005-12-30 | electrical | CM | cold mass | repair | Inversion on wires 13 and 14
357 | 2253 | X-line bellow | 2005-12-22 | mechanical | CM | cold mass | repair | Leak
358 | 2269 | Bus bar A-509 | 2006-01-12 | electrical | CM | cold mass | use as is | Bus bar B type instead A type
359 | 2270 | 02P01081 |  | electrical | CC | pole | repair | Short
360 | 2300 | TT821 | 2006-01-23 | electrical | CM | cold mass main body | repair | Temperature sensor broken
361 | 2316 | 02I01268 | 2006-01-23 | irriversible damage | CC | coil | rejected | Damage by accident during winding
362 | 2325 | 02C91541D | 2006-01-25 | irriversible damage | CC | coil | rejected | Damage by accident during wrapping
363 | 2290 |  | 2006-02-02 | welding | CM | cold mass | repair | Welding defects
364 | 2289 | Bus bar B-573 | 2006-02-08 | mechanical | CM | cold mass | repair | Deformation of bus bar
365 | 2324 | 02I01300 | 2006-02-10 | irriversible damage | CC | coil | rejected | Damage by accident during winding
366 | 2303 |  | 2006-02-10 | electrical | CC | coil | use as is | Displacement of block 6

## Data_Chart
typology | action | Affected object and explication | Tipology
electrical | dismantle | Corrector with low resistance | electrical | mechanical | irriversible damage | component | alignment | welding
electrical | dismantle | Corrector with low resistance | 104 | 96 | 27 | 33 | 28 | 75
electrical | dismantle | Corrector with low resistance
electrical | dismantle | Corrector with low resistance
electrical | dismantle | Corrector with low resistance
mechanical | dismantle | Double protection sheet | Dismantle
electrical | dismantle | Elect. Disch. Betw. QH's and poles P0183 and P0184 | Corrector | QH | Short | Accident | Other
electrical | dismantle | Electrical discharge between QH and pole P0253 | 5 | 17 | 4 | 1 | 8
electrical | dismantle | Electrical problems on QH
electrical | dismantle | Low insulation-G11 piece changed
electrical | dismantle | Low insulation-G11 piece changed
electrical | dismantle | Low insulation-G11 piece changed | Rejected
mechanical | dismantle | Misalignment between half shells before welding | Cable damage | Components | Winding/curing accident | QH
mechanical | dismantle | N-line damaged | 12 | 14 | 8 | 4
electrical | dismantle | Non conforming screws on diode
electrical | dismantle | Non conforming screws on diode
electrical | dismantle | QH failure
electrical | dismantle | QH failure | Repair
electrical | dismantle | QH failure | Component | Bus bar | coil | qh | Geometry | Leak | Other | welding | TT821
electrical | dismantle | QH failure | 7 | 10 | 64 | 6 | 10 | 12 | 9 | 71 | 16
electrical | dismantle | QH failure
electrical | dismantle | QH failure
electrical | dismantle | QH failure
electrical | dismantle | QH failure | Use as is
electrical | dismantle | QH failure | Bus bar | Corrector | Geometry | Wire's inversion | Other | Coil | Welding
electrical | dismantle | QH failure | 9 | 4 | 14 | 11 | 24 | 22 | 4
electrical | dismantle | QH failure
electrical | dismantle | QH failure
electrical | dismantle | QH failure
electrical | dismantle | QH failure | All
mechanical | dismantle | QH failure | Dismantle | Rejected | Repair | Use as is
electrical | dismantle | QH failure-short Vs. Outer | 35 | 38 | 205 | 88
electrical | dismantle | Short circuit
electrical | dismantle | Short circuit on decapole
electrical | dismantle | Short QH to ground
irriversible damage | rejected | Burned during splice operations
irriversible damage | rejected | cable buckled
irriversible damage | rejected | cable buckled
irriversible damage | rejected | cable buckled
irriversible damage | rejected | Cable damaged during splice operations
irriversible damage | rejected | Coil with one turn less
component | rejected | Collars out of tolerance
component | rejected | Collars out of tolerance
irriversible damage | rejected | Cracks on spacers after curing
irriversible damage | rejected | Cracks on spacers after curing
irriversible damage | rejected | Cut of strand
irriversible damage | rejected | Cut strand on head
irriversible damage | rejected | Cut strand on head
irriversible damage | rejected | Damage by accident during winding
irriversible damage | rejected | Damage by accident during winding
irriversible damage | rejected | Damage by accident during wrapping
irriversible damage | rejected | Damaged during installation
mechanical | rejected | Damaged end spacer
irriversible damage | rejected | Decapole with wire cut
irriversible damage | rejected | Defect cable
component | rejected | Defect on bellow
component | rejected | Interlayer spacers out of tolerance
component | rejected | Low insulation
component | rejected | Low insulation
irriversible damage | rejected | Low insulation in corrector
irriversible damage | rejected | Out of tolerance between blocks on layer
component | rejected | Planarity out of tolerance on collars
irriversible damage | rejected | QH failure during test
irriversible damage | rejected | QH failure during test
irriversible damage | rejected | QH failure during test
irriversible damage | rejected | QH failure during test
component | rejected | Sextupole not conforming
irriversible damage | rejected | Short
irriversible damage | rejected | short in head
irriversible damage | rejected | short in head
irriversible damage | rejected | Some c.w. damaged during transport
component | rejected | Transport accident
component | rejected | Transport accident
mechanical | repair | Accident during winding
mechanical | repair | Broken end spacer during winding
component | repair | Burrs on collars
component | repair | Burrs on upper slot of collars
mechanical | repair | Bus bar cable cut too short
component | repair | Bus bars
electrical | repair | Cable cut at wrong length
electrical | repair | Cable cut too short
mechanical | repair | Cable misaligned on three turns
alignment | repair | cbt out of alignment
mechanical | repair | Cold bore tube squeezed
mechanical | repair | Collared coil - total length out of tolerance
component | repair | Collars with burrs
component | repair | Copper wedges end burrs
component | repair | Copper wedges end burrs
component | repair | Copper wedges end burrs
mechanical | repair | Cracks on spacers after curing
mechanical | repair | Curing temp stopped at 140deg.
electrical | repair | Cut cable of QH wire YT221
electrical | repair | Cut cable of QH wire YT221
electrical | repair | Damaged aux. Bus bar
electrical | repair | Damaged bus bar
electrical | repair | Damaged cable during dismounting
mechanical | repair | Damaged end spacer
mechanical | repair | Damaged spacer after Emod measurements
electrical | repair | Damaged wires in capillary
mechanical | repair | Deformation of bus bar
mechanical | repair | Detached cable
mechanical | repair | Detached cable
mechanical | repair | Detached cable
mechanical | repair | Detached cable
mechanical | repair | Detachment
mechanical | repair | Detachment of turn and compression in it
mechanical | repair | End spacer damaged after curing
component | repair | End spacers out of tolerance
component | repair | End spacers out of tolerance
mechanical | repair | Extended cable to bus bar
mechanical | repair | Fish bones deplaced
mechanical | repair | Gap between copper wedge and end spacer
alignment | repair | Geometry
alignment | repair | Geometry
alignment | repair | Geometry
alignment | repair | Geometry
alignment | repair | Geometry
alignment | repair | Geometry
alignment | repair | Geometry
alignment | repair | Geometry
alignment | repair | Geometry
alignment | repair | Geometry
electrical | repair | Inter turn discharge
electrical | repair | Inter turn discharge
electrical | repair | Inter turn discharge - From NCR 081
electrical | repair | Inversion of wire's colors
electrical | repair | Inversion on wires 13 and 14
mechanical | repair | Leak
mechanical | repair | Leak
mechanical | repair | leak
mechanical | repair | leak
mechanical | repair | leak
mechanical | repair | Leak
mechanical | repair | Leak
mechanical | repair | Leak
mechanical | repair | Leak
mechanical | repair | Leak on bellow
welding | repair | Leak on welding
mechanical | repair | Leak on X-line
mechanical | repair | Low curing temperature
electrical | repair | Low insulation resistance
component | repair | Low resistance-High humidity
electrical | repair | Low resistance-High humidity
electrical | repair | Low resistance-High humidity
mechanical | repair | N-Line damaged
electrical | repair | open circuit
component | repair | Oxidation on laminations
mechanical | repair | Polyimide protection sheet glued
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | Pop up of some strands
mechanical | repair | QH damaged
mechanical | repair | Rejlers press
welding | repair | scaled surface-flare weld
welding | repair | scaled surface-flare weld
welding | repair | scaled surface-flare weld
welding | repair | scaled surface-flare weld
welding | repair | scaled surface-flare weld
welding | repair | scaled surface-flare weld
welding | repair | scaled surface-flare weld
welding | repair | scaled surface-flare weld
mechanical | repair | shims
mechanical | repair | shims
electrical | repair | Short
electrical | repair | Short
electrical | repair | Short
electrical | repair | Short
electrical | repair | Short
electrical | repair | Short
electrical | repair | Short
electrical | repair | Short
electrical | repair | Short
electrical | repair | Short
electrical | repair | Short circuit
electrical | repair | Short circuit between layers
electrical | repair | Short circuit between quench heater and pole
electrical | repair | Short circuit between turns
electrical | repair | Short circuit between two poles
electrical | repair | Short in capillary
mechanical | repair | Small detachment of a turn
component | repair | Strand on cable out of position
component | repair | Strand on cable out of position
mechanical | repair | Strand on cable out of position
mechanical | repair | Strand on cable out of position
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
electrical | repair | Temperature sensor broken
mechanical | repair | TT821 position change
electrical | repair | Voltage taps interchanged
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding defects
welding | repair | Welding of flare pass through
welding | repair | Welding of flare pass through
electrical | repair | Wire too short
electrical | repair | Wires damaged
electrical | use as is | Bus bar A type instead B type
electrical | use as is | Bus bar B type instead A type
electrical | use as is | Cable length
component | use as is | Cable of bus bar too short
component | use as is | Cable of bus bar too short
component | use as is | Cable without CERN documents as per tech. spec.
mechanical | use as is | cbt out of tolerance - remeasured by CERN ok
mechanical | use as is | CC felt from wheels to bench
component | use as is | Cleanliness problem
electrical | use as is | Color inversion on wires
alignment | use as is | Corrector reference holes out of tolerance
alignment | use as is | Corrector reference holes out of tolerance
alignment | use as is | Corrector reference holes out of tolerance
alignment | use as is | Corrector reference holes out of tolerance
mechanical | use as is | Curing temp exceeded
mechanical | use as is | Curing temp exceeded
mechanical | use as is | Curing temp exceeded
mechanical | use as is | Defects on layer
electrical | use as is | Displacement of block 6
mechanical | use as is | Gap in head
mechanical | use as is | Gap in head
mechanical | use as is | Gap of end plates out of tolerance
mechanical | use as is | Gap of end plates out of tolerance
alignment | use as is | Geometry
alignment | use as is | Geometry
alignment | use as is | Geometry
alignment | use as is | Geometry
alignment | use as is | Geometry
alignment | use as is | Geometry
alignment | use as is | Geometry
alignment | use as is | Geometry
alignment | use as is | Geometry
alignment | use as is | Geometry - feet
alignment | use as is | Geometry - feet
alignment | use as is | Geometry - twist
alignment | use as is | Geometry - twist
component | use as is | Half shell out of tolerance
electrical | use as is | Inversion of wire's colors
electrical | use as is | Inversion of wire's colors
electrical | use as is | Inversion on wire's colors
electrical | use as is | Inversion on wire's colors
electrical | use as is | Inversion on wire's colors
electrical | use as is | Inversion on wire's colors
mechanical | use as is | Leak test background
mechanical | use as is | Lower shell with grindings on surface
mechanical | use as is | Magnetic measurements b1 out of tolerance
mechanical | use as is | Magnetic measurements b1 out of tolerance
mechanical | use as is | Mark on cable
mechanical | use as is | Mark on cable
mechanical | use as is | Out of tolerance of spacers by respect to dwg.
mechanical | use as is | Out of tolerance of spacers by respect to dwg.
mechanical | use as is | Out of tolerance of spacers by respect to dwg.
component | use as is | Planarity out of tolerance on collars
mechanical | use as is | Planarity out of tolerance on collars type 1 & 2
component | use as is | Polymide tape without serial number
component | use as is | Polymide tape without serial number
mechanical | use as is | Pop up of some strands
mechanical | use as is | Pop up of some strands
electrical | use as is | Short length of cable on Bus bar
electrical | use as is | Short length of cable on Bus bar
electrical | use as is | Short length of cable on Bus bar
electrical | use as is | Short length of cable on Bus bar
mechanical | use as is | Shorter by 2mm by respect to tolerance
mechanical | use as is | Small cracks on saddles
mechanical | use as is | Small marks on cable after Emod measurements
mechanical | use as is | Strand on cable out of position
mechanical | use as is | Support pads out of tolerance
mechanical | use as is | Surface cracks on spacers after curing
component | use as is | Thickness higher than tolerance
mechanical | use as is | Transport accident
mechanical | use as is | TT821 position change
welding | use as is | Welding defects
welding | use as is | Welding defects
welding | use as is | Welding defects
welding | use as is | Welding defects
mechanical | use as is | Winding machine crash
electrical | use as is | Wire EH821 open circuit
electrical | use as is | Wrong connection of spool
component | use as is | Wrong length of cable
electrical | use as is | Wrong reference colour on cables
electrical | use as is | Wrong wires color
electrical |  | damaged cable
mechanical |  | Double protection sheet
electrical |  | Inversion between wires 1 & 2 of aux. Bus bar
mechanical |  | Magnetic measurements out of tolerance
mechanical |  | Magnetic measurements out of tolerance
electrical |  | QH failure
electrical |  | Wrong connection of voltage tap EE841