## Winding
Winding , Curing and Surfacing
Situation at 31/5/05
Equivalent CM done | Equivalent CM to be produced | End of activity | Remaining working weeks | Minimum production rate required (CM/week) | Workers
222 | 194 | 2006-07-31 | 56 | 3.46 | 37
Situation at 31/8/05
Equivalent CM done | Equivalent CM to be produced | End of activity | Remaining working weeks | Minimum production rate required (CM/week) | Workers
255 | 161 | 2006-07-31 | 46 | 3.5 | 37
As in the months of May, June and July the average production rate was 3,42 in order to be able to reach and maintain 3,50 we need to add ( 3,50-3,42)/3,42*37 = 0,86 more worker
This worker ( Mr. Capurro Michele ) will be employed from the 5th of September.

## Poles
Poles assembling
Situation at 31/5/05
Equivalent CM done | Equivalent CM to be produced | End of activity | Remaining working weeks | Minimum production rate required (CM/week) | Workers
216 | 200 | 2006-08-14 | 58 | 3.45 | 6
Situation at 31/8/05
Equivalent CM done | Equivalent CM to be produced | End of activity | Remaining working weeks | Minimum production rate required (CM/week) | Workers
249 | 167 | 2006-07-31 | 47 | 3.5532 | 6
As in the months of May, June and July the average production rate was 3,50 no other workers are required

## Collaring
Collaring
Situation at 31/5/05
Equivalent CM done | Equivalent CM to be produced | End of activity | Remaining working weeks | Minimum production rate required (CM/week) | Workers
207 | 209 | 2006-08-31 | 60 | 3.48 | 19
Situation at 31/8/05
Equivalent CM done | Equivalent CM to be produced | End of activity | Remaining working weeks | Minimum production rate (CM/week) | Workers
240 | 176 | 2006-08-31 | 48 | 3.6667 | 19
As in the months of May, June and July the average production rate was 3,33 in order to be able to reach and maintain 3,67 it seems that we need to add ( 3,67-3,33)/3,33*19 = 1,9 more workers
In June the collaring press was stopped for 2,5 weeks and even if we continued to prepare the collared coils we were not able to complete and test them . Then no workers will be add because we are confident to be able to reach the required production rate with the people already employed.

## CM compl.
Cold mass ready for shipping
Situation at 31/5/05
Equivalent CM done | Equivalent CM to be produced | End of activity | Remaining working weeks | Minimum production rate required (CM/week) | Workers
180 | 236 | 2006-09-30 | 64 | 3.68 | 14
Situation at 31/8/05
Equivalent CM done | Equivalent CM to be produced | End of activity | Remaining working weeks | Minimum production rate required (CM/week) | Workers
209 | 207 | 2006-09-30 | 52 | 3.9808 | 14 +2
As in the months of May, June and July the average production rate was 2,75 in order to be able to reach and maintain 3,98 we need to add ( 3,98-2,75)/2,75*14 = 6,26 more workers.
Taking account that the low production rate in these three months was due also to the training of two new people for laser ( Mr. Pedemonte and Vigo F.) and to some troubles with laser trackers we decided to add only 4 workers : Mr. Pasotti and Vasta already employed from August and Mr. Marroni Stefano and Mr. Geirola from the 5th of September.

## Quality
Quality assurance
In the last months we received more complains from Cern about the low efficiency of our quality assurance group.
We would like to remind that anyway this low efficiency had no impact on the production quality and on the cold masses shipping .
We agree with Cern that this group was underdimensioned and then in september Mr. Bergamini will help our responsible dr. Terzi .
Mr. Bergamini has more than 10 years of experience in quality control and quality assurance in an electrical company.