## Sheet1
Arrival of Magnets |  |  | H. Hayes |  | 2026-07-29
| January | 2007
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Monday | 2007-01-01
Tuesday | 2007-01-02
Wed. | 2007-01-03
Thur. | 2007-01-04
Friday | 2007-01-05
Monday | 2007-01-08 |  |  |  | CERN Opens
Tuesday | 2007-01-09 |  | Ansaldo 2423
Wed. | 2007-01-10
Thur. | 2007-01-11 |  | Ansaldo 2424
Friday | 2007-01-12
Monday | 2007-01-15 |  | Ansaldo 2425
Tuesday | 2007-01-16
Wed. | 2007-01-17 |  | Ansaldo 2598 |  | Ansaldo 2598 returned to CERN
Thur. | 2007-01-18
Friday | 2007-01-19
Monday | 2007-01-22 |  | Ansaldo 2427
Tuesday | 2007-01-23
Wed. | 2007-01-24 |  | Ansaldo 2426
Thur. | 2007-01-25
Friday | 2007-01-26
Monday | 2007-01-29 |  | Ansaldo 2433
Tuesday | 2007-01-30
Wed. | 2007-01-31 |  | Ansaldo 2428 |  |  | Remaining | 23
Noell 3001 Unusable |  |  |  |  | Noell = 416 CM Arrivals on 24/11/2005
Alstom 1005 Destroyed |  |  |  |  | Alstom = 415 CM Arrivals on 08/11/2006
Alstom 1001, 1002 Unusable
Ansaldo 2001 Unusable |  |  |  |  | Ansaldo = 424 CM Arrivals on 31/01/2007
|  | 0 | 8 | 0 | 8 | 8 | 1255
January | 2007 | Alstom | Ansaldo | Noell |  | 2007 | Gr. Total
| February | 2007
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Thur. | 2006-02-01
Friday | 2006-02-02
Monday | 2006-02-05
Tuesday | 2006-02-06 |  | Ansaldo 2432
Wed. | 2006-02-07
Thur. | 2006-02-08 |  | Ansaldo 2551 |  | Ansaldo 2551 returned to CERN
Friday | 2006-02-09
Monday | 2006-02-12 |  | Ansaldo 2434
Tuesday | 2006-02-13
Wed. | 2006-02-14 |  | Ansaldo 2438
Thur. | 2006-02-15
Friday | 2006-02-16
Monday | 2006-02-19
Tuesday | 2006-02-20 |  | Ansaldo 2439
Wed. | 2006-02-21
Thur. | 2006-02-22 |  | Ansaldo 2429
Friday | 2006-02-23
Monday | 2006-02-26 |  | Ansaldo 2421 |  |  | Remaining | 16
Tuesday | 2006-02-27
Wed. | 2006-02-28
Noell 3001 Unusable |  |  |  |  | Noell = 416 CM Arrivals on 24/11/2005
Alstom 1005 Destroyed |  |  |  |  | Alstom = 415 CM Arrivals on 08/11/2006
Alstom 1001, 1002 Unusable
Ansaldo 2001 Unusable |  |  |  |  | Ansaldo = 431 CM Arrivals on 26/02/2007
|  | 0 | 7 | 0 | 7 | 15 | 1262
February | 2007 | Alstom | Ansaldo | Noell |  | 2007 | Gr. Total
| March | 2007
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Thur. | 2006-03-01
Friday | 2006-03-02
Monday | 2006-03-05
Tuesday | 2006-03-06 |  | Ansaldo 2440
Wed. | 2006-03-07
Thur. | 2006-03-08
Friday | 2006-03-09 |  | Ansaldo 2431
Monday | 2006-03-12
Tuesday | 2006-03-13
Wed. | 2006-03-14 |  | Ansaldo 2441
Thur. | 2006-03-15
Friday | 2006-03-16
Monday | 2006-03-19 |  | Ansaldo 2442
Tuesday | 2006-03-20
Wed. | 2006-03-21 |  | Ansaldo 2435
Thur. | 2006-03-22
Friday | 2006-03-23
Monday | 2006-03-26 |  | Ansaldo 2436
Tuesday | 2006-03-27
Wed. | 2006-03-28 |  | Ansaldo 2430 |  |  | Remaining | 9
Thur. | 2006-03-29
Friday | 2006-03-30
Noell 3001 Unusable |  |  |  |  | Noell = 416 CM Arrivals on 24/11/2005
Alstom 1005 Destroyed |  |  |  |  | Alstom = 415 CM Arrivals on 08/11/2006
Alstom 1001, 1002 Unusable
Ansaldo 2001 Unusable |  |  |  |  | Ansaldo = 438 CM Arrivals on 28/03/2007
|  | 0 | 7 | 0 | 7 | 22 | 1269
March | 2007 | Alstom | Ansaldo | Noell |  | 2007 | Gr. Total
| April | 2007
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Monday | 2006-04-02
Tuesday | 2006-04-03
Wed. | 2006-04-04 |  | Ansaldo 2437
Thur. | 2006-04-05
Friday | 2006-04-06
Monday | 2006-04-09
Tuesday | 2006-04-10 |  | Ansaldo 2443
Wed. | 2006-04-11
Thur. | 2006-04-12
Friday | 2006-04-13
Monday | 2006-04-16
Tuesday | 2006-04-17 |  | Ansaldo 2444
Wed. | 2006-04-18
Thur. | 2006-04-19 |  | Ansaldo 2739 |  | Ansaldo 2739 returned to CERN
Friday | 2006-04-20
Monday | 2006-04-23
Tuesday | 2006-04-24 |  | Ansaldo 2445 |  |  | Remaining | 4
Wed. | 2006-04-25
Thur. | 2006-04-26
Friday | 2006-04-27
Monday | 2006-04-30
Noell 3001 Unusable |  |  |  |  | Noell = 416 CM Arrivals on 24/11/2005
Alstom 1005 Destroyed |  |  |  |  | Alstom = 415 CM Arrivals on 08/11/2006
Alstom 1001, 1002 Unusable
Ansaldo 2001 Unusable |  |  |  |  | Ansaldo = 443 CM Arrivals on 24/04/2007
|  | 0 | 5 | 0 | 5 | 27 | 1274
April | 2007 | Alstom | Ansaldo | Noell |  | 2006 | Gr. Total
| May | 2006
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Tuesday | 2006-05-01 |  |  |  | CERN Closed
Wed. | 2006-05-02 |  |  |  | Scheduled
Thur. | 2006-05-03
Friday | 2006-05-04
Monday | 2006-05-07
Tuesday | 2006-05-08
Wed. | 2006-05-09
Thur. | 2006-05-10
Friday | 2006-05-11
Monday | 2006-05-14
Tuesday | 2006-05-15
Wed. | 2006-05-16
Thur. | 2006-05-17
Friday | 2006-05-18
Monday | 2006-05-21
Tuesday | 2006-05-22
Wed. | 2006-05-23
Thur. | 2006-05-24
Friday | 2006-05-25
Monday | 2006-05-28
Tuesday | 2006-05-29
Wed. | 2006-05-30
Thur. | 2006-05-31
Noell=415 CM Arrivals
|  | 0 | 0 | 0 | 0 | 27 | 979
Noell 3001 Unusable |  |  |  |  | Noell = 416 CM Arrivals on 24/11/2005
Alstom 1005 Destroyed |  |  |  |  | Alstom = 415 CM Arrivals on 08/11/2006
Alstom 1001, 1002 Unusable
Ansaldo 2001 Unusable |  |  |  |  | Ansaldo = 443 CM Arrivals on 24/04/2007
May | 2006 | Alstom | Ansaldo | Noell |  | 2006 | Gr. Total
| June | 2006
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Thur. | 2006-06-01 | Alstom 1332
Friday | 2006-06-02 | Alstom 1358 | Ansaldo 2335
Friday | 2006-06-02 |  | Ansaldo 2343
Monday | 2006-06-05
Tuesday | 2006-06-06
Wed. | 2006-06-07 | Alstom 1359 | Ansaldo 2337
Wed. | 2006-06-07 |  | Ansaldo 2345
Thur. | 2006-06-08 | Alstom 1352
Friday | 2006-06-09 | Alstom 1395 | Ansaldo 2344
Friday | 2006-06-09 |  | Ansaldo 2346
Monday | 2006-06-12
Tuesday | 2006-06-13 | Alstom 1277 | Ansaldo 2348
Wed. | 2006-06-14 | Alstom 1360
Thur. | 2006-06-15 | Alstom 1315 | Ansaldo 2324
Friday | 2006-06-16 | Alstom 1356 | Ansaldo 2347
Monday | 2006-06-19
Tuesday | 2006-06-20 | Alstom 1362
Wed. | 2006-06-21 |  | Ansaldo 2358
Thur. | 2006-06-22 | Alstom 1396 | Ansaldo 2356
Friday | 2006-06-23 | Alstom 1397
Monday | 2006-06-26 |  | Ansaldo 2316
Monday | 2006-06-26 |  | Ansaldo 2355
Tuesday | 2006-06-27 | Alstom 1349
Wed. | 2006-06-28 | Alstom 1398
Thur. | 2006-06-29 | Alstom 1364 | Ansaldo 2353
Friday | 2006-06-30 |  | Ansaldo 2354 |  |  | Remaining | 104
Noell=415 CM Arrivals
|  | 15 | 15 | 0 | 30 | 57 | 1009
June | 2006 | Alstom | Ansaldo | Noell |  | 2006 | Gr. Total
| July | 2006
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Monday | 2006-07-03
Tuesday | 2006-07-04 | Alstom 1326 | Ansaldo 2351
Wed. | 2006-07-05
Thur. | 2006-07-06 | Alstom 1363 | Ansaldo 2349
Friday | 2006-07-07 |  | Ansaldo 2352
Monday | 2006-07-10 | Alstom 1399 | Ansaldo 2338
Tuesday | 2006-07-11 | Alstom 1367 | Ansaldo 2350
Wed. | 2006-07-12 |  | Ansaldo 2361
Thur. | 2006-07-13 | Alstom 1406 | Ansaldo 2364
Thur. | 2006-07-13 | Alstom 1404
Friday | 2006-07-14
Monday | 2006-07-17
Tuesday | 2006-07-18 | Alstom 1392 | Ansaldo 2365
Wed. | 2006-07-19 | Alstom 1365 | Ansaldo 2336
Thur. | 2006-07-20 |  | Ansaldo 2362
Friday | 2006-07-21 | Alstom 1368 | Ansaldo 2366
Monday | 2006-07-24 | Alstom 1401
Tuesday | 2006-07-25 |  | Ansaldo 2333
Wed. | 2006-07-26 |  | Ansaldo 2360
Thur. | 2006-07-27 |  |  |  | Ansaldo 2368 to be returned for repairs
Friday | 2006-07-28 |  | Ansaldo 2369 |  |  | Remaining | 80
Monday | 2006-07-31
Noell=415 CM Arrivals
|  | 10 | 14 | 0 | 24 | 81 | 1033
July | 2006 | Alstom | Ansaldo | Noell |  | 2006 | Gr. Total
| August | 2006
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Tuesday | 2006-08-01
Wed. | 2006-08-02
Thur. | 2006-08-03 |  | Ansaldo 2359
Thur. | 2006-08-03 |  | Ansaldo 2370
Friday | 2006-08-04
Monday | 2006-08-07 |  | Ansaldo 2367
Monday | 2006-08-07 |  | Ansaldo 2371
Tuesday | 2006-08-08
Wed. | 2006-08-09 |  | Ansaldo 2373
Thur. | 2006-08-10
Friday | 2006-08-11
Monday | 2006-08-14
Tuesday | 2006-08-15
Wed. | 2006-08-16
Thur. | 2006-08-17
Friday | 2006-08-18 | Alstom 1370
Monday | 2006-08-21
Tuesday | 2006-08-22 |  | Ansaldo 2376
Wed. | 2006-08-23 | Alstom 1403
Thur. | 2006-08-24 |  | Ansaldo 2377
Friday | 2006-08-25 | Alstom 1369
Monday | 2006-08-28
Tuesday | 2006-08-29 |  | Ansaldo 2379
Wed. | 2006-08-30 | Alstom 1400 |  |  |  | Remaining | 68
Thur. | 2006-08-31
Noell=415 CM Arrivals
|  | 4 | 8 | 0 | 12 | 93 | 1045
August | 2006 | Alstom | Ansaldo | Noell |  | 2006 | Gr. Total
| September | 2006
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Friday | 2006-09-01 | Alstom 1374
Monday | 2006-09-04
Tuesday | 2006-09-05 | Alstom 1372 | Ansaldo 2378
Wed. | 2006-09-06 |  | Ansaldo 2383
Thur. | 2006-09-07 | Alstom 1375
Friday | 2006-09-08 | Alstom 1377 | Ansaldo 2375
Friday | 2006-09-08 |  | Ansaldo 2381
Monday | 2006-09-11
Tuesday | 2006-09-12 | Alstom 1379 | Ansaldo 2384
Wed. | 2006-09-13 |  | Ansaldo 2380
Thur. | 2006-09-14 |  | Ansaldo 2385
Friday | 2006-09-15 | Alstom 1376 | Ansaldo 2357
Monday | 2006-09-18 | Alstom 1378
Tuesday | 2006-09-19 | Alstom 1366 | Ansaldo 2386
Wed. | 2006-09-20 |  | Ansaldo 2388
Thur. | 2006-09-21 | Alstom 1371 | Ansaldo 2389
Friday | 2006-09-22 | Alstom 1373
Friday | 2006-09-22
Monday | 2006-09-25 | Alstom 1381 | Ansaldo 2374
Tuesday | 2006-09-26
Wed. | 2006-09-27 |  | Ansaldo 2387
Wed. | 2006-09-27 |  | Ansaldo 2390
Thur. | 2006-09-28 | Alstom 1382
Friday | 2006-09-29 | Alstom 1001 | Ansaldo 2001 | Noell 3001 | Alstom 1001,1002; Ansaldo 2001; Noell 3001 OK
Friday | 2006-09-29 | Alstom 1002 |  |  | Alstom 1001,1002; Ansaldo 2001; Noell 3001 OK
Friday | 2006-09-29 | Alstom 1380 | Ansaldo 2391 |  |  | Remaining | 36
Noell=416 CM Arrivals
|  | 15 | 16 | 1 | 32 | 125 | 1077
September | 2006 | Alstom | Ansaldo | Noell |  | 2006 | Gr. Total
| October | 2006
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Monday | 2006-10-02 |  | Ansaldo 2393
Tuesday | 2006-10-03 | Alstom 1407 | Ansaldo 2392
Wed. | 2006-10-04 |  | Ansaldo 2394
Thur. | 2006-10-05 | Alstom 1409
Friday | 2006-10-06 | Alstom 1408 | Ansaldo 2396
Friday | 2006-10-06
Monday | 2006-10-09 | Alstom 1405
Tuesday | 2006-10-10 |  | Ansaldo 2382
Wed. | 2006-10-11 | Alstom 1410 | Ansaldo 2372
Thur. | 2006-10-12 | Alstom 1411 | Ansaldo 2342
Friday | 2006-10-13 |  | Ansaldo 2325
Monday | 2006-10-16 |  | Ansaldo 2397
Tuesday | 2006-10-17 | Alstom 1412 | Ansaldo 2395
Wed. | 2006-10-18 |  | Ansaldo 2270
Thur. | 2006-10-19 | Alstom 1413
Friday | 2006-10-20 | Alstom 1402 | Ansaldo 2398
Monday | 2006-10-23 |  | Ansaldo 2399
Tuesday | 2006-10-24 | Alstom 1414 | Ansaldo 2405
Wed. | 2006-10-25 |  | Ansaldo 2400
Thur. | 2006-10-26 | Alstom 1415
Friday | 2006-10-27 |  | Ansaldo 2401
Monday | 2006-10-30 | Alstom 1361 | Ansaldo 2403 |  |  | Remaining | 7
Tuesday | 2006-10-31
Noell=416 CM Arrivals
|  | 12 | 17 | 0 | 29 | 154 | 1106
October | 2006 | Alstom | Ansaldo | Noell |  | 2006 | Gr. Total
| November | 2006
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Wed. | 2006-11-01
Thur. | 2006-11-02
Friday | 2006-11-03 |  | Ansaldo 2406
Monday | 2006-11-06 |  | Ansaldo 2404
Tuesday | 2006-11-07 |  | Ansaldo 2407
Wed. | 2006-11-08 | Alstom 1416 | Ansaldo 2408
Thur. | 2006-11-09
Friday | 2006-11-10 |  | Ansaldo 2410
Monday | 2006-11-13
Tuesday | 2006-11-14 |  | Ansaldo 2409 |  | 1232 DipolesDelivered | Remaining | 0
Tuesday | 2006-11-14 |  | Ansaldo 2363 |  | 1278 DipolesToDeliver | Remaining | 45
Wed. | 2006-11-15
Thur. | 2006-11-16 |  | Ansaldo 2411
Friday | 2006-11-17 |  | Ansaldo 2402
Monday | 2006-11-20
Tuesday | 2006-11-21 |  | Ansaldo 2412
Wed. | 2006-11-22 |  | Ansaldo 2414
Wed. | 2006-11-22 |  | Ansaldo 2413
Thur. | 2006-11-23
Friday | 2006-11-24 |  | Ansaldo 2415
Monday | 2006-11-27 |  | Ansaldo 2416 |  |  | Remaining | 38
Tuesday | 2006-11-28
Wed. | 2006-11-29
Thur. | 2006-11-30 |  | Ansaldo 2417 |  | Scheduled
Noell 3001 Unusable |  |  |  |  | Noell = 416 CM Arrivals on 24/11/2005
Alstom 1005 Destroyed |  |  |  |  | Alstom = 415 CM Arrivals on 08/11/2006
Alstom 1001, 1002 Unusable
Ansaldo 2001 Unusable |  |  |  |  | Ansaldo = 409 CM Arrivals on 27/11/2006
|  | 1 | 15 | 0 | 16 | 170 | 1122
November | 2006 | Alstom | Ansaldo | Noell |  | 2006 | Gr. Total
| December | 2006
| Arrival Date | Alstom | Ansaldo | Noell | Comments
Friday | 2006-12-01
Monday | 2006-12-04
Tuesday | 2006-12-05 |  |  |  | Scheduled
Wed. | 2006-12-06
Thur. | 2006-12-07
Friday | 2006-12-08
Monday | 2006-12-11
Tuesday | 2006-12-12
Wed. | 2006-12-13
Thur. | 2006-12-14
Friday | 2006-12-15
Monday | 2006-12-18
Tuesday | 2006-12-19
Wed. | 2006-12-20
Thur. | 2006-12-21
Friday | 2006-12-22 |  |  |  | CERN closes tomorrow
Monday | 2006-12-25
Tuesday | 2006-12-26
Wed. | 2006-12-27
Thur. | 2006-12-28
Friday | 2006-12-29
Noell=416 CM Arrivals
|  | 0 | 0 | 0 | 0 | 170 | 1122
December | 2006 | Alstom | Ansaldo | Noell |  | 2006 | Gr. Total