## Planning
F | [24 empty] | date: 07.10.2003 / 486
2003
| 40/03 |  | 41/03 |  | 42/03 |  | 43/03 |  | 44/03 |  | 45/03 |  | 46/03 |  | 47/03 |  | 48/03 |  | 49/03 |  | 50/03 |  | 51/03 |  | 52/03
ALSTOM |  |  | U0731 | L0531 | U0600 | U0830 | U0332 | U0708 |  |  | L0544 | U0716 |  |  | L0560 | U0803 |  |  | L0646 | U0679 |  |  | L0584 | U0617
|  |  | L0548 | L0566 | U0670 | U0676 | L0528 | U0609 |  |  | L0555 | U0706 |  |  | L0568 | U0783 |  |  | L0648 | U0751 |  |  | L0550 | U0628
|  |  | L0567 | L0554 | L0547 | U0623 | L0529 | U0627 |  |  | L0557 | U0780 |  |  | U0639 | U0753 |  |  | L0571 | L0607 |  |  | L0643 | U0674
|  |  | U0583 | L0558 | U0582 | U0749 | L0572 | L0619 |  |  | U0642 | U0770 |  |  | U0649 | U0742 |  |  | L0647 | U0680 |  |  | L0645 | U0762
NOELL | U0405 | L0478 | U0306 | L0784 | L0588 | U0704 | L0632 | U0759 | U0339 | L0858 | U0490 | L0631 | U0748 | L0788 | L0542 | U0711 | L0587 | U0717 | L0795 | U0741 | L0824 | U0763 | L0857 | U0729
| U0472 | L0517 | U0310 | L0816 | U0700 | L0565 | L0612 | U0699 | U0720 | L0820 | U0519 | L0586 | U0761 | L0516 | L0543 | U0697 | L0573 | U0701 | U0410 | L0883 | L0898 | U0802 | L0863 | U0807
| U0473 | L0474 | U0312 | L0825 | L0635 | U0683 | L0615 | U0765 | U0685 | L0790 | U0521 | L0580 | U0775 | L0523 | L0524 | U0738 | L0652 | U0771 | U0412 | L0896 | L0868 | U0774 | L0823 | U0721
| U0492 | L0523 | U0327 | L0819 | L0590 | U0813 | L0786 | U0768 | U0713 | L0589 | U0744 | L0602 | U0709 | L0549 | L0541 | U0719 | L0513 | U0747 | U0226 | L0882 | L0874 | U0815 | L0891 | U0698
ANSALDO | U0277 | U0285 |  |  | L0533 | U0691 |  |  | L0551 | U0599 |  |  | L0561 | L0614 |  |  | L0575 | L0611 |  |  | U0605 | U0810 | U0633 | U0690
| U0752 | L0658 |  |  | L0545 | U0727 |  |  | L0552 | U0777 |  |  | L0562 | L0620 |  |  | L0576 | L0621 |  |  | L0610 | U0814 | L0636 | U0682
| L0337 | L0340 |  |  | L0546 | U0663 |  |  | L0553 | U0714 |  |  | L0564 | U0712 |  |  | L0577 | U0730 |  |  | L0650 | U0689 | L0526 | L0603
| L0335 | L0352 |  |  | L0601 | U0666 |  |  | U0400 | U0402 |  |  | L0569 | L0618 |  |  | U0585 | U0726 |  |  | L0532 | U0664 | L0527 | U0604
2004
| 1/04 |  | 2/04 |  | 3/04 |  | 4/04 |  | 5/04 |  | 6/04 |  | 7/04 |  | 8/04 |  | 9/04 |  | 10/04 |  | 11/04 |  | 12/04 |  | 13/04
ALSTOM |  |  |  |  | U0671 | U0838 |  |  | U0769 | U0732 |  |  | U0675 | U0653 |  |  | U0750 | U0725 | [6 empty] | L0871 | L0787
[5 empty] | U0672 | U0755 |  |  | U0834 | U0707 |  |  | U0718 | U0665 |  |  | U0678 | U0661 | [6 empty] | U0629 | L0860
[5 empty] | U0684 | U0767 |  |  | U0735 | U0696 |  |  | U0760 | U0705 |  |  | U0806 | L0869 | [6 empty] | U0853 | L0862
[5 empty] | U0686 | U0662 |  |  | U0677 | U0779 |  |  | U0688 | U0693 |  |  | L0901 | L0791 | [6 empty] | U0842 | L0912
NOELL |  |  |  |  | U0854 | L0878 | U0736 | L0799 | U0703 | L0710 | U0434 | L0881 | U0443 | L0925 |  |  | U0808 | L0940 |  |  | U0955 | L0963 | U0832 | L0888 | U0728 | L0889
[5 empty] | U0758 | L0897 | U0746 | L0797 | U0952 | L0536 | U0437 | L0913 | U0444 | L0945 |  |  | U0733 | L0920 |  |  | U0910 | L0895 | U0954 | L0900 | U0960 | L0918
[5 empty] | U0754 | L0866 | U0766 | L0800 | U0953 | L0540 | U0438 | L0927 | U0446 | L0962 |  |  | U0737 | L0899 |  |  | U0958 | L0879 | U0805 | L0885 | U0330 | L0971
[5 empty] | U0667 | L0794 | U0833 | L0864 | U0433 | L0876 | U0441 | L0926 | U0447 | L0949 |  |  | U0764 | L0922 |  |  | U0959 | L0950 | U0831 | L0877 | U0451 | L0974
[5 empty] | U0734 | L0822
[5 empty] | U0702 | L0657
[5 empty] | U0740 | L0892
[5 empty] | U0836 | L0865
ANSALDO |  |  | U0743 | L0695 |  |  | U0715 | L0581 | [10 empty] | U0668 | L0659 |  |  | U0961 | L0537
|  |  | U0669 | L0817 |  |  | U0811 | L0872 | [10 empty] | U0681 | L0579 |  |  | U0924 | L0538
|  |  | U0673 | L0660 |  |  | U0812 | L0861 | [10 empty] | U0835 | L0654 |  |  | U0692 | L0785
|  |  | U0687 | L0776 |  |  | U0739 | U0745 | [10 empty] | U0957 | L0796 |  |  | U0722 | L0793
2004
| 14/04 |  | 15/04 |  | 16/04 |  | 17/04 |  | 18/04 |  | 19/04 |  | 20/04 |  | 21/04 |  | 22/04 |  | 23/04 |  | 24/04 |  | 25/04 |  | 26/04
ALSTOM |  |  | U0837 | L0867 |  |  | U0999 | L0655 | U0966 | L0930 | U0956 | L0637 |  |  | U0996 | L0936 | U1003 | L0847 | U1011 | L0855 |  |  |  |  | U1019 | L0905
|  |  | U0983 | U0932 |  |  | U0975 | L0640 | U1000 | L0778 | U0982 | L0694 |  |  | U0997 | L0856 | U1007 | L0616 | U1012 | L0827 |  |  |  |  | U1020 | L0781
|  |  | U1005 | U0840 |  |  | U0985 | L0904 | U0976 | L0907 | U0984 | L0914 |  |  | U0998 | L0934 | U1009 | L0798 | U1014 | L0884 |  |  |  |  | U1023 | L0951
|  |  | U0978 | L0656 |  |  | U0994 | L0909 | U0977 | L0772 | U0988 | L0818 |  |  | U1002 | L0848 | U1010 | L0944 | U1017 | L0850 |  |  |  |  | U1024 | L0782
NOELL |  |  | U0990 | L0845 | U0992 | L0625 | U0986 | L0634 |  |  | U0448 | L0939 | U0453 | L1063 | U0460 | L1072 | U0465 | L1059 | U0484 | L1076 | U0488 | L1078 | U1194 | L1100 | U0508 | L1099
|  |  | U0987 | L0789 | U0452 | L0981 | U1008 | L0887 |  |  | U0449 | L0902 | U0456 | L1062 | U0462 | L1057 | U0466 | L1083 | U0485 | L1075 | U0491 | L1091 | U0505 | L1302 | U0509 | L1093
|  |  | U0450 | L0973 | U0941 | L1004 | U1018 | L0880 |  |  | U0756 | L0928 | U0458 | L1071 | U0463 | L1068 | U0470 | L1064 | U0486 | L1079 | U0494 | L1077 | U0506 | L1108 | U0965 | L1069
|  |  | U0903 | L0979 | U0921 | L0967 | U0324 | L1052 |  |  | U0757 | L0935 | U0459 | L1054 | U0464 | L1070 | U0482 | L1080 | U0487 | L1082 | U0499 | L1102 | U0507 | L1094 | U1026 | L0821
ANSALDO | L0890 | U0839 |  |  | U0968 | L0641 |  |  | U0995 | L0638 |  |  | U0841 | L1040 | U0852 | L1039 | U0931 | L1031 |  |  | U1015 | L0801 |  |  | U1131 | L1056
| L0870 | U0851 |  |  | U0989 | L0723 |  |  | U1001 | L0651 |  |  | U0843 | L1045 | U0894 | L1038 | U0937 | L1036 |  |  | U1029 | L0906 |  |  | U1132 | L1111
| L0875 | U0923 |  |  | U0993 | L0915 |  |  | U1016 | L0630 |  |  | U0849 | L1030 | U0917 | L1048 | U0942 | L1032 |  |  | U1074 | L1035 |  |  | U1133 | L1086
| L0873 | U0809 |  |  | U0991 | L0724 |  |  | U0972 | L0938 |  |  | U0829 | L1041 | U0929 | L1033 | U1006 | L0644 |  |  | U1087 | L1044 |  |  | U1134 | L1112
2004
| 27/04 |  | 28/04 |  | 29/04 |  | 30/04 |  | 31/04 |  | 32/04 |  | 33/04 |  | 34/04 |  | 35/04 |  | 36/04 |  | 37/04 |  | 38/04 |  | 39/04
ALSTOM | U1025 | L0773 |  |  | U0382 | L0948 | U1167 | L0893 |  |  |  |  | U1182 | L0908 |  |  | U1155 | L0919 |  |  | U1164 | L1073 |  |  | U1219 | L1046
| U1027 | L0911 |  |  | U1178 | L0792 | U1153 | L0946 |  |  |  |  | U1161 | L0916 |  |  | U1188 | L1061 |  |  | U1380 | L1328 |  |  | U1220 | L1034
| U1028 | L0844 |  |  | U1176 | L0828 | U1162 | L0969 |  |  |  |  | U1175 | L0933 |  |  | U1200 | L1115 |  |  | U1207 | L1047 |  |  | U1221 | L1053
| U1140 | L0947 |  |  | U1160 | L0846 | U1168 | L1060 |  |  |  |  | U1157 | L0943 |  |  | U1171 | L1116 |  |  | U1216 | L1042 |  |  | U1226 | L1282
NOELL | U1013 | L0980 | U1143 | L1114 | U1180 | L1118 | U1173 | L1051 | U1166 | L1089 | U1149 | L1081 | U1184 | L1050 | U0240 | L0258 | L0245 | L1271 | U1196 | L1269 | U1230 | L1281 | U1244 | L1268 | U1249 | L1288
| U1021 | L0826 | U1147 | L1117 | U1181 | L1110 | U1169 | L1066 | U1199 | L1090 | U1150 | L1107 | U1191 | L1124 | U0248 | L0259 | U1190 | L1120 | U1197 | L1097 | U1235 | L1294 | U1245 | L1279 | U1251 | L1297
| U1022 | L0964 | U1151 | L0970 | U1179 | L1128 | U1170 | L1085 | U1198 | L1101 | U1159 | L1123 | U1177 | L1126 | U1154 | L1129 | U1193 | L1273 | U1205 | L1213 | U1346 | L1360 | U1247 | L1275 | U1253 | L1312
| U1146 | L1125 | U1065 | L1043 | U1183 | L1105 | U1158 | L1088 | U1174 | L1103 | U1172 | L1113 | U1165 | L1106 | U1186 | L1223 | U1195 | L1283 | U1227 | L1278 | U1241 | L0886 | U1248 | L1284 | U1263 | L1290
ANSALDO |  |  | U1135 | L1058 | U1139 | L1098 | U1145 | L1096 | [6 empty] | U0265 | L1215 |  |  | U1187 | L1084 |  |  | U1203 | L1217
|  |  | U1136 | L1092 | U1141 | L1095 | U1148 | L1130 | [6 empty] | U0495 | L1214 |  |  | U1192 | L1276 |  |  | U1204 | L1210
|  |  | U1137 | L1127 | U1142 | L1121 | U1152 | L0804 | [6 empty] | U1156 | L1272 |  |  | U1201 | L1122 |  |  | U1228 | L1225
|  |  | U1138 | L1049 | U1144 | L1067 | U1163 | L1119 | [6 empty] | U1185 | L1211 |  |  | U1202 | L1218 |  |  | U1246 | L1224
2004
| 40/04 |  | 41/04 |  | 42/04 |  | 43/04 |  | 44/04 |  | 45/04 |  | 46/04 |  | 47/04 |  | 48/04 |  | 49/04 |  | 50/04 |  | 51/04 |  | 52/04
ALSTOM |  |  | U1232 | L1295 | U1208 | L1321 | U1353 | L1344 |  |  | U1420 | L1352 | U1458 | L1280 | U1480 | L1393 |  |  | U1489 | L1382 | U1524 | L1343 | U1471 | L1541
|  |  | U1234 | L1287 | U1212 | L1361 | U1381 | L1354 |  |  | U1421 | L1365 | U1459 | L1378 | U1481 | L1551 |  |  | U1491 | L1402 | U1526 | L1055 | U1473 | L1599
|  |  | U1243 | L1285 | U1222 | L1322 | U1383 | L1385 |  |  | U1422 | L1397 | U1466 | L1369 | U1482 | L1410 |  |  | U1492 | L1356 | U1527 | L1401 | U1476 | L1593
|  |  | U1259 | L1296 | U1237 | L1371 | U1404 | L1347 |  |  | U1425 | L1274 | U1468 | L1367 | U1483 | L1364 |  |  | U1494 | L1345 | U1206 | L1562 | U1477 | L1545
NOELL | U0504 | L1306 | U1238 | L1310 | U1255 | L1309 | U1266 | L1317 | U1411 | L1351 | U1416 | L1348 | U1426 | L1319 | U1430 | L1308 | U1435 | L1370 | U1440 | L1387 | U1445 | L1332 | U1449 | L1409
| U1229 | L1314 | U1239 | L1333 | U1257 | L1336 | U1326 | L1313 | U1412 | L1374 | U1419 | L1330 | U1427 | L1303 | U1431 | L1349 | U1437 | L1403 | U1442 | L1400 | U1446 | L1399 | U1461 | L1528
| U1231 | L1337 | U1240 | L1307 | U1258 | L1301 | U1327 | L1340 | U1414 | L1320 | U1423 | L1363 | U1428 | L1304 | U1433 | L1388 | U1438 | L1373 | U1443 | L1396 | U1447 | L1398 | U1463 | L1329
| U1233 | L1305 | U1242 | L1335 | U1260 | L1315 | U1334 | L1299 | U1415 | L1358 | U1424 | L1318 | U1429 | L1368 | U1434 | L1379 | U1439 | L1372 | U1444 | L1390 | U1448 | L1389 | U1465 | L1331
ANSALDO | U1252 | L1291 | U1250 | L1339 | U1265 | L1289 |  |  | U1405 | L1392 |  |  | U1436 | L1375 |  |  | U1470 | L1546 | U1484 | L1407
| U1256 | L1292 | U1254 | L1341 | U1267 | L1338 |  |  | U1413 | L1362 |  |  | U1441 | L1391 |  |  | U1475 | L1408 | U1485 | L1394
| U1261 | L1277 | U1298 | L1300 | U1270 | L1311 |  |  | U1417 | L1377 |  |  | U1452 | L1406 |  |  | U1478 | L1037 | U1486 | L1376
| U1264 | L1293 | U1262 | L1357 | U1286 | L1350 |  |  | U1418 | L1355 |  |  | U1454 | L1395 |  |  | U1479 | L1386 | U1488 | L1366
2005
| 1/05 |  | 2/05 |  | 3/05 |  | 4/05 |  | 5/05 |  | 6/05 |  | 7/05 |  | 8/05 |  | 9/05 |  | 10/05 |  | 11/05 |  | 12/05 |  | 13/05
ALSTOM |  |  | U1487 | L1548 | U1500 | L1607 | U1511 | L1595 |  |  | U1523 | L1534 | U1574 | L1600 | U1698 | L1654 |  |  | U1690 | L1627 | U0134 | L0859 | U1752 | L0362
|  |  | U1490 | L1552 | U1501 | L1606 | U1513 | L1598 |  |  | U1525 | L1662 | U1575 | L1617 | U1711 | L1655 |  |  | U1708 | L1625 | U0153 | L0123 | U1679 | L1596
|  |  | U1498 | L1639 | U1509 | L1564 | U1521 | L1621 |  |  | U1682 | L1638 | U1577 | L1616 | U1673 | L1661 |  |  | U1713 | L1631 | U1731 | L0087 | U1680 | L1576
|  |  | U1499 | L1613 | U1510 | L1660 | U1522 | L1537 |  |  | U1684 | L1622 | U1605 | L1611 | U1676 | L1663 |  |  | U0127 | L1559 | U1737 | L0093 | U1709 | L1591
NOELL |  |  | U1236 | L1533 | U1455 | L1536 | U1467 | L1555 | U1502 | L1582 | U1529 | L1558 | U1565 | L1583 | U1669 | L1635 | U1691 | L1648 | U1704 | L1652 | U1675 | L0386 | U1683 | L1594 | U1668 | L1822
|  |  | U1450 | L1556 | U1456 | L1561 | U1469 | L1580 | U1512 | L1557 | U1531 | L1589 | U1568 | L1571 | U1670 | L1643 | U1697 | L1651 | U1705 | L1632 | U1725 | L0469 | U1721 | L1666 | U1732 | L1636
|  |  | U1451 | L1579 | U1460 | L1554 | U1472 | L1540 | U1517 | L1604 | U1532 | L1603 | U1569 | L1570 | U1677 | L1626 | U1700 | L1629 | U1712 | L1618 | U1735 | L0420 | U1723 | L1649 | U1681 | L1801
|  |  | U1453 | L1550 | U1464 | L1544 | U1474 | L1578 | U1519 | L1572 | U1560 | L1566 | U1573 | L1614 | U1686 | L1634 | U1701 | L1630 | U1506 | L0388 | U1678 | L1615 | U1728 | L1659 | U1693 | L1780
ANSALDO |  |  | U1495 | L1538 | U1432 | L1553 |  |  | U1496 | L1542 | U1508 | L1610 | U1520 | L1641 |  |  | U1590 | L1359 | U1640 | L1645 | U1692 | L1647 |  |  | U1687 | L1597
|  |  | U1497 | L1342 | U1457 | L1543 |  |  | U1504 | L1656 | U1514 | L1609 | U1530 | L1539 |  |  | U1685 | L1658 | U1642 | L1588 | U1702 | L1650 |  |  | U1689 | L1601
|  |  | U1503 | L1547 | U1462 | L1637 |  |  | U1505 | L1602 | U1515 | L1623 | U1567 | L1209 |  |  | U1665 | L1644 | U1671 | L1608 | U1706 | L1620 |  |  | U1699 | L1585
|  |  | U1516 | L1549 | U1493 | L1535 |  |  | U1507 | L1563 | U1518 | L1586 | U1581 | L1628 |  |  | U1667 | L1646 | U1672 | L1592 | U1674 | L1624 |  |  | U1703 | L1657
2005
| 14/05 |  | 15/05 |  | 16/05 |  | 17/05 |  | 18/05 |  | 19/05 |  | 20/05 |  | 21/05 |  | 22/05 |  | 23/05 |  | 24/05 |  | 25/05 |  | 26/05
ALSTOM | U0116 | L1782 | U1718 | L1841 | U1739 | L1653 |  |  | U1756 | L1773 | U1846 | L1848 | U1862 | L0424 |  |  | U1898 | L1852 | U1860 | L1844 | U1887 | L1960 |  |  | U1912 | L1967
| U0150 | L1783 | U1719 | L1811 | U1740 | L1795 |  |  | U1757 | L1774 | U1854 | L1776 | U1863 | L1833 |  |  | U1899 | L0479 | U2047 | L1979 | U1888 | L1956 |  |  | U1913 | L1788
| U0281 | L1814 | U1720 | L1785 | U1741 | L1792 |  |  | U1758 | L1837 | U1855 | L0213 | U1864 | L0364 |  |  | U1900 | L0480 | U1870 | L1973 | U1889 | L1949 |  |  | U1915 | L1969
| U0294 | L1790 | U1722 | L1787 | U1903 | L1793 |  |  | U1759 | L1831 | U1856 | L0385 | U1865 | L0387 |  |  | U1902 | L1823 | U1873 | L1954 | U1890 | L1986 |  |  | U1916 | L1951
NOELL | U1694 | L1797 | U1724 | L1821 | U1743 | L1800 | U1747 | L1664 | U1760 | L1813 | U1832 | L1810 | U1866 | L0422 | U1872 | L1612 | U1688 | L2017 | U1874 | L1985 | U1891 | L1952 | U1901 | L1982 | U1917 | L1939
| U1695 | L1786 | U1726 | L1808 | U1744 | L1818 | U1748 | L1775 | U1761 | L1812 | U1838 | L1807 | U1867 | L1789 | U1876 | L1817 | U1727 | L1824 | U1875 | L1946 | U1892 | L1976 | U1904 | L1978 | U1918 | L1970
| U1696 | L1796 | U1729 | L1840 | U1745 | L1802 | U1749 | L1836 | U1762 | L1804 | U1839 | L1619 | U1868 | L0365 | U1880 | L1850 | U1742 | L1957 | U1877 | L1914 | U1893 | L1950 | U1906 | L1984 | U1919 | L1955
| U1707 | L1772 | U1730 | L1784 | U1746 | L1806 | U1750 | L1771 | U1770 | L1834 | U1842 | L1820 | U1871 | L1835 | U1883 | L1779 | U1763 | L1997 | U1879 | L1926 | U1894 | L1959 | U1907 | L1980 | U1920 | L1981
ANSALDO | U1714 | L1805 | U1905 | L1851 |  |  | U1751 | L1798 | U1777 | L1815 | U1857 | L1794 |  |  | U1885 | L1633 | U1767 | L1828 | U1881 | L1974 |  |  |  |  | U1908 | L1958
| U1715 | L1809 | U1733 | L1778 |  |  | U1753 | L1765 | U1791 | L0203 | U1858 | L0371 |  |  | U1895 | L1803 | U2043 | L1999 | U1882 | L1923 |  |  |  |  | U1909 | L1948
| U1716 | L1769 | U1734 | L1799 |  |  | U1754 | L1845 | U1826 | L0468 | U1859 | L1849 |  |  | U1896 | L1829 | U1827 | L1924 | U1884 | L1975 |  |  |  |  | U1910 | L1943
| U1717 | L1768 | U1736 | L1847 |  |  | U1755 | L1781 | U1830 | L1766 | U1861 | L1816 |  |  | U1897 | L1764 | U1853 | L1925 | U1886 | L1941 |  |  |  |  | U1911 | L1940
2005
| 27/05 |  | 28/05 |  | 29/05 |  | 30/05 |  | 31/05 |  | 32/05 |  | 33/05 |  | 34/05 |  | 35/05 |  | 36/05 |  | 37/05 |  | 38/05 |  | 39/05
ALSTOM | U1930 | L2014 | [8 empty] | U2030 | L1995 |  |  | U2035 | L1987 | U2048 | L2147 | U2074 | L2009 |  |  | U2062 | L2157 | U2073 | L2177
| U1931 | L2018 | [8 empty] | U2034 | L2007 |  |  | U2036 | L1977 | U2049 | L2077 | U2087 | L2020 |  |  | U2066 | L2183 | U2075 | L2151
| U1932 | L2006 | [8 empty] | U2037 | L1990 |  |  | U2038 | L2004 | U2054 | L2154 | U2089 | L2153 |  |  | U2067 | L2185 | U2080 | L2132
| U1933 | L1944 | [8 empty] | U2039 | L1993 |  |  | U2040 | L1934 | U2060 | L2072 | U2093 | L1945 |  |  | U2069 | L2200 | U2081 | L2169
NOELL | U1935 | L1963 | U2063 | L1929 | U2022 | L2019 |  |  |  |  | U2347 | L2296 | U2355 | L2249
| U1936 | L1988 | U2094 | L2135 | U2023 | L2012 |  |  |  |  | U2348 | L2247 | U2356 | L2286
| U1937 | L1947 | U1966 | L2143 | U2024 | L2015 |  |  |  |  | U2349 | L2269 | U2358 | L2263
| U1964 | L1968 | U2021 | L1998 | U2027 | L2005 |  |  |  |  | U2350 | L2285 | U2359 | L2281
[5 empty] | U2056 | L2164 | [6 empty] | U2341 | L2244
ANSALDO | U1921 | L1992 |  |  | U1965 | L2016 | U2028 | L1983 | U2041 | L2000 |  |  |  |  | U2064 | L1994 | U0475 | L0514 |  |  | U0512 | L0510 | U2057 | L2155 | U2082 | L2195
| U1922 | L1961 |  |  | U2010 | L1962 | U2031 | L1991 | U2042 | L2001 |  |  |  |  | U2068 | L2011 | U0483 | L0518 |  |  | U1938 | L2167 | U2058 | L2205 | U2083 | L2184
| U1927 | L1989 |  |  | U2013 | L1972 | U2032 | L2003 | U2045 | L2002 |  |  |  |  | U2071 | L2136 | U0496 | L0476 |  |  | U2026 | L2140 | U2059 | L2137 | U2085 | L2131
| U1928 | L1953 |  |  | U2029 | L2008 | U2033 | L1971 | U2046 | L1996 |  |  |  |  | U0399 | L0211 | U2070 | L2168 |  |  | U2044 | L2182 | U2061 | L2156 | U2086 | L2191
2005
| 40/05 |  | 41/05 |  | 42/05 |  | 43/05 |  | 44/05 |  | 45/05 |  | 46/05 |  | 47/05 |  | 48/05 |  | 49/05 |  | 50/05 |  | 51/05 |  | 52/05
ALSTOM | U2088 | L2130 |  |  | U2100 | L2181 | U2111 | L2176 | U2122 | L2138 |  |  | U1825 | L2162 | U2053 | L2238 | U2104 | L2213 |  |  | U2025 | L2260 | U2310 | L2242
| U2090 | L2203 |  |  | U2101 | L2170 | U2113 | L2161 | U2123 | L2175 |  |  | U2050 | L2214 | U2055 | L2186 | U2106 | L2189 |  |  | U2303 | L2270 | U2311 | L2258
| U2091 | L2152 |  |  | U2102 | L2150 | U2114 | L2207 | U2124 | L2171 |  |  | U2051 | L2188 | U2065 | L2240 | U2108 | L2165 |  |  | U2305 | L2272 | U2312 | L2252
| U2092 | L2142 |  |  | U2103 | L2159 | U2115 | L2179 | U2127 | L2194 |  |  | U2052 | L2241 | U2076 | L2199 | U2112 | L2198 |  |  | U2309 | L2224 | U2317 | L2283
ANSALDO |  |  | U2095 | L2145 | U2105 | L2173 | U2116 | L2146 |  |  | U2129 | L2178 | U2128 | L2215 |  |  |  |  | U2118 | L2208 | U2134 | L2210 | U2313 | L2232
|  |  | U2096 | L2148 | U2107 | L2204 | U2117 | L2144 |  |  | U2133 | L2174 | U2079 | L2196 |  |  |  |  | U2121 | L2190 | U2306 | L2257 | U2314 | L2227
|  |  | U2098 | L2163 | U2109 | L2209 | U2119 | L2139 |  |  | U2192 | L2166 | U2084 | L2158 |  |  |  |  | U2125 | L2239 | U2307 | L2271 | U2315 | L2197
|  |  | U2099 | L2141 | U2110 | L2172 | U2120 | L2160 |  |  | U2180 | L2187 | U2097 | L2223 |  |  |  |  | U2126 | L2193 | U2308 | L2280 | U2316 | L2219
2006
| 01/06 |  | 02/06 |  | 03/06 |  | 04/06 |  | 05/06 |  | 06/06 |  | 07/06 |  | 08/06 |  | 09/06 |  | 10/06 |  | 11/06 |  | 12/06 |  | 13/06
ALSTOM |  |  | U2318 | L2278 | U2326 | L2220 | U2338 | L2282 |  |  | U2333 | L2279 | U2363 | L2266 | U2371 | L2299 |  |  | U2380 | L2255 | U2388 | L2275 | U2412 | L2276
|  |  | U2319 | L2216 | U2327 | L2202 | U2339 | L2262 |  |  | U2336 | L2273 | U2364 | L2522 | U2372 | L2497 |  |  | U2381 | L2504 | U2391 | L2234 | U2408 | L2259
|  |  | U2320 | L2245 | U2328 | L2222 | U2331 | L2233 |  |  | U2340 | L2206 | U2365 | L2298 | U2373 | L2267 |  |  | U2382 | L2300 | U2392 | L2302 | U2409 | L2261
|  |  | U2325 | L2217 | U2337 | L2277 | U2332 | L2291 |  |  | U2357 | L2486 | U2366 | L2287 | U2375 | L2297 |  |  | U2383 | L2226 | U2395 | L2292 | U2406 | L2533
ANSALDO |  |  | U2321 | L2225 | U2329 | L2231 | U2342 | L2253 |  |  | U2351 | L2243 | U2346 | L2301 | U2368 | L2284 |  |  | U2377 | L2268 | U2385 | L2230 | U2398 | L2495
|  |  | U2322 | L2265 | U2330 | L2251 | U2343 | L2236 |  |  | U2352 | L0520 | U2360 | L2254 | U2369 | L2484 |  |  | U2378 | L2274 | U2386 | L2149 | U2399 | L2492
|  |  | U2323 | L2229 | U2334 | L2235 | U2344 | L2289 |  |  | U2353 | L2246 | U2361 | L2304 | U2370 | L2290 |  |  | U2379 | L2250 | U2387 | L2237 | U2400 | L2485
|  |  | U2324 | L2201 | U2335 | L2264 | U2345 | L2256 |  |  | U2354 | L2218 | U2367 | L2228 | U2376 | L2248 |  |  | U2384 | L2294 | U2396 | L2505 | U2414 | L2491
2006
| 14/06 |  | 15/06 |  | 16/06 |  | 17/06 |  | 18/06 |  | 19/06 |  | 20/06 |  | 21/06 |  | 22/06 |  | 23/06 |  | 24/06 |  | 25/06 |  | 26/06
ALSTOM | U2434 | L2500 | U2457 | L2506 | U2397 | L2518 |  |  | U2417 | L2554 | U2428 | L2544 | U2444 | L2519 |  |  | U2476 | L2525
| U2442 | L2481 | U2458 | L2591 | U2401 | L2524 |  |  | U2419 | L2512 | U2429 | L2531 | U2445 | L2516 |  |  | U2477 | L2546
| U2464 | L2482 | U2459 | L2549 | U2403 | L2587 |  |  | U2420 | L2540 | U2431 | L2487 | U2448 | L2535 |  |  | U2478 | L2513
| U1843 | L2514 | U2460 | L2529 | U2407 | L2545 |  |  | U2421 | L2521 | U2433 | L2560 | U2449 | L2483 |  |  | U2479 | L2530
ANSALDO | U2416 | L2499 | U2078 | L2539 | U2389 | L2501 |  |  | U2410 | L2547 | U2422 | L2562 | U2435 | L2527 |  |  | U2450 | L2517 | U2463 | L2559 | U0501 | U2629 |  |  | U2733 | L2645
| U2418 | L2498 | U2362 | L2523 | U2390 | L2532 |  |  | U2411 | L2561 | U2425 | L2511 | U2438 | L2508 |  |  | U2451 | L2520 | U2736 | L2536 | U1710 | L2626 |  |  | U2734 | L2570
| U2430 | L2489 | U2374 | L2488 | U2393 | L2510 |  |  | U2413 | L2507 | U2426 | L2548 | U2440 | L2558 |  |  | U2452 | L2557 | U2466 | L2590 | U1869 | L2592 |  |  | U2732 | L2632
| U2432 | L2496 | U2503 | L2534 | U2394 | L2509 |  |  | U2415 | L2586 | U2427 | L2552 | U2740 | L2573 |  |  | U2455 | L2555 | U2473 | L2565 | U2735 | L2667 |  |  | U2755 | L2758
2006
| 27/06 |  | 28/06 |  | 29/06 |  | 30/06 |  | 31/06 |  | 32/06 |  | 33/06 |  | 34/06 |  | 35/06 |  | 36/06 |  | 37/06 |  | 38/06 |  | 39/06
ANSALDO | U2729 | L2636 | U2402 | L2567 |  |  | U2424 | L2564 | U2441 | L2553 | U2453 | L2612 |  |  | U2462 | L2528 | U2469 | L2568 | U2474 | L2640 |  |  | U2515 | L2779 | U2588 | L2621
| U2730 | L2581 | U2404 | L2550 |  |  | U2436 | L2563 | U2443 | L2566 | U2454 | L2551 |  |  | U2465 | L2541 | U2470 | L2614 | U2475 | L2543 |  |  | U2526 | L2582 | U2601 | L2620
| U2731 | L2649 | U2405 | L2494 |  |  | U2437 | L2571 | U2446 | L2613 | U2456 | L2493 |  |  | U2467 | L2597 | U2471 | L2538 | U2480 | L2622 |  |  | U2542 | L2575 | U2603 | L2618
| U2727 | L2659 | U2423 | L2502 |  |  | U2439 | L2585 | U2447 | L2577 | U2461 | L2616 |  |  | U2468 | L2569 | U2472 | L2580 | U2490 | L2537 |  |  | U2574 | L2593 | U2604 | L2606
2006
| 40/06 |  | 41/06 |  | 42/06 |  | 43/06 |  | 44/06 |  | 45/06 |  | 46/06 |  | 47/06 |  | 48/06 |  | 49/06 |  | 50/06 |  | 51/06 |  | 52/06
ANSALDO | U2605 | L2607 |  |  | U2628 | L2627 | U2642 | L2624 | U2677 | L2650
| U2610 | L2634 |  |  | U2633 | L2657 | U2648 | L2672 | U2678 | L2608
| U2611 | L2293 |  |  | U2637 | L2556 | U2671 | L2288 | U2682 | L2663
| U2625 | L2589 |  |  | U2638 | L2295 | U2676 | L1942 | U2683 | L2669
CERN/ Extra Shells | U2684 | L2576 | U2688 | L2600 | U2692 | L2654 | U2697 | L2594 | U2701 | L2630 | U2696 | L2596 | U2720 | L2662 | U2724 | L2670 | U2739 | L2599 | U2681 | L2773 | U2707 | L2615 | U2716 | L2579 | U2746 | L2619
| U2685 | L2674 | U2689 | L2668 | U2693 | L2639 | U2698 | L2609 | U2713 | L2675 | U2703 | L2647 | U2721 | L2673 | U2725 | L2661 | U2598 | L2221 | U2702 | L2664 | U2711 | L2772 | U2717 | L2595 | U2750 | L2775
| U2686 | L2583 | U2690 | L2646 | U2694 | L2584 | U2699 | L2776 | U2714 | L2666 | U2704 | L2660 | U2722 | L2643 | U2726 | L2623 | U2644 | L2778 | U2705 | L2655 | U2712 | L2777 | U2718 | L2780 | U2751 | L2602
| U2687 | L2572 | U2691 | L2656 | U2695 | L2651 | U2700 | L2631 | U2679 | L2617 | U2719 | L2653 | U2723 | L2635 | U2738 | L2658 | U2665 | L2774 | U2706 | L2652 | U2715 | L2641 | U2737 | L2578 | U2680 | L2781
CERN/ Extra Shells | U2708 | L2770 | U2741 | L2765 | U2745 | L2761 | U2752 | L2768
| U2709 | L2771 | U2742 | L2760 | U2747 | L2756 | U2753 | L2759
| U2710 | L2763 | U2743 | L2764 | U2748 | L2769 | U2754 | L2757
| U2728 | L2766 | U2744 | L2762 | U2749 | L2767
Note on B8: trachez: Accepted 29/09/2003 CoC Done
Note on B12: trachez: Accepted 29/09/2003 U330 L335 replaced by U752 L658 CoC Done
Note on B46: sberthol: accepted for delivery 05/01/2004 CoC Done
Note on B53: trachez: Accepted for delivery 01/04/04 CoC Done
Note on B57: sberthol: Accepted for delivery 01/04/2004 CoC Done
Note on B72: trachez: Accepted for delivery 08/07/2004 CoC Done
Note on B76: sberthol: Accepted for delivery 11/06/2004 CoC Done
Note on B98: sberthol: Accepted for delivery 06/01/2005 CoCs Done
Note on B102: sberthol: Accepted for delivery 06/01/2005 CoCs Done
Note on B106: sberthol: Accepted for delivery 06/01/2005 CoCs Done
Note on B113: trachez: Accepted for delivery 03/03/2005 CoC Done
Note on B117: trachez: Accepted for delivery 04/03/2005 CoC Done
Note on B122: trachez: Accepted for delivery 03/03/2005 CoC Done
Note on B129: sberthol: Accepted for delivery 20/05/2005
Note on B151: trachez: Accepted for delivery 19/09/2005
Note on B155: Sberthol: Accepted for delivery 19/08/2005
Note on B162: trachez: Accepted for delivery 2/11/2005
Note on B169: sberthol: Accepted for delivery 01/11/2005
Note on B176: sberthol: Accepted for delivery 02/11/2005
Note on B183: sberthol: Accepted for delivery 13/12/2005
Note on D4: trachez: Accepted 29/09/2003 CoC Done
Note on D8: trachez: Accepted 09/10/2003 CoC Done
Note on D31: trachez: accepted for delivery 03/12/2003 CoC Done
Note on D38: trachez: accepted for delivery 19/01/2004 CoC Done
Note on D42: trachez: accepted for delivery 19/01/2004 CoC Done
Note on D57: sberthol: Accepted for delivery 06/04/2004 CoC Done
Note on D61: trachez: Accepted for delivery 01/04/04 CoC Done
Note on D68: trachez: Accepted for delivery 13/07/2004 CoC Done
Note on D72: trachez: Accepted for delivery 13/07/2004 CoC Done
Note on D76: trachez: Accepted for delivery 13/07/2004 CoC Done
Note on D83: trachez: Accepted for delivery 19/10/2004 CoC's Done
Note on D87: trachez: Accepted for delivery 19/10/2004 CoC's Done
Note on D91: sberthol: Acceptance achieved on 20/08/2004 CoC Done
Note on D98: sberthol: Accepted for delivery 06/01/2005 CoCs Done
Note on D102: sberthol: Accepted for delivery 06/01/2005 CoCs Done
Note on D106: sberthol: Accepted for delivery 06/01/2005 CoCs Done
Note on D117: sberthol: Accepted for delivery Final status on 25/05/2005 CoC Done
Note on D133: sberthol: Accepted for delivery 20/05/2005
Note on D140: Sberthol: Accepted for delivery 29/06/2005
Note on D144: Sberthol: Accepted for delivery 29/06/2005
Note on D151: trachez: Accepted for delivery 19/09/2005
Note on D155: trachez: Accepted for delivery 19/09/2005
Note on D162: sberthol: Accepted for delivery 31/10/2005
Note on D176: sberthol: Accepted for delivery 02/11/2005
Note on D183: sberthol: Accepted for delivery 12/12/2005
Note on F4: trachez: Extra delivery Accepted for delivery 10/10/2003 CoC Done
Note on F8: trachez: Accepted for delivery 10/10/2003 CoC Done
Note on F12: trachez: Accepted for delivery 10/10/2003 CoC Done
Note on F19: trachez: accepted for delivery 03/12/2003 CoC Done
Note on F23: trachez: accepted for delivery 03/12/2003 CoC Done
Note on F42: trachez: accepted for delivery 23/01/2004 CoC Done
Note on F46: sberthol: accepted for delivery 25/02/2004 CoC Done
Note on F53: sberthol: Accepted for delivery 20/04/04 CoC Done
Note on F57: sberthol: Accepted for delivery 08/06/2004 CoC Done
Note on F61: trachez: Accepted for delivery 02/04/04 CoC Done
Note on F68: trachez: Accepted for delivery 13/07/2004 CoC Done
Note on F72: trachez: Accepted for delivery 13/07/2004 CoC Done
Note on F76: trachez: Accepted for delivery 20/07/2004 CoC Done
Note on F83: trachez: Accepted for delivery 19/10/2004 CoC's Done
Note on F87: trachez: Accepted for delivery 19/10/2004 CoC's Done
Note on F91: trachez: Accepted for delivery 15/10/2004 CoC's Done
Note on F98: sberthol: Accepted for delivery 07/01/2005 CoC Done
Note on F102: sberthol: Accepted for delivery 06/01/2005 CoC Done
Note on F117: sberthol: Accepted for delivery 04/04/2005 CoC Done
Note on F121: sberthol: Accepted for delivery 18/05/2005 Added to delivery in week 29
Note on F122: trachez: Accepted for delivery 04/03/2005 CoC Done
Note on F129: sberthol: Accepted for delivery 23/05/2005
Note on F133: sberthol: Accepted for delivery 23/05/2005
Note on F140: Sberthol: Accepted for delivery 30/06/2005
Note on F144: Sberthol: Accepted for delivery 30/06/2005
Note on F151: trachez: Accepted for delivery 22/09/2005
Note on F155: trachez: Accepted for delivery 19/09/2005
Note on F169: sberthol: Accepted for delivery 02/11/2005
Note on F176: sberthol: Accepted for delivery 03/11/2005
Note on F183: sberthol: Accepted for delivery 12/12/2005
Note on H4: trachez: accepted for delivery 14/10/2003 CoC Done
Note on H8: trachez: accepted for delivery 14/10/2003 CoC Done
Note on H23: trachez: accepted for delivery 03/12/2003 CoC Done
Note on H31: trachez: accepted for delivery 03/12/2003 CoC Done
Note on H38: trachez: accepted for delivery 23/01/2004 CoC Done
Note on H42: sberthol : accepted for delivery 20/02/2004 CoC Done
Note on H53: sberthol: Accepted for delivery 06/04/2004 CoC Done
Note on H57: sberthol: Accepted for delivery 07/04/2004 CoC Done
Note on H61: trachez: Accepted for delivery 02/04/04 CoC Done
Note on H68: trachez: Accepted for delivery 11/08/04 CoC Done
Note on H72: trachez: Accepted for delivery 20/07/2004 CoC Done
Note on H83: trachez: Accepted for delivery 21/10/2004 CoC's Done
Note on H87: trachez: Accepted for delivery 21/10/2004 CoC's Done
Note on H102: trachez: Accepted for delivery 5/01/2005 CoC Done
Note on H106: trachez: Accepted for delivery 5/01/2005 CoC Done
Note on H122: sberthol: Accepted for delivery 04/04/2005 CoC Done
Note on H129: sberthol: Accepted for delivery 23/05/2005
Note on H133: sberthol: Accepted for delivery 24/05/2005
Note on H140: Sberthol: Accepted for delivery 01/07/2005
Note on H144: Sberthol: Accepted for delivery 01/07/2005
Note on H162: sberthol: Accepted for delivery 31/10/2005
Note on H169: sberthol: Accepted for delivery 02/11/2005
Note on H176: sberthol: Accepted for Delivery 03/11/2005
Note on H183: sberthol: Accepted for delivery 12/12/2005
Note on J8: trachez: accepted for delivery 15/10/2003 CoC Done
Note on J12: trachez: accepted for delivery 15/10/2003 CoC Done
Note on J19: trachez: accepted for delivery 12/12/2003 CoC Done
Note on J23: trachez: accepted for delivery 12/12/2003 CoC Done
Note on J38: sberthol: Accepted for delivery 08/03/2004 CoC Done
Note on J46: sberthol: accepted for delivery 20/02/2004 CoC Done
Note on J57: sberthol: Accepted for delivery 08/04/2004 CoC Done
Note on J72: trachez: Accepted for delivery 09/08/04 CoC Done
Note on J76: trachez: Accepted for delivery 12/08/04 CoC Done
Note on J87: trachez: Accepted for delivery 21/10/2004 CoC's Done
Note on J91: trachez: Accepted for delivery 19/10/2004 CoC's Done
Note on J98: trachez: Accepted for delivery 6/01/2005 CoC Done
Note on J102: trachez: Accepted for delivery 6/01/2005 CoC Done
Note on J106: trachez: Accepted for delivery 6/01/2005 CoC Done
Note on J122: sberthol: Accepted for delivery 04/04/2005 CoC Done
Note on J129: sberthol: Accepted for delivery 24/05/2005
Note on J151: trachez: Accepted for delivery 12/10/2005
Note on J155: trachez: Accepted for delivery 25/09/2005
Note on J162: sberthol: Accepted for delivery 31/10/2005
Note on J169: sberthol: Accepted for delivery 02/11/2005
Note on J176: sberthol: Accepted for delivery 03/11/2005
Note on L4: trachez: accepted for delivery 20/10/2003 CoC Done
Note on L8: trachez: accepted for delivery 20/10/2003 CoC Done
Note on L23: trachez: accepted for delivery 12/12/2003 CoC Done
Note on L38: sberthol: accepted for delivery 08/03/2004 CoC Done
Note on L42: trachez: accepted for delivery 15/12/2003 CoC Done
Note on L57: sberthol: Accepted for delivery 08/04/2004 CoC Done
Note on L68: trachez: Accepted for delivery 12/08/04 CoC Done
Note on L72: trachez: Accepted for delivery 11/08/04 CoC Done
Note on L83: trachez: Accepted for delivery 21/10/2004 CoC's Done
Note on L87: trachez: Accepted for delivery 22/10/2004 CoC's Done
Note on L91: trachez: Accepted for delivery 19/10/2004 CoC's Done
Note on L98: trachez: Accepted for delivery 7/01/2005 CoC Done
Note on L102: trachez: Accepted for delivery 7/01/2005 CoC Done
Note on L106: trachez: Accepted for delivery 12/01/2005 CoC Done
Note on L113: trachez: Accepted for delivery 04/03/2005 CoC Done Moved in week 32
Note on L117: Sberthol: Accepted for delivery 01/07/2005
Note on L133: sberthol: Accepted for delivery 24/05/2005
Note on L140: trachez: Accepted for delivery 25/07/2005
Note on L144: Sberthol: Accepted for delivery 01/07/2005
Note on L151: trachez: Accepted for delivery 12/10/2005
Note on L155: trachez: Accepted for delivery 12/10/2005
Note on L162: sberthol: Accepted for delivery 31/10/2005
Note on L176: trachez: Accepted for delivery 11/12/2005
Note on N8: trachez: accepted for delivery 20/10/2003 CoC Done
Note on N12: trachez: accepted for delivery 20/10/2003 CoC Done
Note on N19: trachez: accepted for delivery 15/12/2003 CoC Done
Note on N23: trachez: accepted for delivery 15/12/2003 CoC Done
Note on N42: sberthol: accepted for delivery 08/03/2004 CoC Done
Note on N46: sberthol: accepted for delivery 08/03/2004 CoC Done
Note on N53: sberthol: Accepted for delivery 07/04/2004 CoC Done
Note on N57: sberthol: Accepted for delivery 08/04/2004 CoC Done
Note on N68: sberthol: Accepted for delivery 17/08/2004 CoC Done
Note on N72: trachez: Accepted for delivery 11/08/04 CoC Done
Note on N76: trachez: Accepted for delivery 13/08/04 Delivered in week 44 CoC Done
Note on N83: trachez: Accepted for delivery 22/10/2004 CoC's Done
Note on N87: trachez: Accepted for delivery 26/10/2004 CoC's Done
Note on N91: trachez: Accepted for delivery 21/10/2004 CoC's Done
Note on N98: trachez: Accepted for delivery 12/01/2005 CoC Done
Note on N102: trachez: Accepted for delivery 12/01/2005 CoC Done
Note on N117: Sberthol: Accepted for delivery 01/07/2005
Note on N129: sberthol: Accepted for delivery 24/05/2005
Note on N133: sberthol: Accepted for delivery 25/05/2005
Note on N140: trachez: Accepted for delivery 05/08/2005
Note on N144: trachez: Accepted for delivery 05/08/2005
Note on N151: trachez: Accepted for delivery 31/10/2005
Note on N155: trachez: Accepted for delivery 31/10/2005
Note on N176: trachez: Accepted for delivery 11/12/2005
Note on P4: trachez: accepted for delivery 20/10/2003 CoC Done
Note on P8: trachez: accepted for delivery 21/10/2003 CoC Done
Note on P38: trachez: Accepted for delivery 24/03/04 Coc done
Note on P42: sberthol: accepted for delivery 08/03/2004 CoC Done
Note on P46: trachez: Accepted for delivery 08/03/04 Coc done
Note on P57: trachez: Accepted for Delivery 19/05/04 CoC Done
Note on P61: trachez: Accepted for Delivery 19/05/04 CoC Done
Note on P68: sberthol: Accepted for delivery 18/08/2004 CoC Done
Note on P72: sberthol: Accepted for delivery 18/08/2004 CoC Done
Note on P83: trachez: Accepted for delivery 22/11/2004 CoC Done
Note on P87: trachez: Accepted for delivery 22/11/2004 CoC Done
Note on P102: sberthol: Accepted for delivery 22/02/2005 CoC Done
Note on P106: sberthol: Accepted for delivery 23/02/2005 CoC Done
Note on P113: sberthol: Accepted for delivery 06/04/2005 CoC Done
Note on P122: sberthol: Accepted for delivery 07/04/2005
Note on P129: sberthol: Accepted for delivery 25/05/2005
Note on P140: Sberthol: Accepted for delivery 15/08/2005
Note on P144: trachez: Accepted for delivery 05/08/2005
Note on P162: sberthol: Accepted for delivery 31/10/2005
Note on P176: trachez: Accepted for delivery 11/12/2005
Note on R8: trachez: accepted for delivery 22/10/2003 CoC Done
Note on R12: trachez: accepted for delivery 22/10/2003 CoC Done
Note on R19: sberthol: accepted for delivery 05/01/2004 CoC Done
Note on R23: sberthol: accepted for delivery 05/01/2004 CoC Done
Note on R38: sberthol: Accepted for delivery 31/03/2004 CoC Done
Note on R42: trachez: Accepted for delivery 08/03/04 Coc done
Note on R46: trachez: Accepted for delivery 25/03/04 CoC Done
Note on R53: sberthol: Accepted for delivery 14/04/2004 CoC Done
Note on R57: sberthol: Accepted for delivery 16/06/2004 CoC Done L0245 was delivered instead of U1189
Note on R72: sberthol: Accepted for delivery 18/08/2004 CoC Done
Note on R76: sberthol: Accepted for delivery 18/08/2004 CoC Done
Note on R87: trachez: Accepted for delivery 22/11/2004 CoC Done
Note on R91: trachez: Accepted for delivery 22/10/2004 CoC's Done
Note on R98: sberthol: Accepted for delivery 23/02/2005 CoC Done
Note on R102: sberthol: Accepted for delivery 23/02/2005 CoC Done
Note on R106: sberthol: Accepted for delivery 24/02/2005 CoC Done
Note on R113: sberthol: Accepted for delivery 06/04/2005
Note on R122: sberthol: Accepted for delivery 18/05/2005
Note on R129: sberthol: Accepted for delivery 25/05/2005
Note on R151: trachez: Accepted for delivery 1/11/2005
Note on R155: trachez: Accepted for delivery 1/11/2005
Note on R162: sberthol: Accepted for delivery 01/11/2005
Note on R176: trachez: Accepted for delivery 11/12/2005
Note on T4: trachez: accepted for delivery 22/10/2003 CoC Done
Note on T8: trachez: accepted for delivery 22/10/2003 CoC Done
Note on T31: trachez: accepted for delivery 15/12/2003 CoC Done
Note on T38: sberthol: Accepted for delivery 01/04/2004 CoC Done
Note on T42: trachez: Accepted for delivery 25/03/04 CoC Done
Note on T57: sberthol: Accepted for delivery 15/06/2004 CoC Done
Note on T61: sberthol: Accepted for deli very 16/06/2004 CoC Done
Note on T68: sberthol: Accepted for delivery 19/08/2004 CoC Done
Note on T72: sberthol: Accepted for delivery 19/08/2004 CoC Done
Note on T76: sberthol: Accepted for delivery 18/08/2004 CoC Done
Note on T83: trachez: Accepted for delivery 22/11/2004 CoC Done
Note on T87: trachez: Accepted for delivery 22/11/2004 CoC Done
Note on T91: trachez: Accepted for delivery 26/10/2004 CoC's Done
Note on T98: sberthol: Accepted for delivery 24/02/2005 CoC Done
Note on T102: sberthol: Accepted for delivery 24/02/2005 CoC Done
Note on T106: sberthol: Accepted for delivey 24/02/2005 CoC Done
Note on T113: sberthol: Accepted for delivery 07/04/2005
Note on T133: sberthol: Accepted for delivery 25/05/2005
Note on T140: Sberthol: Accepted for delivery 16/08/2005
Note on T144: Sberthol: Accepted for delivery 15/08/2005
Note on T155: trachez: Accepted for delivery 1/11/2005
Note on T162: sberthol: Accepted for delivery 01/11/2005
Note on T176: trachez: Accepted for delivery 11/12/2005
Note on V8: trachez: accepted for delivery 27/10/2003 CoC Done
Note on V12: trachez: accepted for delivery 27/10/2003 CoC Done
Note on V23: sberthol: accepted for drlivery 05/01/2004 CoC Done
Note on V42: trachez: Accepted for delivery 25/03/04 CoC Done
Note on V46: sberthol: Accepted for delivery 01/04/2004 CoC Done
Note on V53: sberthol: Accepted for delivery 09/08/04 CoC Done
Note on V57: sberthol: Accepted for delivery 09/08/04 CoC Done 2 additionnal paired shell (U0233 and U1189) will be delivered
Note on V68: trachez: Accepted for delivery 15/10/2004 CoC's Done
Note on V72: sberthol: Accepted for delivery 23/08/2004 CoC Done
Note on V76: trachez: Delayed by Ansaldo(no respect of the time for cancellation<15 days) 2600 € for bring back truck
Note on V83: trachez: Accepted for delivery 07/12/2004 CoC Done
Note on V87: trachez: Accepted for delivery 07/12/2004 CoC Done
Note on V91: trachez: Accepted for delivery 07/12/2004 CoC Done
Note on V98: trachez: Accepted for delivery 01/03/2005 CoC Done
Note on V102: trachez: Accepted for delivery 01/03/2005 CoC Done
Note on V122: sberthol: Accepted for delivery 18/05/2005
Note on V129: Sberthol: Accepted for delivery 29/06/2005
Note on V133: Sberthol: Accepted for delivery 29/06/2005
Note on V140: Sberthol: Accepted for delivery 17/08/2005
Note on V144: Sberthol: Accepted for delivery 16/08/2005
Note on V155: trachez: Accepted for delivery 2/11/2005
Note on V176: trachez: Accepted for delivery 11/12/2005
Note on X4: trachez: accepted for delivery 27/10/2003 CoC Done
Note on X8: trachez: accepted for delivery 27/10/2003 CoC Done
Note on X12: trachez: accepted for delivery 27/10/2003 CoC Done
Note on X23: sberthol: accepted for delivery 05/01/2004 CoC Done
Note on X31: trachez: accepted for delivery 15/12/2003 CoC Done
Note on X42: sberthol: Accepted for delivery 12/05/04 CoCs done
Note on X57: sberthol: Accepted for delivery 11/06/2004 CoC Done
Note on X61: sberthol: Accepted for delivery 11/06/2004 CoC Done
Note on X68: trachez: Accepted for delivery 15/10/2004 CoC's Done
Note on X72: sberthol: Accepted for delivery 23/08/2004 CoC Done
Note on X83: trachez: Accepted for delivery 10/12/2004 CoC Done
Note on X87: trachez: Accepted for delivery 10/12/2004 CoC Done
Note on X102: trachez: Accepted for delivery 02/03/2005 CoC Done
Note on X113: sberthol: Accepted for delivery 18/05/2005
Note on X122: sberthol: Accepted for delivery 19/05/2005
Note on X129: trachez: Accepted for delivery 29/06/2005
Note on X133: Sberthol: Accepted for delivery 29/06/2005
Note on X140: Sberthol: Accepted for delivery 19/08/2005
Note on X144: Sberthol: Accepted for delivery 17/08/2005
Note on X162: sberthol: Accepted for Delivery 01/11/2005
Note on X176: sberthol: Accepted for delivery 13/12/2005
Note on Z19: trachez: accepted for delivery 19/01/2004 CoC Done
Note on Z23: trachez: accepted for delivery 19/01/2004 CoC Done
Note on Z38: trachez: Accepted for delivery 01/04/04 CoC Done
Note on Z42: sberthol: Accepted for delivery 31/03/2004 CoC Done
Note on Z46: trachez: Accepted for delivery 01/04/04 CoC Done
Note on Z53: sberthol: Accepted for delivery 10/06/2004 CoC Done
Note on Z57: sberthol: Accepted for delivery 11/06/2004 CoC Done
Note on Z87: sberthol: Accepted for delivery 06/01/2005 CoCs Done
Note on Z91: sberthol: Accepted for delivery 06/01/2005 CoCs Done
Note on Z98: trachez: Accepted for delivery 02/03/2005 CoC Done
Note on Z102: trachez: Accepted for delivery 03/03/2005 CoC Done
Note on Z106: trachez: Accepted for delivery 02/03/2005 CoC Done
Note on Z113: sberthol: Accepted for delivery 19/05/2005
Note on Z122: sberthol: Accepted for delivery 19/05/2005
Note on Z155: trachez: Accepted for delivery 2/11/2005
Note on Z162: sberthol: Accepted for Delivery 01/11/2005
Note on Z176: sberthol: Accepted for delivery 13/12/2005

## Dbase
Week | Shell | Accepted on | Destination
40/03 | 0 |  | ALSTOM
40/03 | 0 |  | ALSTOM
40/03 | 0 |  | ALSTOM
40/03 | 0 |  | ALSTOM
40/03 | U0405 | 2003-09-29 | NOELL
40/03 | U0472 | 2003-09-29 | NOELL
40/03 | U0473 | 2003-09-29 | NOELL
40/03 | U0492 | 2003-09-29 | NOELL
40/03 | U0277 | 2003-09-29 | ANSALDO
40/03 | U0752 | 2003-09-29 | ANSALDO
40/03 | L0337 | 2003-09-29 | ANSALDO
40/03 | L0335 | 2003-09-29 | ANSALDO
40/03 | 0 |  | ALSTOM
40/03 | 0 |  | ALSTOM
40/03 | 0 |  | ALSTOM
40/03 | 0 |  | ALSTOM
40/03 | L0478 | 2003-09-29 | NOELL
40/03 | L0517 | 2003-09-29 | NOELL
40/03 | L0474 | 2003-09-29 | NOELL
40/03 | L0523 | 2003-09-29 | NOELL
40/03 | U0285 | 2003-09-29 | ANSALDO
40/03 | L0658 | 2003-09-29 | ANSALDO
40/03 | L0340 | 2003-09-29 | ANSALDO
40/03 | L0352 | 2003-09-29 | ANSALDO
41/03 | U0731 | 2003-09-29 | ALSTOM
41/03 | L0548 | 2003-09-29 | ALSTOM
41/03 | L0567 | 2003-09-29 | ALSTOM
41/03 | U0583 | 2003-09-29 | ALSTOM
41/03 | U0306 | 2003-10-09 | NOELL
41/03 | U0310 | 2003-10-10 | NOELL
41/03 | U0312 | 2003-10-11 | NOELL
41/03 | U0327 | 2003-10-12 | NOELL
41/03 | 0 |  | ANSALDO
41/03 | 0 |  | ANSALDO
41/03 | 0 |  | ANSALDO
41/03 | 0 |  | ANSALDO
41/03 | L0531 | 2003-09-29 | ALSTOM
41/03 | L0566 | 2003-09-29 | ALSTOM
41/03 | L0554 | 2003-09-29 | ALSTOM
41/03 | L0558 | 2003-09-29 | ALSTOM
41/03 | L0784 | 2003-10-09 | NOELL
41/03 | L0816 | 2003-10-10 | NOELL
41/03 | L0825 | 2003-10-10 | NOELL
41/03 | L0819 | 2003-10-10 | NOELL
41/03 | 0 |  | ANSALDO
41/03 | 0 |  | ANSALDO
41/03 | 0 |  | ANSALDO
41/03 | 0 |  | ANSALDO
42/03 | U0600 | 2003-10-10 | ALSTOM
42/03 | U0670 | 2003-10-10 | ALSTOM
42/03 | L0547 | 2003-10-10 | ALSTOM
42/03 | U0582 | 2003-10-10 | ALSTOM
42/03 | L0588 | 2003-10-10 | NOELL
42/03 | U0700 | 2003-10-10 | NOELL
42/03 | L0635 | 2003-10-10 | NOELL
42/03 | L0590 | 2003-10-10 | NOELL
42/03 | L0533 | 2003-10-10 | ANSALDO
42/03 | L0545 | 2003-10-10 | ANSALDO
42/03 | L0546 | 2003-10-10 | ANSALDO
42/03 | L0601 | 2003-10-10 | ANSALDO
42/03 | U0830 | 2003-10-10 | ALSTOM
42/03 | U0676 | 2003-10-10 | ALSTOM
42/03 | U0623 | 2003-10-10 | ALSTOM
42/03 | U0749 | 2003-10-10 | ALSTOM
42/03 | U0704 | 2003-10-10 | NOELL
42/03 | L0565 | 2003-10-10 | NOELL
42/03 | U0683 | 2003-10-10 | NOELL
42/03 | U0813 | 2003-10-10 | NOELL
42/03 | U0691 | 2003-10-10 | ANSALDO
42/03 | U0727 | 2003-10-10 | ANSALDO
42/03 | U0663 | 2003-10-10 | ANSALDO
42/03 | U0666 | 2003-10-10 | ANSALDO
43/03 | U0332 | 2003-10-14 | ALSTOM
43/03 | L0528 | 2003-10-14 | ALSTOM
43/03 | L0529 | 2003-10-14 | ALSTOM
43/03 | L0572 | 2003-10-14 | ALSTOM
43/03 | L0632 | 2003-10-14 | NOELL
43/03 | L0612 | 2003-10-14 | NOELL
43/03 | L0615 | 2003-10-14 | NOELL
43/03 | L0786 | 2003-10-14 | NOELL
43/03 | 0 |  | ANSALDO
43/03 | 0 |  | ANSALDO
43/03 | 0 |  | ANSALDO
43/03 | 0 |  | ANSALDO
43/03 | U0708 | 2003-10-14 | ALSTOM
43/03 | U0609 | 2003-10-14 | ALSTOM
43/03 | U0627 | 2003-10-14 | ALSTOM
43/03 | L0619 | 2003-10-14 | ALSTOM
43/03 | U0759 | 2003-10-14 | NOELL
43/03 | U0699 | 2003-10-14 | NOELL
43/03 | U0765 | 2003-10-14 | NOELL
43/03 | U0768 | 2003-10-14 | NOELL
43/03 | 0 |  | ANSALDO
43/03 | 0 |  | ANSALDO
43/03 | 0 |  | ANSALDO
43/03 | 0 |  | ANSALDO
44/03 | 0 |  | ALSTOM
44/03 | 0 |  | ALSTOM
44/03 | 0 |  | ALSTOM
44/03 | 0 |  | ALSTOM
44/03 | U0339 | 2003-10-15 | NOELL
44/03 | U0720 | 2003-10-15 | NOELL
44/03 | U0685 | 2003-10-15 | NOELL
44/03 | U0713 | 2003-10-15 | NOELL
44/03 | L0551 | 2003-10-15 | ANSALDO
44/03 | L0552 | 2003-10-15 | ANSALDO
44/03 | L0553 | 2003-10-15 | ANSALDO
44/03 | U0400 | 2003-10-15 | ANSALDO
44/03 | 0 |  | ALSTOM
44/03 | 0 |  | ALSTOM
44/03 | 0 |  | ALSTOM
44/03 | 0 |  | ALSTOM
44/03 | L0858 | 2003-10-15 | NOELL
44/03 | L0820 | 2003-10-15 | NOELL
44/03 | L0790 | 2003-10-15 | NOELL
44/03 | L0589 | 2003-10-15 | NOELL
44/03 | U0599 | 2003-10-15 | ANSALDO
44/03 | U0777 | 2003-10-15 | ANSALDO
44/03 | U0714 | 2003-10-15 | ANSALDO
44/03 | U0402 | 2003-10-15 | ANSALDO
45/03 | L0544 | 2003-10-20 | ALSTOM
45/03 | L0555 | 2003-10-20 | ALSTOM
45/03 | L0557 | 2003-10-20 | ALSTOM
45/03 | U0642 | 2003-10-20 | ALSTOM
45/03 | U0490 | 2003-10-20 | NOELL
45/03 | U0519 | 2003-10-20 | NOELL
45/03 | U0521 | 2003-10-20 | NOELL
45/03 | U0744 | 2003-10-20 | NOELL
45/03 | 0 |  | ANSALDO
45/03 | 0 |  | ANSALDO
45/03 | 0 |  | ANSALDO
45/03 | 0 |  | ANSALDO
45/03 | U0716 | 2003-10-20 | ALSTOM
45/03 | U0706 | 2003-10-20 | ALSTOM
45/03 | U0780 | 2003-10-20 | ALSTOM
45/03 | U0770 | 2003-10-20 | ALSTOM
45/03 | L0631 | 2003-10-20 | NOELL
45/03 | L0586 | 2003-10-20 | NOELL
45/03 | L0580 | 2003-10-20 | NOELL
45/03 | L0602 | 2003-10-20 | NOELL
45/03 | 0 |  | ANSALDO
45/03 | 0 |  | ANSALDO
45/03 | 0 |  | ANSALDO
45/03 | 0 |  | ANSALDO
46/03 | 0 |  | ALSTOM
46/03 | 0 |  | ALSTOM
46/03 | 0 |  | ALSTOM
46/03 | 0 |  | ALSTOM
46/03 | U0748 | 2003-10-20 | NOELL
46/03 | U0761 | 2003-10-20 | NOELL
46/03 | U0775 | 2003-10-20 | NOELL
46/03 | U0709 | 2003-10-20 | NOELL
46/03 | L0561 | 2003-10-20 | ANSALDO
46/03 | L0562 | 2003-10-20 | ANSALDO
46/03 | L0564 | 2003-10-20 | ANSALDO
46/03 | L0569 | 2003-10-20 | ANSALDO
46/03 | 0 |  | ALSTOM
46/03 | 0 |  | ALSTOM
46/03 | 0 |  | ALSTOM
46/03 | 0 |  | ALSTOM
46/03 | L0788 | 2003-10-20 | NOELL
46/03 | L0516 | 2003-10-20 | NOELL
46/03 | L0523 | 2003-10-20 | NOELL
46/03 | L0549 | 2003-10-20 | NOELL
46/03 | L0614 | 2003-10-20 | ANSALDO
46/03 | L0620 | 2003-10-20 | ANSALDO
46/03 | U0712 | 2003-10-20 | ANSALDO
46/03 | L0618 | 2003-10-20 | ANSALDO
47/03 | L0560 | 2003-10-20 | ALSTOM
47/03 | L0568 | 2003-10-20 | ALSTOM
47/03 | U0639 | 2003-10-20 | ALSTOM
47/03 | U0649 | 2003-10-20 | ALSTOM
47/03 | L0542 | 2003-10-21 | NOELL
47/03 | L0543 | 2003-10-21 | NOELL
47/03 | L0524 | 2003-10-21 | NOELL
47/03 | L0541 | 2003-10-21 | NOELL
47/03 | 0 |  | ANSALDO
47/03 | 0 |  | ANSALDO
47/03 | 0 |  | ANSALDO
47/03 | 0 |  | ANSALDO
47/03 | U0803 | 2003-10-20 | ALSTOM
47/03 | U0783 | 2003-10-20 | ALSTOM
47/03 | U0753 | 2003-10-20 | ALSTOM
47/03 | U0742 | 2003-10-20 | ALSTOM
47/03 | U0711 | 2003-10-21 | NOELL
47/03 | U0697 | 2003-10-21 | NOELL
47/03 | U0738 | 2003-10-21 | NOELL
47/03 | U0719 | 2003-10-21 | NOELL
47/03 | 0 |  | ANSALDO
47/03 | 0 |  | ANSALDO
47/03 | 0 |  | ANSALDO
47/03 | 0 |  | ANSALDO
48/03 | 0 |  | ALSTOM
48/03 | 0 |  | ALSTOM
48/03 | 0 |  | ALSTOM
48/03 | 0 |  | ALSTOM
48/03 | L0587 | 2003-10-22 | NOELL
48/03 | L0573 | 2003-10-22 | NOELL
48/03 | L0652 | 2003-10-22 | NOELL
48/03 | L0513 | 2003-10-22 | NOELL
48/03 | L0575 | 2003-10-22 | ANSALDO
48/03 | L0576 | 2003-10-22 | ANSALDO
48/03 | L0577 | 2003-10-22 | ANSALDO
48/03 | U0585 | 2003-10-22 | ANSALDO
48/03 | 0 |  | ALSTOM
48/03 | 0 |  | ALSTOM
48/03 | 0 |  | ALSTOM
48/03 | 0 |  | ALSTOM
48/03 | U0717 | 2003-10-22 | NOELL
48/03 | U0701 | 2003-10-22 | NOELL
48/03 | U0771 | 2003-10-22 | NOELL
48/03 | U0747 | 2003-10-22 | NOELL
48/03 | L0611 | 2003-10-22 | ANSALDO
48/03 | L0621 | 2003-10-22 | ANSALDO
48/03 | U0730 | 2003-10-22 | ANSALDO
48/03 | U0726 | 2003-10-22 | ANSALDO
49/03 | L0646 | 2003-10-22 | ALSTOM
49/03 | L0648 | 2003-10-22 | ALSTOM
49/03 | L0571 | 2003-10-22 | ALSTOM
49/03 | L0647 | 2003-10-22 | ALSTOM
49/03 | L0795 | 2003-10-22 | NOELL
49/03 | U0410 | 2003-10-22 | NOELL
49/03 | U0412 | 2003-10-22 | NOELL
49/03 | U0226 | 2003-10-22 | NOELL
49/03 | 0 |  | ANSALDO
49/03 | 0 |  | ANSALDO
49/03 | 0 |  | ANSALDO
49/03 | 0 |  | ANSALDO
49/03 | U0679 | 2003-10-22 | ALSTOM
49/03 | U0751 | 2003-10-22 | ALSTOM
49/03 | L0607 | 2003-10-22 | ALSTOM
49/03 | U0680 | 2003-10-22 | ALSTOM
49/03 | U0741 | 2003-10-22 | NOELL
49/03 | L0883 | 2003-10-22 | NOELL
49/03 | L0896 | 2003-10-22 | NOELL
49/03 | L0882 | 2003-10-22 | NOELL
49/03 | 0 |  | ANSALDO
49/03 | 0 |  | ANSALDO
49/03 | 0 |  | ANSALDO
49/03 | 0 |  | ANSALDO
50/03 | 0 |  | ALSTOM
50/03 | 0 |  | ALSTOM
50/03 | 0 |  | ALSTOM
50/03 | 0 |  | ALSTOM
50/03 | L0824 | 2003-10-27 | NOELL
50/03 | L0898 | 2003-10-27 | NOELL
50/03 | L0868 | 2003-10-27 | NOELL
50/03 | L0874 | 2003-10-27 | NOELL
50/03 | U0605 | 2003-10-27 | ANSALDO
50/03 | L0610 | 2003-10-27 | ANSALDO
50/03 | L0650 | 2003-10-27 | ANSALDO
50/03 | L0532 | 2003-10-27 | ANSALDO
50/03 | 0 |  | ALSTOM
50/03 | 0 |  | ALSTOM
50/03 | 0 |  | ALSTOM
50/03 | 0 |  | ALSTOM
50/03 | U0763 | 2003-10-27 | NOELL
50/03 | U0802 | 2003-10-27 | NOELL
50/03 | U0774 | 2003-10-27 | NOELL
50/03 | U0815 | 2003-10-27 | NOELL
50/03 | U0810 | 2003-10-27 | ANSALDO
50/03 | U0814 | 2003-10-27 | ANSALDO
50/03 | U0689 | 2003-10-27 | ANSALDO
50/03 | U0664 | 2003-10-27 | ANSALDO
51/03 | L0584 | 2003-10-27 | ALSTOM
51/03 | L0550 | 2003-10-27 | ALSTOM
51/03 | L0643 | 2003-10-27 | ALSTOM
51/03 | L0645 | 2003-10-27 | ALSTOM
51/03 | L0857 | 2003-10-27 | NOELL
51/03 | L0863 | 2003-10-27 | NOELL
51/03 | L0823 | 2003-10-27 | NOELL
51/03 | L0891 | 2003-10-27 | NOELL
51/03 | U0633 | 2003-10-27 | ANSALDO
51/03 | L0636 | 2003-10-27 | ANSALDO
51/03 | L0526 | 2003-10-27 | ANSALDO
51/03 | L0527 | 2003-10-27 | ANSALDO
51/03 | U0617 | 2003-10-27 | ALSTOM
51/03 | U0628 | 2003-10-27 | ALSTOM
51/03 | U0674 | 2003-10-27 | ALSTOM
51/03 | U0762 | 2003-10-27 | ALSTOM
51/03 | U0729 | 2003-10-27 | NOELL
51/03 | U0807 | 2003-10-27 | NOELL
51/03 | U0721 | 2003-10-27 | NOELL
51/03 | U0698 | 2003-10-27 | NOELL
51/03 | U0690 | 2003-10-27 | ANSALDO
51/03 | U0682 | 2003-10-27 | ANSALDO
51/03 | L0603 | 2003-10-27 | ANSALDO
51/03 | U0604 | 2003-10-27 | ANSALDO
52/03 | 0 |  | ALSTOM
52/03 | 0 |  | ALSTOM
52/03 | 0 |  | ALSTOM
52/03 | 0 |  | ALSTOM
52/03 | 0 |  | NOELL
52/03 | 0 |  | NOELL
52/03 | 0 |  | NOELL
52/03 | 0 |  | NOELL
52/03 | 0 |  | ANSALDO
52/03 | 0 |  | ANSALDO
52/03 | 0 |  | ANSALDO
52/03 | 0 |  | ANSALDO
52/03 | 0 |  | ALSTOM
52/03 | 0 |  | ALSTOM
52/03 | 0 |  | ALSTOM
52/03 | 0 |  | ALSTOM
52/03 | 0 |  | NOELL
52/03 | 0 |  | NOELL
52/03 | 0 |  | NOELL
52/03 | 0 |  | NOELL
52/03 | 0 |  | ANSALDO
52/03 | 0 |  | ANSALDO
52/03 | 0 |  | ANSALDO
52/03 | 0 |  | ANSALDO
1/04 | 0 |  | ALSTOM
1/04 | 0 |  | ALSTOM
1/04 | 0 |  | ALSTOM
1/04 | 0 |  | ALSTOM
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | ANSALDO
1/04 | 0 |  | ANSALDO
1/04 | 0 |  | ANSALDO
1/04 | 0 |  | ANSALDO
1/04 | 0 |  | ALSTOM
1/04 | 0 |  | ALSTOM
1/04 | 0 |  | ALSTOM
1/04 | 0 |  | ALSTOM
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | NOELL
1/04 | 0 |  | ANSALDO
1/04 | 0 |  | ANSALDO
1/04 | 0 |  | ANSALDO
1/04 | 0 |  | ANSALDO
2/04 | 0 |  | ALSTOM
2/04 | 0 |  | ALSTOM
2/04 | 0 |  | ALSTOM
2/04 | 0 |  | ALSTOM
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | U0743 | 2003-12-03 | ANSALDO
2/04 | U0669 | 2003-12-03 | ANSALDO
2/04 | U0673 | 2003-12-03 | ANSALDO
2/04 | U0687 | 2003-12-03 | ANSALDO
2/04 | 0 |  | ALSTOM
2/04 | 0 |  | ALSTOM
2/04 | 0 |  | ALSTOM
2/04 | 0 |  | ALSTOM
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | 0 |  | NOELL
2/04 | L0695 | 2003-12-03 | ANSALDO
2/04 | L0817 | 2003-12-03 | ANSALDO
2/04 | L0660 | 2003-12-03 | ANSALDO
2/04 | L0776 | 2003-12-03 | ANSALDO
3/04 | U0671 | 2003-12-03 | ALSTOM
3/04 | U0672 | 2003-12-03 | ALSTOM
3/04 | U0684 | 2003-12-03 | ALSTOM
3/04 | U0686 | 2003-12-03 | ALSTOM
3/04 | U0854 | 2003-12-03 | NOELL
3/04 | U0758 | 2003-12-03 | NOELL
3/04 | U0754 | 2003-12-03 | NOELL
3/04 | U0667 | 2003-12-03 | NOELL
3/04 | U0734 | 2003-12-03 | NOELL
3/04 | U0702 | 2003-12-03 | NOELL
3/04 | U0740 | 2003-12-03 | NOELL
3/04 | U0836 | 2003-12-03 | NOELL
3/04 | 0 |  | ANSALDO
3/04 | 0 |  | ANSALDO
3/04 | 0 |  | ANSALDO
3/04 | 0 |  | ANSALDO
3/04 | U0838 | 2003-12-03 | ALSTOM
3/04 | U0755 | 2003-12-03 | ALSTOM
3/04 | U0767 | 2003-12-03 | ALSTOM
3/04 | U0662 | 2003-12-03 | ALSTOM
3/04 | L0878 | 2003-12-03 | NOELL
3/04 | L0897 | 2003-12-03 | NOELL
3/04 | L0866 | 2003-12-03 | NOELL
3/04 | L0794 | 2003-12-03 | NOELL
3/04 | L0822 | 2003-12-03 | NOELL
3/04 | L0657 | 2003-12-03 | NOELL
3/04 | L0892 | 2003-12-03 | NOELL
3/04 | L0865 | 2003-12-03 | NOELL
3/04 | 0 |  | ANSALDO
3/04 | 0 |  | ANSALDO
3/04 | 0 |  | ANSALDO
3/04 | 0 |  | ANSALDO
4/04 | 0 |  | ALSTOM
4/04 | 0 |  | ALSTOM
4/04 | 0 |  | ALSTOM
4/04 | 0 |  | ALSTOM
4/04 | U0736 | 2003-12-03 | NOELL
4/04 | U0746 | 2003-12-03 | NOELL
4/04 | U0766 | 2003-12-03 | NOELL
4/04 | U0833 | 2003-12-03 | NOELL
4/04 | U0715 | 2003-12-03 | ANSALDO
4/04 | U0811 | 2003-12-03 | ANSALDO
4/04 | U0812 | 2003-12-03 | ANSALDO
4/04 | U0739 | 2003-12-03 | ANSALDO
4/04 | 0 |  | ALSTOM
4/04 | 0 |  | ALSTOM
4/04 | 0 |  | ALSTOM
4/04 | 0 |  | ALSTOM
4/04 | L0799 | 2003-12-03 | NOELL
4/04 | L0797 | 2003-12-03 | NOELL
4/04 | L0800 | 2003-12-03 | NOELL
4/04 | L0864 | 2003-12-03 | NOELL
4/04 | L0581 | 2003-12-03 | ANSALDO
4/04 | L0872 | 2003-12-03 | ANSALDO
4/04 | L0861 | 2003-12-03 | ANSALDO
4/04 | U0745 | 2003-12-03 | ANSALDO
5/04 | U0769 | 2003-12-12 | ALSTOM
5/04 | U0834 | 2003-12-12 | ALSTOM
5/04 | U0735 | 2003-12-12 | ALSTOM
5/04 | U0677 | 2003-12-12 | ALSTOM
5/04 | U0703 | 2003-12-12 | NOELL
5/04 | U0952 | 2003-12-12 | NOELL
5/04 | U0953 | 2003-12-12 | NOELL
5/04 | U0433 | 2003-12-12 | NOELL
5/04 | 0 |  | ANSALDO
5/04 | 0 |  | ANSALDO
5/04 | 0 |  | ANSALDO
5/04 | 0 |  | ANSALDO
5/04 | U0732 | 2003-12-12 | ALSTOM
5/04 | U0707 | 2003-12-12 | ALSTOM
5/04 | U0696 | 2003-12-12 | ALSTOM
5/04 | U0779 | 2003-12-12 | ALSTOM
5/04 | L0710 | 2003-12-12 | NOELL
5/04 | L0536 | 2003-12-12 | NOELL
5/04 | L0540 | 2003-12-12 | NOELL
5/04 | L0876 | 2003-12-12 | NOELL
5/04 | 0 |  | ANSALDO
5/04 | 0 |  | ANSALDO
5/04 | 0 |  | ANSALDO
5/04 | 0 |  | ANSALDO
6/04 | 0 |  | ALSTOM
6/04 | 0 |  | ALSTOM
6/04 | 0 |  | ALSTOM
6/04 | 0 |  | ALSTOM
6/04 | U0434 | 2003-12-12 | NOELL
6/04 | U0437 | 2003-12-12 | NOELL
6/04 | U0438 | 2003-12-12 | NOELL
6/04 | U0441 | 2003-12-12 | NOELL
6/04 | 0 |  | ANSALDO
6/04 | 0 |  | ANSALDO
6/04 | 0 |  | ANSALDO
6/04 | 0 |  | ANSALDO
6/04 | 0 |  | ALSTOM
6/04 | 0 |  | ALSTOM
6/04 | 0 |  | ALSTOM
6/04 | 0 |  | ALSTOM
6/04 | L0881 | 2003-12-12 | NOELL
6/04 | L0913 | 2003-12-12 | NOELL
6/04 | L0927 | 2003-12-12 | NOELL
6/04 | L0926 | 2003-12-12 | NOELL
6/04 | 0 |  | ANSALDO
6/04 | 0 |  | ANSALDO
6/04 | 0 |  | ANSALDO
6/04 | 0 |  | ANSALDO
7/04 | U0675 | 2003-12-15 | ALSTOM
7/04 | U0718 | 2003-12-15 | ALSTOM
7/04 | U0760 | 2003-12-15 | ALSTOM
7/04 | U0688 | 2003-12-15 | ALSTOM
7/04 | U0443 | 2003-12-15 | NOELL
7/04 | U0444 | 2003-12-15 | NOELL
7/04 | U0446 | 2003-12-15 | NOELL
7/04 | U0447 | 2003-12-15 | NOELL
7/04 | 0 |  | ANSALDO
7/04 | 0 |  | ANSALDO
7/04 | 0 |  | ANSALDO
7/04 | 0 |  | ANSALDO
7/04 | U0653 | 2003-12-15 | ALSTOM
7/04 | U0665 | 2003-12-15 | ALSTOM
7/04 | U0705 | 2003-12-15 | ALSTOM
7/04 | U0693 | 2003-12-15 | ALSTOM
7/04 | L0925 | 2003-12-15 | NOELL
7/04 | L0945 | 2003-12-15 | NOELL
7/04 | L0962 | 2003-12-15 | NOELL
7/04 | L0949 | 2003-12-15 | NOELL
7/04 | 0 |  | ANSALDO
7/04 | 0 |  | ANSALDO
7/04 | 0 |  | ANSALDO
7/04 | 0 |  | ANSALDO
8/04 | 0 |  | ALSTOM
8/04 | 0 |  | ALSTOM
8/04 | 0 |  | ALSTOM
8/04 | 0 |  | ALSTOM
8/04 | 0 |  | NOELL
8/04 | 0 |  | NOELL
8/04 | 0 |  | NOELL
8/04 | 0 |  | NOELL
8/04 | 0 |  | ANSALDO
8/04 | 0 |  | ANSALDO
8/04 | 0 |  | ANSALDO
8/04 | 0 |  | ANSALDO
8/04 | 0 |  | ALSTOM
8/04 | 0 |  | ALSTOM
8/04 | 0 |  | ALSTOM
8/04 | 0 |  | ALSTOM
8/04 | 0 |  | NOELL
8/04 | 0 |  | NOELL
8/04 | 0 |  | NOELL
8/04 | 0 |  | NOELL
8/04 | 0 |  | ANSALDO
8/04 | 0 |  | ANSALDO
8/04 | 0 |  | ANSALDO
8/04 | 0 |  | ANSALDO
9/04 | U0750 | 2004-01-05 | ALSTOM
9/04 | U0678 | 2004-01-05 | ALSTOM
9/04 | U0806 | 2004-01-05 | ALSTOM
9/04 | L0901 | 2004-01-05 | ALSTOM
9/04 | U0808 | 2004-01-05 | NOELL
9/04 | U0733 | 2004-01-05 | NOELL
9/04 | U0737 | 2004-01-05 | NOELL
9/04 | U0764 | 2004-01-05 | NOELL
9/04 | 0 |  | ANSALDO
9/04 | 0 |  | ANSALDO
9/04 | 0 |  | ANSALDO
9/04 | 0 |  | ANSALDO
9/04 | U0725 | 2004-01-05 | ALSTOM
9/04 | U0661 | 2004-01-05 | ALSTOM
9/04 | L0869 | 2004-01-05 | ALSTOM
9/04 | L0791 | 2004-01-05 | ALSTOM
9/04 | L0940 | 2004-01-05 | NOELL
9/04 | L0920 | 2004-01-05 | NOELL
9/04 | L0899 | 2004-01-05 | NOELL
9/04 | L0922 | 2004-01-05 | NOELL
9/04 | 0 |  | ANSALDO
9/04 | 0 |  | ANSALDO
9/04 | 0 |  | ANSALDO
9/04 | 0 |  | ANSALDO
10/04 | 0 |  | ALSTOM
10/04 | 0 |  | ALSTOM
10/04 | 0 |  | ALSTOM
10/04 | 0 |  | ALSTOM
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | U0668 | 2003-12-15 | ANSALDO
10/04 | U0681 | 2003-12-15 | ANSALDO
10/04 | U0835 | 2003-12-15 | ANSALDO
10/04 | U0957 | 2003-12-15 | ANSALDO
10/04 | 0 |  | ALSTOM
10/04 | 0 |  | ALSTOM
10/04 | 0 |  | ALSTOM
10/04 | 0 |  | ALSTOM
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | 0 |  | NOELL
10/04 | L0659 | 2003-12-15 | ANSALDO
10/04 | L0579 | 2003-12-15 | ANSALDO
10/04 | L0654 | 2003-12-15 | ANSALDO
10/04 | L0796 | 2003-12-15 | ANSALDO
11/04 | 0 |  | ALSTOM
11/04 | 0 |  | ALSTOM
11/04 | 0 |  | ALSTOM
11/04 | 0 |  | ALSTOM
11/04 | U0955 | 2004-01-05 | NOELL
11/04 | U0910 | 2004-01-05 | NOELL
11/04 | U0958 | 2004-01-05 | NOELL
11/04 | U0959 | 2004-01-05 | NOELL
11/04 | 0 |  | NOELL
11/04 | 0 |  | NOELL
11/04 | 0 |  | NOELL
11/04 | 0 |  | NOELL
11/04 | 0 |  | ANSALDO
11/04 | 0 |  | ANSALDO
11/04 | 0 |  | ANSALDO
11/04 | 0 |  | ANSALDO
11/04 | 0 |  | ALSTOM
11/04 | 0 |  | ALSTOM
11/04 | 0 |  | ALSTOM
11/04 | 0 |  | ALSTOM
11/04 | L0963 | 2004-01-05 | NOELL
11/04 | L0895 | 2004-01-05 | NOELL
11/04 | L0879 | 2004-01-05 | NOELL
11/04 | L0950 | 2004-01-05 | NOELL
11/04 | 0 |  | NOELL
11/04 | 0 |  | NOELL
11/04 | 0 |  | NOELL
11/04 | 0 |  | NOELL
11/04 | 0 |  | ANSALDO
11/04 | 0 |  | ANSALDO
11/04 | 0 |  | ANSALDO
11/04 | 0 |  | ANSALDO
12/04 | 0 |  | ALSTOM
12/04 | 0 |  | ALSTOM
12/04 | 0 |  | ALSTOM
12/04 | 0 |  | ALSTOM
12/04 | U0832 | 2004-01-05 | NOELL
12/04 | U0954 | 2004-01-05 | NOELL
12/04 | U0805 | 2004-01-05 | NOELL
12/04 | U0831 | 2004-01-05 | NOELL
12/04 | 0 |  | NOELL
12/04 | 0 |  | NOELL
12/04 | 0 |  | NOELL
12/04 | 0 |  | NOELL
12/04 | U0961 | 2003-12-15 | ANSALDO
12/04 | U0924 | 2003-12-15 | ANSALDO
12/04 | U0692 | 2003-12-15 | ANSALDO
12/04 | U0722 | 2003-12-15 | ANSALDO
12/04 | 0 |  | ALSTOM
12/04 | 0 |  | ALSTOM
12/04 | 0 |  | ALSTOM
12/04 | 0 |  | ALSTOM
12/04 | L0888 | 2004-01-05 | NOELL
12/04 | L0900 | 2004-01-05 | NOELL
12/04 | L0885 | 2004-01-05 | NOELL
12/04 | L0877 | 2004-01-05 | NOELL
12/04 | 0 |  | NOELL
12/04 | 0 |  | NOELL
12/04 | 0 |  | NOELL
12/04 | 0 |  | NOELL
12/04 | L0537 | 2003-12-15 | ANSALDO
12/04 | L0538 | 2003-12-15 | ANSALDO
12/04 | L0785 | 2003-12-15 | ANSALDO
12/04 | L0793 | 2003-12-15 | ANSALDO
13/04 | L0871 | 2004-01-19 | ALSTOM
13/04 | U0629 | 2004-01-19 | ALSTOM
13/04 | U0853 | 2004-01-19 | ALSTOM
13/04 | U0842 | 2004-01-19 | ALSTOM
13/04 | U0728 | 2004-01-19 | NOELL
13/04 | U0960 | 2004-01-19 | NOELL
13/04 | U0330 | 2004-01-19 | NOELL
13/04 | U0451 | 2004-01-19 | NOELL
13/04 | 0 |  | NOELL
13/04 | 0 |  | NOELL
13/04 | 0 |  | NOELL
13/04 | 0 |  | NOELL
13/04 | 0 |  | ANSALDO
13/04 | 0 |  | ANSALDO
13/04 | 0 |  | ANSALDO
13/04 | 0 |  | ANSALDO
13/04 | L0787 | 2004-01-19 | ALSTOM
13/04 | L0860 | 2004-01-19 | ALSTOM
13/04 | L0862 | 2004-01-19 | ALSTOM
13/04 | L0912 | 2004-01-19 | ALSTOM
13/04 | L0889 | 2004-01-19 | NOELL
13/04 | L0918 | 2004-01-19 | NOELL
13/04 | L0971 | 2004-01-19 | NOELL
13/04 | L0974 | 2004-01-19 | NOELL
13/04 | 0 |  | NOELL
13/04 | 0 |  | NOELL
13/04 | 0 |  | NOELL
13/04 | 0 |  | NOELL
13/04 | 0 |  | ANSALDO
13/04 | 0 |  | ANSALDO
13/04 | 0 |  | ANSALDO
13/04 | 0 |  | ANSALDO
14/04 | 0 |  | ALSTOM
14/04 | 0 |  | ALSTOM
14/04 | 0 |  | ALSTOM
14/04 | 0 |  | ALSTOM
14/04 | 0 |  | NOELL
14/04 | 0 |  | NOELL
14/04 | 0 |  | NOELL
14/04 | 0 |  | NOELL
14/04 | L0890 | 2004-01-05 | ANSALDO
14/04 | L0870 | 2004-01-05 | ANSALDO
14/04 | L0875 | 2004-01-05 | ANSALDO
14/04 | L0873 | 2004-01-05 | ANSALDO
14/04 | 0 |  | ALSTOM
14/04 | 0 |  | ALSTOM
14/04 | 0 |  | ALSTOM
14/04 | 0 |  | ALSTOM
14/04 | 0 |  | NOELL
14/04 | 0 |  | NOELL
14/04 | 0 |  | NOELL
14/04 | 0 |  | NOELL
14/04 | U0839 | 2004-01-05 | ANSALDO
14/04 | U0851 | 2004-01-05 | ANSALDO
14/04 | U0923 | 2004-01-05 | ANSALDO
14/04 | U0809 | 2004-01-05 | ANSALDO
15/04 | U0837 | 2004-01-19 | ALSTOM
15/04 | U0983 | 2004-01-19 | ALSTOM
15/04 | U1005 | 2004-01-19 | ALSTOM
15/04 | U0978 | 2004-01-19 | ALSTOM
15/04 | U0990 | 2004-01-19 | NOELL
15/04 | U0987 | 2004-01-19 | NOELL
15/04 | U0450 | 2004-01-19 | NOELL
15/04 | U0903 | 2004-01-19 | NOELL
15/04 | 0 |  | ANSALDO
15/04 | 0 |  | ANSALDO
15/04 | 0 |  | ANSALDO
15/04 | 0 |  | ANSALDO
15/04 | L0867 | 2004-01-19 | ALSTOM
15/04 | U0932 | 2004-01-19 | ALSTOM
15/04 | U0840 | 2004-01-19 | ALSTOM
15/04 | L0656 | 2004-01-19 | ALSTOM
15/04 | L0845 | 2004-01-19 | NOELL
15/04 | L0789 | 2004-01-19 | NOELL
15/04 | L0973 | 2004-01-19 | NOELL
15/04 | L0979 | 2004-01-19 | NOELL
15/04 | 0 |  | ANSALDO
15/04 | 0 |  | ANSALDO
15/04 | 0 |  | ANSALDO
15/04 | 0 |  | ANSALDO
16/04 | 0 |  | ALSTOM
16/04 | 0 |  | ALSTOM
16/04 | 0 |  | ALSTOM
16/04 | 0 |  | ALSTOM
16/04 | U0992 | 2004-01-23 | NOELL
16/04 | U0452 | 2004-01-23 | NOELL
16/04 | U0941 | 2004-01-23 | NOELL
16/04 | U0921 | 2004-01-23 | NOELL
16/04 | U0968 | 2004-02-25 | ANSALDO
16/04 | U0989 | 2004-02-25 | ANSALDO
16/04 | U0993 | 2004-02-25 | ANSALDO
16/04 | U0991 | 2004-02-25 | ANSALDO
16/04 | 0 |  | ALSTOM
16/04 | 0 |  | ALSTOM
16/04 | 0 |  | ALSTOM
16/04 | 0 |  | ALSTOM
16/04 | L0625 | 2004-01-23 | NOELL
16/04 | L0981 | 2004-01-23 | NOELL
16/04 | L1004 | 2004-01-23 | NOELL
16/04 | L0967 | 2004-01-23 | NOELL
16/04 | L0641 | 2004-02-25 | ANSALDO
16/04 | L0723 | 2004-02-25 | ANSALDO
16/04 | L0915 | 2004-02-25 | ANSALDO
16/04 | L0724 | 2004-02-25 | ANSALDO
17/04 | U0999 | 2004-01-23 | ALSTOM
17/04 | U0975 | 2004-01-23 | ALSTOM
17/04 | U0985 | 2004-01-23 | ALSTOM
17/04 | U0994 | 2004-01-23 | ALSTOM
17/04 | U0986 | 2004-02-20 | NOELL
17/04 | U1008 | 2004-02-20 | NOELL
17/04 | U1018 | 2004-02-20 | NOELL
17/04 | U0324 | 2004-02-20 | NOELL
17/04 | 0 |  | ANSALDO
17/04 | 0 |  | ANSALDO
17/04 | 0 |  | ANSALDO
17/04 | 0 |  | ANSALDO
17/04 | L0655 | 2004-01-23 | ALSTOM
17/04 | L0640 | 2004-01-23 | ALSTOM
17/04 | L0904 | 2004-01-23 | ALSTOM
17/04 | L0909 | 2004-01-23 | ALSTOM
17/04 | L0634 | 2004-02-20 | NOELL
17/04 | L0887 | 2004-02-20 | NOELL
17/04 | L0880 | 2004-02-20 | NOELL
17/04 | L1052 | 2004-02-20 | NOELL
17/04 | 0 |  | ANSALDO
17/04 | 0 |  | ANSALDO
17/04 | 0 |  | ANSALDO
17/04 | 0 |  | ANSALDO
18/04 | U0966 | 2004-03-08 | ALSTOM
18/04 | U1000 | 2004-03-08 | ALSTOM
18/04 | U0976 | 2004-03-08 | ALSTOM
18/04 | U0977 | 2004-03-08 | ALSTOM
18/04 | 0 |  | NOELL
18/04 | 0 |  | NOELL
18/04 | 0 |  | NOELL
18/04 | 0 |  | NOELL
18/04 | U0995 | 2004-02-20 | ANSALDO
18/04 | U1001 | 2004-02-20 | ANSALDO
18/04 | U1016 | 2004-02-20 | ANSALDO
18/04 | U0972 | 2004-02-20 | ANSALDO
18/04 | L0930 | 2004-03-08 | ALSTOM
18/04 | L0778 | 2004-03-08 | ALSTOM
18/04 | L0907 | 2004-03-08 | ALSTOM
18/04 | L0772 | 2004-03-08 | ALSTOM
18/04 | 0 |  | NOELL
18/04 | 0 |  | NOELL
18/04 | 0 |  | NOELL
18/04 | 0 |  | NOELL
18/04 | L0638 | 2004-02-20 | ANSALDO
18/04 | L0651 | 2004-02-20 | ANSALDO
18/04 | L0630 | 2004-02-20 | ANSALDO
18/04 | L0938 | 2004-02-20 | ANSALDO
19/04 | U0956 | 2004-03-08 | ALSTOM
19/04 | U0982 | 2004-03-08 | ALSTOM
19/04 | U0984 | 2004-03-08 | ALSTOM
19/04 | U0988 | 2004-03-08 | ALSTOM
19/04 | U0448 | 2003-12-15 | NOELL
19/04 | U0449 | 2003-12-15 | NOELL
19/04 | U0756 | 2003-12-15 | NOELL
19/04 | U0757 | 2003-12-15 | NOELL
19/04 | 0 |  | ANSALDO
19/04 | 0 |  | ANSALDO
19/04 | 0 |  | ANSALDO
19/04 | 0 |  | ANSALDO
19/04 | L0637 | 2004-03-08 | ALSTOM
19/04 | L0694 | 2004-03-08 | ALSTOM
19/04 | L0914 | 2004-03-08 | ALSTOM
19/04 | L0818 | 2004-03-08 | ALSTOM
19/04 | L0939 | 2003-12-15 | NOELL
19/04 | L0902 | 2003-12-15 | NOELL
19/04 | L0928 | 2003-12-15 | NOELL
19/04 | L0935 | 2003-12-15 | NOELL
19/04 | 0 |  | ANSALDO
19/04 | 0 |  | ANSALDO
19/04 | 0 |  | ANSALDO
19/04 | 0 |  | ANSALDO
20/04 | 0 |  | ALSTOM
20/04 | 0 |  | ALSTOM
20/04 | 0 |  | ALSTOM
20/04 | 0 |  | ALSTOM
20/04 | U0453 | 2004-03-08 | NOELL
20/04 | U0456 | 2004-03-08 | NOELL
20/04 | U0458 | 2004-03-08 | NOELL
20/04 | U0459 | 2004-03-08 | NOELL
20/04 | U0841 | 2004-03-08 | ANSALDO
20/04 | U0843 | 2004-03-08 | ANSALDO
20/04 | U0849 | 2004-03-08 | ANSALDO
20/04 | U0829 | 2004-03-08 | ANSALDO
20/04 | 0 |  | ALSTOM
20/04 | 0 |  | ALSTOM
20/04 | 0 |  | ALSTOM
20/04 | 0 |  | ALSTOM
20/04 | L1063 | 2004-03-08 | NOELL
20/04 | L1062 | 2004-03-08 | NOELL
20/04 | L1071 | 2004-03-08 | NOELL
20/04 | L1054 | 2004-03-08 | NOELL
20/04 | L1040 | 2004-03-08 | ANSALDO
20/04 | L1045 | 2004-03-08 | ANSALDO
20/04 | L1030 | 2004-03-08 | ANSALDO
20/04 | L1041 | 2004-03-08 | ANSALDO
21/04 | U0996 | 2004-03-24 | ALSTOM
21/04 | U0997 | 2004-03-24 | ALSTOM
21/04 | U0998 | 2004-03-24 | ALSTOM
21/04 | U1002 | 2004-03-24 | ALSTOM
21/04 | U0460 | 2004-03-08 | NOELL
21/04 | U0462 | 2004-03-08 | NOELL
21/04 | U0463 | 2004-03-08 | NOELL
21/04 | U0464 | 2004-03-08 | NOELL
21/04 | U0852 | 2004-03-08 | ANSALDO
21/04 | U0894 | 2004-03-08 | ANSALDO
21/04 | U0917 | 2004-03-08 | ANSALDO
21/04 | U0929 | 2004-03-08 | ANSALDO
21/04 | L0936 | 2004-03-24 | ALSTOM
21/04 | L0856 | 2004-03-24 | ALSTOM
21/04 | L0934 | 2004-03-24 | ALSTOM
21/04 | L0848 | 2004-03-24 | ALSTOM
21/04 | L1072 | 2004-03-08 | NOELL
21/04 | L1057 | 2004-03-08 | NOELL
21/04 | L1068 | 2004-03-08 | NOELL
21/04 | L1070 | 2004-03-08 | NOELL
21/04 | L1039 | 2004-03-08 | ANSALDO
21/04 | L1038 | 2004-03-08 | ANSALDO
21/04 | L1048 | 2004-03-08 | ANSALDO
21/04 | L1033 | 2004-03-08 | ANSALDO
22/04 | U1003 | 2004-03-31 | ALSTOM
22/04 | U1007 | 2004-03-31 | ALSTOM
22/04 | U1009 | 2004-03-31 | ALSTOM
22/04 | U1010 | 2004-03-31 | ALSTOM
22/04 | U0465 | 2004-03-08 | NOELL
22/04 | U0466 | 2004-03-08 | NOELL
22/04 | U0470 | 2004-03-08 | NOELL
22/04 | U0482 | 2004-03-08 | NOELL
22/04 | U0931 | 2004-03-25 | ANSALDO
22/04 | U0937 | 2004-03-25 | ANSALDO
22/04 | U0942 | 2004-03-25 | ANSALDO
22/04 | U1006 | 2004-03-25 | ANSALDO
22/04 | L0847 | 2004-03-31 | ALSTOM
22/04 | L0616 | 2004-03-31 | ALSTOM
22/04 | L0798 | 2004-03-31 | ALSTOM
22/04 | L0944 | 2004-03-31 | ALSTOM
22/04 | L1059 | 2004-03-08 | NOELL
22/04 | L1083 | 2004-03-08 | NOELL
22/04 | L1064 | 2004-03-08 | NOELL
22/04 | L1080 | 2004-03-08 | NOELL
22/04 | L1031 | 2004-03-25 | ANSALDO
22/04 | L1036 | 2004-03-25 | ANSALDO
22/04 | L1032 | 2004-03-25 | ANSALDO
22/04 | L0644 | 2004-03-25 | ANSALDO
23/04 | U1011 | 2004-04-01 | ALSTOM
23/04 | U1012 | 2004-04-01 | ALSTOM
23/04 | U1014 | 2004-04-01 | ALSTOM
23/04 | U1017 | 2004-04-01 | ALSTOM
23/04 | U0484 | 2004-03-25 | NOELL
23/04 | U0485 | 2004-03-25 | NOELL
23/04 | U0486 | 2004-03-25 | NOELL
23/04 | U0487 | 2004-03-25 | NOELL
23/04 | 0 |  | ANSALDO
23/04 | 0 |  | ANSALDO
23/04 | 0 |  | ANSALDO
23/04 | 0 |  | ANSALDO
23/04 | L0855 | 2004-04-01 | ALSTOM
23/04 | L0827 | 2004-04-01 | ALSTOM
23/04 | L0884 | 2004-04-01 | ALSTOM
23/04 | L0850 | 2004-04-01 | ALSTOM
23/04 | L1076 | 2004-03-25 | NOELL
23/04 | L1075 | 2004-03-25 | NOELL
23/04 | L1079 | 2004-03-25 | NOELL
23/04 | L1082 | 2004-03-25 | NOELL
23/04 | 0 |  | ANSALDO
23/04 | 0 |  | ANSALDO
23/04 | 0 |  | ANSALDO
23/04 | 0 |  | ANSALDO
24/04 | 0 |  | ALSTOM
24/04 | 0 |  | ALSTOM
24/04 | 0 |  | ALSTOM
24/04 | 0 |  | ALSTOM
24/04 | U0488 | 2004-03-25 | NOELL
24/04 | U0491 | 2004-03-25 | NOELL
24/04 | U0494 | 2004-03-25 | NOELL
24/04 | U0499 | 2004-03-25 | NOELL
24/04 | U1015 | 2004-04-01 | ANSALDO
24/04 | U1029 | 2004-04-01 | ANSALDO
24/04 | U1074 | 2004-04-01 | ANSALDO
24/04 | U1087 | 2004-04-01 | ANSALDO
24/04 | 0 |  | ALSTOM
24/04 | 0 |  | ALSTOM
24/04 | 0 |  | ALSTOM
24/04 | 0 |  | ALSTOM
24/04 | L1078 | 2004-03-25 | NOELL
24/04 | L1091 | 2004-03-25 | NOELL
24/04 | L1077 | 2004-03-25 | NOELL
24/04 | L1102 | 2004-03-25 | NOELL
24/04 | L0801 | 2004-04-01 | ANSALDO
24/04 | L0906 | 2004-04-01 | ANSALDO
24/04 | L1035 | 2004-04-01 | ANSALDO
24/04 | L1044 | 2004-04-01 | ANSALDO
25/04 | 0 |  | ALSTOM
25/04 | 0 |  | ALSTOM
25/04 | 0 |  | ALSTOM
25/04 | 0 |  | ALSTOM
25/04 | U1194 | 2004-05-12 | NOELL
25/04 | U0505 | 2004-05-12 | NOELL
25/04 | U0506 | 2004-05-12 | NOELL
25/04 | U0507 | 2004-05-12 | NOELL
25/04 | 0 |  | ANSALDO
25/04 | 0 |  | ANSALDO
25/04 | 0 |  | ANSALDO
25/04 | 0 |  | ANSALDO
25/04 | 0 |  | ALSTOM
25/04 | 0 |  | ALSTOM
25/04 | 0 |  | ALSTOM
25/04 | 0 |  | ALSTOM
25/04 | L1100 | 2004-05-12 | NOELL
25/04 | L1302 | 2004-05-12 | NOELL
25/04 | L1108 | 2004-05-12 | NOELL
25/04 | L1094 | 2004-05-12 | NOELL
25/04 | 0 |  | ANSALDO
25/04 | 0 |  | ANSALDO
25/04 | 0 |  | ANSALDO
25/04 | 0 |  | ANSALDO
26/04 | U1019 | 2004-04-01 | ALSTOM
26/04 | U1020 | 2004-04-01 | ALSTOM
26/04 | U1023 | 2004-04-01 | ALSTOM
26/04 | U1024 | 2004-04-01 | ALSTOM
26/04 | U0508 | 2004-03-31 | NOELL
26/04 | U0509 | 2004-03-31 | NOELL
26/04 | U0965 | 2004-03-31 | NOELL
26/04 | U1026 | 2004-03-31 | NOELL
26/04 | U1131 | 2004-04-01 | ANSALDO
26/04 | U1132 | 2004-04-01 | ANSALDO
26/04 | U1133 | 2004-04-01 | ANSALDO
26/04 | U1134 | 2004-04-01 | ANSALDO
26/04 | L0905 | 2004-04-01 | ALSTOM
26/04 | L0781 | 2004-04-01 | ALSTOM
26/04 | L0951 | 2004-04-01 | ALSTOM
26/04 | L0782 | 2004-04-01 | ALSTOM
26/04 | L1099 | 2004-03-31 | NOELL
26/04 | L1093 | 2004-03-31 | NOELL
26/04 | L1069 | 2004-03-31 | NOELL
26/04 | L0821 | 2004-03-31 | NOELL
26/04 | L1056 | 2004-04-01 | ANSALDO
26/04 | L1111 | 2004-04-01 | ANSALDO
26/04 | L1086 | 2004-04-01 | ANSALDO
26/04 | L1112 | 2004-04-01 | ANSALDO
27/04 | U1025 | 2004-04-01 | ALSTOM
27/04 | U1027 | 2004-04-01 | ALSTOM
27/04 | U1028 | 2004-04-01 | ALSTOM
27/04 | U1140 | 2004-04-01 | ALSTOM
27/04 | U1013 | 2004-04-01 | NOELL
27/04 | U1021 | 2004-04-01 | NOELL
27/04 | U1022 | 2004-04-01 | NOELL
27/04 | U1146 | 2004-04-01 | NOELL
27/04 | 0 |  | ANSALDO
27/04 | 0 |  | ANSALDO
27/04 | 0 |  | ANSALDO
27/04 | 0 |  | ANSALDO
27/04 | L0773 | 2004-04-01 | ALSTOM
27/04 | L0911 | 2004-04-01 | ALSTOM
27/04 | L0844 | 2004-04-01 | ALSTOM
27/04 | L0947 | 2004-04-01 | ALSTOM
27/04 | L0980 | 2004-04-01 | NOELL
27/04 | L0826 | 2004-04-01 | NOELL
27/04 | L0964 | 2004-04-01 | NOELL
27/04 | L1125 | 2004-04-01 | NOELL
27/04 | 0 |  | ANSALDO
27/04 | 0 |  | ANSALDO
27/04 | 0 |  | ANSALDO
27/04 | 0 |  | ANSALDO
28/04 | 0 |  | ALSTOM
28/04 | 0 |  | ALSTOM
28/04 | 0 |  | ALSTOM
28/04 | 0 |  | ALSTOM
28/04 | U1143 | 2004-04-06 | NOELL
28/04 | U1147 | 2004-04-06 | NOELL
28/04 | U1151 | 2004-04-06 | NOELL
28/04 | U1065 | 2004-04-06 | NOELL
28/04 | U1135 | 2004-04-01 | ANSALDO
28/04 | U1136 | 2004-04-01 | ANSALDO
28/04 | U1137 | 2004-04-01 | ANSALDO
28/04 | U1138 | 2004-04-01 | ANSALDO
28/04 | 0 |  | ALSTOM
28/04 | 0 |  | ALSTOM
28/04 | 0 |  | ALSTOM
28/04 | 0 |  | ALSTOM
28/04 | L1114 | 2004-04-06 | NOELL
28/04 | L1117 | 2004-04-06 | NOELL
28/04 | L0970 | 2004-04-06 | NOELL
28/04 | L1043 | 2004-04-06 | NOELL
28/04 | L1058 | 2004-04-01 | ANSALDO
28/04 | L1092 | 2004-04-01 | ANSALDO
28/04 | L1127 | 2004-04-01 | ANSALDO
28/04 | L1049 | 2004-04-01 | ANSALDO
29/04 | U0382 | 2004-04-20 | ALSTOM
29/04 | U1178 | 2004-04-20 | ALSTOM
29/04 | U1176 | 2004-04-20 | ALSTOM
29/04 | U1160 | 2004-04-20 | ALSTOM
29/04 | U1180 | 2004-06-08 | NOELL
29/04 | U1181 | 2004-06-08 | NOELL
29/04 | U1179 | 2004-06-08 | NOELL
29/04 | U1183 | 2004-06-08 | NOELL
29/04 | U1139 | 2004-04-02 | ANSALDO
29/04 | U1141 | 2004-04-02 | ANSALDO
29/04 | U1142 | 2004-04-02 | ANSALDO
29/04 | U1144 | 2004-04-02 | ANSALDO
29/04 | L0948 | 2004-04-20 | ALSTOM
29/04 | L0792 | 2004-04-20 | ALSTOM
29/04 | L0828 | 2004-04-20 | ALSTOM
29/04 | L0846 | 2004-04-20 | ALSTOM
29/04 | L1118 | 2004-06-08 | NOELL
29/04 | L1110 | 2004-06-08 | NOELL
29/04 | L1128 | 2004-06-08 | NOELL
29/04 | L1105 | 2004-06-08 | NOELL
29/04 | L1098 | 2004-04-02 | ANSALDO
29/04 | L1095 | 2004-04-02 | ANSALDO
29/04 | L1121 | 2004-04-02 | ANSALDO
29/04 | L1067 | 2004-04-02 | ANSALDO
30/04 | U1167 | 2004-04-06 | ALSTOM
30/04 | U1153 | 2004-04-06 | ALSTOM
30/04 | U1162 | 2004-04-06 | ALSTOM
30/04 | U1168 | 2004-04-06 | ALSTOM
30/04 | U1173 | 2004-04-02 | NOELL
30/04 | U1169 | 2004-04-02 | NOELL
30/04 | U1170 | 2004-04-02 | NOELL
30/04 | U1158 | 2004-04-02 | NOELL
30/04 | U1145 | 2004-04-07 | ANSALDO
30/04 | U1148 | 2004-04-07 | ANSALDO
30/04 | U1152 | 2004-04-07 | ANSALDO
30/04 | U1163 | 2004-04-07 | ANSALDO
30/04 | L0893 | 2004-04-06 | ALSTOM
30/04 | L0946 | 2004-04-06 | ALSTOM
30/04 | L0969 | 2004-04-06 | ALSTOM
30/04 | L1060 | 2004-04-06 | ALSTOM
30/04 | L1051 | 2004-04-02 | NOELL
30/04 | L1066 | 2004-04-02 | NOELL
30/04 | L1085 | 2004-04-02 | NOELL
30/04 | L1088 | 2004-04-02 | NOELL
30/04 | L1096 | 2004-04-07 | ANSALDO
30/04 | L1130 | 2004-04-07 | ANSALDO
30/04 | L0804 | 2004-04-07 | ANSALDO
30/04 | L1119 | 2004-04-07 | ANSALDO
31/04 | 0 |  | ALSTOM
31/04 | 0 |  | ALSTOM
31/04 | 0 |  | ALSTOM
31/04 | 0 |  | ALSTOM
31/04 | U1166 | 2004-04-08 | NOELL
31/04 | U1199 | 2004-04-08 | NOELL
31/04 | U1198 | 2004-04-08 | NOELL
31/04 | U1174 | 2004-04-08 | NOELL
31/04 | 0 |  | ANSALDO
31/04 | 0 |  | ANSALDO
31/04 | 0 |  | ANSALDO
31/04 | 0 |  | ANSALDO
31/04 | 0 |  | ALSTOM
31/04 | 0 |  | ALSTOM
31/04 | 0 |  | ALSTOM
31/04 | 0 |  | ALSTOM
31/04 | L1089 | 2004-04-08 | NOELL
31/04 | L1090 | 2004-04-08 | NOELL
31/04 | L1101 | 2004-04-08 | NOELL
31/04 | L1103 | 2004-04-08 | NOELL
31/04 | 0 |  | ANSALDO
31/04 | 0 |  | ANSALDO
31/04 | 0 |  | ANSALDO
31/04 | 0 |  | ANSALDO
32/04 | 0 |  | ALSTOM
32/04 | 0 |  | ALSTOM
32/04 | 0 |  | ALSTOM
32/04 | 0 |  | ALSTOM
32/04 | U1149 | 2004-04-08 | NOELL
32/04 | U1150 | 2004-04-08 | NOELL
32/04 | U1159 | 2004-04-08 | NOELL
32/04 | U1172 | 2004-04-08 | NOELL
32/04 | 0 |  | ANSALDO
32/04 | 0 |  | ANSALDO
32/04 | 0 |  | ANSALDO
32/04 | 0 |  | ANSALDO
32/04 | 0 |  | ALSTOM
32/04 | 0 |  | ALSTOM
32/04 | 0 |  | ALSTOM
32/04 | 0 |  | ALSTOM
32/04 | L1081 | 2004-04-08 | NOELL
32/04 | L1107 | 2004-04-08 | NOELL
32/04 | L1123 | 2004-04-08 | NOELL
32/04 | L1113 | 2004-04-08 | NOELL
32/04 | 0 |  | ANSALDO
32/04 | 0 |  | ANSALDO
32/04 | 0 |  | ANSALDO
32/04 | 0 |  | ANSALDO
33/04 | U1182 | 2004-04-07 | ALSTOM
33/04 | U1161 | 2004-04-07 | ALSTOM
33/04 | U1175 | 2004-04-07 | ALSTOM
33/04 | U1157 | 2004-04-07 | ALSTOM
33/04 | U1184 | 2004-04-08 | NOELL
33/04 | U1191 | 2004-04-08 | NOELL
33/04 | U1177 | 2004-04-08 | NOELL
33/04 | U1165 | 2004-04-08 | NOELL
33/04 | 0 |  | ANSALDO
33/04 | 0 |  | ANSALDO
33/04 | 0 |  | ANSALDO
33/04 | 0 |  | ANSALDO
33/04 | L0908 | 2004-04-07 | ALSTOM
33/04 | L0916 | 2004-04-07 | ALSTOM
33/04 | L0933 | 2004-04-07 | ALSTOM
33/04 | L0943 | 2004-04-07 | ALSTOM
33/04 | L1050 | 2004-04-08 | NOELL
33/04 | L1124 | 2004-04-08 | NOELL
33/04 | L1126 | 2004-04-08 | NOELL
33/04 | L1106 | 2004-04-08 | NOELL
33/04 | 0 |  | ANSALDO
33/04 | 0 |  | ANSALDO
33/04 | 0 |  | ANSALDO
33/04 | 0 |  | ANSALDO
34/04 | 0 |  | ALSTOM
34/04 | 0 |  | ALSTOM
34/04 | 0 |  | ALSTOM
34/04 | 0 |  | ALSTOM
34/04 | U0240 | 2004-05-19 | NOELL
34/04 | U0248 | 2004-05-19 | NOELL
34/04 | U1154 | 2004-05-19 | NOELL
34/04 | U1186 | 2004-05-19 | NOELL
34/04 | U0265 | 2004-05-19 | ANSALDO
34/04 | U0495 | 2004-05-19 | ANSALDO
34/04 | U1156 | 2004-05-19 | ANSALDO
34/04 | U1185 | 2004-05-19 | ANSALDO
34/04 | 0 |  | ALSTOM
34/04 | 0 |  | ALSTOM
34/04 | 0 |  | ALSTOM
34/04 | 0 |  | ALSTOM
34/04 | L0258 | 2004-05-19 | NOELL
34/04 | L0259 | 2004-05-19 | NOELL
34/04 | L1129 | 2004-05-19 | NOELL
34/04 | L1223 | 2004-05-19 | NOELL
34/04 | L1215 | 2004-05-19 | ANSALDO
34/04 | L1214 | 2004-05-19 | ANSALDO
34/04 | L1272 | 2004-05-19 | ANSALDO
34/04 | L1211 | 2004-05-19 | ANSALDO
35/04 | U1155 | 2004-04-14 | ALSTOM
35/04 | U1188 | 2004-04-14 | ALSTOM
35/04 | U1200 | 2004-04-14 | ALSTOM
35/04 | U1171 | 2004-04-14 | ALSTOM
35/04 | U0245 | 2004-06-16 | NOELL
35/04 | U1190 | 2004-06-16 | NOELL
35/04 | U1193 | 2004-06-16 | NOELL
35/04 | U1195 | 2004-06-16 | NOELL
35/04 | 0 |  | ANSALDO
35/04 | 0 |  | ANSALDO
35/04 | 0 |  | ANSALDO
35/04 | 0 |  | ANSALDO
35/04 | L0919 | 2004-04-14 | ALSTOM
35/04 | L1061 | 2004-04-14 | ALSTOM
35/04 | L1115 | 2004-04-14 | ALSTOM
35/04 | L1116 | 2004-04-14 | ALSTOM
35/04 | L1271 | 2004-06-16 | NOELL
35/04 | L1120 | 2004-06-16 | NOELL
35/04 | L1273 | 2004-06-16 | NOELL
35/04 | L1283 | 2004-06-16 | NOELL
35/04 | 0 |  | ANSALDO
35/04 | 0 |  | ANSALDO
35/04 | 0 |  | ANSALDO
35/04 | 0 |  | ANSALDO
36/04 | 0 |  | ALSTOM
36/04 | 0 |  | ALSTOM
36/04 | 0 |  | ALSTOM
36/04 | 0 |  | ALSTOM
36/04 | U1196 | 2004-06-15 | NOELL
36/04 | U1197 | 2004-06-15 | NOELL
36/04 | U1205 | 2004-06-15 | NOELL
36/04 | U1227 | 2004-06-15 | NOELL
36/04 | U1187 | 2004-06-16 | ANSALDO
36/04 | U1192 | 2004-06-16 | ANSALDO
36/04 | U1201 | 2004-06-16 | ANSALDO
36/04 | U1202 | 2004-06-16 | ANSALDO
36/04 | 0 |  | ALSTOM
36/04 | 0 |  | ALSTOM
36/04 | 0 |  | ALSTOM
36/04 | 0 |  | ALSTOM
36/04 | L1269 | 2004-06-15 | NOELL
36/04 | L1097 | 2004-06-15 | NOELL
36/04 | L1213 | 2004-06-15 | NOELL
36/04 | L1278 | 2004-06-15 | NOELL
36/04 | L1084 | 2004-06-16 | ANSALDO
36/04 | L1276 | 2004-06-16 | ANSALDO
36/04 | L1122 | 2004-06-16 | ANSALDO
36/04 | L1218 | 2004-06-16 | ANSALDO
37/04 | U1164 | 2004-08-09 | ALSTOM
37/04 | U1380 | 2004-08-09 | ALSTOM
37/04 | U1207 | 2004-08-09 | ALSTOM
37/04 | U1216 | 2004-08-09 | ALSTOM
37/04 | U1230 | 2004-08-09 | NOELL
37/04 | U1235 | 2004-08-09 | NOELL
37/04 | U1346 | 2004-08-09 | NOELL
37/04 | U1241 | 2004-08-09 | NOELL
37/04 | U0233 | 2004-08-09 | NOELL
37/04 | 0 |  | ANSALDO
37/04 | 0 |  | ANSALDO
37/04 | 0 |  | ANSALDO
37/04 | 0 |  | ANSALDO
37/04 | L1073 | 2004-08-09 | ALSTOM
37/04 | L1328 | 2004-08-09 | ALSTOM
37/04 | L1047 | 2004-08-09 | ALSTOM
37/04 | L1042 | 2004-08-09 | ALSTOM
37/04 | L1281 | 2004-08-09 | NOELL
37/04 | L1294 | 2004-08-09 | NOELL
37/04 | L1360 | 2004-08-09 | NOELL
37/04 | L0886 | 2004-08-09 | NOELL
37/04 | U1189 | 2004-08-09 | NOELL
37/04 | 0 |  | ANSALDO
37/04 | 0 |  | ANSALDO
37/04 | 0 |  | ANSALDO
37/04 | 0 |  | ANSALDO
38/04 | 0 |  | ALSTOM
38/04 | 0 |  | ALSTOM
38/04 | 0 |  | ALSTOM
38/04 | 0 |  | ALSTOM
38/04 | U1244 | 2004-06-11 | NOELL
38/04 | U1245 | 2004-06-11 | NOELL
38/04 | U1247 | 2004-06-11 | NOELL
38/04 | U1248 | 2004-06-11 | NOELL
38/04 | U1203 | 2004-06-11 | ANSALDO
38/04 | U1204 | 2004-06-11 | ANSALDO
38/04 | U1228 | 2004-06-11 | ANSALDO
38/04 | U1246 | 2004-06-11 | ANSALDO
38/04 | 0 |  | ALSTOM
38/04 | 0 |  | ALSTOM
38/04 | 0 |  | ALSTOM
38/04 | 0 |  | ALSTOM
38/04 | L1268 | 2004-06-11 | NOELL
38/04 | L1279 | 2004-06-11 | NOELL
38/04 | L1275 | 2004-06-11 | NOELL
38/04 | L1284 | 2004-06-11 | NOELL
38/04 | L1217 | 2004-06-11 | ANSALDO
38/04 | L1210 | 2004-06-11 | ANSALDO
38/04 | L1225 | 2004-06-11 | ANSALDO
38/04 | L1224 | 2004-06-11 | ANSALDO
39/04 | U1219 | 2004-06-10 | ALSTOM
39/04 | U1220 | 2004-06-10 | ALSTOM
39/04 | U1221 | 2004-06-10 | ALSTOM
39/04 | U1226 | 2004-06-10 | ALSTOM
39/04 | U1249 | 2004-06-11 | NOELL
39/04 | U1251 | 2004-06-11 | NOELL
39/04 | U1253 | 2004-06-11 | NOELL
39/04 | U1263 | 2004-06-11 | NOELL
39/04 | 0 |  | ANSALDO
39/04 | 0 |  | ANSALDO
39/04 | 0 |  | ANSALDO
39/04 | 0 |  | ANSALDO
39/04 | L1046 | 2004-06-10 | ALSTOM
39/04 | L1034 | 2004-06-10 | ALSTOM
39/04 | L1053 | 2004-06-10 | ALSTOM
39/04 | L1282 | 2004-06-10 | ALSTOM
39/04 | L1288 | 2004-06-11 | NOELL
39/04 | L1297 | 2004-06-11 | NOELL
39/04 | L1312 | 2004-06-11 | NOELL
39/04 | L1290 | 2004-06-11 | NOELL
39/04 | 0 |  | ANSALDO
39/04 | 0 |  | ANSALDO
39/04 | 0 |  | ANSALDO
39/04 | 0 |  | ANSALDO
40/04 | 0 |  | ALSTOM
40/04 | 0 |  | ALSTOM
40/04 | 0 |  | ALSTOM
40/04 | 0 |  | ALSTOM
40/04 | U0504 | 2004-07-08 | NOELL
40/04 | U1229 | 2004-07-08 | NOELL
40/04 | U1231 | 2004-07-08 | NOELL
40/04 | U1233 | 2004-07-08 | NOELL
40/04 | U1252 | 2004-06-11 | ANSALDO
40/04 | U1256 | 2004-06-11 | ANSALDO
40/04 | U1261 | 2004-06-11 | ANSALDO
40/04 | U1264 | 2004-06-11 | ANSALDO
40/04 | 0 |  | ALSTOM
40/04 | 0 |  | ALSTOM
40/04 | 0 |  | ALSTOM
40/04 | 0 |  | ALSTOM
40/04 | L1306 | 2004-07-08 | NOELL
40/04 | L1314 | 2004-07-08 | NOELL
40/04 | L1337 | 2004-07-08 | NOELL
40/04 | L1305 | 2004-07-08 | NOELL
40/04 | L1291 | 2004-06-11 | ANSALDO
40/04 | L1292 | 2004-06-11 | ANSALDO
40/04 | L1277 | 2004-06-11 | ANSALDO
40/04 | L1293 | 2004-06-11 | ANSALDO
41/04 | U1232 | 2004-07-13 | ALSTOM
41/04 | U1234 | 2004-07-13 | ALSTOM
41/04 | U1243 | 2004-07-13 | ALSTOM
41/04 | U1259 | 2004-07-13 | ALSTOM
41/04 | U1238 | 2004-07-13 | NOELL
41/04 | U1239 | 2004-07-13 | NOELL
41/04 | U1240 | 2004-07-13 | NOELL
41/04 | U1242 | 2004-07-13 | NOELL
41/04 | U1250 | 2004-07-13 | ANSALDO
41/04 | U1254 | 2004-07-13 | ANSALDO
41/04 | U1298 | 2004-07-13 | ANSALDO
41/04 | U1262 | 2004-07-13 | ANSALDO
41/04 | L1295 | 2004-07-13 | ALSTOM
41/04 | L1287 | 2004-07-13 | ALSTOM
41/04 | L1285 | 2004-07-13 | ALSTOM
41/04 | L1296 | 2004-07-13 | ALSTOM
41/04 | L1310 | 2004-07-13 | NOELL
41/04 | L1333 | 2004-07-13 | NOELL
41/04 | L1307 | 2004-07-13 | NOELL
41/04 | L1335 | 2004-07-13 | NOELL
41/04 | L1339 | 2004-07-13 | ANSALDO
41/04 | L1341 | 2004-07-13 | ANSALDO
41/04 | L1300 | 2004-07-13 | ANSALDO
41/04 | L1357 | 2004-07-13 | ANSALDO
42/04 | U1208 | 2004-07-13 | ALSTOM
42/04 | U1212 | 2004-07-13 | ALSTOM
42/04 | U1222 | 2004-07-13 | ALSTOM
42/04 | U1237 | 2004-07-13 | ALSTOM
42/04 | U1255 | 2004-07-13 | NOELL
42/04 | U1257 | 2004-07-13 | NOELL
42/04 | U1258 | 2004-07-13 | NOELL
42/04 | U1260 | 2004-07-13 | NOELL
42/04 | U1265 | 2004-07-20 | ANSALDO
42/04 | U1267 | 2004-07-20 | ANSALDO
42/04 | U1270 | 2004-07-20 | ANSALDO
42/04 | U1286 | 2004-07-20 | ANSALDO
42/04 | L1321 | 2004-07-13 | ALSTOM
42/04 | L1361 | 2004-07-13 | ALSTOM
42/04 | L1322 | 2004-07-13 | ALSTOM
42/04 | L1371 | 2004-07-13 | ALSTOM
42/04 | L1309 | 2004-07-13 | NOELL
42/04 | L1336 | 2004-07-13 | NOELL
42/04 | L1301 | 2004-07-13 | NOELL
42/04 | L1315 | 2004-07-13 | NOELL
42/04 | L1289 | 2004-07-20 | ANSALDO
42/04 | L1338 | 2004-07-20 | ANSALDO
42/04 | L1311 | 2004-07-20 | ANSALDO
42/04 | L1350 | 2004-07-20 | ANSALDO
43/04 | U1353 | 2004-08-11 | ALSTOM
43/04 | U1381 | 2004-08-11 | ALSTOM
43/04 | U1383 | 2004-08-11 | ALSTOM
43/04 | U1404 | 2004-08-11 | ALSTOM
43/04 | U1266 | 2004-07-20 | NOELL
43/04 | U1326 | 2004-07-20 | NOELL
43/04 | U1327 | 2004-07-20 | NOELL
43/04 | U1334 | 2004-07-20 | NOELL
43/04 | 0 |  | ANSALDO
43/04 | 0 |  | ANSALDO
43/04 | 0 |  | ANSALDO
43/04 | 0 |  | ANSALDO
43/04 | L1344 | 2004-08-11 | ALSTOM
43/04 | L1354 | 2004-08-11 | ALSTOM
43/04 | L1385 | 2004-08-11 | ALSTOM
43/04 | L1347 | 2004-08-11 | ALSTOM
43/04 | L1317 | 2004-07-20 | NOELL
43/04 | L1313 | 2004-07-20 | NOELL
43/04 | L1340 | 2004-07-20 | NOELL
43/04 | L1299 | 2004-07-20 | NOELL
43/04 | 0 |  | ANSALDO
43/04 | 0 |  | ANSALDO
43/04 | 0 |  | ANSALDO
43/04 | 0 |  | ANSALDO
44/04 | 0 |  | ALSTOM
44/04 | 0 |  | ALSTOM
44/04 | 0 |  | ALSTOM
44/04 | 0 |  | ALSTOM
44/04 | U1411 | 2004-08-09 | NOELL
44/04 | U1412 | 2004-08-09 | NOELL
44/04 | U1414 | 2004-08-09 | NOELL
44/04 | U1415 | 2004-08-09 | NOELL
44/04 | U1405 | 2004-08-12 | ANSALDO
44/04 | U1413 | 2004-08-12 | ANSALDO
44/04 | U1417 | 2004-08-12 | ANSALDO
44/04 | U1418 | 2004-08-12 | ANSALDO
44/04 | 0 |  | ALSTOM
44/04 | 0 |  | ALSTOM
44/04 | 0 |  | ALSTOM
44/04 | 0 |  | ALSTOM
44/04 | L1351 | 2004-08-09 | NOELL
44/04 | L1374 | 2004-08-09 | NOELL
44/04 | L1320 | 2004-08-09 | NOELL
44/04 | L1358 | 2004-08-09 | NOELL
44/04 | L1392 | 2004-08-12 | ANSALDO
44/04 | L1362 | 2004-08-12 | ANSALDO
44/04 | L1377 | 2004-08-12 | ANSALDO
44/04 | L1355 | 2004-08-12 | ANSALDO
45/04 | U1420 | 2004-08-12 | ALSTOM
45/04 | U1421 | 2004-08-12 | ALSTOM
45/04 | U1422 | 2004-08-12 | ALSTOM
45/04 | U1425 | 2004-08-12 | ALSTOM
45/04 | U1416 | 2004-08-11 | NOELL
45/04 | U1419 | 2004-08-11 | NOELL
45/04 | U1423 | 2004-08-11 | NOELL
45/04 | U1424 | 2004-08-11 | NOELL
45/04 | 0 |  | ANSALDO
45/04 | 0 |  | ANSALDO
45/04 | 0 |  | ANSALDO
45/04 | 0 |  | ANSALDO
45/04 | L1352 | 2004-08-12 | ALSTOM
45/04 | L1365 | 2004-08-12 | ALSTOM
45/04 | L1397 | 2004-08-12 | ALSTOM
45/04 | L1274 | 2004-08-12 | ALSTOM
45/04 | L1348 | 2004-08-11 | NOELL
45/04 | L1330 | 2004-08-11 | NOELL
45/04 | L1363 | 2004-08-11 | NOELL
45/04 | L1318 | 2004-08-11 | NOELL
45/04 | 0 |  | ANSALDO
45/04 | 0 |  | ANSALDO
45/04 | 0 |  | ANSALDO
45/04 | 0 |  | ANSALDO
46/04 | U1458 | 2004-08-17 | ALSTOM
46/04 | U1459 | 2004-08-17 | ALSTOM
46/04 | U1466 | 2004-08-17 | ALSTOM
46/04 | U1468 | 2004-08-17 | ALSTOM
46/04 | U1426 | 2004-08-11 | NOELL
46/04 | U1427 | 2004-08-11 | NOELL
46/04 | U1428 | 2004-08-11 | NOELL
46/04 | U1429 | 2004-08-11 | NOELL
46/04 | U1436 | 2004-08-13 | ANSALDO
46/04 | U1441 | 2004-08-13 | ANSALDO
46/04 | U1452 | 2004-08-13 | ANSALDO
46/04 | U1454 | 2004-08-13 | ANSALDO
46/04 | L1280 | 2004-08-17 | ALSTOM
46/04 | L1378 | 2004-08-17 | ALSTOM
46/04 | L1369 | 2004-08-17 | ALSTOM
46/04 | L1367 | 2004-08-17 | ALSTOM
46/04 | L1319 | 2004-08-11 | NOELL
46/04 | L1303 | 2004-08-11 | NOELL
46/04 | L1304 | 2004-08-11 | NOELL
46/04 | L1368 | 2004-08-11 | NOELL
46/04 | L1375 | 2004-08-13 | ANSALDO
46/04 | L1391 | 2004-08-13 | ANSALDO
46/04 | L1406 | 2004-08-13 | ANSALDO
46/04 | L1395 | 2004-08-13 | ANSALDO
47/04 | U1480 | 2004-08-18 | ALSTOM
47/04 | U1481 | 2004-08-18 | ALSTOM
47/04 | U1482 | 2004-08-18 | ALSTOM
47/04 | U1483 | 2004-08-18 | ALSTOM
47/04 | U1430 | 2004-08-18 | NOELL
47/04 | U1431 | 2004-08-18 | NOELL
47/04 | U1433 | 2004-08-18 | NOELL
47/04 | U1434 | 2004-08-18 | NOELL
47/04 | 0 |  | ANSALDO
47/04 | 0 |  | ANSALDO
47/04 | 0 |  | ANSALDO
47/04 | 0 |  | ANSALDO
47/04 | L1393 | 2004-08-18 | ALSTOM
47/04 | L1551 | 2004-08-18 | ALSTOM
47/04 | L1410 | 2004-08-18 | ALSTOM
47/04 | L1364 | 2004-08-18 | ALSTOM
47/04 | L1308 | 2004-08-18 | NOELL
47/04 | L1349 | 2004-08-18 | NOELL
47/04 | L1388 | 2004-08-18 | NOELL
47/04 | L1379 | 2004-08-18 | NOELL
47/04 | 0 |  | ANSALDO
47/04 | 0 |  | ANSALDO
47/04 | 0 |  | ANSALDO
47/04 | 0 |  | ANSALDO
48/04 | 0 |  | ALSTOM
48/04 | 0 |  | ALSTOM
48/04 | 0 |  | ALSTOM
48/04 | 0 |  | ALSTOM
48/04 | U1435 | 2004-08-18 | NOELL
48/04 | U1437 | 2004-08-18 | NOELL
48/04 | U1438 | 2004-08-18 | NOELL
48/04 | U1439 | 2004-08-18 | NOELL
48/04 | U1470 | 2004-08-18 | ANSALDO
48/04 | U1475 | 2004-08-18 | ANSALDO
48/04 | U1478 | 2004-08-18 | ANSALDO
48/04 | U1479 | 2004-08-18 | ANSALDO
48/04 | 0 |  | ALSTOM
48/04 | 0 |  | ALSTOM
48/04 | 0 |  | ALSTOM
48/04 | 0 |  | ALSTOM
48/04 | L1370 | 2004-08-18 | NOELL
48/04 | L1403 | 2004-08-18 | NOELL
48/04 | L1373 | 2004-08-18 | NOELL
48/04 | L1372 | 2004-08-18 | NOELL
48/04 | L1546 | 2004-08-18 | ANSALDO
48/04 | L1408 | 2004-08-18 | ANSALDO
48/04 | L1037 | 2004-08-18 | ANSALDO
48/04 | L1386 | 2004-08-18 | ANSALDO
49/04 | U1489 | 2004-08-19 | ALSTOM
49/04 | U1491 | 2004-08-19 | ALSTOM
49/04 | U1492 | 2004-08-19 | ALSTOM
49/04 | U1494 | 2004-08-19 | ALSTOM
49/04 | U1440 | 2004-08-19 | NOELL
49/04 | U1442 | 2004-08-19 | NOELL
49/04 | U1443 | 2004-08-19 | NOELL
49/04 | U1444 | 2004-08-19 | NOELL
49/04 | U1484 | 2004-08-18 | ANSALDO
49/04 | U1485 | 2004-08-18 | ANSALDO
49/04 | U1486 | 2004-08-18 | ANSALDO
49/04 | U1488 | 2004-08-18 | ANSALDO
49/04 | L1382 | 2004-08-19 | ALSTOM
49/04 | L1402 | 2004-08-19 | ALSTOM
49/04 | L1356 | 2004-08-19 | ALSTOM
49/04 | L1345 | 2004-08-19 | ALSTOM
49/04 | L1387 | 2004-08-19 | NOELL
49/04 | L1400 | 2004-08-19 | NOELL
49/04 | L1396 | 2004-08-19 | NOELL
49/04 | L1390 | 2004-08-19 | NOELL
49/04 | L1407 | 2004-08-18 | ANSALDO
49/04 | L1394 | 2004-08-18 | ANSALDO
49/04 | L1376 | 2004-08-18 | ANSALDO
49/04 | L1366 | 2004-08-18 | ANSALDO
50/04 | U1524 | 2004-10-15 | ALSTOM
50/04 | U1526 | 2004-10-15 | ALSTOM
50/04 | U1527 | 2004-10-15 | ALSTOM
50/04 | U1206 | 2004-10-15 | ALSTOM
50/04 | U1445 | 2004-08-23 | NOELL
50/04 | U1446 | 2004-08-23 | NOELL
50/04 | U1447 | 2004-08-23 | NOELL
50/04 | U1448 | 2004-08-23 | NOELL
50/04 | 0 |  | ANSALDO
50/04 | 0 |  | ANSALDO
50/04 | 0 |  | ANSALDO
50/04 | 0 |  | ANSALDO
50/04 | L1343 | 2004-10-15 | ALSTOM
50/04 | L1055 | 2004-10-15 | ALSTOM
50/04 | L1401 | 2004-10-15 | ALSTOM
50/04 | L1562 | 2004-10-15 | ALSTOM
50/04 | L1332 | 2004-08-23 | NOELL
50/04 | L1399 | 2004-08-23 | NOELL
50/04 | L1398 | 2004-08-23 | NOELL
50/04 | L1389 | 2004-08-23 | NOELL
50/04 | 0 |  | ANSALDO
50/04 | 0 |  | ANSALDO
50/04 | 0 |  | ANSALDO
50/04 | 0 |  | ANSALDO
51/04 | U1471 | 2004-10-15 | ALSTOM
51/04 | U1473 | 2004-10-15 | ALSTOM
51/04 | U1476 | 2004-10-15 | ALSTOM
51/04 | U1477 | 2004-10-15 | ALSTOM
51/04 | U1449 | 2004-08-23 | NOELL
51/04 | U1461 | 2004-08-23 | NOELL
51/04 | U1463 | 2004-08-23 | NOELL
51/04 | U1465 | 2004-08-23 | NOELL
51/04 | 0 |  | ANSALDO
51/04 | 0 |  | ANSALDO
51/04 | 0 |  | ANSALDO
51/04 | 0 |  | ANSALDO
51/04 | L1541 | 2004-10-15 | ALSTOM
51/04 | L1599 | 2004-10-15 | ALSTOM
51/04 | L1593 | 2004-10-15 | ALSTOM
51/04 | L1545 | 2004-10-15 | ALSTOM
51/04 | L1409 | 2004-08-23 | NOELL
51/04 | L1528 | 2004-08-23 | NOELL
51/04 | L1329 | 2004-08-23 | NOELL
51/04 | L1331 | 2004-08-23 | NOELL
51/04 | 0 |  | ANSALDO
51/04 | 0 |  | ANSALDO
51/04 | 0 |  | ANSALDO
51/04 | 0 |  | ANSALDO
52/04 | 0 |  | ALSTOM
52/04 | 0 |  | ALSTOM
52/04 | 0 |  | ALSTOM
52/04 | 0 |  | ALSTOM
52/04 | 0 |  | NOELL
52/04 | 0 |  | NOELL
52/04 | 0 |  | NOELL
52/04 | 0 |  | NOELL
52/04 | 0 |  | ANSALDO
52/04 | 0 |  | ANSALDO
52/04 | 0 |  | ANSALDO
52/04 | 0 |  | ANSALDO
52/04 | 0 |  | ALSTOM
52/04 | 0 |  | ALSTOM
52/04 | 0 |  | ALSTOM
52/04 | 0 |  | ALSTOM
52/04 | 0 |  | NOELL
52/04 | 0 |  | NOELL
52/04 | 0 |  | NOELL
52/04 | 0 |  | NOELL
52/04 | 0 |  | ANSALDO
52/04 | 0 |  | ANSALDO
52/04 | 0 |  | ANSALDO
52/04 | 0 |  | ANSALDO
1/05 | 0 |  | ALSTOM
1/05 | 0 |  | ALSTOM
1/05 | 0 |  | ALSTOM
1/05 | 0 |  | ALSTOM
1/05 | 0 |  | NOELL
1/05 | 0 |  | NOELL
1/05 | 0 |  | NOELL
1/05 | 0 |  | NOELL
1/05 | 0 |  | ANSALDO
1/05 | 0 |  | ANSALDO
1/05 | 0 |  | ANSALDO
1/05 | 0 |  | ANSALDO
1/05 | 0 |  | ALSTOM
1/05 | 0 |  | ALSTOM
1/05 | 0 |  | ALSTOM
1/05 | 0 |  | ALSTOM
1/05 | 0 |  | NOELL
1/05 | 0 |  | NOELL
1/05 | 0 |  | NOELL
1/05 | 0 |  | NOELL
1/05 | 0 |  | ANSALDO
1/05 | 0 |  | ANSALDO
1/05 | 0 |  | ANSALDO
1/05 | 0 |  | ANSALDO
2/05 | U1487 | 2004-10-19 | ALSTOM
2/05 | U1490 | 2004-10-19 | ALSTOM
2/05 | U1498 | 2004-10-19 | ALSTOM
2/05 | U1499 | 2004-10-19 | ALSTOM
2/05 | U1236 | 2004-10-19 | NOELL
2/05 | U1450 | 2004-10-19 | NOELL
2/05 | U1451 | 2004-10-19 | NOELL
2/05 | U1453 | 2004-10-19 | NOELL
2/05 | U1495 | 2004-10-15 | ANSALDO
2/05 | U1497 | 2004-10-15 | ANSALDO
2/05 | U1503 | 2004-10-15 | ANSALDO
2/05 | U1516 | 2004-10-15 | ANSALDO
2/05 | L1548 | 2004-10-19 | ALSTOM
2/05 | L1552 | 2004-10-19 | ALSTOM
2/05 | L1639 | 2004-10-19 | ALSTOM
2/05 | L1613 | 2004-10-19 | ALSTOM
2/05 | L1533 | 2004-10-19 | NOELL
2/05 | L1556 | 2004-10-19 | NOELL
2/05 | L1579 | 2004-10-19 | NOELL
2/05 | L1550 | 2004-10-19 | NOELL
2/05 | L1538 | 2004-10-15 | ANSALDO
2/05 | L1342 | 2004-10-15 | ANSALDO
2/05 | L1547 | 2004-10-15 | ANSALDO
2/05 | L1549 | 2004-10-15 | ANSALDO
3/05 | U1500 | 2004-10-19 | ALSTOM
3/05 | U1501 | 2004-10-19 | ALSTOM
3/05 | U1509 | 2004-10-19 | ALSTOM
3/05 | U1510 | 2004-10-19 | ALSTOM
3/05 | U1455 | 2004-10-19 | NOELL
3/05 | U1456 | 2004-10-19 | NOELL
3/05 | U1460 | 2004-10-19 | NOELL
3/05 | U1464 | 2004-10-19 | NOELL
3/05 | U1432 | 2004-10-19 | ANSALDO
3/05 | U1457 | 2004-10-19 | ANSALDO
3/05 | U1462 | 2004-10-19 | ANSALDO
3/05 | U1493 | 2004-10-19 | ANSALDO
3/05 | L1607 | 2004-10-19 | ALSTOM
3/05 | L1606 | 2004-10-19 | ALSTOM
3/05 | L1564 | 2004-10-19 | ALSTOM
3/05 | L1660 | 2004-10-19 | ALSTOM
3/05 | L1536 | 2004-10-19 | NOELL
3/05 | L1561 | 2004-10-19 | NOELL
3/05 | L1554 | 2004-10-19 | NOELL
3/05 | L1544 | 2004-10-19 | NOELL
3/05 | L1553 | 2004-10-19 | ANSALDO
3/05 | L1543 | 2004-10-19 | ANSALDO
3/05 | L1637 | 2004-10-19 | ANSALDO
3/05 | L1535 | 2004-10-19 | ANSALDO
4/05 | U1511 | 2004-10-21 | ALSTOM
4/05 | U1513 | 2004-10-21 | ALSTOM
4/05 | U1521 | 2004-10-21 | ALSTOM
4/05 | U1522 | 2004-10-21 | ALSTOM
4/05 | U1467 | 2004-10-21 | NOELL
4/05 | U1469 | 2004-10-21 | NOELL
4/05 | U1472 | 2004-10-21 | NOELL
4/05 | U1474 | 2004-10-21 | NOELL
4/05 | 0 |  | ANSALDO
4/05 | 0 |  | ANSALDO
4/05 | 0 |  | ANSALDO
4/05 | 0 |  | ANSALDO
4/05 | L1595 | 2004-10-21 | ALSTOM
4/05 | L1598 | 2004-10-21 | ALSTOM
4/05 | L1621 | 2004-10-21 | ALSTOM
4/05 | L1537 | 2004-10-21 | ALSTOM
4/05 | L1555 | 2004-10-21 | NOELL
4/05 | L1580 | 2004-10-21 | NOELL
4/05 | L1540 | 2004-10-21 | NOELL
4/05 | L1578 | 2004-10-21 | NOELL
4/05 | 0 |  | ANSALDO
4/05 | 0 |  | ANSALDO
4/05 | 0 |  | ANSALDO
4/05 | 0 |  | ANSALDO
5/05 | 0 |  | ALSTOM
5/05 | 0 |  | ALSTOM
5/05 | 0 |  | ALSTOM
5/05 | 0 |  | ALSTOM
5/05 | U1502 | 2004-10-21 | NOELL
5/05 | U1512 | 2004-10-21 | NOELL
5/05 | U1517 | 2004-10-21 | NOELL
5/05 | U1519 | 2004-10-21 | NOELL
5/05 | U1496 | 2004-10-19 | ANSALDO
5/05 | U1504 | 2004-10-19 | ANSALDO
5/05 | U1505 | 2004-10-19 | ANSALDO
5/05 | U1507 | 2004-10-19 | ANSALDO
5/05 | 0 |  | ALSTOM
5/05 | 0 |  | ALSTOM
5/05 | 0 |  | ALSTOM
5/05 | 0 |  | ALSTOM
5/05 | L1582 | 2004-10-21 | NOELL
5/05 | L1557 | 2004-10-21 | NOELL
5/05 | L1604 | 2004-10-21 | NOELL
5/05 | L1572 | 2004-10-21 | NOELL
5/05 | L1542 | 2004-10-19 | ANSALDO
5/05 | L1656 | 2004-10-19 | ANSALDO
5/05 | L1602 | 2004-10-19 | ANSALDO
5/05 | L1563 | 2004-10-19 | ANSALDO
6/05 | U1523 | 2004-10-21 | ALSTOM
6/05 | U1525 | 2004-10-21 | ALSTOM
6/05 | U1682 | 2004-10-21 | ALSTOM
6/05 | U1684 | 2004-10-21 | ALSTOM
6/05 | U1529 | 2004-10-22 | NOELL
6/05 | U1531 | 2004-10-22 | NOELL
6/05 | U1532 | 2004-10-22 | NOELL
6/05 | U1560 | 2004-10-22 | NOELL
6/05 | U1508 | 2004-10-21 | ANSALDO
6/05 | U1514 | 2004-10-21 | ANSALDO
6/05 | U1515 | 2004-10-21 | ANSALDO
6/05 | U1518 | 2004-10-21 | ANSALDO
6/05 | L1534 | 2004-10-21 | ALSTOM
6/05 | L1662 | 2004-10-21 | ALSTOM
6/05 | L1638 | 2004-10-21 | ALSTOM
6/05 | L1622 | 2004-10-21 | ALSTOM
6/05 | L1558 | 2004-10-22 | NOELL
6/05 | L1589 | 2004-10-22 | NOELL
6/05 | L1603 | 2004-10-22 | NOELL
6/05 | L1566 | 2004-10-22 | NOELL
6/05 | L1610 | 2004-10-21 | ANSALDO
6/05 | L1609 | 2004-10-21 | ANSALDO
6/05 | L1623 | 2004-10-21 | ANSALDO
6/05 | L1586 | 2004-10-21 | ANSALDO
7/05 | U1574 | 2004-10-22 | ALSTOM
7/05 | U1575 | 2004-10-22 | ALSTOM
7/05 | U1577 | 2004-10-22 | ALSTOM
7/05 | U1605 | 2004-10-22 | ALSTOM
7/05 | U1565 | 2004-10-26 | NOELL
7/05 | U1568 | 2004-10-26 | NOELL
7/05 | U1569 | 2004-10-26 | NOELL
7/05 | U1573 | 2004-10-26 | NOELL
7/05 | U1520 | 2004-10-22 | ANSALDO
7/05 | U1530 | 2004-10-22 | ANSALDO
7/05 | U1567 | 2004-10-22 | ANSALDO
7/05 | U1581 | 2004-10-22 | ANSALDO
7/05 | L1600 | 2004-10-22 | ALSTOM
7/05 | L1617 | 2004-10-22 | ALSTOM
7/05 | L1616 | 2004-10-22 | ALSTOM
7/05 | L1611 | 2004-10-22 | ALSTOM
7/05 | L1583 | 2004-10-26 | NOELL
7/05 | L1571 | 2004-10-26 | NOELL
7/05 | L1570 | 2004-10-26 | NOELL
7/05 | L1614 | 2004-10-26 | NOELL
7/05 | L1641 | 2004-10-22 | ANSALDO
7/05 | L1539 | 2004-10-22 | ANSALDO
7/05 | L1209 | 2004-10-22 | ANSALDO
7/05 | L1628 | 2004-10-22 | ANSALDO
8/05 | U1698 | 2004-11-22 | ALSTOM
8/05 | U1711 | 2004-11-22 | ALSTOM
8/05 | U1673 | 2004-11-22 | ALSTOM
8/05 | U1676 | 2004-11-22 | ALSTOM
8/05 | U1669 | 2004-11-22 | NOELL
8/05 | U1670 | 2004-11-22 | NOELL
8/05 | U1677 | 2004-11-22 | NOELL
8/05 | U1686 | 2004-11-22 | NOELL
8/05 | 0 |  | ANSALDO
8/05 | 0 |  | ANSALDO
8/05 | 0 |  | ANSALDO
8/05 | 0 |  | ANSALDO
8/05 | L1654 | 2004-11-22 | ALSTOM
8/05 | L1655 | 2004-11-22 | ALSTOM
8/05 | L1661 | 2004-11-22 | ALSTOM
8/05 | L1663 | 2004-11-22 | ALSTOM
8/05 | L1635 | 2004-11-22 | NOELL
8/05 | L1643 | 2004-11-22 | NOELL
8/05 | L1626 | 2004-11-22 | NOELL
8/05 | L1634 | 2004-11-22 | NOELL
8/05 | 0 |  | ANSALDO
8/05 | 0 |  | ANSALDO
8/05 | 0 |  | ANSALDO
8/05 | 0 |  | ANSALDO
9/05 | 0 |  | ALSTOM
9/05 | 0 |  | ALSTOM
9/05 | 0 |  | ALSTOM
9/05 | 0 |  | ALSTOM
9/05 | U1691 | 2004-11-22 | NOELL
9/05 | U1697 | 2004-11-22 | NOELL
9/05 | U1700 | 2004-11-22 | NOELL
9/05 | U1701 | 2004-11-22 | NOELL
9/05 | U1590 | 2004-10-22 | ANSALDO
9/05 | U1685 | 2004-10-22 | ANSALDO
9/05 | U1665 | 2004-10-22 | ANSALDO
9/05 | U1667 | 2004-10-22 | ANSALDO
9/05 | 0 |  | ALSTOM
9/05 | 0 |  | ALSTOM
9/05 | 0 |  | ALSTOM
9/05 | 0 |  | ALSTOM
9/05 | L1648 | 2004-11-22 | NOELL
9/05 | L1651 | 2004-11-22 | NOELL
9/05 | L1629 | 2004-11-22 | NOELL
9/05 | L1630 | 2004-11-22 | NOELL
9/05 | L1359 | 2004-10-22 | ANSALDO
9/05 | L1658 | 2004-10-22 | ANSALDO
9/05 | L1644 | 2004-10-22 | ANSALDO
9/05 | L1646 | 2004-10-22 | ANSALDO
10/05 | U1690 | 2004-11-22 | ALSTOM
10/05 | U1708 | 2004-11-22 | ALSTOM
10/05 | U1713 | 2004-11-22 | ALSTOM
10/05 | U0127 | 2004-11-22 | ALSTOM
10/05 | U1704 | 2004-11-22 | NOELL
10/05 | U1705 | 2004-11-22 | NOELL
10/05 | U1712 | 2004-11-22 | NOELL
10/05 | U1506 | 2004-11-22 | NOELL
10/05 | U1640 | 2004-10-26 | ANSALDO
10/05 | U1642 | 2004-10-26 | ANSALDO
10/05 | U1671 | 2004-10-26 | ANSALDO
10/05 | U1672 | 2004-10-26 | ANSALDO
10/05 | L1627 | 2004-11-22 | ALSTOM
10/05 | L1625 | 2004-11-22 | ALSTOM
10/05 | L1631 | 2004-11-22 | ALSTOM
10/05 | L1559 | 2004-11-22 | ALSTOM
10/05 | L1652 | 2004-11-22 | NOELL
10/05 | L1632 | 2004-11-22 | NOELL
10/05 | L1618 | 2004-11-22 | NOELL
10/05 | L0388 | 2004-11-22 | NOELL
10/05 | L1645 | 2004-10-26 | ANSALDO
10/05 | L1588 | 2004-10-26 | ANSALDO
10/05 | L1608 | 2004-10-26 | ANSALDO
10/05 | L1592 | 2004-10-26 | ANSALDO
11/05 | U0134 | 2004-12-07 | ALSTOM
11/05 | U0153 | 2004-12-07 | ALSTOM
11/05 | U1731 | 2004-12-07 | ALSTOM
11/05 | U1737 | 2004-12-07 | ALSTOM
11/05 | U1675 | 2004-12-07 | NOELL
11/05 | U1725 | 2004-12-07 | NOELL
11/05 | U1735 | 2004-12-07 | NOELL
11/05 | U1678 | 2004-12-07 | NOELL
11/05 | U1692 | 2004-12-07 | ANSALDO
11/05 | U1702 | 2004-12-07 | ANSALDO
11/05 | U1706 | 2004-12-07 | ANSALDO
11/05 | U1674 | 2004-12-07 | ANSALDO
11/05 | L0859 | 2004-12-07 | ALSTOM
11/05 | L0123 | 2004-12-07 | ALSTOM
11/05 | L0087 | 2004-12-07 | ALSTOM
11/05 | L0093 | 2004-12-07 | ALSTOM
11/05 | L0386 | 2004-12-07 | NOELL
11/05 | L0469 | 2004-12-07 | NOELL
11/05 | L0420 | 2004-12-07 | NOELL
11/05 | L1615 | 2004-12-07 | NOELL
11/05 | L1647 | 2004-12-07 | ANSALDO
11/05 | L1650 | 2004-12-07 | ANSALDO
11/05 | L1620 | 2004-12-07 | ANSALDO
11/05 | L1624 | 2004-12-07 | ANSALDO
12/05 | U1752 | 2004-12-10 | ALSTOM
12/05 | U1679 | 2004-12-10 | ALSTOM
12/05 | U1680 | 2004-12-10 | ALSTOM
12/05 | U1709 | 2004-12-10 | ALSTOM
12/05 | U1683 | 2004-12-10 | NOELL
12/05 | U1721 | 2004-12-10 | NOELL
12/05 | U1723 | 2004-12-10 | NOELL
12/05 | U1728 | 2004-12-10 | NOELL
12/05 | 0 |  | ANSALDO
12/05 | 0 |  | ANSALDO
12/05 | 0 |  | ANSALDO
12/05 | 0 |  | ANSALDO
12/05 | L0362 | 2004-12-10 | ALSTOM
12/05 | L1596 | 2004-12-10 | ALSTOM
12/05 | L1576 | 2004-12-10 | ALSTOM
12/05 | L1591 | 2004-12-10 | ALSTOM
12/05 | L1594 | 2004-12-10 | NOELL
12/05 | L1666 | 2004-12-10 | NOELL
12/05 | L1649 | 2004-12-10 | NOELL
12/05 | L1659 | 2004-12-10 | NOELL
12/05 | 0 |  | ANSALDO
12/05 | 0 |  | ANSALDO
12/05 | 0 |  | ANSALDO
12/05 | 0 |  | ANSALDO
13/05 | 0 |  | ALSTOM
13/05 | 0 |  | ALSTOM
13/05 | 0 |  | ALSTOM
13/05 | 0 |  | ALSTOM
13/05 | U1668 | 2005-01-06 | NOELL
13/05 | U1732 | 2005-01-06 | NOELL
13/05 | U1681 | 2005-01-06 | NOELL
13/05 | U1693 | 2005-01-06 | NOELL
13/05 | U1687 | 2005-01-06 | ANSALDO
13/05 | U1689 | 2005-01-06 | ANSALDO
13/05 | U1699 | 2005-01-06 | ANSALDO
13/05 | U1703 | 2005-01-06 | ANSALDO
13/05 | 0 |  | ALSTOM
13/05 | 0 |  | ALSTOM
13/05 | 0 |  | ALSTOM
13/05 | 0 |  | ALSTOM
13/05 | L1822 | 2005-01-06 | NOELL
13/05 | L1636 | 2005-01-06 | NOELL
13/05 | L1801 | 2005-01-06 | NOELL
13/05 | L1780 | 2005-01-06 | NOELL
13/05 | L1597 | 2005-01-06 | ANSALDO
13/05 | L1601 | 2005-01-06 | ANSALDO
13/05 | L1585 | 2005-01-06 | ANSALDO
13/05 | L1657 | 2005-01-06 | ANSALDO
14/05 | U0116 | 2005-01-06 | ALSTOM
14/05 | U0150 | 2005-01-06 | ALSTOM
14/05 | U0281 | 2005-01-06 | ALSTOM
14/05 | U0294 | 2005-01-06 | ALSTOM
14/05 | U1694 | 2005-01-06 | NOELL
14/05 | U1695 | 2005-01-06 | NOELL
14/05 | U1696 | 2005-01-06 | NOELL
14/05 | U1707 | 2005-01-06 | NOELL
14/05 | U1714 | 2005-01-06 | ANSALDO
14/05 | U1715 | 2005-01-06 | ANSALDO
14/05 | U1716 | 2005-01-06 | ANSALDO
14/05 | U1717 | 2005-01-06 | ANSALDO
14/05 | L1782 | 2005-01-06 | ALSTOM
14/05 | L1783 | 2005-01-06 | ALSTOM
14/05 | L1814 | 2005-01-06 | ALSTOM
14/05 | L1790 | 2005-01-06 | ALSTOM
14/05 | L1797 | 2005-01-06 | NOELL
14/05 | L1786 | 2005-01-06 | NOELL
14/05 | L1796 | 2005-01-06 | NOELL
14/05 | L1772 | 2005-01-06 | NOELL
14/05 | L1805 | 2005-01-06 | ANSALDO
14/05 | L1809 | 2005-01-06 | ANSALDO
14/05 | L1769 | 2005-01-06 | ANSALDO
14/05 | L1768 | 2005-01-06 | ANSALDO
15/05 | U1718 | 2005-01-06 | ALSTOM
15/05 | U1719 | 2005-01-06 | ALSTOM
15/05 | U1720 | 2005-01-06 | ALSTOM
15/05 | U1722 | 2005-01-06 | ALSTOM
15/05 | U1724 | 2005-01-06 | NOELL
15/05 | U1726 | 2005-01-06 | NOELL
15/05 | U1729 | 2005-01-06 | NOELL
15/05 | U1730 | 2005-01-06 | NOELL
15/05 | U1905 | 2005-01-06 | ANSALDO
15/05 | U1733 | 2005-01-06 | ANSALDO
15/05 | U1734 | 2005-01-06 | ANSALDO
15/05 | U1736 | 2005-01-06 | ANSALDO
15/05 | L1841 | 2005-01-06 | ALSTOM
15/05 | L1811 | 2005-01-06 | ALSTOM
15/05 | L1785 | 2005-01-06 | ALSTOM
15/05 | L1787 | 2005-01-06 | ALSTOM
15/05 | L1821 | 2005-01-06 | NOELL
15/05 | L1808 | 2005-01-06 | NOELL
15/05 | L1840 | 2005-01-06 | NOELL
15/05 | L1784 | 2005-01-06 | NOELL
15/05 | L1851 | 2005-01-06 | ANSALDO
15/05 | L1778 | 2005-01-06 | ANSALDO
15/05 | L1799 | 2005-01-06 | ANSALDO
15/05 | L1847 | 2005-01-06 | ANSALDO
16/05 | U1739 | 2005-01-07 | ALSTOM
16/05 | U1740 | 2005-01-07 | ALSTOM
16/05 | U1741 | 2005-01-07 | ALSTOM
16/05 | U1903 | 2005-01-07 | ALSTOM
16/05 | U1743 | 2005-01-06 | NOELL
16/05 | U1744 | 2005-01-06 | NOELL
16/05 | U1745 | 2005-01-06 | NOELL
16/05 | U1746 | 2005-01-06 | NOELL
16/05 | 0 |  | ANSALDO
16/05 | 0 |  | ANSALDO
16/05 | 0 |  | ANSALDO
16/05 | 0 |  | ANSALDO
16/05 | L1653 | 2005-01-07 | ALSTOM
16/05 | L1795 | 2005-01-07 | ALSTOM
16/05 | L1792 | 2005-01-07 | ALSTOM
16/05 | L1793 | 2005-01-07 | ALSTOM
16/05 | L1800 | 2005-01-06 | NOELL
16/05 | L1818 | 2005-01-06 | NOELL
16/05 | L1802 | 2005-01-06 | NOELL
16/05 | L1806 | 2005-01-06 | NOELL
16/05 | 0 |  | ANSALDO
16/05 | 0 |  | ANSALDO
16/05 | 0 |  | ANSALDO
16/05 | 0 |  | ANSALDO
17/05 | 0 |  | ALSTOM
17/05 | 0 |  | ALSTOM
17/05 | 0 |  | ALSTOM
17/05 | 0 |  | ALSTOM
17/05 | U1747 | 2005-01-05 | NOELL
17/05 | U1748 | 2005-01-05 | NOELL
17/05 | U1749 | 2005-01-05 | NOELL
17/05 | U1750 | 2005-01-05 | NOELL
17/05 | U1751 | 2005-01-05 | ANSALDO
17/05 | U1753 | 2005-01-05 | ANSALDO
17/05 | U1754 | 2005-01-05 | ANSALDO
17/05 | U1755 | 2005-01-05 | ANSALDO
17/05 | 0 |  | ALSTOM
17/05 | 0 |  | ALSTOM
17/05 | 0 |  | ALSTOM
17/05 | 0 |  | ALSTOM
17/05 | L1664 | 2005-01-05 | NOELL
17/05 | L1775 | 2005-01-05 | NOELL
17/05 | L1836 | 2005-01-05 | NOELL
17/05 | L1771 | 2005-01-05 | NOELL
17/05 | L1798 | 2005-01-05 | ANSALDO
17/05 | L1765 | 2005-01-05 | ANSALDO
17/05 | L1845 | 2005-01-05 | ANSALDO
17/05 | L1781 | 2005-01-05 | ANSALDO
18/05 | U1756 | 2005-01-06 | ALSTOM
18/05 | U1757 | 2005-01-06 | ALSTOM
18/05 | U1758 | 2005-01-06 | ALSTOM
18/05 | U1759 | 2005-01-06 | ALSTOM
18/05 | U1760 | 2005-01-06 | NOELL
18/05 | U1761 | 2005-01-06 | NOELL
18/05 | U1762 | 2005-01-06 | NOELL
18/05 | U1770 | 2005-01-06 | NOELL
18/05 | U1777 | 2005-01-06 | ANSALDO
18/05 | U1791 | 2005-01-06 | ANSALDO
18/05 | U1826 | 2005-01-06 | ANSALDO
18/05 | U1830 | 2005-01-06 | ANSALDO
18/05 | L1773 | 2005-01-06 | ALSTOM
18/05 | L1774 | 2005-01-06 | ALSTOM
18/05 | L1837 | 2005-01-06 | ALSTOM
18/05 | L1831 | 2005-01-06 | ALSTOM
18/05 | L1813 | 2005-01-06 | NOELL
18/05 | L1812 | 2005-01-06 | NOELL
18/05 | L1804 | 2005-01-06 | NOELL
18/05 | L1834 | 2005-01-06 | NOELL
18/05 | L1815 | 2005-01-06 | ANSALDO
18/05 | L0203 | 2005-01-06 | ANSALDO
18/05 | L0468 | 2005-01-06 | ANSALDO
18/05 | L1766 | 2005-01-06 | ANSALDO
19/05 | U1846 | 2005-01-07 | ALSTOM
19/05 | U1854 | 2005-01-07 | ALSTOM
19/05 | U1855 | 2005-01-07 | ALSTOM
19/05 | U1856 | 2005-01-07 | ALSTOM
19/05 | U1832 | 2005-01-07 | NOELL
19/05 | U1838 | 2005-01-07 | NOELL
19/05 | U1839 | 2005-01-07 | NOELL
19/05 | U1842 | 2005-01-07 | NOELL
19/05 | U1857 | 2005-01-12 | ANSALDO
19/05 | U1858 | 2005-01-12 | ANSALDO
19/05 | U1859 | 2005-01-12 | ANSALDO
19/05 | U1861 | 2005-01-12 | ANSALDO
19/05 | L1848 | 2005-01-07 | ALSTOM
19/05 | L1776 | 2005-01-07 | ALSTOM
19/05 | L0213 | 2005-01-07 | ALSTOM
19/05 | L0385 | 2005-01-07 | ALSTOM
19/05 | L1810 | 2005-01-07 | NOELL
19/05 | L1807 | 2005-01-07 | NOELL
19/05 | L1619 | 2005-01-07 | NOELL
19/05 | L1820 | 2005-01-07 | NOELL
19/05 | L1794 | 2005-01-12 | ANSALDO
19/05 | L0371 | 2005-01-12 | ANSALDO
19/05 | L1849 | 2005-01-12 | ANSALDO
19/05 | L1816 | 2005-01-12 | ANSALDO
20/05 | U1862 | 2005-01-12 | ALSTOM
20/05 | U1863 | 2005-01-12 | ALSTOM
20/05 | U1864 | 2005-01-12 | ALSTOM
20/05 | U1865 | 2005-01-12 | ALSTOM
20/05 | U1866 | 2005-01-12 | NOELL
20/05 | U1867 | 2005-01-12 | NOELL
20/05 | U1868 | 2005-01-12 | NOELL
20/05 | U1871 | 2005-01-12 | NOELL
20/05 | 0 |  | ANSALDO
20/05 | 0 |  | ANSALDO
20/05 | 0 |  | ANSALDO
20/05 | 0 |  | ANSALDO
20/05 | L0424 | 2005-01-12 | ALSTOM
20/05 | L1833 | 2005-01-12 | ALSTOM
20/05 | L0364 | 2005-01-12 | ALSTOM
20/05 | L0387 | 2005-01-12 | ALSTOM
20/05 | L0422 | 2005-01-12 | NOELL
20/05 | L1789 | 2005-01-12 | NOELL
20/05 | L0365 | 2005-01-12 | NOELL
20/05 | L1835 | 2005-01-12 | NOELL
20/05 | 0 |  | ANSALDO
20/05 | 0 |  | ANSALDO
20/05 | 0 |  | ANSALDO
20/05 | 0 |  | ANSALDO
21/05 | 0 |  | ALSTOM
21/05 | 0 |  | ALSTOM
21/05 | 0 |  | ALSTOM
21/05 | 0 |  | ALSTOM
21/05 | U1872 | 2005-02-22 | NOELL
21/05 | U1876 | 2005-02-22 | NOELL
21/05 | U1880 | 2005-02-22 | NOELL
21/05 | U1883 | 2005-02-22 | NOELL
21/05 | U1885 | 2005-02-23 | ANSALDO
21/05 | U1895 | 2005-02-23 | ANSALDO
21/05 | U1896 | 2005-02-23 | ANSALDO
21/05 | U1897 | 2005-02-23 | ANSALDO
21/05 | 0 |  | ALSTOM
21/05 | 0 |  | ALSTOM
21/05 | 0 |  | ALSTOM
21/05 | 0 |  | ALSTOM
21/05 | L1612 | 2005-02-22 | NOELL
21/05 | L1817 | 2005-02-22 | NOELL
21/05 | L1850 | 2005-02-22 | NOELL
21/05 | L1779 | 2005-02-22 | NOELL
21/05 | L1633 | 2005-02-23 | ANSALDO
21/05 | L1803 | 2005-02-23 | ANSALDO
21/05 | L1829 | 2005-02-23 | ANSALDO
21/05 | L1764 | 2005-02-23 | ANSALDO
22/05 | U1898 | 2005-02-23 | ALSTOM
22/05 | U1899 | 2005-02-23 | ALSTOM
22/05 | U1900 | 2005-02-23 | ALSTOM
22/05 | U1902 | 2005-02-23 | ALSTOM
22/05 | U1688 | 2005-02-23 | NOELL
22/05 | U1727 | 2005-02-23 | NOELL
22/05 | U1742 | 2005-02-23 | NOELL
22/05 | U1763 | 2005-02-23 | NOELL
22/05 | U1767 | 2005-02-24 | ANSALDO
22/05 | U2043 | 2005-02-24 | ANSALDO
22/05 | U1827 | 2005-02-24 | ANSALDO
22/05 | U1853 | 2005-02-24 | ANSALDO
22/05 | L1852 | 2005-02-23 | ALSTOM
22/05 | L0479 | 2005-02-23 | ALSTOM
22/05 | L0480 | 2005-02-23 | ALSTOM
22/05 | L1823 | 2005-02-23 | ALSTOM
22/05 | L2017 | 2005-02-23 | NOELL
22/05 | L1824 | 2005-02-23 | NOELL
22/05 | L1957 | 2005-02-23 | NOELL
22/05 | L1997 | 2005-02-23 | NOELL
22/05 | L1828 | 2005-02-24 | ANSALDO
22/05 | L1999 | 2005-02-24 | ANSALDO
22/05 | L1924 | 2005-02-24 | ANSALDO
22/05 | L1925 | 2005-02-24 | ANSALDO
23/05 | U1860 | 2005-02-24 | ALSTOM
23/05 | U2047 | 2005-02-24 | ALSTOM
23/05 | U1870 | 2005-02-24 | ALSTOM
23/05 | U1873 | 2005-02-24 | ALSTOM
23/05 | U1874 | 2005-02-24 | NOELL
23/05 | U1875 | 2005-02-24 | NOELL
23/05 | U1877 | 2005-02-24 | NOELL
23/05 | U1879 | 2005-02-24 | NOELL
23/05 | U1881 | 2005-02-24 | ANSALDO
23/05 | U1882 | 2005-02-24 | ANSALDO
23/05 | U1884 | 2005-02-24 | ANSALDO
23/05 | U1886 | 2005-02-24 | ANSALDO
23/05 | L1844 | 2005-02-24 | ALSTOM
23/05 | L1979 | 2005-02-24 | ALSTOM
23/05 | L1973 | 2005-02-24 | ALSTOM
23/05 | L1954 | 2005-02-24 | ALSTOM
23/05 | L1985 | 2005-02-24 | NOELL
23/05 | L1946 | 2005-02-24 | NOELL
23/05 | L1914 | 2005-02-24 | NOELL
23/05 | L1926 | 2005-02-24 | NOELL
23/05 | L1974 | 2005-02-24 | ANSALDO
23/05 | L1923 | 2005-02-24 | ANSALDO
23/05 | L1975 | 2005-02-24 | ANSALDO
23/05 | L1941 | 2005-02-24 | ANSALDO
24/05 | U1887 | 2005-03-01 | ALSTOM
24/05 | U1888 | 2005-03-01 | ALSTOM
24/05 | U1889 | 2005-03-01 | ALSTOM
24/05 | U1890 | 2005-03-01 | ALSTOM
24/05 | U1891 | 2005-03-01 | NOELL
24/05 | U1892 | 2005-03-01 | NOELL
24/05 | U1893 | 2005-03-01 | NOELL
24/05 | U1894 | 2005-03-01 | NOELL
24/05 | 0 |  | ANSALDO
24/05 | 0 |  | ANSALDO
24/05 | 0 |  | ANSALDO
24/05 | 0 |  | ANSALDO
24/05 | L1960 | 2005-03-01 | ALSTOM
24/05 | L1956 | 2005-03-01 | ALSTOM
24/05 | L1949 | 2005-03-01 | ALSTOM
24/05 | L1986 | 2005-03-01 | ALSTOM
24/05 | L1952 | 2005-03-01 | NOELL
24/05 | L1976 | 2005-03-01 | NOELL
24/05 | L1950 | 2005-03-01 | NOELL
24/05 | L1959 | 2005-03-01 | NOELL
24/05 | 0 |  | ANSALDO
24/05 | 0 |  | ANSALDO
24/05 | 0 |  | ANSALDO
24/05 | 0 |  | ANSALDO
25/05 | 0 |  | ALSTOM
25/05 | 0 |  | ALSTOM
25/05 | 0 |  | ALSTOM
25/05 | 0 |  | ALSTOM
25/05 | U1901 | 2005-03-02 | NOELL
25/05 | U1904 | 2005-03-02 | NOELL
25/05 | U1906 | 2005-03-02 | NOELL
25/05 | U1907 | 2005-03-02 | NOELL
25/05 | 0 |  | ANSALDO
25/05 | 0 |  | ANSALDO
25/05 | 0 |  | ANSALDO
25/05 | 0 |  | ANSALDO
25/05 | 0 |  | ALSTOM
25/05 | 0 |  | ALSTOM
25/05 | 0 |  | ALSTOM
25/05 | 0 |  | ALSTOM
25/05 | L1982 | 2005-03-02 | NOELL
25/05 | L1978 | 2005-03-02 | NOELL
25/05 | L1984 | 2005-03-02 | NOELL
25/05 | L1980 | 2005-03-02 | NOELL
25/05 | 0 |  | ANSALDO
25/05 | 0 |  | ANSALDO
25/05 | 0 |  | ANSALDO
25/05 | 0 |  | ANSALDO
26/05 | U1912 | 2005-03-02 | ALSTOM
26/05 | U1913 | 2005-03-02 | ALSTOM
26/05 | U1915 | 2005-03-02 | ALSTOM
26/05 | U1916 | 2005-03-02 | ALSTOM
26/05 | U1917 | 2005-03-03 | NOELL
26/05 | U1918 | 2005-03-03 | NOELL
26/05 | U1919 | 2005-03-03 | NOELL
26/05 | U1920 | 2005-03-03 | NOELL
26/05 | U1908 | 2005-03-02 | ANSALDO
26/05 | U1909 | 2005-03-02 | ANSALDO
26/05 | U1910 | 2005-03-02 | ANSALDO
26/05 | U1911 | 2005-03-02 | ANSALDO
26/05 | L1967 | 2005-03-02 | ALSTOM
26/05 | L1788 | 2005-03-02 | ALSTOM
26/05 | L1969 | 2005-03-02 | ALSTOM
26/05 | L1951 | 2005-03-02 | ALSTOM
26/05 | L1939 | 2005-03-03 | NOELL
26/05 | L1970 | 2005-03-03 | NOELL
26/05 | L1955 | 2005-03-03 | NOELL
26/05 | L1981 | 2005-03-03 | NOELL
26/05 | L1958 | 2005-03-02 | ANSALDO
26/05 | L1948 | 2005-03-02 | ANSALDO
26/05 | L1943 | 2005-03-02 | ANSALDO
26/05 | L1940 | 2005-03-02 | ANSALDO
27/05 | U1930 | 2005-03-03 | ALSTOM
27/05 | U1931 | 2005-03-03 | ALSTOM
27/05 | U1932 | 2005-03-03 | ALSTOM
27/05 | U1933 | 2005-03-03 | ALSTOM
27/05 | U1935 | 2005-03-04 | NOELL
27/05 | U1936 | 2005-03-04 | NOELL
27/05 | U1937 | 2005-03-04 | NOELL
27/05 | U1964 | 2005-03-04 | NOELL
27/05 | 0 |  | NOELL
27/05 | U1921 | 2005-03-03 | ANSALDO
27/05 | U1922 | 2005-03-03 | ANSALDO
27/05 | U1927 | 2005-03-03 | ANSALDO
27/05 | U1928 | 2005-03-03 | ANSALDO
27/05 | L2014 | 2005-03-03 | ALSTOM
27/05 | L2018 | 2005-03-03 | ALSTOM
27/05 | L2006 | 2005-03-03 | ALSTOM
27/05 | L1944 | 2005-03-03 | ALSTOM
27/05 | L1963 | 2005-03-04 | NOELL
27/05 | L1988 | 2005-03-04 | NOELL
27/05 | L1947 | 2005-03-04 | NOELL
27/05 | L1968 | 2005-03-04 | NOELL
27/05 | 0 |  | NOELL
27/05 | L1992 | 2005-03-03 | ANSALDO
27/05 | L1961 | 2005-03-03 | ANSALDO
27/05 | L1989 | 2005-03-03 | ANSALDO
27/05 | L1953 | 2005-03-03 | ANSALDO
28/05 | 0 |  | ALSTOM
28/05 | 0 |  | ALSTOM
28/05 | 0 |  | ALSTOM
28/05 | 0 |  | ALSTOM
28/05 | U2063 | 2005-03-04 | NOELL
28/05 | U2094 | 2005-03-04 | NOELL
28/05 | U1966 | 2005-03-04 | NOELL
28/05 | U2021 | 2005-03-04 | NOELL
28/05 | 0 |  | NOELL
28/05 | 0 |  | ANSALDO
28/05 | 0 |  | ANSALDO
28/05 | 0 |  | ANSALDO
28/05 | 0 |  | ANSALDO
28/05 | 0 |  | ALSTOM
28/05 | 0 |  | ALSTOM
28/05 | 0 |  | ALSTOM
28/05 | 0 |  | ALSTOM
28/05 | L1929 | 2005-03-04 | NOELL
28/05 | L2135 | 2005-03-04 | NOELL
28/05 | L2143 | 2005-03-04 | NOELL
28/05 | L1998 | 2005-03-04 | NOELL
28/05 | 0 |  | NOELL
28/05 | 0 |  | ANSALDO
28/05 | 0 |  | ANSALDO
28/05 | 0 |  | ANSALDO
28/05 | 0 |  | ANSALDO
29/05 | 0 |  | ALSTOM
29/05 | 0 |  | ALSTOM
29/05 | 0 |  | ALSTOM
29/05 | 0 |  | ALSTOM
29/05 | U2022 | 2005-04-04 | NOELL
29/05 | U2023 | 2005-04-04 | NOELL
29/05 | U2024 | 2005-04-04 | NOELL
29/05 | U2027 | 2005-04-04 | NOELL
29/05 | U2056 | 2005-05-18 | NOELL
29/05 | U1965 | 2005-03-04 | ANSALDO
29/05 | U2010 | 2005-03-04 | ANSALDO
29/05 | U2013 | 2005-03-04 | ANSALDO
29/05 | U2029 | 2005-03-04 | ANSALDO
29/05 | 0 |  | ALSTOM
29/05 | 0 |  | ALSTOM
29/05 | 0 |  | ALSTOM
29/05 | 0 |  | ALSTOM
29/05 | L2019 | 2005-04-04 | NOELL
29/05 | L2012 | 2005-04-04 | NOELL
29/05 | L2015 | 2005-04-04 | NOELL
29/05 | L2005 | 2005-04-04 | NOELL
29/05 | L2164 | 2005-05-18 | NOELL
29/05 | L2016 | 2005-03-04 | ANSALDO
29/05 | L1962 | 2005-03-04 | ANSALDO
29/05 | L1972 | 2005-03-04 | ANSALDO
29/05 | L2008 | 2005-03-04 | ANSALDO
30/05 | 0 |  | ALSTOM
30/05 | 0 |  | ALSTOM
30/05 | 0 |  | ALSTOM
30/05 | 0 |  | ALSTOM
30/05 | 0 |  | NOELL
30/05 | 0 |  | NOELL
30/05 | 0 |  | NOELL
30/05 | 0 |  | NOELL
30/05 | 0 |  | NOELL
30/05 | U2028 | 2005-04-04 | ANSALDO
30/05 | U2031 | 2005-04-04 | ANSALDO
30/05 | U2032 | 2005-04-04 | ANSALDO
30/05 | U2033 | 2005-04-04 | ANSALDO
30/05 | 0 |  | ALSTOM
30/05 | 0 |  | ALSTOM
30/05 | 0 |  | ALSTOM
30/05 | 0 |  | ALSTOM
30/05 | 0 |  | NOELL
30/05 | 0 |  | NOELL
30/05 | 0 |  | NOELL
30/05 | 0 |  | NOELL
30/05 | 0 |  | NOELL
30/05 | L1983 | 2005-04-04 | ANSALDO
30/05 | L1991 | 2005-04-04 | ANSALDO
30/05 | L2003 | 2005-04-04 | ANSALDO
30/05 | L1971 | 2005-04-04 | ANSALDO
31/05 | 0 |  | ALSTOM
31/05 | 0 |  | ALSTOM
31/05 | 0 |  | ALSTOM
31/05 | 0 |  | ALSTOM
31/05 | 0 |  | NOELL
31/05 | 0 |  | NOELL
31/05 | 0 |  | NOELL
31/05 | 0 |  | NOELL
31/05 | 0 |  | NOELL
31/05 | U2041 | 2005-04-04 | ANSALDO
31/05 | U2042 | 2005-04-04 | ANSALDO
31/05 | U2045 | 2005-04-04 | ANSALDO
31/05 | U2046 | 2005-04-04 | ANSALDO
31/05 | 0 |  | ALSTOM
31/05 | 0 |  | ALSTOM
31/05 | 0 |  | ALSTOM
31/05 | 0 |  | ALSTOM
31/05 | 0 |  | NOELL
31/05 | 0 |  | NOELL
31/05 | 0 |  | NOELL
31/05 | 0 |  | NOELL
31/05 | 0 |  | NOELL
31/05 | L2000 | 2005-04-04 | ANSALDO
31/05 | L2001 | 2005-04-04 | ANSALDO
31/05 | L2002 | 2005-04-04 | ANSALDO
31/05 | L1996 | 2005-04-04 | ANSALDO
32/05 | U2030 | 2005-03-04 | ALSTOM
32/05 | U2034 | 2005-03-04 | ALSTOM
32/05 | U2037 | 2005-03-04 | ALSTOM
32/05 | U2039 | 2005-03-04 | ALSTOM
32/05 | U2347 | 2005-07-01 | NOELL
32/05 | U2348 | 2005-07-01 | NOELL
32/05 | U2349 | 2005-07-01 | NOELL
32/05 | U2350 | 2005-07-01 | NOELL
32/05 | 0 |  | NOELL
32/05 | 0 |  | ANSALDO
32/05 | 0 |  | ANSALDO
32/05 | 0 |  | ANSALDO
32/05 | 0 |  | ANSALDO
32/05 | L1995 | 2005-03-04 | ALSTOM
32/05 | L2007 | 2005-03-04 | ALSTOM
32/05 | L1990 | 2005-03-04 | ALSTOM
32/05 | L1993 | 2005-03-04 | ALSTOM
32/05 | L2296 | 2005-07-01 | NOELL
32/05 | L2247 | 2005-07-01 | NOELL
32/05 | L2269 | 2005-07-01 | NOELL
32/05 | L2285 | 2005-07-01 | NOELL
32/05 | 0 |  | NOELL
32/05 | 0 |  | ANSALDO
32/05 | 0 |  | ANSALDO
32/05 | 0 |  | ANSALDO
32/05 | 0 |  | ANSALDO
33/05 | 0 |  | ALSTOM
33/05 | 0 |  | ALSTOM
33/05 | 0 |  | ALSTOM
33/05 | 0 |  | ALSTOM
33/05 | U2355 | 2005-07-01 | NOELL
33/05 | U2356 | 2005-07-01 | NOELL
33/05 | U2358 | 2005-07-01 | NOELL
33/05 | U2359 | 2005-07-01 | NOELL
33/05 | U2341 | 2005-07-01 | NOELL
33/05 | 0 |  | ANSALDO
33/05 | 0 |  | ANSALDO
33/05 | 0 |  | ANSALDO
33/05 | 0 |  | ANSALDO
33/05 | 0 |  | ALSTOM
33/05 | 0 |  | ALSTOM
33/05 | 0 |  | ALSTOM
33/05 | 0 |  | ALSTOM
33/05 | L2249 | 2005-07-01 | NOELL
33/05 | L2286 | 2005-07-01 | NOELL
33/05 | L2263 | 2005-07-01 | NOELL
33/05 | L2281 | 2005-07-01 | NOELL
33/05 | L2244 | 2005-07-01 | NOELL
33/05 | 0 |  | ANSALDO
33/05 | 0 |  | ANSALDO
33/05 | 0 |  | ANSALDO
33/05 | 0 |  | ANSALDO
34/05 | U2035 | 2005-04-06 | ALSTOM
34/05 | U2036 | 2005-04-06 | ALSTOM
34/05 | U2038 | 2005-04-06 | ALSTOM
34/05 | U2040 | 2005-04-06 | ALSTOM
34/05 | 0 |  | NOELL
34/05 | 0 |  | NOELL
34/05 | 0 |  | NOELL
34/05 | 0 |  | NOELL
34/05 | 0 |  | NOELL
34/05 | U2064 | 2005-04-07 | ANSALDO
34/05 | U2068 | 2005-04-07 | ANSALDO
34/05 | U2071 | 2005-04-07 | ANSALDO
34/05 | U0399 | 2005-04-07 | ANSALDO
34/05 | L1987 | 2005-04-06 | ALSTOM
34/05 | L1977 | 2005-04-06 | ALSTOM
34/05 | L2004 | 2005-04-06 | ALSTOM
34/05 | L1934 | 2005-04-06 | ALSTOM
34/05 | 0 |  | NOELL
34/05 | 0 |  | NOELL
34/05 | 0 |  | NOELL
34/05 | 0 |  | NOELL
34/05 | 0 |  | NOELL
34/05 | L1994 | 2005-04-07 | ANSALDO
34/05 | L2011 | 2005-04-07 | ANSALDO
34/05 | L2136 | 2005-04-07 | ANSALDO
34/05 | L0211 | 2005-04-07 | ANSALDO
35/05 | U2048 | 2005-04-06 | ALSTOM
35/05 | U2049 | 2005-04-06 | ALSTOM
35/05 | U2054 | 2005-04-06 | ALSTOM
35/05 | U2060 | 2005-04-06 | ALSTOM
35/05 | 0 |  | NOELL
35/05 | 0 |  | NOELL
35/05 | 0 |  | NOELL
35/05 | 0 |  | NOELL
35/05 | 0 |  | NOELL
35/05 | U0475 | 2005-05-18 | ANSALDO
35/05 | U0483 | 2005-05-18 | ANSALDO
35/05 | U0496 | 2005-05-18 | ANSALDO
35/05 | U2070 | 2005-05-18 | ANSALDO
35/05 | L2147 | 2005-04-06 | ALSTOM
35/05 | L2077 | 2005-04-06 | ALSTOM
35/05 | L2154 | 2005-04-06 | ALSTOM
35/05 | L2072 | 2005-04-06 | ALSTOM
35/05 | 0 |  | NOELL
35/05 | 0 |  | NOELL
35/05 | 0 |  | NOELL
35/05 | 0 |  | NOELL
35/05 | 0 |  | NOELL
35/05 | L0514 | 2005-05-18 | ANSALDO
35/05 | L0518 | 2005-05-18 | ANSALDO
35/05 | L0476 | 2005-05-18 | ANSALDO
35/05 | L2168 | 2005-05-18 | ANSALDO
36/05 | U2074 | 2005-04-07 | ALSTOM
36/05 | U2087 | 2005-04-07 | ALSTOM
36/05 | U2089 | 2005-04-07 | ALSTOM
36/05 | U2093 | 2005-04-07 | ALSTOM
36/05 | 0 |  | NOELL
36/05 | 0 |  | NOELL
36/05 | 0 |  | NOELL
36/05 | 0 |  | NOELL
36/05 | 0 |  | NOELL
36/05 | 0 |  | ANSALDO
36/05 | 0 |  | ANSALDO
36/05 | 0 |  | ANSALDO
36/05 | 0 |  | ANSALDO
36/05 | L2009 | 2005-04-07 | ALSTOM
36/05 | L2020 | 2005-04-07 | ALSTOM
36/05 | L2153 | 2005-04-07 | ALSTOM
36/05 | L1945 | 2005-04-07 | ALSTOM
36/05 | 0 |  | NOELL
36/05 | 0 |  | NOELL
36/05 | 0 |  | NOELL
36/05 | 0 |  | NOELL
36/05 | 0 |  | NOELL
36/05 | 0 |  | ANSALDO
36/05 | 0 |  | ANSALDO
36/05 | 0 |  | ANSALDO
36/05 | 0 |  | ANSALDO
37/05 | 0 |  | ALSTOM
37/05 | 0 |  | ALSTOM
37/05 | 0 |  | ALSTOM
37/05 | 0 |  | ALSTOM
37/05 | 0 |  | NOELL
37/05 | 0 |  | NOELL
37/05 | 0 |  | NOELL
37/05 | 0 |  | NOELL
37/05 | 0 |  | NOELL
37/05 | U0512 | 2005-05-18 | ANSALDO
37/05 | U1938 | 2005-05-18 | ANSALDO
37/05 | U2026 | 2005-05-18 | ANSALDO
37/05 | U2044 | 2005-05-18 | ANSALDO
37/05 | 0 |  | ALSTOM
37/05 | 0 |  | ALSTOM
37/05 | 0 |  | ALSTOM
37/05 | 0 |  | ALSTOM
37/05 | 0 |  | NOELL
37/05 | 0 |  | NOELL
37/05 | 0 |  | NOELL
37/05 | 0 |  | NOELL
37/05 | 0 |  | NOELL
37/05 | L0510 | 2005-05-18 | ANSALDO
37/05 | L2167 | 2005-05-18 | ANSALDO
37/05 | L2140 | 2005-05-18 | ANSALDO
37/05 | L2182 | 2005-05-18 | ANSALDO
38/05 | U2062 | 2005-05-18 | ALSTOM
38/05 | U2066 | 2005-05-18 | ALSTOM
38/05 | U2067 | 2005-05-18 | ALSTOM
38/05 | U2069 | 2005-05-18 | ALSTOM
38/05 | 0 |  | NOELL
38/05 | 0 |  | NOELL
38/05 | 0 |  | NOELL
38/05 | 0 |  | NOELL
38/05 | 0 |  | NOELL
38/05 | U2057 | 2005-05-19 | ANSALDO
38/05 | U2058 | 2005-05-19 | ANSALDO
38/05 | U2059 | 2005-05-19 | ANSALDO
38/05 | U2061 | 2005-05-19 | ANSALDO
38/05 | L2157 | 2005-05-18 | ALSTOM
38/05 | L2183 | 2005-05-18 | ALSTOM
38/05 | L2185 | 2005-05-18 | ALSTOM
38/05 | L2200 | 2005-05-18 | ALSTOM
38/05 | 0 |  | NOELL
38/05 | 0 |  | NOELL
38/05 | 0 |  | NOELL
38/05 | 0 |  | NOELL
38/05 | 0 |  | NOELL
38/05 | L2155 | 2005-05-19 | ANSALDO
38/05 | L2205 | 2005-05-19 | ANSALDO
38/05 | L2137 | 2005-05-19 | ANSALDO
38/05 | L2156 | 2005-05-19 | ANSALDO
39/05 | U2073 | 2005-05-19 | ALSTOM
39/05 | U2075 | 2005-05-19 | ALSTOM
39/05 | U2080 | 2005-05-19 | ALSTOM
39/05 | U2081 | 2005-05-19 | ALSTOM
39/05 | 0 |  | NOELL
39/05 | 0 |  | NOELL
39/05 | 0 |  | NOELL
39/05 | 0 |  | NOELL
39/05 | 0 |  | NOELL
39/05 | U2082 | 2005-05-19 | ANSALDO
39/05 | U2083 | 2005-05-19 | ANSALDO
39/05 | U2085 | 2005-05-19 | ANSALDO
39/05 | U2086 | 2005-05-19 | ANSALDO
39/05 | L2177 | 2005-05-19 | ALSTOM
39/05 | L2151 | 2005-05-19 | ALSTOM
39/05 | L2132 | 2005-05-19 | ALSTOM
39/05 | L2169 | 2005-05-19 | ALSTOM
39/05 | 0 |  | NOELL
39/05 | 0 |  | NOELL
39/05 | 0 |  | NOELL
39/05 | 0 |  | NOELL
39/05 | 0 |  | NOELL
39/05 | L2195 | 2005-05-19 | ANSALDO
39/05 | L2184 | 2005-05-19 | ANSALDO
39/05 | L2131 | 2005-05-19 | ANSALDO
39/05 | L2191 | 2005-05-19 | ANSALDO
40/05 | U2088 | 2005-05-20 | ALSTOM
40/05 | U2090 | 2005-05-20 | ALSTOM
40/05 | U2091 | 2005-05-20 | ALSTOM
40/05 | U2092 | 2005-05-20 | ALSTOM
40/05 | 0 |  | ANSALDO
40/05 | 0 |  | ANSALDO
40/05 | 0 |  | ANSALDO
40/05 | 0 |  | ANSALDO
40/05 | L2130 | 2005-05-20 | ALSTOM
40/05 | L2203 | 2005-05-20 | ALSTOM
40/05 | L2152 | 2005-05-20 | ALSTOM
40/05 | L2142 | 2005-05-20 | ALSTOM
40/05 | 0 |  | ANSALDO
40/05 | 0 |  | ANSALDO
40/05 | 0 |  | ANSALDO
40/05 | 0 |  | ANSALDO
41/05 | 0 |  | ALSTOM
41/05 | 0 |  | ALSTOM
41/05 | 0 |  | ALSTOM
41/05 | 0 |  | ALSTOM
41/05 | U2095 | 2005-05-20 | ANSALDO
41/05 | U2096 | 2005-05-20 | ANSALDO
41/05 | U2098 | 2005-05-20 | ANSALDO
41/05 | U2099 | 2005-05-20 | ANSALDO
41/05 | 0 |  | ALSTOM
41/05 | 0 |  | ALSTOM
41/05 | 0 |  | ALSTOM
41/05 | 0 |  | ALSTOM
41/05 | L2145 | 2005-05-20 | ANSALDO
41/05 | L2148 | 2005-05-20 | ANSALDO
41/05 | L2163 | 2005-05-20 | ANSALDO
41/05 | L2141 | 2005-05-20 | ANSALDO
42/05 | U2100 | 2005-05-23 | ALSTOM
42/05 | U2101 | 2005-05-23 | ALSTOM
42/05 | U2102 | 2005-05-23 | ALSTOM
42/05 | U2103 | 2005-05-23 | ALSTOM
42/05 | U2105 | 2005-05-23 | ANSALDO
42/05 | U2107 | 2005-05-23 | ANSALDO
42/05 | U2109 | 2005-05-23 | ANSALDO
42/05 | U2110 | 2005-05-23 | ANSALDO
42/05 | L2181 | 2005-05-23 | ALSTOM
42/05 | L2170 | 2005-05-23 | ALSTOM
42/05 | L2150 | 2005-05-23 | ALSTOM
42/05 | L2159 | 2005-05-23 | ALSTOM
42/05 | L2173 | 2005-05-23 | ANSALDO
42/05 | L2204 | 2005-05-23 | ANSALDO
42/05 | L2209 | 2005-05-23 | ANSALDO
42/05 | L2172 | 2005-05-23 | ANSALDO
43/05 | U2111 | 2005-05-24 | ALSTOM
43/05 | U2113 | 2005-05-24 | ALSTOM
43/05 | U2114 | 2005-05-24 | ALSTOM
43/05 | U2115 | 2005-05-24 | ALSTOM
43/05 | U2116 | 2005-05-24 | ANSALDO
43/05 | U2117 | 2005-05-24 | ANSALDO
43/05 | U2119 | 2005-05-24 | ANSALDO
43/05 | U2120 | 2005-05-24 | ANSALDO
43/05 | L2176 | 2005-05-24 | ALSTOM
43/05 | L2161 | 2005-05-24 | ALSTOM
43/05 | L2207 | 2005-05-24 | ALSTOM
43/05 | L2179 | 2005-05-24 | ALSTOM
43/05 | L2146 | 2005-05-24 | ANSALDO
43/05 | L2144 | 2005-05-24 | ANSALDO
43/05 | L2139 | 2005-05-24 | ANSALDO
43/05 | L2160 | 2005-05-24 | ANSALDO
44/05 | U2122 | 2005-05-24 | ALSTOM
44/05 | U2123 | 2005-05-24 | ALSTOM
44/05 | U2124 | 2005-05-24 | ALSTOM
44/05 | U2127 | 2005-05-24 | ALSTOM
44/05 | 0 |  | ANSALDO
44/05 | 0 |  | ANSALDO
44/05 | 0 |  | ANSALDO
44/05 | 0 |  | ANSALDO
44/05 | L2138 | 2005-05-24 | ALSTOM
44/05 | L2175 | 2005-05-24 | ALSTOM
44/05 | L2171 | 2005-05-24 | ALSTOM
44/05 | L2194 | 2005-05-24 | ALSTOM
44/05 | 0 |  | ANSALDO
44/05 | 0 |  | ANSALDO
44/05 | 0 |  | ANSALDO
44/05 | 0 |  | ANSALDO
45/05 | 0 |  | ALSTOM
45/05 | 0 |  | ALSTOM
45/05 | 0 |  | ALSTOM
45/05 | 0 |  | ALSTOM
45/05 | U2129 | 2005-05-24 | ANSALDO
45/05 | U2133 | 2005-05-24 | ANSALDO
45/05 | U2192 | 2005-05-24 | ANSALDO
45/05 | U2180 | 2005-05-24 | ANSALDO
45/05 | 0 |  | ALSTOM
45/05 | 0 |  | ALSTOM
45/05 | 0 |  | ALSTOM
45/05 | 0 |  | ALSTOM
45/05 | L2178 | 2005-05-24 | ANSALDO
45/05 | L2174 | 2005-05-24 | ANSALDO
45/05 | L2166 | 2005-05-24 | ANSALDO
45/05 | L2187 | 2005-05-24 | ANSALDO
46/05 | U1825 | 2005-05-24 | ALSTOM
46/05 | U2050 | 2005-05-24 | ALSTOM
46/05 | U2051 | 2005-05-24 | ALSTOM
46/05 | U2052 | 2005-05-24 | ALSTOM
46/05 | U2128 | 2005-05-25 | ANSALDO
46/05 | U2079 | 2005-05-25 | ANSALDO
46/05 | U2084 | 2005-05-25 | ANSALDO
46/05 | U2097 | 2005-05-25 | ANSALDO
46/05 | L2162 | 2005-05-24 | ALSTOM
46/05 | L2214 | 2005-05-24 | ALSTOM
46/05 | L2188 | 2005-05-24 | ALSTOM
46/05 | L2241 | 2005-05-24 | ALSTOM
46/05 | L2215 | 2005-05-25 | ANSALDO
46/05 | L2196 | 2005-05-25 | ANSALDO
46/05 | L2158 | 2005-05-25 | ANSALDO
46/05 | L2223 | 2005-05-25 | ANSALDO
47/05 | U2053 | 2005-05-25 | ALSTOM
47/05 | U2055 | 2005-05-25 | ALSTOM
47/05 | U2065 | 2005-05-25 | ALSTOM
47/05 | U2076 | 2005-05-25 | ALSTOM
47/05 | 0 |  | ANSALDO
47/05 | 0 |  | ANSALDO
47/05 | 0 |  | ANSALDO
47/05 | 0 |  | ANSALDO
47/05 | L2238 | 2005-05-25 | ALSTOM
47/05 | L2186 | 2005-05-25 | ALSTOM
47/05 | L2240 | 2005-05-25 | ALSTOM
47/05 | L2199 | 2005-05-25 | ALSTOM
47/05 | 0 |  | ANSALDO
47/05 | 0 |  | ANSALDO
47/05 | 0 |  | ANSALDO
47/05 | 0 |  | ANSALDO
48/05 | U2104 | 2005-05-25 | ALSTOM
48/05 | U2106 | 2005-05-25 | ALSTOM
48/05 | U2108 | 2005-05-25 | ALSTOM
48/05 | U2112 | 2005-05-25 | ALSTOM
48/05 | 0 |  | ANSALDO
48/05 | 0 |  | ANSALDO
48/05 | 0 |  | ANSALDO
48/05 | 0 |  | ANSALDO
48/05 | L2213 | 2005-05-25 | ALSTOM
48/05 | L2189 | 2005-05-25 | ALSTOM
48/05 | L2165 | 2005-05-25 | ALSTOM
48/05 | L2198 | 2005-05-25 | ALSTOM
48/05 | 0 |  | ANSALDO
48/05 | 0 |  | ANSALDO
48/05 | 0 |  | ANSALDO
48/05 | 0 |  | ANSALDO
49/05 | 0 |  | ALSTOM
49/05 | 0 |  | ALSTOM
49/05 | 0 |  | ALSTOM
49/05 | 0 |  | ALSTOM
49/05 | U2118 | 2005-05-25 | ANSALDO
49/05 | U2121 | 2005-05-25 | ANSALDO
49/05 | U2125 | 2005-05-25 | ANSALDO
49/05 | U2126 | 2005-05-25 | ANSALDO
49/05 | 0 |  | ALSTOM
49/05 | 0 |  | ALSTOM
49/05 | 0 |  | ALSTOM
49/05 | 0 |  | ALSTOM
49/05 | L2208 | 2005-05-25 | ANSALDO
49/05 | L2190 | 2005-05-25 | ANSALDO
49/05 | L2239 | 2005-05-25 | ANSALDO
49/05 | L2193 | 2005-05-25 | ANSALDO
50/05 | U2025 | 2005-06-29 | ALSTOM
50/05 | U2303 | 2005-06-29 | ALSTOM
50/05 | U2305 | 2005-06-29 | ALSTOM
50/05 | U2309 | 2005-06-29 | ALSTOM
50/05 | U2134 | 2005-06-29 | ANSALDO
50/05 | U2306 | 2005-06-29 | ANSALDO
50/05 | U2307 | 2005-06-29 | ANSALDO
50/05 | U2308 | 2005-06-29 | ANSALDO
50/05 | L2260 | 2005-06-29 | ALSTOM
50/05 | L2270 | 2005-06-29 | ALSTOM
50/05 | L2272 | 2005-06-29 | ALSTOM
50/05 | L2224 | 2005-06-29 | ALSTOM
50/05 | L2210 | 2005-06-29 | ANSALDO
50/05 | L2257 | 2005-06-29 | ANSALDO
50/05 | L2271 | 2005-06-29 | ANSALDO
50/05 | L2280 | 2005-06-29 | ANSALDO
51/05 | U2310 | 2005-06-29 | ALSTOM
51/05 | U2311 | 2005-06-29 | ALSTOM
51/05 | U2312 | 2005-06-29 | ALSTOM
51/05 | U2317 | 2005-06-29 | ALSTOM
51/05 | U2313 | 2005-06-29 | ANSALDO
51/05 | U2314 | 2005-06-29 | ANSALDO
51/05 | U2315 | 2005-06-29 | ANSALDO
51/05 | U2316 | 2005-06-29 | ANSALDO
51/05 | L2242 | 2005-06-29 | ALSTOM
51/05 | L2258 | 2005-06-29 | ALSTOM
51/05 | L2252 | 2005-06-29 | ALSTOM
51/05 | L2283 | 2005-06-29 | ALSTOM
51/05 | L2232 | 2005-06-29 | ANSALDO
51/05 | L2227 | 2005-06-29 | ANSALDO
51/05 | L2197 | 2005-06-29 | ANSALDO
51/05 | L2219 | 2005-06-29 | ANSALDO
52/05 | 0 |  | ALSTOM
52/05 | 0 |  | ALSTOM
52/05 | 0 |  | ALSTOM
52/05 | 0 |  | ALSTOM
52/05 | 0 |  | ANSALDO
52/05 | 0 |  | ANSALDO
52/05 | 0 |  | ANSALDO
52/05 | 0 |  | ANSALDO
52/05 | 0 |  | ALSTOM
52/05 | 0 |  | ALSTOM
52/05 | 0 |  | ALSTOM
52/05 | 0 |  | ALSTOM
52/05 | 0 |  | ANSALDO
52/05 | 0 |  | ANSALDO
52/05 | 0 |  | ANSALDO
52/05 | 0 |  | ANSALDO
01/06 | 0 |  | ALSTOM
01/06 | 0 |  | ALSTOM
01/06 | 0 |  | ALSTOM
01/06 | 0 |  | ALSTOM
01/06 | 0 |  | ANSALDO
01/06 | 0 |  | ANSALDO
01/06 | 0 |  | ANSALDO
01/06 | 0 |  | ANSALDO
01/06 | 0 |  | ALSTOM
01/06 | 0 |  | ALSTOM
01/06 | 0 |  | ALSTOM
01/06 | 0 |  | ALSTOM
01/06 | 0 |  | ANSALDO
01/06 | 0 |  | ANSALDO
01/06 | 0 |  | ANSALDO
01/06 | 0 |  | ANSALDO
02/06 | U2318 | 2005-06-29 | ALSTOM
02/06 | U2319 | 2005-06-29 | ALSTOM
02/06 | U2320 | 2005-06-29 | ALSTOM
02/06 | U2325 | 2005-06-29 | ALSTOM
02/06 | U2321 | 2005-06-29 | ANSALDO
02/06 | U2322 | 2005-06-29 | ANSALDO
02/06 | U2323 | 2005-06-29 | ANSALDO
02/06 | U2324 | 2005-06-29 | ANSALDO
02/06 | L2278 | 2005-06-29 | ALSTOM
02/06 | L2216 | 2005-06-29 | ALSTOM
02/06 | L2245 | 2005-06-29 | ALSTOM
02/06 | L2217 | 2005-06-29 | ALSTOM
02/06 | L2225 | 2005-06-29 | ANSALDO
02/06 | L2265 | 2005-06-29 | ANSALDO
02/06 | L2229 | 2005-06-29 | ANSALDO
02/06 | L2201 | 2005-06-29 | ANSALDO
03/06 | U2326 | 2005-06-30 | ALSTOM
03/06 | U2327 | 2005-06-30 | ALSTOM
03/06 | U2328 | 2005-06-30 | ALSTOM
03/06 | U2337 | 2005-06-30 | ALSTOM
03/06 | U2329 | 2005-06-29 | ANSALDO
03/06 | U2330 | 2005-06-29 | ANSALDO
03/06 | U2334 | 2005-06-29 | ANSALDO
03/06 | U2335 | 2005-06-29 | ANSALDO
03/06 | L2220 | 2005-06-30 | ALSTOM
03/06 | L2202 | 2005-06-30 | ALSTOM
03/06 | L2222 | 2005-06-30 | ALSTOM
03/06 | L2277 | 2005-06-30 | ALSTOM
03/06 | L2231 | 2005-06-29 | ANSALDO
03/06 | L2251 | 2005-06-29 | ANSALDO
03/06 | L2235 | 2005-06-29 | ANSALDO
03/06 | L2264 | 2005-06-29 | ANSALDO
04/06 | U2338 | 2005-07-01 | ALSTOM
04/06 | U2339 | 2005-07-01 | ALSTOM
04/06 | U2331 | 2005-07-01 | ALSTOM
04/06 | U2332 | 2005-07-01 | ALSTOM
04/06 | U2342 | 2005-07-01 | ANSALDO
04/06 | U2343 | 2005-07-01 | ANSALDO
04/06 | U2344 | 2005-07-01 | ANSALDO
04/06 | U2345 | 2005-07-01 | ANSALDO
04/06 | L2282 | 2005-07-01 | ALSTOM
04/06 | L2262 | 2005-07-01 | ALSTOM
04/06 | L2233 | 2005-07-01 | ALSTOM
04/06 | L2291 | 2005-07-01 | ALSTOM
04/06 | L2253 | 2005-07-01 | ANSALDO
04/06 | L2236 | 2005-07-01 | ANSALDO
04/06 | L2289 | 2005-07-01 | ANSALDO
04/06 | L2256 | 2005-07-01 | ANSALDO
05/06 | 0 |  | ALSTOM
05/06 | 0 |  | ALSTOM
05/06 | 0 |  | ALSTOM
05/06 | 0 |  | ALSTOM
05/06 | 0 |  | ANSALDO
05/06 | 0 |  | ANSALDO
05/06 | 0 |  | ANSALDO
05/06 | 0 |  | ANSALDO
05/06 | 0 |  | ALSTOM
05/06 | 0 |  | ALSTOM
05/06 | 0 |  | ALSTOM
05/06 | 0 |  | ALSTOM
05/06 | 0 |  | ANSALDO
05/06 | 0 |  | ANSALDO
05/06 | 0 |  | ANSALDO
05/06 | 0 |  | ANSALDO
06/06 | U2333 | 2005-07-25 | ALSTOM
06/06 | U2336 | 2005-07-25 | ALSTOM
06/06 | U2340 | 2005-07-25 | ALSTOM
06/06 | U2357 | 2005-07-25 | ALSTOM
06/06 | U2351 | 2005-07-01 | ANSALDO
06/06 | U2352 | 2005-07-01 | ANSALDO
06/06 | U2353 | 2005-07-01 | ANSALDO
06/06 | U2354 | 2005-07-01 | ANSALDO
06/06 | L2279 | 2005-07-25 | ALSTOM
06/06 | L2273 | 2005-07-25 | ALSTOM
06/06 | L2206 | 2005-07-25 | ALSTOM
06/06 | L2486 | 2005-07-25 | ALSTOM
06/06 | L2243 | 2005-07-01 | ANSALDO
06/06 | L0520 | 2005-07-01 | ANSALDO
06/06 | L2246 | 2005-07-01 | ANSALDO
06/06 | L2218 | 2005-07-01 | ANSALDO
07/06 | U2363 | 2005-08-05 | ALSTOM
07/06 | U2364 | 2005-08-05 | ALSTOM
07/06 | U2365 | 2005-08-05 | ALSTOM
07/06 | U2366 | 2005-08-05 | ALSTOM
07/06 | U2346 | 2005-08-05 | ANSALDO
07/06 | U2360 | 2005-08-05 | ANSALDO
07/06 | U2361 | 2005-08-05 | ANSALDO
07/06 | U2367 | 2005-08-05 | ANSALDO
07/06 | L2266 | 2005-08-05 | ALSTOM
07/06 | L2522 | 2005-08-05 | ALSTOM
07/06 | L2298 | 2005-08-05 | ALSTOM
07/06 | L2287 | 2005-08-05 | ALSTOM
07/06 | L2301 | 2005-08-05 | ANSALDO
07/06 | L2254 | 2005-08-05 | ANSALDO
07/06 | L2304 | 2005-08-05 | ANSALDO
07/06 | L2228 | 2005-08-05 | ANSALDO
08/06 | U2371 | 2005-08-15 | ALSTOM
08/06 | U2372 | 2005-08-15 | ALSTOM
08/06 | U2373 | 2005-08-15 | ALSTOM
08/06 | U2375 | 2005-08-15 | ALSTOM
08/06 | U2368 | 2005-08-05 | ANSALDO
08/06 | U2369 | 2005-08-05 | ANSALDO
08/06 | U2370 | 2005-08-05 | ANSALDO
08/06 | U2376 | 2005-08-05 | ANSALDO
08/06 | L2299 | 2005-08-15 | ALSTOM
08/06 | L2497 | 2005-08-15 | ALSTOM
08/06 | L2267 | 2005-08-15 | ALSTOM
08/06 | L2297 | 2005-08-15 | ALSTOM
08/06 | L2284 | 2005-08-05 | ANSALDO
08/06 | L2484 | 2005-08-05 | ANSALDO
08/06 | L2290 | 2005-08-05 | ANSALDO
08/06 | L2248 | 2005-08-05 | ANSALDO
09/06 | 0 |  | ALSTOM
09/06 | 0 |  | ALSTOM
09/06 | 0 |  | ALSTOM
09/06 | 0 |  | ALSTOM
09/06 | 0 |  | ANSALDO
09/06 | 0 |  | ANSALDO
09/06 | 0 |  | ANSALDO
09/06 | 0 |  | ANSALDO
09/06 | 0 |  | ALSTOM
09/06 | 0 |  | ALSTOM
09/06 | 0 |  | ALSTOM
09/06 | 0 |  | ALSTOM
09/06 | 0 |  | ANSALDO
09/06 | 0 |  | ANSALDO
09/06 | 0 |  | ANSALDO
09/06 | 0 |  | ANSALDO
10/06 | U2380 | 2005-08-16 | ALSTOM
10/06 | U2381 | 2005-08-16 | ALSTOM
10/06 | U2382 | 2005-08-16 | ALSTOM
10/06 | U2383 | 2005-08-16 | ALSTOM
10/06 | U2377 | 2005-08-15 | ANSALDO
10/06 | U2378 | 2005-08-15 | ANSALDO
10/06 | U2379 | 2005-08-15 | ANSALDO
10/06 | U2384 | 2005-08-15 | ANSALDO
10/06 | L2255 | 2005-08-16 | ALSTOM
10/06 | L2504 | 2005-08-16 | ALSTOM
10/06 | L2300 | 2005-08-16 | ALSTOM
10/06 | L2226 | 2005-08-16 | ALSTOM
10/06 | L2268 | 2005-08-15 | ANSALDO
10/06 | L2274 | 2005-08-15 | ANSALDO
10/06 | L2250 | 2005-08-15 | ANSALDO
10/06 | L2294 | 2005-08-15 | ANSALDO
11/06 | U2388 | 2005-08-17 | ALSTOM
11/06 | U2391 | 2005-08-17 | ALSTOM
11/06 | U2392 | 2005-08-17 | ALSTOM
11/06 | U2395 | 2005-08-17 | ALSTOM
11/06 | U2385 | 2005-08-16 | ANSALDO
11/06 | U2386 | 2005-08-16 | ANSALDO
11/06 | U2387 | 2005-08-16 | ANSALDO
11/06 | U2396 | 2005-08-16 | ANSALDO
11/06 | L2275 | 2005-08-17 | ALSTOM
11/06 | L2234 | 2005-08-17 | ALSTOM
11/06 | L2302 | 2005-08-17 | ALSTOM
11/06 | L2292 | 2005-08-17 | ALSTOM
11/06 | L2230 | 2005-08-16 | ANSALDO
11/06 | L2149 | 2005-08-16 | ANSALDO
11/06 | L2237 | 2005-08-16 | ANSALDO
11/06 | L2505 | 2005-08-16 | ANSALDO
12/06 | U2412 | 2005-08-19 | ALSTOM
12/06 | U2408 | 2005-08-19 | ALSTOM
12/06 | U2409 | 2005-08-19 | ALSTOM
12/06 | U2406 | 2005-08-19 | ALSTOM
12/06 | U2398 | 2005-08-17 | ANSALDO
12/06 | U2399 | 2005-08-17 | ANSALDO
12/06 | U2400 | 2005-08-17 | ANSALDO
12/06 | U2414 | 2005-08-17 | ANSALDO
12/06 | L2276 | 2005-08-19 | ALSTOM
12/06 | L2259 | 2005-08-19 | ALSTOM
12/06 | L2261 | 2005-08-19 | ALSTOM
12/06 | L2533 | 2005-08-19 | ALSTOM
12/06 | L2495 | 2005-08-17 | ANSALDO
12/06 | L2492 | 2005-08-17 | ANSALDO
12/06 | L2485 | 2005-08-17 | ANSALDO
12/06 | L2491 | 2005-08-17 | ANSALDO
13/06 | 0 |  | ALSTOM
13/06 | 0 |  | ALSTOM
13/06 | 0 |  | ALSTOM
13/06 | 0 |  | ALSTOM
13/06 | 0 |  | ANSALDO
13/06 | 0 |  | ANSALDO
13/06 | 0 |  | ANSALDO
13/06 | 0 |  | ANSALDO
13/06 | 0 |  | ALSTOM
13/06 | 0 |  | ALSTOM
13/06 | 0 |  | ALSTOM
13/06 | 0 |  | ALSTOM
13/06 | 0 |  | ANSALDO
13/06 | 0 |  | ANSALDO
13/06 | 0 |  | ANSALDO
13/06 | 0 |  | ANSALDO
14/06 | U2434 | 2005-09-19 | ALSTOM
14/06 | U2442 | 2005-09-19 | ALSTOM
14/06 | U2464 | 2005-09-19 | ALSTOM
14/06 | U1843 | 2005-09-19 | ALSTOM
14/06 | U2416 | 2005-08-19 | ANSALDO
14/06 | U2418 | 2005-08-19 | ANSALDO
14/06 | U2430 | 2005-08-19 | ANSALDO
14/06 | U2432 | 2005-08-19 | ANSALDO
14/06 | L2500 | 2005-09-19 | ALSTOM
14/06 | L2481 | 2005-09-19 | ALSTOM
14/06 | L2482 | 2005-09-19 | ALSTOM
14/06 | L2514 | 2005-09-19 | ALSTOM
14/06 | L2499 | 2005-08-19 | ANSALDO
14/06 | L2498 | 2005-08-19 | ANSALDO
14/06 | L2489 | 2005-08-19 | ANSALDO
14/06 | L2496 | 2005-08-19 | ANSALDO
15/06 | U2457 | 2005-09-20 | ALSTOM
15/06 | U2458 | 2005-09-20 | ALSTOM
15/06 | U2459 | 2005-09-20 | ALSTOM
15/06 | U2460 | 2005-09-20 | ALSTOM
15/06 | U2078 | 2005-09-19 | ANSALDO
15/06 | U2362 | 2005-09-19 | ANSALDO
15/06 | U2374 | 2005-09-19 | ANSALDO
15/06 | U2503 | 2005-09-19 | ANSALDO
15/06 | L2506 | 2005-09-20 | ALSTOM
15/06 | L2591 | 2005-09-20 | ALSTOM
15/06 | L2549 | 2005-09-20 | ALSTOM
15/06 | L2529 | 2005-09-20 | ALSTOM
15/06 | L2539 | 2005-09-19 | ANSALDO
15/06 | L2523 | 2005-09-19 | ANSALDO
15/06 | L2488 | 2005-09-19 | ANSALDO
15/06 | L2534 | 2005-09-19 | ANSALDO
16/06 | U2397 | 2005-09-22 | ALSTOM
16/06 | U2401 | 2005-09-22 | ALSTOM
16/06 | U2403 | 2005-09-22 | ALSTOM
16/06 | U2407 | 2005-09-22 | ALSTOM
16/06 | U2389 | 2005-09-20 | ANSALDO
16/06 | U2390 | 2005-09-20 | ANSALDO
16/06 | U2393 | 2005-09-20 | ANSALDO
16/06 | U2394 | 2005-09-20 | ANSALDO
16/06 | L2518 | 2005-09-22 | ALSTOM
16/06 | L2524 | 2005-09-22 | ALSTOM
16/06 | L2587 | 2005-09-22 | ALSTOM
16/06 | L2545 | 2005-09-22 | ALSTOM
16/06 | L2501 | 2005-09-20 | ANSALDO
16/06 | L2532 | 2005-09-20 | ANSALDO
16/06 | L2510 | 2005-09-20 | ANSALDO
16/06 | L2509 | 2005-09-20 | ANSALDO
17/06 | 0 |  | ALSTOM
17/06 | 0 |  | ALSTOM
17/06 | 0 |  | ALSTOM
17/06 | 0 |  | ALSTOM
17/06 | 0 |  | ANSALDO
17/06 | 0 |  | ANSALDO
17/06 | 0 |  | ANSALDO
17/06 | 0 |  | ANSALDO
17/06 | 0 |  | ALSTOM
17/06 | 0 |  | ALSTOM
17/06 | 0 |  | ALSTOM
17/06 | 0 |  | ALSTOM
17/06 | 0 |  | ANSALDO
17/06 | 0 |  | ANSALDO
17/06 | 0 |  | ANSALDO
17/06 | 0 |  | ANSALDO
18/06 | U2417 | 2005-10-12 | ALSTOM
18/06 | U2419 | 2005-10-12 | ALSTOM
18/06 | U2420 | 2005-10-12 | ALSTOM
18/06 | U2421 | 2005-10-12 | ALSTOM
18/06 | U2410 | 2005-09-25 | ANSALDO
18/06 | U2411 | 2005-09-25 | ANSALDO
18/06 | U2413 | 2005-09-25 | ANSALDO
18/06 | U2415 | 2005-09-25 | ANSALDO
18/06 | L2554 | 2005-10-12 | ALSTOM
18/06 | L2512 | 2005-10-12 | ALSTOM
18/06 | L2540 | 2005-10-12 | ALSTOM
18/06 | L2521 | 2005-10-12 | ALSTOM
18/06 | L2547 | 2005-09-25 | ANSALDO
18/06 | L2561 | 2005-09-25 | ANSALDO
18/06 | L2507 | 2005-09-25 | ANSALDO
18/06 | L2586 | 2005-09-25 | ANSALDO
19/06 | U2428 | 2005-10-12 | ALSTOM
19/06 | U2429 | 2005-10-12 | ALSTOM
19/06 | U2431 | 2005-10-12 | ALSTOM
19/06 | U2433 | 2005-10-12 | ALSTOM
19/06 | U2422 | 2005-10-12 | ANSALDO
19/06 | U2425 | 2005-10-12 | ANSALDO
19/06 | U2426 | 2005-10-12 | ANSALDO
19/06 | U2427 | 2005-10-12 | ANSALDO
19/06 | L2544 | 2005-10-12 | ALSTOM
19/06 | L2531 | 2005-10-12 | ALSTOM
19/06 | L2487 | 2005-10-12 | ALSTOM
19/06 | L2560 | 2005-10-12 | ALSTOM
19/06 | L2562 | 2005-10-12 | ANSALDO
19/06 | L2511 | 2005-10-12 | ANSALDO
19/06 | L2548 | 2005-10-12 | ANSALDO
19/06 | L2552 | 2005-10-12 | ANSALDO
20/06 | U2444 | 2005-10-31 | ALSTOM
20/06 | U2445 | 2005-10-31 | ALSTOM
20/06 | U2448 | 2005-10-31 | ALSTOM
20/06 | U2449 | 2005-10-31 | ALSTOM
20/06 | U2435 | 2005-10-31 | ANSALDO
20/06 | U2438 | 2005-10-31 | ANSALDO
20/06 | U2440 | 2005-10-31 | ANSALDO
20/06 | U2740 | 2005-10-31 | ANSALDO
20/06 | L2519 | 2005-10-31 | ALSTOM
20/06 | L2516 | 2005-10-31 | ALSTOM
20/06 | L2535 | 2005-10-31 | ALSTOM
20/06 | L2483 | 2005-10-31 | ALSTOM
20/06 | L2527 | 2005-10-31 | ANSALDO
20/06 | L2508 | 2005-10-31 | ANSALDO
20/06 | L2558 | 2005-10-31 | ANSALDO
20/06 | L2573 | 2005-10-31 | ANSALDO
21/06 | 0 |  | ALSTOM
21/06 | 0 |  | ALSTOM
21/06 | 0 |  | ALSTOM
21/06 | 0 |  | ALSTOM
21/06 | 0 |  | ANSALDO
21/06 | 0 |  | ANSALDO
21/06 | 0 |  | ANSALDO
21/06 | 0 |  | ANSALDO
21/06 | 0 |  | ALSTOM
21/06 | 0 |  | ALSTOM
21/06 | 0 |  | ALSTOM
21/06 | 0 |  | ALSTOM
21/06 | 0 |  | ANSALDO
21/06 | 0 |  | ANSALDO
21/06 | 0 |  | ANSALDO
21/06 | 0 |  | ANSALDO
22/06 | U2476 | 2005-11-01 | ALSTOM
22/06 | U2477 | 2005-11-01 | ALSTOM
22/06 | U2478 | 2005-11-01 | ALSTOM
22/06 | U2479 | 2005-11-01 | ALSTOM
22/06 | U2450 | 2005-11-01 | ANSALDO
22/06 | U2451 | 2005-11-01 | ANSALDO
22/06 | U2452 | 2005-11-01 | ANSALDO
22/06 | U2455 | 2005-11-01 | ANSALDO
22/06 | L2525 | 2005-11-01 | ALSTOM
22/06 | L2546 | 2005-11-01 | ALSTOM
22/06 | L2513 | 2005-11-01 | ALSTOM
22/06 | L2530 | 2005-11-01 | ALSTOM
22/06 | L2517 | 2005-11-01 | ANSALDO
22/06 | L2520 | 2005-11-01 | ANSALDO
22/06 | L2557 | 2005-11-01 | ANSALDO
22/06 | L2555 | 2005-11-01 | ANSALDO
23/06 | 0 |  | ALSTOM
23/06 | 0 |  | ALSTOM
23/06 | 0 |  | ALSTOM
23/06 | 0 |  | ALSTOM
23/06 | U2463 | 2005-11-01 | ANSALDO
23/06 | U2736 | 2005-11-01 | ANSALDO
23/06 | U2466 | 2005-11-01 | ANSALDO
23/06 | U2473 | 2005-11-01 | ANSALDO
23/06 | 0 |  | ALSTOM
23/06 | 0 |  | ALSTOM
23/06 | 0 |  | ALSTOM
23/06 | 0 |  | ALSTOM
23/06 | L2559 |  | ANSALDO
23/06 | L2536 | 2005-11-01 | ANSALDO
23/06 | L2590 | 2005-11-01 | ANSALDO
23/06 | L2565 | 2005-11-01 | ANSALDO
24/06 | 0 | 2005-11-01 | ALSTOM
24/06 | 0 |  | ALSTOM
24/06 | 0 |  | ALSTOM
24/06 | 0 |  | ALSTOM
24/06 | U0501 | 2005-11-02 | ANSALDO
24/06 | U1710 | 2005-11-02 | ANSALDO
24/06 | U1869 | 2005-11-02 | ANSALDO
24/06 | U2735 | 2005-11-02 | ANSALDO
24/06 | 0 |  | ALSTOM
24/06 | 0 |  | ALSTOM
24/06 | 0 |  | ALSTOM
24/06 | 0 |  | ALSTOM
24/06 | U2629 | 2005-11-02 | ANSALDO
24/06 | L2626 | 2005-11-02 | ANSALDO
24/06 | L2592 | 2005-11-02 | ANSALDO
24/06 | L2667 | 2005-11-02 | ANSALDO
25/06 | 0 |  | ALSTOM
25/06 | 0 |  | ALSTOM
25/06 | 0 |  | ALSTOM
25/06 | 0 |  | ALSTOM
25/06 | 0 |  | ANSALDO
25/06 | 0 |  | ANSALDO
25/06 | 0 |  | ANSALDO
25/06 | 0 |  | ANSALDO
25/06 | 0 |  | ALSTOM
25/06 | 0 |  | ALSTOM
25/06 | 0 |  | ALSTOM
25/06 | 0 |  | ALSTOM
25/06 | 0 |  | ANSALDO
25/06 | 0 |  | ANSALDO
25/06 | 0 |  | ANSALDO
25/06 | 0 |  | ANSALDO
26/06 | 0 |  | ALSTOM
26/06 | 0 |  | ALSTOM
26/06 | 0 |  | ALSTOM
26/06 | 0 |  | ALSTOM
26/06 | U2733 | 2005-11-02 | ANSALDO
26/06 | U2734 | 2005-11-02 | ANSALDO
26/06 | U2732 | 2005-11-02 | ANSALDO
26/06 | #REF! | 2005-11-02 | ANSALDO
26/06 | 0 |  | ALSTOM
26/06 | 0 |  | ALSTOM
26/06 | 0 |  | ALSTOM
26/06 | 0 |  | ALSTOM
26/06 | L2645 | 2005-11-02 | ANSALDO
26/06 | L2570 | 2005-11-02 | ANSALDO
26/06 | L2632 | 2005-11-02 | ANSALDO
26/06 | #REF! | 2005-11-02 | ANSALDO
27/06 | U2729 | 2005-11-02 | ANSALDO
27/06 | U2730 | 2005-11-02 | ANSALDO
27/06 | U2731 | 2005-11-02 | ANSALDO
27/06 | U2727 | 2005-11-02 | ANSALDO
27/06 | L2636 | 2005-11-02 | ANSALDO
27/06 | L2581 | 2005-11-02 | ANSALDO
27/06 | L2649 | 2005-11-02 | ANSALDO
27/06 | L2659 | 2005-11-02 | ANSALDO
28/06 | U2402 | 2005-10-31 | ANSALDO
28/06 | U2404 | 2005-10-31 | ANSALDO
28/06 | U2405 | 2005-10-31 | ANSALDO
28/06 | U2423 | 2005-10-31 | ANSALDO
28/06 | L2567 | 2005-10-31 | ANSALDO
28/06 | L2550 | 2005-10-31 | ANSALDO
28/06 | L2494 | 2005-10-31 | ANSALDO
28/06 | L2502 | 2005-10-31 | ANSALDO
29/06 | 0 |  | ANSALDO
29/06 | 0 |  | ANSALDO
29/06 | 0 |  | ANSALDO
29/06 | 0 |  | ANSALDO
29/06 | 0 |  | ANSALDO
29/06 | 0 |  | ANSALDO
29/06 | 0 |  | ANSALDO
29/06 | 0 |  | ANSALDO
30/06 | U2424 | 2005-10-31 | ANSALDO
30/06 | U2436 | 2005-10-31 | ANSALDO
30/06 | U2437 | 2005-10-31 | ANSALDO
30/06 | U2439 | 2005-10-31 | ANSALDO
30/06 | L2564 | 2005-10-31 | ANSALDO
30/06 | L2563 | 2005-10-31 | ANSALDO
30/06 | L2571 | 2005-10-31 | ANSALDO
30/06 | L2585 | 2005-10-31 | ANSALDO
31/06 | U2441 | 2005-10-31 | ANSALDO
31/06 | U2443 | 2005-10-31 | ANSALDO
31/06 | U2446 | 2005-10-31 | ANSALDO
31/06 | U2447 | 2005-10-31 | ANSALDO
31/06 | L2553 | 2005-10-31 | ANSALDO
31/06 | L2566 | 2005-10-31 | ANSALDO
31/06 | L2613 | 2005-10-31 | ANSALDO
31/06 | L2577 | 2005-10-31 | ANSALDO
32/06 | U2453 | 2005-10-31 | ANSALDO
32/06 | U2454 | 2005-10-31 | ANSALDO
32/06 | U2456 | 2005-10-31 | ANSALDO
32/06 | U2461 | 2005-10-31 | ANSALDO
32/06 | L2612 | 2005-10-31 | ANSALDO
32/06 | L2551 | 2005-10-31 | ANSALDO
32/06 | L2493 | 2005-10-31 | ANSALDO
32/06 | L2616 | 2005-10-31 | ANSALDO
33/06 | 0 |  | ANSALDO
33/06 | 0 |  | ANSALDO
33/06 | 0 |  | ANSALDO
33/06 | 0 |  | ANSALDO
33/06 | 0 |  | ANSALDO
33/06 | 0 |  | ANSALDO
33/06 | 0 |  | ANSALDO
33/06 | 0 |  | ANSALDO
34/06 | U2462 | 2005-10-31 | ANSALDO
34/06 | U2465 | 2005-10-31 | ANSALDO
34/06 | U2467 | 2005-10-31 | ANSALDO
34/06 | U2468 | 2005-10-31 | ANSALDO
34/06 | L2528 | 2005-10-31 | ANSALDO
34/06 | L2541 | 2005-10-31 | ANSALDO
34/06 | L2597 | 2005-10-31 | ANSALDO
34/06 | L2569 | 2005-10-31 | ANSALDO
35/06 | U2469 | 2005-11-01 | ANSALDO
35/06 | U2470 | 2005-11-01 | ANSALDO
35/06 | U2471 | 2005-11-01 | ANSALDO
35/06 | U2472 | 2005-11-01 | ANSALDO
35/06 | L2568 | 2005-11-01 | ANSALDO
35/06 | L2614 | 2005-11-01 | ANSALDO
35/06 | L2538 | 2005-11-01 | ANSALDO
35/06 | L2580 | 2005-11-01 | ANSALDO
36/06 | U2474 | 2005-11-01 | ANSALDO
36/06 | U2475 | 2005-11-01 | ANSALDO
36/06 | U2480 | 2005-11-01 | ANSALDO
36/06 | U2490 | 2005-11-01 | ANSALDO
36/06 | L2640 | 2005-11-01 | ANSALDO
36/06 | L2543 | 2005-11-01 | ANSALDO
36/06 | L2622 | 2005-11-01 | ANSALDO
36/06 | L2537 | 2005-11-01 | ANSALDO
37/06 | 0 |  | ANSALDO
37/06 | 0 |  | ANSALDO
37/06 | 0 |  | ANSALDO
37/06 | 0 |  | ANSALDO
37/06 | 0 |  | ANSALDO
37/06 | 0 |  | ANSALDO
37/06 | 0 |  | ANSALDO
37/06 | 0 |  | ANSALDO
38/06 | U2515 | 2005-11-01 | ANSALDO
38/06 | U2526 | 2005-11-01 | ANSALDO
38/06 | U2542 | 2005-11-01 | ANSALDO
38/06 | U2574 | 2005-11-01 | ANSALDO
38/06 | L2779 | 2005-11-01 | ANSALDO
38/06 | L2582 | 2005-11-01 | ANSALDO
38/06 | L2575 | 2005-11-01 | ANSALDO
38/06 | L2593 | 2005-11-01 | ANSALDO
39/06 | U2588 | 2005-11-01 | ANSALDO
39/06 | U2601 | 2005-11-01 | ANSALDO
39/06 | U2603 | 2005-11-01 | ANSALDO
39/06 | U2604 | 2005-11-01 | ANSALDO
39/06 | L2621 | 2005-11-01 | ANSALDO
39/06 | L2620 | 2005-11-01 | ANSALDO
39/06 | L2618 | 2005-11-01 | ANSALDO
39/06 | L2606 | 2005-11-01 | ANSALDO
40/06 | U2605 | 2005-11-01 | ANSALDO
40/06 | U2610 | 2005-11-01 | ANSALDO
40/06 | U2611 | 2005-11-01 | ANSALDO
40/06 | U2625 | 2005-11-01 | ANSALDO
40/06 | L2607 | 2005-11-01 | ANSALDO
40/06 | L2634 | 2005-11-01 | ANSALDO
40/06 | L2293 | 2005-11-01 | ANSALDO
40/06 | L2589 | 2005-11-01 | ANSALDO
41/06 | 0 |  | ANSALDO
41/06 | 0 |  | ANSALDO
41/06 | 0 |  | ANSALDO
41/06 | 0 |  | ANSALDO
41/06 | 0 |  | ANSALDO
41/06 | 0 |  | ANSALDO
41/06 | 0 |  | ANSALDO
41/06 | 0 |  | ANSALDO
42/06 | U2628 | 2005-11-02 | ANSALDO
42/06 | U2633 | 2005-11-02 | ANSALDO
42/06 | U2637 | 2005-11-02 | ANSALDO
42/06 | U2638 | 2005-11-02 | ANSALDO
42/06 | L2627 | 2005-11-02 | ANSALDO
42/06 | L2657 | 2005-11-02 | ANSALDO
42/06 | L2556 | 2005-11-02 | ANSALDO
42/06 | L2295 | 2005-11-02 | ANSALDO
43/06 | U2642 | 2005-11-02 | ANSALDO
43/06 | U2648 | 2005-11-02 | ANSALDO
43/06 | U2671 | 2005-11-02 | ANSALDO
43/06 | U2676 | 2005-11-02 | ANSALDO
43/06 | L2624 | 2005-11-02 | ANSALDO
43/06 | L2672 | 2005-11-02 | ANSALDO
43/06 | L2288 | 2005-11-02 | ANSALDO
43/06 | L1942 | 2005-11-02 | ANSALDO
44/06 | U2677 | 2005-11-02 | ANSALDO
44/06 | U2678 | 2005-11-02 | ANSALDO
44/06 | U2682 | 2005-11-02 | ANSALDO
44/06 | U2683 | 2005-11-02 | ANSALDO
44/06 | L2650 | 2005-11-02 | ANSALDO
44/06 | L2608 | 2005-11-02 | ANSALDO
44/06 | L2663 | 2005-11-02 | ANSALDO
44/06 | L2669 | 2005-11-02 | ANSALDO
45/06 | 0 |  | ANSALDO
45/06 | 0 |  | ANSALDO
45/06 | 0 |  | ANSALDO
45/06 | 0 |  | ANSALDO
45/06 | 0 |  | ANSALDO
45/06 | 0 |  | ANSALDO
45/06 | 0 |  | ANSALDO
45/06 | 0 |  | ANSALDO
46/06 | 0 |  | ANSALDO
46/06 | 0 |  | ANSALDO
46/06 | 0 |  | ANSALDO
46/06 | 0 |  | ANSALDO
46/06 | 0 |  | ANSALDO
46/06 | 0 |  | ANSALDO
46/06 | 0 |  | ANSALDO
46/06 | 0 |  | ANSALDO
47/06 | 0 |  | ANSALDO
47/06 | 0 |  | ANSALDO
47/06 | 0 |  | ANSALDO
47/06 | 0 |  | ANSALDO
47/06 | 0 |  | ANSALDO
47/06 | 0 |  | ANSALDO
47/06 | 0 |  | ANSALDO
47/06 | 0 |  | ANSALDO
48/06 | 0 |  | ANSALDO
48/06 | 0 |  | ANSALDO
48/06 | 0 |  | ANSALDO
48/06 | 0 |  | ANSALDO
48/06 | 0 |  | ANSALDO
48/06 | 0 |  | ANSALDO
48/06 | 0 |  | ANSALDO
48/06 | 0 |  | ANSALDO
49/06 | 0 |  | ANSALDO
49/06 | 0 |  | ANSALDO
49/06 | 0 |  | ANSALDO
49/06 | 0 |  | ANSALDO
49/06 | 0 |  | ANSALDO
49/06 | 0 |  | ANSALDO
49/06 | 0 |  | ANSALDO
49/06 | 0 |  | ANSALDO
50/06 | 0 |  | ANSALDO
50/06 | 0 |  | ANSALDO
50/06 | 0 |  | ANSALDO
50/06 | 0 |  | ANSALDO
50/06 | 0 |  | ANSALDO
50/06 | 0 |  | ANSALDO
50/06 | 0 |  | ANSALDO
50/06 | 0 |  | ANSALDO
51/06 | 0 |  | ANSALDO
51/06 | 0 |  | ANSALDO
51/06 | 0 |  | ANSALDO
51/06 | 0 |  | ANSALDO
51/06 | 0 |  | ANSALDO
51/06 | 0 |  | ANSALDO
51/06 | 0 |  | ANSALDO
51/06 | 0 |  | ANSALDO
52/06 | 0 |  | ANSALDO
52/06 | 0 |  | ANSALDO
52/06 | 0 |  | ANSALDO
52/06 | 0 |  | ANSALDO
52/06 | 0 |  | ANSALDO
52/06 | 0 |  | ANSALDO
52/06 | 0 |  | ANSALDO
52/06 | 0 |  | ANSALDO
| U2684 | 2005-11-02 | CERN SPARE
| U2685 | 2005-11-02 | CERN SPARE
| U2686 | 2005-11-02 | CERN SPARE
| U2687 | 2005-11-02 | CERN SPARE
| L2576 | 2005-11-02 | CERN SPARE
| L2674 | 2005-11-02 | CERN SPARE
| L2583 | 2005-11-02 | CERN SPARE
| L2572 | 2005-11-02 | CERN SPARE
| U2688 | 2005-11-02 | CERN SPARE
| U2689 | 2005-11-02 | CERN SPARE
| U2690 | 2005-11-02 | CERN SPARE
| U2691 | 2005-11-02 | CERN SPARE
| L2600 | 2005-11-02 | CERN SPARE
| L2668 | 2005-11-02 | CERN SPARE
| L2646 | 2005-11-02 | CERN SPARE
| L2656 | 2005-11-02 | CERN SPARE
| U2692 | 2005-11-03 | CERN SPARE
| U2693 | 2005-11-03 | CERN SPARE
| U2694 | 2005-11-03 | CERN SPARE
| U2695 | 2005-11-03 | CERN SPARE
| L2654 | 2005-11-03 | CERN SPARE
| L2639 | 2005-11-03 | CERN SPARE
| L2584 | 2005-11-03 | CERN SPARE
| L2651 | 2005-11-03 | CERN SPARE
| U2697 | 2005-11-03 | CERN SPARE
| U2698 | 2005-11-03 | CERN SPARE
| U2699 | 2005-11-03 | CERN SPARE
| U2700 | 2005-11-03 | CERN SPARE
| L2594 | 2005-11-03 | CERN SPARE
| L2609 | 2005-11-03 | CERN SPARE
| L2776 | 2005-11-03 | CERN SPARE
| L2631 | 2005-11-03 | CERN SPARE
| U2701 | 2005-11-03 | CERN SPARE
| U2713 | 2005-11-03 | CERN SPARE
| U2714 | 2005-11-03 | CERN SPARE
| U2679 | 2005-11-03 | CERN SPARE
| L2630 | 2005-11-03 | CERN SPARE
| L2675 | 2005-11-03 | CERN SPARE
| L2666 | 2005-11-03 | CERN SPARE
| L2617 | 2005-11-03 | CERN SPARE
| U2696 |  | CERN SPARE
| U2703 |  | CERN SPARE
| U2704 |  | CERN SPARE
| U2719 |  | CERN SPARE
| L2596 |  | CERN SPARE
| L2647 |  | CERN SPARE
| L2660 |  | CERN SPARE
| L2653 |  | CERN SPARE
| U2720 |  | CERN SPARE
| U2721 |  | CERN SPARE
| U2722 |  | CERN SPARE
| U2723 |  | CERN SPARE
| L2662 |  | CERN SPARE
| L2673 |  | CERN SPARE
| L2643 |  | CERN SPARE
| L2635 |  | CERN SPARE
| U2724 |  | CERN SPARE
| U2725 |  | CERN SPARE
| U2726 |  | CERN SPARE
| U2738 |  | CERN SPARE
| L2670 |  | CERN SPARE
| L2661 |  | CERN SPARE
| L2623 |  | CERN SPARE
| L2658 |  | CERN SPARE
| U2739 |  | CERN SPARE
| U2598 |  | CERN SPARE
| U2644 |  | CERN SPARE
| U2665 |  | CERN SPARE
| L2599 |  | CERN SPARE
| L2221 |  | CERN SPARE
| L2778 |  | CERN SPARE
| L2774 |  | CERN SPARE
| U2681 |  | CERN SPARE
| U2702 |  | CERN SPARE
| U2705 |  | CERN SPARE
| U2706 |  | CERN SPARE
| L2773 |  | CERN SPARE
| L2664 |  | CERN SPARE
| L2655 |  | CERN SPARE
| L2652 |  | CERN SPARE
| U2707 |  | CERN SPARE
| U2711 |  | CERN SPARE
| U2712 |  | CERN SPARE
| U2715 |  | CERN SPARE
| L2615 |  | CERN SPARE
| L2772 |  | CERN SPARE
| L2777 |  | CERN SPARE
| L2641 |  | CERN SPARE
| U2716 |  | CERN SPARE
| U2717 |  | CERN SPARE
| U2718 |  | CERN SPARE
| U2737 |  | CERN SPARE
| L2579 |  | CERN SPARE
| L2595 |  | CERN SPARE
| L2780 |  | CERN SPARE
| L2578 |  | CERN SPARE
| U2746 |  | CERN SPARE
| U2750 |  | CERN SPARE
| U2751 |  | CERN SPARE
| #REF! |  | CERN SPARE
| L2619 |  | CERN SPARE
| L2775 |  | CERN SPARE
| L2602 |  | CERN SPARE
| #REF! |  | CERN SPARE

## legend
Do not deliver
Uxxxx Lxxxx | Shells already invoiced
45/05 | 0 | ANSALDO