Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 03 and 04  - 2005

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | Up to 2172 inner layers and 2171 for outer layers |
| Pole assembled and tested |  | Up to 2166 |
| Collared coils finished and tested |  | 159 items (*) |
| Cold masses welded |  | 152 items |
| Cold masses in course of finishing |  | 12 |
| Ready for pressure and leak test |  | 2 |
| Cold masses ready for delivery |  | 3 |
| Cold masses delivered |  | 135 items (**) |

Short summary (tooling, NCRs, outstanding problems): (*) two collared coils lost for demounting of 4 collared coils (2013,2049 , 2069 and 2073) (**) CM 2525 is not included