Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 01 and 02 - 2005

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | Up to 2166 |
| Pole assembled and tested |  | Up to 2160 |
| Collared coils finished and tested |  | 155 items |
| Cold masses welded |  | 146 items |
| Cold masses in course of finishing |  | 11 |
| Ready for pressure and leak test |  | 2 |
| Cold masses ready for delivery |  | 2 |
| Cold masses delivered |  | 131 items |

Short summary (tooling, NCRs, outstanding problems): Four cold masses were disassembled in week 52 and 1. Three collared coils were disassembled in week 02 and CM 2525 was adjusted and tested . The week 01 had only three working days.