Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 05 and 06  - 2006

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | Up to 2178 inner layers and 2177 for outer layers |
| Pole assembled and tested |  | Up to 2171 (*) |
| Collared coils finished and tested |  | 165 items |
| Cold masses welded |  | 158 items |
| Cold masses in course of finishing |  | 13 |
| Ready for pressure and leak test |  | 1 |
| Cold masses ready for delivery |  | 2 |
| Cold masses delivered |  | 142 items |

Short summary (tooling, NCRs, outstanding problems): (*) We measured also c.c. 2073 completely and one pole of 2158