Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 39 and 40  - 2005

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | 272.5 for inner and for outer layers |
| Pole assembled and tested |  | 268 items |
| Collared coils finished and tested |  | 256 items |
| Cold masses welded |  | 246 items |
| Cold masses in course of finishing |  | 20 |
| Ready for pressure and leak test |  | 3 |
| Cold masses ready for delivery |  | 1 |
| Cold masses delivered |  | 222 items |

Short summary (tooling, NCRs, outstanding problems): 29/9/2005 one day of strike and 4/10/2005 half day of strike. The CM 2229 was repaired retested and sent back to Cern.