Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 43 and 44  - 2005

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | 286 for inner and 285 for outer layers |
| Pole assembled and tested |  | 278 items |
| Collared coils finished and tested |  | 270 items (*) |
| Cold masses welded |  | 257 items |
| Cold masses in course of finishing |  | 18 |
| Ready for pressure and leak test |  | 2 |
| Cold masses ready for delivery |  | 2 |
| Cold masses delivered |  | 235 items |

Short summary (tooling, NCRs, outstanding problems): Half day of strike the 26th of October. 1st of November – holiday (*) Collared coil 2549 has been collared and tested – c.c. 2253 remeasured with short moles.