Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 45 and 46  - 2005

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | 293 for inner and 292 for outer layers |
| Pole assembled and tested |  | 286 items |
| Collared coils finished and tested |  | 279 items (*) |
| Cold masses welded |  | 264 items |
| Cold masses in course of finishing |  | 18 |
| Ready for pressure and leak test |  | 2 |
| Cold masses ready for delivery |  | 3 |
| Cold masses delivered |  | 241 items |

Short summary (tooling, NCRs, outstanding problems): (*) Two working days lost for substitution of one cylinder of the collaring press.