Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 1 and 2  - 2006

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | 312 inner and 311 outer layers (*) |
| Pole assembled and tested |  | 306 items |
| Collared coils finished and tested |  | 298 items |
| Cold masses welded |  | 280 items |
| Cold masses in course of finishing |  | 13 |
| Ready for pressure and leak test |  | 0 (**) |
| Cold masses ready for delivery |  | 4 |
| Cold masses delivered |  | 263 items |

Short summary (tooling, NCRs, outstanding problems): Half day of strike on the 13th of January. (*) Winding machine CSA1 out of work on the 12 and 13th of January. (**) CM 2270 found with low insulation between poles and ground just before to weld the end covers; to be opened.