Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 5 and 6 - 2006

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | 326 inner and 324.5 outer layers |
| Pole assembled and tested |  | 317 items |
| Collared coils finished and tested |  | 311 items |
| Cold masses welded |  | 294 items |
| Cold masses in course of finishing |  | 13 |
| Ready for pressure and leak test |  | 1 |
| Cold masses ready for delivery |  | 4 |
| Cold masses delivered |  | 276 items |

Short summary (tooling, NCRs, outstanding problems): -Maintenance on curing press CTE1 . -Problem on winding machine CSA1. -Recollaring of c.c.2278. -Decollaring of c.c. 2303 -Two shifts lost in winding,curing,surfacing and pole assembling for crane out of work on the 10th of February. -One pole of c.c. 2315 with short circuit .Demounted and one inner layer put aside. -One inner layer of c.c. 2324 lost for incident on the winding machine.