Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 7 and 8 - 2006

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | 332.5 inner and 331.5 outer layers |
| Pole assembled and tested |  | 324 items |
| Collared coils finished and tested |  | 317 items |
| Cold masses welded |  | 301 items |
| Cold masses in course of finishing |  | 13 |
| Ready for pressure and leak test |  | 1 |
| Cold masses ready for delivery |  | 2 |
| Cold masses delivered |  | 285 items |

Short summary (tooling, NCRs, outstanding problems): -Problem on winding machine CSA1 ( two shifts lost) -Collared coil 2303 disassembled for Q.H. interruption. -Short mole measurement on c.c. 2549 -Maintenance on harmonic measurements devices DIMM4 and DIMM6