Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 11 and 12 - 2006

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | 345 inner and 345outer layers |
| Pole assembled and tested |  | 337 items |
| Collared coils finished and tested |  | 329 items |
| Cold masses welded |  | 315 items |
| Cold masses in course of finishing |  | 11 |
| Ready for pressure and leak test |  | 2 |
| Cold masses ready for delivery |  | 3 |
| Cold masses delivered |  | 299 items |

Short summary (tooling, NCRs, outstanding problems): -Changing of cylinders on the collaring press( 8/3-15/3.) -CM 2549 has been welded -C.c. 2569 has been prepared for collaring -Two shifts lost on CM 2307 for laser problems