Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 09 and 10  - 2006

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | Up to 2186 for inner and 2187 for outer layers (*) |
| Pole assembled and tested |  | Up to 2182 |
| Collared coils finished and tested |  | 174 items (**) |
| Cold masses welded |  | 170 items |
| Cold masses in course of finishing |  | 15 |
| Ready for pressure and leak test |  | 1 |
| Cold masses ready for delivery |  | 1 |
| Cold masses delivered |  | 152 items |

Short summary (tooling, NCRs, outstanding problems): (*) 6 inner layers and one outer layer for c.c. 2513 and 2532 were wound and cured. (**) C.c. 2073 was recollared and measured. In week 9 we had two days of snow and only few people could come to work.