Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 13 and 14   - 2005

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | Up to 2198 for inner and for outer layers |
| Pole assembled and tested |  | Up to 2191 |
| Collared coils finished and tested |  | 184 items (*) |
| Cold masses welded |  | 182 items |
| Cold masses in course of finishing |  | 19 |
| Ready for pressure and leak test |  | 1 |
| Cold masses ready for delivery |  | 3 |
| Cold masses delivered |  | 159 items |

Short summary (tooling, NCRs, outstanding problems): (*) In these two weeks c.c. 2513 and 2532 have been reassembled and tested.