Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 17 and 18   - 2005

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | Up to 2211 for inner and for outer layers |
| Pole assembled and tested |  | Up to 2204 |
| Collared coils finished and tested |  | 196 items (*) |
| Cold masses welded |  | 191 items |
| Cold masses in course of finishing |  | 18 |
| Ready for pressure and leak test |  | 2 |
| Cold masses ready for delivery |  | 2 |
| Cold masses delivered |  | 169 items |

Short summary (tooling, NCRs, outstanding problems): (*) C.c. 2194 has been demounted for interturn short circuit. Big problems of collaring on several coils and central rod removing for c.c. 2194.