Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 19 and 20   - 2005

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | Up to 2218 for inner and for outer layers |
| Pole assembled and tested |  | Up to 2211 |
| Collared coils finished and tested |  | 203 items |
| Cold masses welded |  | 197 items |
| Cold masses in course of finishing |  | 19 |
| Ready for pressure and leak test |  | 1 |
| Cold masses ready for delivery |  | 2 |
| Cold masses delivered |  | 175 items |

Short summary (tooling, NCRs, outstanding problems):