Cold mass assembler:     Ansaldo Superconduttori

Status report on weeks 23 and 24   - 2005

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | Up to 2232 for inner and 2231 for outer layers |
| Pole assembled and tested |  | Up to 2224 |
| Collared coils finished and tested |  | 212 items (*) |
| Cold masses welded |  | 205 items (**) |
| Cold masses in course of finishing |  | 18 |
| Ready for pressure and leak test |  | 1 |
| Cold masses ready for delivery |  | 1 |
| Cold masses delivered |  | 185 items (***) |

Short summary (tooling, NCRs, outstanding problems): One day of strike – 10th of June (*) Collaring press in revamping from 3/6 ; still not working. (**) Two days of stop on laser device. (***) Transportation problem for incident on Frejus tunnel.