Cold mass assembler: Ansaldo Superconduttori

Status report on weeks 35 and 36 - 2004

|  | These two weeks | Total |
| --- | --- | --- |
| Layers wound, including curing and surfacing |  | - 2128 inner - 2127 outer |
| Pole assembled |  | Up to 2124 |
| Collared coils finished |  | 109 items |
| Cold masses welded | 3 welded | 103 items |
| Cold masses in course of finishing | 6 | - |
| Ready for pressure and leak test | - | - |
| Cold masses ready for delivery | 2 | - |
| Cold masses delivered |  | 95 items |

Short summary (tooling, NCRs, outstanding problems): - Problem with the Servo Robot control system sorted out in week 36 (substituted the power supply of the Pilot 4000 unit) - 1 week lost for the longitudinal welding; - One cold mass, already welded, has been opened (2087) - there was a short; - The collaring press revamping has been completed and the machine re-tested and commissioned in week 36. A first collaring operation is in progress this Friday 3rd September; - During the shutdown of the collaring-press, 3 magnets have been pre-collared. These shall be collared very quickly. We were expecting more (another 3 is being assembled and quasi ready for pre-collaring)!