## Sheet1
| 24 mar week 12 | Prod. Rate of week 12 | 31 mar week 13 | Prod. Rate of week 13 | 07 apr week 14 | Prod. Rate of week 14 | 14 apr week 15 | Prod. Rate of week 15 | 21 aqpr week 16 | Prod. Rate of week 16 | 28 apr week 17 | Prod. Rate of week 17 | 05 mai week 18 | Prod. Rate of week 18
Winding on Dip 1000 | 2346 1 layers | 8 layers | 2349 1 layers | 8 layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers
Winding on Dip 1500 | 2345 4 layers | 8 layers | 2347 3 layers** | 5 layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers
Winding on CSA1 | 2346 3 layers | 6 layers | 2348 2 layers** | 7 layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers
Winding on CSA2 | 2345 3 layers | 7 layers | 2347 3 layers | 4 layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers | 23xx x layers | x layers
Total layers wound | 1389 inn.Lay. 1386 out.Lay. | 29 3,625 | 1402 inn.Lay. 1397 out.Lay. | 24 3,0 | 13xx inn.Lay. 13xx out.Lay. | x x | 13xx inn.Lay. 13xx out.Lay. | x x | 13xx inn.Lay. 13xx out.Lay. | x x | 13xx inn.Lay. 13xx out.Lay. | x x | 13xx inn.Lay. 13xx out.Lay. | x x
Collared coils | 332 | 4 | 335 | 3 | x | x | x | x | x | x | x | x | x | x
Tested collared coils | 327 | 3 | 330 | 3 | x | x | x | x | x | x | x | x | x | x
Cold mass ready for shipping | 299 | 4 | 302 | 3 | x | x | x | x | x | x | x | x | x | x
**winding remaining layers for CM2316, CM2324, CM2325