## Sheet1
| 05 mai week 18 | Prod. Rate of week 18 | 12 mai week 19 | Prod. Rate of week 19 | 19 mai week 20 | Prod. Rate of week 20 | 27 mai week 21 | Prod. Rate of week 21 | 02 jun week 22 | Prod. Rate of week 22 | 09 jun week 23 | Prod. Rate of week 23 | 16 jun week 24 | Prod. Rate of week 24
Winding on Dip 1000 | 2363 1 layers | 5 layers | 2366 3 layers | 6 layers | 2368 4 layers | 5 layers | 2372 4 layers | 8 layers | 2375 2 layers | 6 layers | 23xx x layers | x layers | 23xx x layers | x layers
Winding on Dip 1500 | 2362 4 layers | 5 layers | 2367 1 layers | 9 layers | 2369 2 layers | 5 layers | 2371 4 layers | 6 layers | 2376 2 layers | 6 layers | 23xx x layers | x layers | 23xx x layers | x layers
Winding on CSA1 | 2360 4 layers | 6 layers | 2364 3 layers | 7 layers | 2369 3 layers | 8 layers | 2373 1 layers | 6 layers | 2375 4 layers | 7 layers | 23xx x layers | x layers | 23xx x layers | x layers
Winding on CSA2 | 2361 3 layers | 5 layers | 2365 3 layers | 8 layers | 2368 4 layers | 9 layers | 2372 4 layers | 8 layers | 2374 3 layers** | 4 layers | 23xx x layers | x layers | 23xx x layers | x layers
Total layers wound | 1459 inn.Lay. 1452 out.Lay. | 21 2,625 | 1474 inn.Lay. 1467 out.Lay. | 30 3,75 | 1484 inn.Lay. 1484 out.Lay. | 27 3,375 | 1498 inn.Lay. 1498 out.Lay. | 28 3,5 | 14xx inn.Lay. 14xx out.Lay. | 23 2,875 | 14xx inn.Lay. 14xx out.Lay. | xx x,x | 14xx inn.Lay. 14xx out.Lay. | xx x,x
Collared coils | 347 | 3 | 351 | 4 | 354 | 3 | 359 | 5 | 362 | 3 | x | x | x | x
Tested collared coils | 345 | 2 | 349 | 4 | 353 | 4 | 356 | 3 | 358 | 2 | x | x | x | x
Cold mass ready for shipping | 321 | 3 | 323 | 2 | 327 | 4 | 332 | 5 | 336 | 4 | x | x | x | x
**Winding remaining layer of 2342