## overview
ITP20-HCMBA-2016
| OVERVIEW ASSEMBLY COLD MASS Nr. HCMBA-2016 | [5 empty] | TrackerID: | 583
| Date: | 06/08/03
CORRECTOR MAGNETS
Sextupole Corrector Magnets
| Status: |  |  | V1 | OK
All data completed
|  |  |  | V2 | OK
Deca/Octopole Corrector Magnets
|  |  |  | V1 | OK
| Magnet type: |  | A
|  |  |  | V2 | OK |  |  |  | Document not signed at the firm
No remarks
Document not signed at CERN
END-COVERS
|  |  |  | Conn. Side | OK | #REF! |  |  | Existing survey data
| Status: |  |  |  |  | #REF!
| All data completed |  |  | Lyre Side | OK | #REF! |  |  | Existing shape data
#REF!
Existing statistical data
COLD FEET PADS
|  |  |  | Conn. Side | OK | #REF!
#REF!
| Status: |  |  | Central | OK | #REF!
| All data completed |  |  |  |  | #REF!
|  |  |  | Lyre Side | OK | #REF!
#REF!
COLD MASS TOTAL LENGTH
Status:
| All data completed |  |  | OK (T=20°C)
SHAPE
| Status: |  |  | V1
| Existing shape data |  |  |  | Out of tolerance
V2
Out of tolerance
TUBE ENDS
|  |  |  | V1, Conn. Side | OK | #REF!
#REF!
| Status: |  |  | V2, Conn. Side | OK | #REF!
| All data completed |  |  |  |  | #REF!
|  |  |  | V1, Lyre Side | OK | #REF!
#REF!
|  |  |  | V2, Lyre Side | OK | #REF!
#REF!
| Prepared by (Operator): |  |  | Caserza B.
| Checked by (Project Engineer): |  |  | Caserza B.
Approved by (Firm responsible):
Checked by (CERN's inspector):
Checked at CERN by (Project Enginner):
Start new Traveller
Magnet shape
Go to remarks
Go to survey data
Go to statistical data
Go to shape data
Signature
Traveller2_3.xls (Last modification: 21/07/2003)
The input files for this Traveller must be created with the macro:
Midplane2_3.xls
SAVE
more...
more...
more...
more...
more...
more...

## remarks
ITP20-HCMBA-2016
OVERVIEW ASSEMBLY COLD MASS Nr. HCMBA-2016
| Date: | 06/08/03
| Prepared by (Operator): | Caserza B.
| Checked by (Project Engineer): | Caserza B.
| Approved by (Firm responsible): | Gagliardi P.
Checked by (CERN's inspector):
Checked at CERN by (Project Enginner):
Remarks:
CORRECTOR MAGNETS
Sextupole Corrector Magnets
V1
V2
Decapole Corrector Magnets
V1
V2
END-COVERS
Conn. Side
Lyre Side
COLD FEET PADS
Conn. Side
Central
Lyre Side
COLD MASS TOTAL LENGTH
SHAPE
V1
V2
TUBE ENDS
V1, Conn. Side
V2, Conn. Side
V1, Lyre Side
V2, Lyre Side
To overview

## correctors
Sextupole on V1 (outer)
(all dimensions in mm, all values after welding)
Local Coordinate System: End Plate Lyre Side
Id. Nr. | MCS-MA-I0117
theoretical values |  |  |  | measured values
Xt | Zt |  |  | Xm | Ym | Zm
-97.26 | 0 |  | point1 | -97.294 | 93.804 | 69.98
|  |  | point2 | -97.246 | 94.52 | -70.043
|  |  |  | -97.27 |  | -0.0315
| delta = (measured-theoretical) |  |  | tolerance
| DX | DZ | DR | t
| -0.01 | -0.0315 | 0.033049 | 0.3 | OK
Sextupole on V2 (inner)
(all dimensions in mm, all values after tack welding)
Local Coordinate System: End Plate Lyre Side
Id. Nr. | MCS-MA-I0131
theoretical values |  |  |  | measured values
Xt | Zt |  |  | Xm | Ym | Zm
97.26 | 0 |  | point3 | 97.305 | 94.572 | 70.053
|  |  | point4 | 97.339 | 95.008 | -69.965
|  |  |  | 97.322 |  | 0.044
| delta = (measured-theoretical) |  |  | tolerance
| DX | DZ | DR | t
| 0.062 | 0.044 | 0.076026 | 0.3 | OK
Deca/Octopole on V1 and Deca/Octopole on V2
(all dimensions in mm, all values after welding)
Local Coordinate System: End Plate Connection Side (see "more info")
Id. Nr. | MCDO-MA-0164 |  | V1
| MCDO-MA-0171 |  | V2
theoretical values |  |  |  | measured values
Xt | Zt |  |  | Xm | Ym | Zm
97.26 | 0 |  | point1 | -27.212 | 83.846 | -0.013
|  |  | point2 | 167.259 | 83.46 | 0.041
|  |  | V1 | -97.212 |  | -0.032437
|  |  | V2 | 97.259 |  | 0.021563
| delta = (measured-theoretical) |  |  | tolerance
V1
| DX | DZ | DR | t
| 0.048003 | -0.032437 | 0.057935 | 0.3 | OK
| delta = (theoretical-measured) |  |  | tolerance
V2
| DX | DZ | DR | t
| -0.0009973 | 0.021563 | 0.021586 | 0.3 | OK
To overview
more info
To overview
more info

## end_covers
End-Cover Connection Side
(all dimensions in mm or mrad, all values after welding)
Local Coordinate System: End-Cover Connection Side
Id. Nr. | 90108-36
Reference points of the plane "C" : D9-D10-D11
| theoretical values |  |  | measured values
| Xth | Yth | Zth | Xm | Ym | Zm
D9 | -247 | 0 | 0 | -246.941 | -11.984 | -0.156 |  | Sign convention for angles:
D10 | 247 | 0 | 0 | 247.264 | -12.014 | -0.158
D11 | 0 | 0 | 247 | 0.119 | -11.965 | 246.944
Center | 0 | 0 | 0 | 0.161 | -11.999 | -0.158
|  |  |  | Reflector offset: |  | 12
Angles between end cover and theoretical plane C
|  | theoretical values |  | measured values |  | ±tolerance
Around X axis |  | 0 |  | -0.1376 |  | 1 | OK
Around Z axis |  | 0 |  | -0.060704 |  | 1 | OK
Localisation of Planes A and B ( 1.5 mm) (see more info page for details)
|  | Plane A | OK
|  | Plane B | OK
End-Cover Lyre Side
(all dimensions in mm or mrad, all values after welding)
Local Coordinate System: End-Cover Lyre Side
Id. Nr. | 90109-61
Reference points of the plane "L" : D9-D10-D11
| theoretical values |  |  | measured values
| Xth | Yth | Zth | Xm | Ym | Zm
D9 | 247 | 0 | 0 | 247.06 | 11.948 | 0.451
D10 | -247 | 0 | 0 | -247.011 | 12.008 | 0.313
D11 | 0 | 0 | 247 | -0.022 | 12.004 | 247.416
Center | 0 | 0 | 0 | 0.024 | 11.978 | 0.38
Reflector offset:
Angles between end cover and theoretical plane L
|  | theoretical values |  | measured values |  | ±tolerance
Around X axis |  | 0 |  | 0.10525 |  | 1 | OK
Around Z axis |  | 0 |  | -0.12144 |  | 1 | OK
Localisation of Planes A and B ( 1.5 mm) (see more info page for details)
|  | Plane A | OK
|  | Plane B | OK
To overview
more info
To overview
more info

## cold_feet_pads
Connection Side Support
(all dimensions in mm or mrad, all values after welding)
For all supports: Local Coordinate System: Cold Mass Center
Id. Nr. | 30
Position of center of cold foot pad
theoretical values |  |  | measured values
Xth | Yth | Zth | Xm | Ym | Zm
5.18 | -5400 | -294 | 4.592 | -5399.961 | -293.894
| delta theoretical-measured |  |  | tolerances
| DX | DY | DZ | ±toly | ±tolz
| -0.588 | 0.039 | 0.106 | 1 | 0.6 | OK
Parallelism between Cold Foot Pad and Mid Plane
|  | theoretical | measured |  | ±tolerance
| Around | 0 | 0.207 |  | 3.34 | OK
Longitudinal Axis
| Around | 0 | 1.158 |  | 2.76 | OK
Transversal Axis
Central Support
(all dimensions in mm or mrad, all values after welding)
Id. Nr. | 31
Position of center of cold foot pad
theoretical values |  |  | measured values
Xth | Yth | Zth | Xm | Ym | Zm
0 | 0 | -294 | -3.218 | -0.361 | -293.883
| delta theoretical-measured |  |  | tolerances
| DX | DY | DZ | ±toly | ±tolz
| -3.218 | -0.361 | 0.117 | 0.5 | 0.6 | OK
Parallelism between Cold Foot Pad and Mid Plane
|  | theoretical | measured |  | ±tolerance
| Around | 0 | 0.6 |  | 1.67 | OK
Longitudinal Axis
| Around | 0 | 0.7 |  | 1.38 | OK
Transversal Axis
Lyre Side Support
(all dimensions in mm or mrad, all values after welding)
Id. Nr. | 29
Position of center of cold foot pad
theoretical values |  |  | measured values
Xth | Yth | Zth | Xm | Ym | Zm
5.18 | 5400 | -294 | -0.328 | 5399.506 | -294.139
| delta theoretical-measured |  |  | tolerances
| DX | DY | DZ | ±toly | ±tolz
| -5.508 | -0.494 | -0.139 | 1 | 0.6 | OK
Parallelism between Cold Foot Pad and Mid Plane
|  | theoretical | measured |  | ±tolerance
| Around | 0 | 1.5 |  | 3.34 | OK
Longitudinal Axis
| Around | 0 | 0.9 |  | 2.76 | OK
Transversal Axis
To overview
more info
To overview
more info
To overview
more info

## total_length
Cold Mass Total Length
(all dimensions in mm)
Distance between the centers of Circle C and Circle L
(all points expressed in a commun coordinate system)
| measured values |  |  |  | Temperature(°C)
| Xm | Ym | Zm |  | Tenvironment | 34
Center C | 0.069 | -12 | 0.177 |  | Tcold mass (Tcm) | 32
Center L | 0.13 | 15173.31 | 0.542
reflector offset: |  |  | 12
total length(T=Tcm) |  |  | 15161.31
total length(T=20°C)* |  |  | 15158.7629
theoretical total length |  |  | 15158
|  | delta measured-theoretical |  | ±tolerance
| T=Tcm | 3.31 |  | 2
| T=20°C | 0.7629 |  |  | OK (T=20°C)
*The cold mass total length at 20°C is calculated as follows:
L(T=20°C)=L(T=Tcm)-DL
| being: | DL=a×L(T=Tcm)×DT
DT=Tcm-20°C
a=1.4×10-5°C-1
To overview
more info

## shape
Horizontal Shape of Tubes V1 and V2
(all dimensions in mm, all values after assembly cold mass)
Theoretical Coordinate System with origin on Connection Side End Plate
Is the offset of tube V1 lower than the tolerance? |  | No
Is the offset of tube V2 lower than the tolerance? |  | No
Is the quality of measurement within the tolerance? |  | Yes
Is the twist within the tolerance? |  | Yes
Vertical Shape of Tubes V1 and V2
(all dimensions in mm, all values after assembly cold mass)
Total Offset of Tubes V1 and V2
(all dimensions in mm, all values after assembly cold mass)
Total Offset = (Horizontal Offset)2 + (Vertical Offset)2
Twist between Tubes V1 and V2
(all dimensions in mrad, all values after assembly cold mass)
To overview
more info
to data
To overview
more info
to data

## tube ends
Connection Side End
(all dimensions in mm or mrad)
Local Coordinate System: End-Cover Connection Side
All values Measured on the outer diameter of the flanges
Center of the flanges
theoretical values |  |  | measured values |  |  | delta = (measured-theoretical) |  |  |  | Toler. R | Toler. Y
Xth | Yth | Zth | Xm | Ym | Zm | DX | DY | DZ | DR | tr | ±ty
theoretical values Xth: Center V1 |  | OK
-97.26 | -64 | 0 | -97.216 | -64.185 | -0.162 | 0.044 | -0.185 | -0.162 | 0.16787 | 0.6 | 0.5
theoretical values Xth: Center V2 |  | OK
97.26 | -64 | 0 | 97.298 | -64.227 | -0.19 | 0.038 | -0.227 | -0.19 | 0.19376 | 0.6 | 0.5
Outer diameter of the flanges
| Theoretical value |  | Measured value |  | Tolerance
| fth |  | fm |  | fmax | fmin
V1 |  |  | 75.9 |  | 75.95 | 75.75 | OK
V2 |  |  | 75.88 |  | 75.95 | 75.75 | OK
Perpendicularity of the flanges
| Theoretical value |  | Measured value |  | Toler.
| Angle |  | Angle |  | Angle
V1 | 0 |  | 0.13 |  | 4 | OK
V2 | 0 |  | 0.56 |  | 4 | OK
Position of V1 flange |  |  |  | Position of V2 flange
|  | +Z |  |  |  | +Z
|  |  | +X |  |  |  | +X
|  | o |  |  |  | o
Lyre Side End
(all dimensions in mm or mrad)
Local Coordinate System: End-Cover Lyre Side
All values measured on the outer diameter of the flanges
Center of the flanges
theoretical values Xth: theoretical values; measured values Xm: measured values; delta = (measured-theoretical) DX: delta = (measured-theoretical); Toler. R tr: Toler. R | Toler. Y
Xth | Yth | Zth | Xm | Ym | Zm | DX | DY | DZ | DR | tr | ±ty
theoretical values Xth: Center V1 |  | OK
-97.26 | 64 | 0 | -97.33 | 64.2 | 0.001 | -0.07 | 0.2 | 0.001 | 0.070007 | 0.6 | 0.5
theoretical values Xth: Center V2 |  | OK
97.26 | 64 | 0 | 97.354 | 64.093 | 0.004 | 0.094 | 0.093 | 0.004 | 0.094085 | 0.6 | 0.5
Outer diameter of the flanges
| Theoretical value |  | Measured value |  | Tolerance
| f |  | f |  | fmax | fmin
V1 |  |  | 73.38 |  | 73.45 | 73.25 | OK
V2 |  |  | 73.39 |  | 73.45 | 73.25 | OK
Perpendicularity of the flanges
| Theoretical value |  | Measured value |  | Toler.
| Angle |  | Angle |  | Angle
V1 | 0 |  | 1.09 |  | 4 | OK
V2 | 0 |  | 1.3 |  | 4 | OK
| Position of V1 flange |  |  |  | Position of V2 flange
|  | +Z |  |  |  | +Z
+X |  | o |  | +X | o
To overview
more info
To overview
more info

## survey
Survey Data
(all dimensions in mm)
Theoretical Coordinate System with origin on Connection Side End Plate
Vertical Position of the Tubes V1 and V2 measured at the Longitudinal Position of the Cold Feet Pads
| Longitudinal Position | z_V1 | z_V2 | z_average
Connection | 2180 | 0.21996 | 0.4157 | 0.31783
Center | 7580 | 0.13102 | 0.13548 | 0.13325
Lyre | 12980 | 0.072359 | 0.052839 | 0.062599
Longitudinal Axis
(origin on CS end-plate)
Vertical
or Z- Axis
To overview

## statistics
Statistical Data
(all dimensions in mm)
FALSE
Position of Tube Ends
Local Coordinate System: Rotated End-Cover Connection or Lyra Side
Where:
X=Transversal Axis
Y=Longitudinal Axis
Z=Vertical Axis
|  | V1 | V2
Dx_conn_side_v1 |  | -0.185 | Dx_lyra_side_v1 | 0.2
Dz_conn_side_v1 |  | -0.162 | Dz_lyra_side_v1 | 0.001
Dx_conn_side_v2 |  | -0.227 | Dx_lyra_side_v2 | 0.093
Dz_conn_side_v2 |  | -0.19 | Dz_lyra_side_v2 | 0.004
Max, Min and RMS of Deviation on shape V1 and V2
Rotated Theoretical Coordinate System
(X=Transversal Axis Y=Longitudinal Axis Z=Vertical Axis)
Max Dx V1 |  | 1.0124 | Max Dx V2 | 1.1083
Max Dz V1 |  | 0.648 | Max Dz V2 | 0.586
Min Dx V1 |  | -0.49027 | Min Dx v2 | -0.45393
Min Dz V1 |  | -0.496 | Min Dz v2 | -0.717
|  | RMS dx V1 | 0.45754
|  | RMS dx V2 | 0.42142
|  | RMS dz V1 | 0.2611
|  | RMS dz V2 | 0.27517
Z
X
Y
To overview

## data shape
pointID | x | y_meas | z_meas | x__theor | z_theor | +tol_x | -tol_x | +tol_z | -tol_z | offset | x_m-x_th | y_twist | twist | tw-av | av(tw) | +tol_tw-av | -tol_tw-av | x_meas_null | theor_null | tol+_null | tol-_null
ext1 | -97.464 | 361.247 | -0.262 | -98.1815 | 0 | -97.1815 | -99.1815 | 1 | -1 | 0.76384 | 0.7175 | 361.247 | 0.63233 | 0.75954 | -0.12721 | 5.8728 | -6.1272 | -0.204 | -0.9215 | 0.078501 | -1.9215
ext2 | -97.6 | 470.894 | -0.477 | -98.4604 | 0 | -97.4604 | -99.4604 | 1 | -1 | 0.98377 | 0.86039 | 470.894 | 1.2338 | 1.361 | -0.12721 | 5.8728 | -6.1272 | -0.34 | -1.2004 | -0.20039 | -2.2004
ext3 | -98.598 | 876.202 | -0.073 | -99.4557 | 0 | -98.4557 | -100.4557 | 1 | -1 | 0.86083 | 0.85773 | 876.202 | 2.1283 | 2.2555 | -0.12721 | 5.8728 | -6.1272 | -1.338 | -2.1957 | -1.1957 | -3.1957
ext4 | -98.828 | 967.241 | -0.155 | -99.6713 | 0 | -98.6713 | -100.6713 | 1 | -1 | 0.8574 | 0.84327 | 967.241 | 1.0899 | 1.2171 | -0.12721 | 5.8728 | -6.1272 | -1.568 | -2.4113 | -1.4113 | -3.4113
ext5 | -100.079 | 1391.158 | 0.068 | -100.6361 | 0 | -99.6361 | -101.6361 | 1 | -1 | 0.56122 | 0.55709 | 1391.158 | 0.80197 | 0.92919 | -0.12721 | 5.8728 | -6.1272 | -2.819 | -3.3761 | -2.3761 | -4.3761
ext6 | -100.185 | 1463.954 | 0.069 | -100.7953 | 0 | -99.7953 | -101.7953 | 1 | -1 | 0.61423 | 0.61034 | 1463.954 | 0.93564 | 1.0629 | -0.12721 | 5.8728 | -6.1272 | -2.925 | -3.5353 | -2.5353 | -4.5353
ext7 | -101.36 | 1905.085 | 0.205 | -101.7201 | 0 | -100.7201 | -102.7201 | 1 | -1 | 0.41434 | 0.36008 | 1905.085 | -0.31359 | -0.18638 | -0.12721 | 5.8728 | -6.1272 | -4.1 | -4.4601 | -3.4601 | -5.4601
ext8 | -101.445 | 1954.772 | 0.268 | -101.8199 | 0 | -100.8199 | -102.8199 | 1 | -1 | 0.46084 | 0.3749 | 1954.772 | 0.2519 | 0.37912 | -0.12721 | 5.8728 | -6.1272 | -4.185 | -4.5599 | -3.5599 | -5.5599
ext9 | -102.621 | 2418.887 | 0.169 | -102.7099 | 0 | -101.7099 | -103.7099 | 1 | -1 | 0.19097 | 0.088923 | 2418.887 | -2.1437 | -2.0165 | -0.12721 | 5.8728 | -6.1272 | -5.361 | -5.4499 | -4.4499 | -6.4499
ext10 | -102.622 | 2452.694 | 0.112 | -102.7718 | 0 | -101.7718 | -103.7718 | 1 | -1 | 0.18701 | 0.14976 | 2452.694 | -2.1283 | -2.0011 | -0.12721 | 5.8728 | -6.1272 | -5.362 | -5.5118 | -4.5118 | -6.5118
ext11 | -103.672 | 2932.724 | 0.061 | -103.606 | 0 | -102.606 | -104.606 | 1 | -1 | 0.089905 | -0.066044 | 2932.724 | -2.6784 | -2.5512 | -0.12721 | 5.8728 | -6.1272 | -6.412 | -6.346 | -5.346 | -7.346
ext12 | -103.638 | 2948.217 | 0.021 | -103.6315 | 0 | -102.6315 | -104.6315 | 1 | -1 | 0.021979 | -0.0064856 | 2948.217 | -2.7401 | -2.6129 | -0.12721 | 5.8728 | -6.1272 | -6.378 | -6.3715 | -5.3715 | -7.3715
ext13 | -104.511 | 3441.774 | -0.095 | -104.4011 | 0 | -103.4011 | -105.4011 | 1 | -1 | 0.14529 | -0.10993 | 3441.774 | -2.2825 | -2.1553 | -0.12721 | 5.8728 | -6.1272 | -7.251 | -7.1411 | -6.1411 | -8.1411
ext14 | -104.594 | 3447.05 | -0.087 | -104.4088 | 0 | -103.4088 | -105.4088 | 1 | -1 | 0.20459 | -0.18517 | 3447.05 | -2.2466 | -2.1193 | -0.12721 | 5.8728 | -6.1272 | -7.334 | -7.1488 | -6.1488 | -8.1488
ext15 | -105.282 | 3936.691 | -0.059 | -105.0858 | 0 | -104.0858 | -106.0858 | 1 | -1 | 0.20491 | -0.19624 | 3936.691 | -0.67345 | -0.54624 | -0.12721 | 5.8728 | -6.1272 | -8.022 | -7.8258 | -6.8258 | -8.8258
ext16 | -105.391 | 3961.064 | -0.107 | -105.1172 | 0 | -104.1172 | -106.1172 | 1 | -1 | 0.29393 | -0.27377 | 3961.064 | -0.9305 | -0.80328 | -0.12721 | 5.8728 | -6.1272 | -8.131 | -7.8572 | -6.8572 | -8.8572
ext17 | -105.856 | 4436.688 | -0.056 | -105.689 | 0 | -104.689 | -106.689 | 1 | -1 | 0.17609 | -0.16695 | 4436.688 | -0.19535 | -0.068138 | -0.12721 | 5.8728 | -6.1272 | -8.596 | -8.429 | -7.429 | -9.429
ext18 | -106.055 | 4473.606 | -0.09 | -105.7301 | 0 | -104.7301 | -106.7301 | 1 | -1 | 0.33717 | -0.32493 | 4473.606 | -0.49866 | -0.37145 | -0.12721 | 5.8728 | -6.1272 | -8.795 | -8.4701 | -7.4701 | -9.4701
ext19 | -106.389 | 4933.744 | 0.008 | -106.2007 | 0 | -105.2007 | -107.2007 | 1 | -1 | 0.1885 | -0.18833 | 4933.744 | 0.051409 | 0.17862 | -0.12721 | 5.8728 | -6.1272 | -9.129 | -8.9407 | -7.9407 | -9.9407
ext20 | -106.503 | 4987.282 | -0.043 | -106.2505 | 0 | -105.2505 | -107.2505 | 1 | -1 | 0.2561 | -0.25246 | 4987.282 | -0.2519 | -0.12469 | -0.12721 | 5.8728 | -6.1272 | -9.243 | -8.9905 | -7.9905 | -9.9905
ext21 | -106.817 | 5434.644 | 0.085 | -106.6274 | 0 | -105.6274 | -107.6274 | 1 | -1 | 0.2078 | -0.18962 | 5434.644 | 1.0385 | 1.1657 | -0.12721 | 5.8728 | -6.1272 | -9.557 | -9.3674 | -8.3674 | -10.3674
ext22 | -106.924 | 5500.652 | -0.063 | -106.677 | 0 | -105.677 | -107.677 | 1 | -1 | 0.25494 | -0.24704 | 5500.652 | 0.29817 | 0.42538 | -0.12721 | 5.8728 | -6.1272 | -9.664 | -9.417 | -8.417 | -10.417
ext23 | -107.19 | 5932.563 | 0.151 | -106.9631 | 0 | -105.9631 | -107.9631 | 1 | -1 | 0.27252 | -0.22686 | 5932.563 | 0.98704 | 1.1143 | -0.12721 | 5.8728 | -6.1272 | -9.93 | -9.7031 | -8.7031 | -10.7031
ext24 | -107.363 | 6013.883 | 0.038 | -107.0096 | 0 | -106.0096 | -108.0096 | 1 | -1 | 0.35544 | -0.3534 | 6013.883 | 0.46782 | 0.59503 | -0.12721 | 5.8728 | -6.1272 | -10.103 | -9.7496 | -8.7496 | -10.7496
ext25 | -107.458 | 6429.294 | 0.193 | -107.2102 | 0 | -106.2102 | -108.2102 | 1 | -1 | 0.31406 | -0.24775 | 6429.294 | 0.16965 | 0.29686 | -0.12721 | 5.8728 | -6.1272 | -10.198 | -9.9502 | -8.9502 | -10.9502
ext26 | -107.587 | 6527.271 | 0.141 | -107.2486 | 0 | -106.2486 | -108.2486 | 1 | -1 | 0.36657 | -0.33837 | 6527.271 | 0.37528 | 0.5025 | -0.12721 | 5.8728 | -6.1272 | -10.327 | -9.9886 | -8.9886 | -10.9886
ext27 | -107.622 | 6926.618 | 0.228 | -107.3698 | 0 | -106.3698 | -108.3698 | 1 | -1 | 0.34001 | -0.25224 | 6926.618 | -0.0051409 | 0.12207 | -0.12721 | 5.8728 | -6.1272 | -10.362 | -10.1098 | -9.1098 | -11.1098
ext28 | -107.729 | 7038.874 | 0.129 | -107.3936 | 0 | -106.3936 | -108.3936 | 1 | -1 | 0.35935 | -0.3354 | 7038.874 | -0.23134 | -0.10412 | -0.12721 | 5.8728 | -6.1272 | -10.469 | -10.1336 | -9.1336 | -11.1336
ext29 | -107.766 | 7419.086 | 0.27 | -107.4411 | 0 | -106.4411 | -108.4411 | 1 | -1 | 0.42248 | -0.32494 | 7419.086 | 0.2519 | 0.37912 | -0.12721 | 5.8728 | -6.1272 | -10.506 | -10.1811 | -9.1811 | -11.1811
ext30 | -107.913 | 7551.778 | 0.125 | -107.4455 | 0 | -106.4455 | -108.4455 | 1 | -1 | 0.4839 | -0.46748 | 7551.778 | -0.041127 | 0.086087 | -0.12721 | 5.8728 | -6.1272 | -10.653 | -10.1855 | -9.1855 | -11.1855
ext31 | -107.738 | 7912.948 | 0.202 | -107.426 | 0 | -106.426 | -108.426 | 1 | -1 | 0.37172 | -0.31205 | 7912.948 | 0.21078 | 0.33799 | -0.12721 | 5.8728 | -6.1272 | -10.478 | -10.166 | -9.166 | -11.166
ext32 | -107.857 | 8063.931 | 0.158 | -107.404 | 0 | -106.404 | -108.404 | 1 | -1 | 0.47974 | -0.45297 | 8063.931 | 0.5038 | 0.63102 | -0.12721 | 5.8728 | -6.1272 | -10.597 | -10.144 | -9.144 | -11.144
ext33 | -107.563 | 8405.754 | 0.101 | -107.3244 | 0 | -106.3244 | -108.3244 | 1 | -1 | 0.25906 | -0.23857 | 8405.754 | -0.2262 | -0.098984 | -0.12721 | 5.8728 | -6.1272 | -10.303 | -10.0644 | -9.0644 | -11.0644
ext34 | -107.67 | 8576.861 | 0.102 | -107.269 | 0 | -106.269 | -108.269 | 1 | -1 | 0.41378 | -0.40101 | 8576.861 | 0.44211 | 0.56933 | -0.12721 | 5.8728 | -6.1272 | -10.41 | -10.009 | -9.009 | -11.009
ext35 | -107.383 | 8898.18 | 0.095 | -107.1367 | 0 | -106.1367 | -108.1367 | 1 | -1 | 0.26395 | -0.24626 | 8898.18 | 0.077113 | 0.20433 | -0.12721 | 5.8728 | -6.1272 | -10.123 | -9.8767 | -8.8767 | -10.8767
ext36 | -107.373 | 9089.479 | -0.02 | -107.0406 | 0 | -106.0406 | -108.0406 | 1 | -1 | 0.33303 | -0.33243 | 9089.479 | 0.23648 | 0.36369 | -0.12721 | 5.8728 | -6.1272 | -10.113 | -9.7806 | -8.7806 | -10.7806
ext37 | -107.117 | 9390.126 | -0.036 | -106.8631 | 0 | -105.8631 | -107.8631 | 1 | -1 | 0.25641 | -0.25387 | 9390.126 | -0.38556 | -0.25835 | -0.12721 | 5.8728 | -6.1272 | -9.857 | -9.6031 | -8.6031 | -10.6031
ext38 | -107.111 | 9601.431 | -0.183 | -106.7192 | 0 | -105.7192 | -107.7192 | 1 | -1 | 0.43244 | -0.39181 | 9601.431 | 0.31359 | 0.44081 | -0.12721 | 5.8728 | -6.1272 | -9.851 | -9.4592 | -8.4592 | -10.4592
ext39 | -106.802 | 9881.565 | -0.223 | -106.5039 | 0 | -105.5039 | -107.5039 | 1 | -1 | 0.37229 | -0.29811 | 9881.565 | -0.61176 | -0.48455 | -0.12721 | 5.8728 | -6.1272 | -9.542 | -9.2439 | -8.2439 | -10.2439
ext40 | -106.74 | 10112.95 | -0.342 | -106.305 | 0 | -105.305 | -107.305 | 1 | -1 | 0.55334 | -0.435 | 10112.95 | -0.27761 | -0.15039 | -0.12721 | 5.8728 | -6.1272 | -9.48 | -9.045 | -8.045 | -10.045
ext41 | -106.398 | 10375.6 | -0.23 | -106.0562 | 0 | -105.0562 | -107.0562 | 1 | -1 | 0.41199 | -0.34182 | 10375.6 | -0.18507 | -0.057857 | -0.12721 | 5.8728 | -6.1272 | -9.138 | -8.7962 | -7.7962 | -9.7962
ext42 | -106.409 | 10375.6 | -0.328 | -106.0562 | 0 | -105.0562 | -107.0562 | 1 | -1 | 0.48173 | -0.35282 | 10375.6 | 0.43183 | 0.55905 | -0.12721 | 5.8728 | -6.1272 | -9.149 | -8.7962 | -7.7962 | -9.7962
ext43 | -106.243 | 10626.1 | -0.438 | -105.796 | 0 | -104.796 | -106.796 | 1 | -1 | 0.62581 | -0.44698 | 10626.1 | -0.85852 | -0.73131 | -0.12721 | 5.8728 | -6.1272 | -8.983 | -8.536 | -7.536 | -9.536
ext44 | -105.878 | 10842.49 | -0.489 | -105.5533 | 0 | -104.5533 | -106.5533 | 1 | -1 | 0.58697 | -0.32468 | 10842.49 | -0.14394 | -0.01673 | -0.12721 | 5.8728 | -6.1272 | -8.618 | -8.2933 | -7.2933 | -9.2933
ext45 | -105.685 | 11138.2 | -0.496 | -105.1947 | 0 | -104.1947 | -106.1947 | 1 | -1 | 0.69741 | -0.49027 | 11138.2 | -1.8918 | -1.7646 | -0.12721 | 5.8728 | -6.1272 | -8.425 | -7.9347 | -6.9347 | -8.9347
ext46 | -105.277 | 11332.37 | -0.375 | -104.9424 | 0 | -103.9424 | -105.9424 | 1 | -1 | 0.5026 | -0.33464 | 11332.37 | 0.23134 | 0.35855 | -0.12721 | 5.8728 | -6.1272 | -8.017 | -7.6824 | -6.6824 | -8.6824
ext47 | -104.878 | 11651.13 | -0.43 | -104.499 | 0 | -103.499 | -105.499 | 1 | -1 | 0.57319 | -0.37901 | 11651.13 | -1.9792 | -1.852 | -0.12721 | 5.8728 | -6.1272 | -7.618 | -7.239 | -6.239 | -8.239
ext48 | -104.522 | 11820.22 | -0.421 | -104.2491 | 0 | -103.2491 | -105.2491 | 1 | -1 | 0.50169 | -0.27286 | 11820.22 | -0.32901 | -0.2018 | -0.12721 | 5.8728 | -6.1272 | -7.262 | -6.9891 | -5.9891 | -7.9891
ext49 | -104.491 | 11820.23 | -0.289 | -104.2491 | 0 | -103.2491 | -105.2491 | 1 | -1 | 0.37686 | -0.24188 | 11820.23 | -0.61176 | -0.48455 | -0.12721 | 5.8728 | -6.1272 | -7.231 | -6.9891 | -5.9891 | -7.9891
ext50 | -103.988 | 12162.49 | -0.315 | -103.7123 | 0 | -102.7123 | -104.7123 | 1 | -1 | 0.41863 | -0.27573 | 12162.49 | 0.17993 | 0.30714 | -0.12721 | 5.8728 | -6.1272 | -6.728 | -6.4523 | -5.4523 | -7.4523
ext51 | -103.61 | 12286.86 | -0.147 | -103.5069 | 0 | -102.5069 | -104.5069 | 1 | -1 | 0.17957 | -0.10314 | 12286.86 | -1.1361 | -1.0089 | -0.12721 | 5.8728 | -6.1272 | -6.35 | -6.2469 | -5.2469 | -7.2469
ext52 | -102.876 | 12676.21 | -0.07 | -102.8283 | 0 | -101.8283 | -103.8283 | 1 | -1 | 0.084718 | -0.047719 | 12676.21 | 0.066831 | 0.19405 | -0.12721 | 5.8728 | -6.1272 | -5.616 | -5.5683 | -4.5683 | -6.5683
ext53 | -102.519 | 12779.44 | 0.114 | -102.6393 | 0 | -101.6393 | -103.6393 | 1 | -1 | 0.16575 | 0.12033 | 12779.44 | -0.80711 | -0.6799 | -0.12721 | 5.8728 | -6.1272 | -5.259 | -5.3793 | -4.3793 | -6.3793
ext54 | -101.626 | 13188.83 | 0.029 | -101.8527 | 0 | -100.8527 | -102.8527 | 1 | -1 | 0.2285 | 0.22665 | 13188.83 | -0.24162 | -0.11441 | -0.12721 | 5.8728 | -6.1272 | -4.366 | -4.5927 | -3.5927 | -5.5927
ext55 | -101.351 | 13269.43 | 0.28 | -101.6908 | 0 | -100.6908 | -102.6908 | 1 | -1 | 0.44026 | 0.33975 | 13269.43 | -0.73 | -0.60279 | -0.12721 | 5.8728 | -6.1272 | -4.091 | -4.4308 | -3.4308 | -5.4308
ext56 | -100.281 | 13700.09 | 0.171 | -100.7865 | 0 | -99.7865 | -101.7865 | 1 | -1 | 0.53368 | 0.50554 | 13700.09 | 0.43697 | 0.56419 | -0.12721 | 5.8728 | -6.1272 | -3.021 | -3.5265 | -2.5265 | -4.5265
ext57 | -99.984 | 13762.54 | 0.39 | -100.65 | 0 | -99.65 | -101.65 | 1 | -1 | 0.77175 | 0.66595 | 13762.54 | 1.4497 | 1.5769 | -0.12721 | 5.8728 | -6.1272 | -2.724 | -3.39 | -2.39 | -4.39
ext58 | -98.745 | 14214.48 | 0.364 | -99.6201 | 0 | -98.6201 | -100.6201 | 1 | -1 | 0.9478 | 0.87511 | 14214.48 | 2.3802 | 2.5074 | -0.12721 | 5.8728 | -6.1272 | -1.485 | -2.3601 | -1.3601 | -3.3601
ext59 | -98.55 | 14256.62 | 0.559 | -99.5204 | 0 | -98.5204 | -100.5204 | 1 | -1 | 1.1199 | 0.97039 | 14256.62 | 2.5961 | 2.7233 | -0.12721 | 5.8728 | -6.1272 | -1.29 | -2.2604 | -1.2604 | -3.2604
ext60 | -98.508 | 14256.62 | 0.426 | -99.5204 | 0 | -98.5204 | -100.5204 | 1 | -1 | 1.0984 | 1.0124 | [6 empty] | -1.248 | -2.2604 | -1.2604 | -3.2604
ext61 | -97.416 | 14722.7 | 0.648 | -98.3753 | 0 | -97.3753 | -99.3753 | 1 | -1 | 1.1576 | 0.95927 | [6 empty] | -0.156 | -1.1153 | -0.11527 | -2.1153
ext62 | -97.498 | 14726.17 | 0.451 | -98.3665 | 0 | -97.3665 | -99.3665 | 1 | -1 | 0.97858 | 0.86846 | [6 empty] | -0.238 | -1.1065 | -0.10646 | -2.1065
int1 | 96.688 | 331.916 | -0.385 | 96.4139 | 0 | 97.4139 | 95.4139 | 1 | -1 | 0.47259 | 0.27407 | [6 empty] | -0.572 | -0.84607 | 0.15393 | -1.8461
int2 | 96.614 | 424.172 | -0.717 | 96.1787 | 0 | 97.1787 | 95.1787 | 1 | -1 | 0.83877 | 0.43526 | [6 empty] | -0.646 | -1.0813 | -0.081262 | -2.0813
int3 | 95.844 | 846.986 | -0.487 | 95.1347 | 0 | 96.1347 | 94.1347 | 1 | -1 | 0.86039 | 0.7093 | [6 empty] | -1.416 | -2.1253 | -1.1253 | -3.1253
int4 | 95.676 | 927.828 | -0.367 | 94.9423 | 0 | 95.9423 | 93.9423 | 1 | -1 | 0.82035 | 0.73368 | [6 empty] | -1.584 | -2.3177 | -1.3177 | -3.3177
int5 | 94.51 | 1362.965 | -0.088 | 93.9467 | 0 | 94.9467 | 92.9467 | 1 | -1 | 0.5701 | 0.56327 | [6 empty] | -2.75 | -3.3133 | -2.3133 | -4.3133
int6 | 94.346 | 1429.848 | -0.113 | 93.7997 | 0 | 94.7997 | 92.7997 | 1 | -1 | 0.55789 | 0.54633 | [6 empty] | -2.914 | -3.4603 | -2.4603 | -4.4603
int7 | 93.176 | 1878.193 | 0.266 | 92.855 | 0 | 93.855 | 91.855 | 1 | -1 | 0.41693 | 0.32105 | [6 empty] | -4.084 | -4.405 | -3.405 | -5.405
int8 | 93.103 | 1933.218 | 0.219 | 92.7439 | 0 | 93.7439 | 91.7439 | 1 | -1 | 0.42059 | 0.35907 | [6 empty] | -4.157 | -4.5161 | -3.5161 | -5.5161
int9 | 92.003 | 2393.651 | 0.586 | 91.8571 | 0 | 92.8571 | 90.8571 | 1 | -1 | 0.60388 | 0.14586 | [6 empty] | -5.257 | -5.4029 | -4.4029 | -6.4029
int10 | 91.959 | 2438.761 | 0.526 | 91.7743 | 0 | 92.7743 | 90.7743 | 1 | -1 | 0.55748 | 0.18469 | [6 empty] | -5.301 | -5.4857 | -4.4857 | -6.4857
int11 | 90.962 | 2907.873 | 0.582 | 90.9559 | 0 | 91.9559 | 89.9559 | 1 | -1 | 0.58203 | 0.0061449 | [6 empty] | -6.298 | -6.3041 | -5.3041 | -7.3041
int12 | 90.971 | 2941.59 | 0.554 | 90.9 | 0 | 91.9 | 89.9 | 1 | -1 | 0.55853 | 0.070957 | [6 empty] | -6.289 | -6.36 | -5.36 | -7.36
int13 | 90.039 | 3423.241 | 0.349 | 90.1469 | 0 | 91.1469 | 89.1469 | 1 | -1 | 0.3653 | -0.1079 | [6 empty] | -7.221 | -7.1131 | -6.1131 | -8.1131
int14 | 90.077 | 3443.738 | 0.35 | 90.1167 | 0 | 91.1167 | 89.1167 | 1 | -1 | 0.35224 | -0.039679 | [6 empty] | -7.183 | -7.1433 | -6.1433 | -8.1433
int15 | 89.319 | 3938.286 | 0.072 | 89.4328 | 0 | 90.4328 | 88.4328 | 1 | -1 | 0.13467 | -0.11381 | [6 empty] | -7.941 | -7.8272 | -6.8272 | -8.8272
int16 | 89.368 | 3946.936 | 0.074 | 89.4216 | 0 | 90.4216 | 88.4216 | 1 | -1 | 0.091383 | -0.053618 | [6 empty] | -7.892 | -7.8384 | -6.8384 | -8.8384
int17 | 88.701 | 4447.648 | -0.018 | 88.8194 | 0 | 89.8194 | 87.8194 | 1 | -1 | 0.11972 | -0.11836 | [6 empty] | -8.559 | -8.4406 | -7.4406 | -9.4406
int18 | 88.66 | 4452.783 | 0.007 | 88.8136 | 0 | 89.8136 | 87.8136 | 1 | -1 | 0.1538 | -0.15364 | [6 empty] | -8.6 | -8.4464 | -7.4464 | -9.4464
int19 | 88.169 | 4953.229 | -0.002 | 88.3017 | 0 | 89.3017 | 87.3017 | 1 | -1 | 0.13271 | -0.13269 | [6 empty] | -9.091 | -8.9583 | -7.9583 | -9.9583
int20 | 88.126 | 4965.839 | 0.006 | 88.2899 | 0 | 89.2899 | 87.2899 | 1 | -1 | 0.16405 | -0.16395 | [6 empty] | -9.134 | -8.9701 | -7.9701 | -9.9701
int21 | 87.67 | 5458.327 | -0.117 | 87.8753 | 0 | 88.8753 | 86.8753 | 1 | -1 | 0.23628 | -0.20528 | [6 empty] | -9.59 | -9.3847 | -8.3847 | -10.3847
int22 | 87.578 | 5482.425 | -0.121 | 87.8572 | 0 | 88.8572 | 86.8572 | 1 | -1 | 0.3043 | -0.27921 | [6 empty] | -9.682 | -9.4028 | -8.4028 | -10.4028
int23 | 87.311 | 5964.592 | -0.041 | 87.5389 | 0 | 88.5389 | 86.5389 | 1 | -1 | 0.23158 | -0.22792 | [6 empty] | -9.949 | -9.7211 | -8.7211 | -10.7211
int24 | 87.216 | 5996.464 | -0.053 | 87.5208 | 0 | 88.5208 | 86.5208 | 1 | -1 | 0.30937 | -0.30479 | [6 empty] | -10.044 | -9.7392 | -8.7392 | -10.7392
int25 | 87.029 | 6470.54 | 0.16 | 87.2938 | 0 | 88.2938 | 86.2938 | 1 | -1 | 0.3094 | -0.26481 | [6 empty] | -10.231 | -9.9662 | -8.9662 | -10.9662
int26 | 86.932 | 6509.653 | 0.068 | 87.2787 | 0 | 88.2787 | 86.2787 | 1 | -1 | 0.35326 | -0.34665 | [6 empty] | -10.328 | -9.9813 | -8.9813 | -10.9813
int27 | 86.907 | 6971.842 | 0.229 | 87.1407 | 0 | 88.1407 | 86.1407 | 1 | -1 | 0.32722 | -0.23373 | [6 empty] | -10.353 | -10.1193 | -9.1193 | -11.1193
int28 | 86.813 | 7025.174 | 0.174 | 87.1297 | 0 | 88.1297 | 86.1297 | 1 | -1 | 0.36135 | -0.3167 | [6 empty] | -10.447 | -10.1303 | -9.1303 | -11.1303
int29 | 86.718 | 7469.257 | 0.221 | 87.0772 | 0 | 88.0772 | 86.0772 | 1 | -1 | 0.4217 | -0.35915 | [6 empty] | -10.542 | -10.1828 | -9.1828 | -11.1828
int30 | 86.693 | 7542.334 | 0.133 | 87.0752 | 0 | 88.0752 | 86.0752 | 1 | -1 | 0.4047 | -0.38222 | [6 empty] | -10.567 | -10.1848 | -9.1848 | -11.1848
int31 | 86.661 | 7966.938 | 0.161 | 87.1016 | 0 | 88.1016 | 86.1016 | 1 | -1 | 0.46908 | -0.44059 | [6 empty] | -10.599 | -10.1584 | -9.1584 | -11.1584
int32 | 86.662 | 8060.009 | 0.06 | 87.1159 | 0 | 88.1159 | 86.1159 | 1 | -1 | 0.45788 | -0.45393 | [6 empty] | -10.598 | -10.1441 | -9.1441 | -11.1441
int33 | 86.85 | 8461.29 | 0.145 | 87.2131 | 0 | 88.2131 | 86.2131 | 1 | -1 | 0.39094 | -0.36305 | [6 empty] | -10.41 | -10.0469 | -9.0469 | -11.0469
int34 | 86.873 | 8577.525 | 0.016 | 87.2519 | 0 | 88.2519 | 86.2519 | 1 | -1 | 0.37922 | -0.37888 | [6 empty] | -10.387 | -10.0081 | -9.0081 | -11.0081
int35 | 87.069 | 8960.897 | 0.08 | 87.414 | 0 | 88.414 | 86.414 | 1 | -1 | 0.35414 | -0.34499 | [6 empty] | -10.191 | -9.846 | -8.846 | -10.846
int36 | 87.144 | 9092.826 | -0.066 | 87.4819 | 0 | 88.4819 | 86.4819 | 1 | -1 | 0.34425 | -0.33786 | [6 empty] | -10.116 | -9.7781 | -8.7781 | -10.7781
int37 | 87.347 | 9459.775 | 0.039 | 87.7032 | 0 | 88.7032 | 86.7032 | 1 | -1 | 0.35832 | -0.35619 | [6 empty] | -9.913 | -9.5568 | -8.5568 | -10.5568
int38 | 87.437 | 9607.37 | -0.244 | 87.8057 | 0 | 88.8057 | 86.8057 | 1 | -1 | 0.44214 | -0.36871 | [6 empty] | -9.823 | -9.4543 | -8.4543 | -10.4543
int39 | 87.772 | 9958.576 | -0.104 | 88.0808 | 0 | 89.0808 | 87.0808 | 1 | -1 | 0.32586 | -0.30882 | [6 empty] | -9.488 | -9.1792 | -8.1792 | -10.1792
int40 | 87.843 | 10122.75 | -0.288 | 88.2245 | 0 | 89.2245 | 87.2245 | 1 | -1 | 0.47797 | -0.38146 | [6 empty] | -9.417 | -9.0355 | -8.0355 | -10.0355
int41 | 88.158 | 10452.66 | -0.194 | 88.5421 | 0 | 89.5421 | 87.5421 | 1 | -1 | 0.43031 | -0.3841 | [6 empty] | -9.102 | -8.7179 | -7.7179 | -9.7179
int42 | 88.321 | 10637.03 | -0.412 | 88.7365 | 0 | 89.7365 | 87.7365 | 1 | -1 | 0.58511 | -0.41546 | [6 empty] | -8.939 | -8.5235 | -7.5235 | -9.5235
int43 | 88.729 | 10953.35 | -0.271 | 89.0981 | 0 | 90.0981 | 88.0981 | 1 | -1 | 0.4579 | -0.36909 | [6 empty] | -8.531 | -8.1619 | -7.1619 | -9.1619
int44 | 88.977 | 11152.29 | -0.461 | 89.3438 | 0 | 90.3438 | 88.3438 | 1 | -1 | 0.58909 | -0.36675 | [6 empty] | -8.283 | -7.9162 | -6.9162 | -8.9162
int45 | 89.425 | 11455.59 | -0.128 | 89.7454 | 0 | 90.7454 | 88.7454 | 1 | -1 | 0.34498 | -0.32036 | [6 empty] | -7.835 | -7.5146 | -6.5146 | -8.5146
int46 | 89.743 | 11667.84 | -0.42 | 90.0459 | 0 | 91.0459 | 89.0459 | 1 | -1 | 0.51781 | -0.30286 | [6 empty] | -7.517 | -7.2141 | -6.2141 | -8.2141
int47 | 90.199 | 11953.66 | -0.045 | 90.4758 | 0 | 91.4758 | 89.4758 | 1 | -1 | 0.28047 | -0.27683 | [6 empty] | -7.061 | -6.7842 | -5.7842 | -7.7842
int48 | 90.583 | 12181.48 | -0.357 | 90.8394 | 0 | 91.8394 | 89.8394 | 1 | -1 | 0.43951 | -0.25636 | [6 empty] | -6.677 | -6.4206 | -5.4206 | -7.4206
int49 | 91.166 | 12446.59 | -0.17 | 91.2856 | 0 | 92.2856 | 90.2856 | 1 | -1 | 0.20787 | -0.11962 | [6 empty] | -6.094 | -5.9744 | -4.9744 | -6.9744
int50 | 91.695 | 12696.04 | -0.35 | 91.7283 | 0 | 92.7283 | 90.7283 | 1 | -1 | 0.35158 | -0.033336 | [6 empty] | -5.565 | -5.5317 | -4.5317 | -6.5317
int51 | 92.311 | 12943.61 | 0.074 | 92.1896 | 0 | 93.1896 | 91.1896 | 1 | -1 | 0.14218 | 0.1214 | [6 empty] | -4.949 | -5.0704 | -4.0704 | -6.0704
int52 | 92.946 | 13213.6 | -0.083 | 92.7175 | 0 | 93.7175 | 91.7175 | 1 | -1 | 0.24314 | 0.22853 | [6 empty] | -4.314 | -4.5425 | -3.5425 | -5.5425
int53 | 93.552 | 13441.45 | 0.271 | 93.1831 | 0 | 94.1831 | 92.1831 | 1 | -1 | 0.45773 | 0.36888 | [6 empty] | -3.708 | -4.0769 | -3.0769 | -5.0769
int54 | 94.381 | 13732.12 | 0.076 | 93.804 | 0 | 94.804 | 92.804 | 1 | -1 | 0.58203 | 0.57705 | [6 empty] | -2.879 | -3.456 | -2.456 | -4.456
int55 | 94.974 | 13937.73 | 0.422 | 94.2612 | 0 | 95.2612 | 93.2612 | 1 | -1 | 0.82831 | 0.71275 | [6 empty] | -2.286 | -2.9988 | -1.9988 | -3.9988
int56 | 96.013 | 14245.51 | 0.086 | 94.9739 | 0 | 95.9739 | 93.9739 | 1 | -1 | 1.0427 | 1.0391 | [6 empty] | -1.247 | -2.2861 | -1.2861 | -3.2861
int57 | 96.531 | 14432.25 | 0.108 | 95.4227 | 0 | 96.4227 | 94.4227 | 1 | -1 | 1.1136 | 1.1083 | [6 empty] | -0.729 | -1.8373 | -0.83734 | -2.8373
int58 | 97.202 | 14760.3 | -0.099 | 96.2411 | 0 | 97.2411 | 95.2411 | 1 | -1 | 0.96602 | 0.96093 | [6 empty] | -0.058 | -1.0189 | -0.018933 | -2.0189
int59 | 97.358 | 14932.39 | 0.054 | 96.6799 | 0 | 97.6799 | 95.6799 | 1 | -1 | 0.68025 | 0.6781 | [6 empty] | 0.098 | -0.5801 | 0.4199 | -1.5801
BACK

## info_cm
Points measured:
the theoretical and measured values are expressed in a local coordinate system created
as follows:
Point1
Point2
Point3
Point4
outer sextupole magnet
inner sextupole magnet
Point1
Point2
outer decapole magnet
inner decapole magnet
BACK
sextupole: lyre side
theoretical coordinate system with origin on the end-plate, obtained after transformation and analysis of the mid-plane measurements and then translated over +Y to have its origin on the lyre side end-plate and then rotated around the z-axis over -2.5mrad
deca/octopole: connection side
theoretical coordinate system with origin on the end-plate, obtained after transformation and analysis of the mid-plane measurements and then rotated around the z-axis over +2.5mrad

## info_ec
D9,D10,D11: |  |  |  | Sign convention for angles:
on the end covers
Plane C = plane containing D9, D10 and D11 on the Connection Side
Plane L = plane containing D9, D10 and D11 on the Lyre Side
Theoretical Values and Coordinate systems
the theoretical and measured values are expressed in a local coordinate system created as follows:
connexion side
theoretical coordinate system, obtained after transformation and analysis of the mid-plane measurements
translated to have its origin at the intersection of the C-plane and the theoretical V1-V2-average line
and then rotated around the z-axis over +2.5mrad
lyre side
theoretical coordinate system with origin on the end-cover, obtained after transformation and analysis of the mid-plane measurements
translated to have its origin at the intersection of the L-plane and the theoretical V1-V2-average line
and then rotated around the z-axis over -2.5mrad
Tolerances:
Tolerances Connection Side (same for Lyre Side):
BACK
BACK

## info_cf
Theoretical values and Coordinate system:
Top view of cold mass and it's cold feet pads, showing the coordinate system used
The coordinate system is based on the theoretical system (obtained after transformation and analysis of the mid-plane measurements)
but has been translated to have its origin in the center of the central support cold feet pad.
Tolerances:
Nominal value and tolerances of distance between feet:
Nominal Value and tolerances of vertical position of feet:
Tolerance on parallelism between plane of feet pad and plane V1-V2:
| Length of cold feet pad=360mm. Tolerance of parrallelism becomes: |  | angle <= 0.5/360 mrad = 1.38 mrad for the central support pad
angle <=1/360 mrad = 2.76 mrad for the external ones
| Width of cold feet pad=300mm. Tolerance of parrallelism becomes: |  | angle <= 0.5/300 mrad = 1.67 mrad for the central support pad
angle <= 1/300 mrad = 3.34 mrad for the external ones
BACK

## info_tl
Tolerances:
Nominal Value and Tolerance of Total Length:
BACK

## info_sh
Theoretical values and Coordinate system:
The coordinate system used is the theoretical system, obtained after transformation and analysis of the mid-plane measurements
The (x=0) of the theoretical coordinate system lies on the (outside of) the end-plate of the connection side
Tolerances:
theoretic shape of the cold bore tubes and the tolerances imposed (all dimensions in mm)
BACK

## info_te
Theoretical values and Coordinate systems
the theoretical and measured values are expressed in a local coordinate system created as follows:
Connection side
theoretical coordinate system with origin on the end-cover, obtained after transformation and analysis of the mid-plane measurements
then translated to have its origin at the intersection of the C-plane and the theoretical V1-V2-average line
and rotated around the z-axis over +2.5mrad
Lyre side
theoretical coordinate system with origin on the end-cover, obtained after transformation and analysis of the mid-plane measurements
then translated to have its origin at the intersection of the L-plane and the theoretical V1-V2-average line
and rotated around the z-axis over -2.5mrad
Tolerances:
The total offset of each tube extremity must be <= 0.3 mm
(Total Offset = (Horizontal Offset)2 + (Vertical Offset)2 )
BACK
BACK