## Sheet1
Annex 2
THERMOMETER TT821 VERIFICATIONS
Magnet N°: HCMBBLA001-02000157
Thermometer N°: CX_LS_X20592 |  |  | 1 | 2 | 3 | 4
Thermometer situation | Date | Cold mass | Resistance | Resistance | Resistance | Resistance | Checked by | Remark
|  | Temperature | V+,V-,I+,I- | V-, I- | V+, I+ | V+,V-,I+,I-/GND
|  | °C | W | W | W | MW
Expected value |  | 10<T<32 | Ref. Value (1) | Ref. Val.(1) | Ref. Val.(1) | R>40
|  |  | +/- 3W | +/- 1W | +/- 1W
Reference value given by CERN | 2004-04-14 | 22 | 57.97 | 4.51 | 4.53 | OVLD | CERN
At delivery | 2005-01-31 | 12 | 59.57 | 4.37 | 4.36 | OVLD | PAVESE
After mounting on the half-yoke | 2005-02-03 | 16 | 58.85 | 4.41 | 4.39 | OVLD | REPETTO
After turning over of the half-yoke | 2005-02-03 | 16 | 58.82 | 4.41 | 4.4 | OVLD | REPETTO
After pressing of the yoke | 2005-02-07 | 12 | 59.54 | 4.37 | 4.37 | OVLD | REPETTO
After longitudinal welding | 2005-02-09 | 12 | 59.55 | 4.39 | 4.38 | OVLD | PAVESE
on cut wire | [5 empty] | OVLD
After finishing of instrum. wiring | 2005-03-04 | 13 | 59.53 | 4.3 | 4.32 | OVLD | PAVESE
After complete electrical test | 2005-03-04 | 13 | 59.52 | 4.33 | 4.34 | OVLD | PAVESE
After welding of end covers | 2005-03-07 | 14 | 59.53 | 4.39 | 4.42 | OVLD | PAVESE
After mounting of capillary (IFS) | 2005-03-12 | 16 | 58.25 | 3.47 | 3.47 | OVLD | REPETTO
After pressure test | 2005-03-16 | 18 | 58.1 | 3.48 | 3.46 | OVLD | PAVESE
After complete electrical test | 2005-03-16 | 18 | 58.1 | 3.49 | 3.47 | OVLD | PAVESE
|  |  | W4W meth. | W2W meth. | W2W meth. | W2W method
(1) The reference values are those written in the last row of the Thermometer Traveller supplied by CERN with the thermometer itself.
For information the temperature sensitivity at ambient temperature is approximately -0.25 W / °C
Resistance measurements are performed with Keithley 2000 or Hewlett Packard 34401A multimeter.
|  |  | 6 contacts Wago connector |  | Multimeter
6
Scheme for 4 wires resistance measurement method |  |  | 5
W4 function |  |  | 4 | I - green | Input LO
|  |  | 3 | I+ yellow | Input HI
|  |  | 2 | V - red | Sense LO
|  |  | 1 | V+ black | Sense HI
1 | 2 |  |  |  |  | 3 |  | 4
Colore boccola Colore boccola |  | Colore boccola |  |  |  | Colore boccola
Nero
Rosso
Giallo
Blu
Rosso
Blu
Nero
Giallo
Massa
Tutte le
boccole
HP 34401A
HP 34401A
HP 34401A
HP 34401A