## overview
ITP20-HCMBB-2002
| OVERVIEW ASSEMBLY COLD MASS Nr. HCMBB-2002 | [5 empty] | TrackerID: | 583
| Date: | 30/06/03
CORRECTOR MAGNETS
Sextupole Corrector Magnets
| Status: |  |  | V1 | OK
|  |  |  | V2 | OK
All data completed
| Magnet type: |  | B
No Deca/Octopoles present
There are written remarks
Document not signed at CERN
END-COVERS
|  |  |  | Conn. Side | OK | #REF! |  |  | Existing survey data
| Status: |  |  |  |  | #REF!
| All data completed |  |  | Lyre Side | OK | #REF! |  |  | Existing shape data
#REF!
Existing statistical data
COLD FEET PADS
|  |  |  | Conn. Side | OK | #REF!
#REF!
| Status: |  |  | Central | OK | #REF!
| All data completed |  |  |  |  | #REF!
|  |  |  | Lyre Side | OK | #REF!
#REF!
COLD MASS TOTAL LENGTH
Status:
| All data completed |  |  | OK (T=20°C)
SHAPE
| Status: |  |  | V1
| Existing shape data |  |  |  | Out of tolerance
V2
Out of tolerance
Twist out of tolerance
TUBE ENDS
|  |  |  | V1, Conn. Side | OK | #REF!
#REF!
| Status: |  |  | V2, Conn. Side |  | #REF!
| All data completed |  |  |  | Out of tolerance | #REF!
|  |  |  | V1, Lyre Side |  | #REF!
[5 empty] | Out of tolerance | #REF!
|  |  |  | V2, Lyre Side |  | #REF!
[5 empty] | Out of tolerance | #REF!
| Prepared by (Operator): |  |  | Caserza Bruno
| Checked by (Project Engineer): |  |  | Caserza Bruno
| Approved by (Firm responsible): |  |  | Gagliardi P.
| Checked by (CERN's inspector): |  |  | Jurgen Heer
Checked at CERN by (Project Enginner):
Start new Traveller
Magnet shape
Go to remarks
Go to survey data
Go to statistical data
Go to shape data
Signature
Traveller2_2.xls (Last modification: 24/04/2003)
The input files for this Traveller must be created with the macro:
Midplane2_2.xls
SAVE
more...
more...
more...
more...
more...
more...

## remarks
ITP20-HCMBB-2002
OVERVIEW ASSEMBLY COLD MASS Nr. HCMBB-2002
| Date: | 30/06/03
| Prepared by (Operator): | Caserza Bruno
| Checked by (Project Engineer): | Caserza Bruno
| Approved by (Firm responsible): | Gagliardi P.
| Checked by (CERN's inspector): | Jurgen Heer
Checked at CERN by (Project Enginner):
Remarks:
CORRECTOR MAGNETS
Sextupole Corrector Magnets
V1
V2
Decapole Corrector Magnets
V1
V2
END-COVERS
Conn. Side
Lyre Side
COLD FEET PADS
Conn. Side
Central
Lyre Side
COLD MASS TOTAL LENGTH
SHAPE
V1 | new tollerance +- 6 mrad
V2
TUBE ENDS
V1, Conn. Side
V2, Conn. Side | new tollerance 64 +-0.5
V1, Lyre Side | new tollerance 64 +-0.5
V2, Lyre Side | new tollerance 64 +-0.5
To overview

## correctors
Sextupole on V1 (outer)
(all dimensions in mm, all values after welding)
Local Coordinate System: End Plate Lyre Side
Id. Nr. | MCS-MA-I0026
theoretical values |  |  |  | measured values
Xt | Zt |  |  | Xm | Ym | Zm
-97.26 | 0 |  | point1 | -97.231 | 94.247 | 70.085
|  |  | point2 | -97.328 | 94.028 | -69.935
|  |  |  | -97.2795 |  | 0.075
| delta = (measured-theoretical) |  |  | tolerance
| DX | DZ | DR | t
| -0.0195 | 0.075 | 0.077494 | 0.3 | OK
Sextupole on V2 (inner)
(all dimensions in mm, all values after tack welding)
Local Coordinate System: End Plate Lyre Side
Id. Nr. | MCS-MA-I0031
theoretical values |  |  |  | measured values
Xt | Zt |  |  | Xm | Ym | Zm
97.26 | 0 |  | point3 | 97.316 | 94.713 | 69.89
|  |  | point4 | 97.207 | 94.472 | -70.075
|  |  |  | 97.2615 |  | -0.0925
| delta = (measured-theoretical) |  |  | tolerance
| DX | DZ | DR | t
| 0.0015 | -0.0925 | 0.092512 | 0.3 | OK
Deca/Octopole on V1 and Deca/Octopole on V2
(all dimensions in mm, all values after welding)
Local Coordinate System: End Plate Connection Side (see "more info")
Id. Nr. |  |  | V1
V2
theoretical values |  |  |  | measured values
Xt | Zt |  |  | Xm | Ym | Zm
97.26 | 0 |  | point1
point2
V1
V2
| delta = (measured-theoretical) |  |  | tolerance
V1
| DX | DZ | DR | t
0.3
| delta = (theoretical-measured) |  |  | tolerance
V2
| DX | DZ | DR | t
0.3
To overview
more info
To overview
more info

## end_covers
End-Cover Connection Side
(all dimensions in mm or mrad, all values after welding)
Local Coordinate System: End-Cover Connection Side
Id. Nr. | 90096-108
Reference points of the plane "C" : D9-D10-D11
| theoretical values |  |  | measured values
| Xth | Yth | Zth | Xm | Ym | Zm
D9 | -247 | 0 | 0 | -246.972 | -12.034 | -0.337 |  | Sign convention for angles:
D10 | 247 | 0 | 0 | 247.169 | -11.977 | 0.297
D11 | 0 | 0 | 247 | -0.196 | -12.014 | 246.987
Center | 0 | 0 | 0 | 0.098 | -12.005 | -0.084
|  |  |  | Reflector offset: |  | 12
Angles between end cover and theoretical plane C
|  | theoretical values |  | measured values |  | ±tolerance
Around X axis |  | 0 |  | 0.036427 |  | 0.40486 | OK
Around Z axis |  | 0 |  | 0.11535 |  | 0.40486 | OK
Localisation of Planes A and B ( 1 mm) (see more info page for details)
|  | Plane A | OK
|  | Plane B | OK
End-Cover Lyre Side
(all dimensions in mm or mrad, all values after welding)
Local Coordinate System: End-Cover Lyre Side
Id. Nr. | 90078-44
Reference points of the plane "L" : D9-D10-D11
| theoretical values |  |  | measured values
| Xth | Yth | Zth | Xm | Ym | Zm
D9 | 247 | 0 | 0 | 247.096 | 12.056 | 0.068
D10 | -247 | 0 | 0 | -246.985 | 12.15 | -0.492
D11 | 0 | 0 | 247 | -0.341 | 12.159 | 246.842
Center | 0 | 0 | 0 | 0.056 | 12.103 | -0.199
|  |  |  | Reflector offset: |  | 12
Angles between end cover and theoretical plane L
|  | theoretical values |  | measured values |  | ±tolerance
Around X axis |  | 0 |  | 0.22668 |  | 0.40486 | OK
Around Z axis |  | 0 |  | -0.19025 |  | 0.40486 | OK
Localisation of Planes A and B ( 1 mm) (see more info page for details)
|  | Plane A | OK
|  | Plane B | OK
To overview
more info
To overview
more info

## cold_feet_pads
Connection Side Support
(all dimensions in mm or mrad, all values after welding)
For all supports: Local Coordinate System: Cold Mass Center
Id. Nr. | 71
Position of center of cold foot pad
theoretical values |  |  | measured values
Xth | Yth | Zth | Xm | Ym | Zm
5.18 | -5400 | -294 | 5.553 | -5399.613 | -293.6
| delta theoretical-measured |  |  | tolerances
| DX | DY | DZ | ±toly | ±tolz
| 0.373 | 0.387 | 0.4 | 1 | 0.5 | OK
Parallelism between Cold Foot Pad and Mid Plane
|  | theoretical | measured |  | ±tolerance
| Around | 0 | 3.171 |  | 3.34 | OK
Longitudinal Axis
| Around | 0 | 0.386 |  | 2.76 | OK
Transversal Axis
Central Support
(all dimensions in mm or mrad, all values after welding)
Id. Nr. | 82
Position of center of cold foot pad
theoretical values |  |  | measured values
Xth | Yth | Zth | Xm | Ym | Zm
0 | 0 | -294 | -0.23 | -0.21 | -293.77
| delta theoretical-measured |  |  | tolerances
| DX | DY | DZ | ±toly | ±tolz
| -0.23 | -0.21 | 0.23 | 0.5 | 0.5 | OK
Parallelism between Cold Foot Pad and Mid Plane
|  | theoretical | measured |  | ±tolerance
| Around | 0 | 1.327 |  | 1.67 | OK
Longitudinal Axis
| Around | 0 | 0.602 |  | 1.38 | OK
Transversal Axis
Lyre Side Support
(all dimensions in mm or mrad, all values after welding)
Id. Nr. | 68
Position of center of cold foot pad
theoretical values |  |  | measured values
Xth | Yth | Zth | Xm | Ym | Zm
5.18 | 5400 | -294 | 2.44 | 5400.343 | -293.845
| delta theoretical-measured |  |  | tolerances
| DX | DY | DZ | ±toly | ±tolz
| -2.74 | 0.343 | 0.155 | 1 | 0.5 | OK
Parallelism between Cold Foot Pad and Mid Plane
|  | theoretical | measured |  | ±tolerance
| Around | 0 | 2.473 |  | 3.34 | OK
Longitudinal Axis
| Around | 0 | 0.354 |  | 2.76 | OK
Transversal Axis
To overview
more info
To overview
more info
To overview
more info

## total_length
Cold Mass Total Length
(all dimensions in mm)
Distance between the centers of Circle C and Circle L
(all points expressed in a commun coordinate system)
| measured values |  |  |  | Temperature(°C)
| Xm | Ym | Zm |  | Tenvironment | 34
Center C | 0.052 | -12 | -0.114 |  | Tcold mass (Tcm) | 32
Center L | 38.131 | 15173.999 | -0.411
reflector offset: |  |  | 12
total length(T=Tcm) |  |  | 15162.0467
total length(T=20°C)* |  |  | 15159.4995
theoretical total length |  |  | 15158
|  | delta measured-theoretical |  | ±tolerance
| T=Tcm | 4.0467 |  | 2
| T=20°C | 1.4995 |  |  | OK (T=20°C)
*The cold mass total length at 20°C is calculated as follows:
L(T=20°C)=L(T=Tcm)-DL
| being: | DL=a×L(T=Tcm)×DT
DT=Tcm-20°C
a=1.4×10-5°C-1
To overview
more info

## shape
Horizontal Shape of Tubes V1 and V2
(all dimensions in mm, all values after assembly cold mass)
Theoretical Coordinate System with origin on Connection Side End Plate
Is the offset of tube V1 lower than the tolerance? |  | No
Is the offset of tube V2 lower than the tolerance? |  | No
Is the quality of measurement within the tolerance? |  | Yes
Is the twist within the tolerance? |  | No
Vertical Shape of Tubes V1 and V2
(all dimensions in mm, all values after assembly cold mass)
Total Offset of Tubes V1 and V2
(all dimensions in mm, all values after assembly cold mass)
Total Offset = (Horizontal Offset)2 + (Vertical Offset)2
Twist between Tubes V1 and V2
(all dimensions in mrad, all values after assembly cold mass)
To overview
more info
to data
To overview
more info
to data

## tube ends
Connection Side End
(all dimensions in mm or mrad)
Local Coordinate System: End-Cover Connection Side
All values Measured on the outer diameter of the flanges
Center of the flanges
theoretical values |  |  | measured values |  |  | delta = (measured-theoretical) |  |  |  | Toler. R | Toler. Y
Xth | Yth | Zth | Xm | Ym | Zm | DX | DY | DZ | DR | tr | ty
theoretical values Xth: Center V1 | OK
-97.26 | -64 | 0 | -97.205 | -64.198 | 0.001 | 0.055 | -0.198 | 0.001 | 0.055009 | 0.3 | 0.3
Center V2
97.26 | -64 | 0 | 97.181 | -64.34 | -0.046 | -0.079 | -0.34 | -0.046 | 0.091417 | 0.3 | 0.3 | NOT OK
Outer diameter of the flanges
| Theoretical value |  | Measured value |  | Tolerance
| fth |  | fm |  | fmax | fmin
V1 |  |  | 75.9 |  | 75.95 | 75.85 | OK
V2 |  |  | 75.93 |  | 75.95 | 75.85 | OK
Perpendicularity of the flanges
| Theoretical value |  | Measured value |  | Toler.
| Angle |  | Angle |  | Angle
V1 | 0 |  | 3.6 |  | 4 | OK
V2 | 0 |  | 1.97 |  | 4 | OK
Position of V1 flange |  |  |  | Position of V2 flange
|  | +Z |  |  |  | +Z
|  | o | +X |  |  |  | +X
o
Lyre Side End
(all dimensions in mm or mrad)
Local Coordinate System: End-Cover Lyre Side
All values measured on the outer diameter of the flanges
Center of the flanges
theoretical values |  |  | measured values |  |  | delta = (measured-theoretical) |  |  |  | Toler. R | Toler. Y
Xth | Yth | Zth | Xm | Ym | Zm | DX | DY | DZ | DR | tr | ty
Center V1
-97.26 | 64 | 0 | -97.192 | 64.403 | -0.26 | 0.068 | 0.403 | -0.26 | 0.26875 | 0.3 | 0.3 | NOT OK
Center V2
97.26 | 64 | 0 | 97.264 | 64.388 | -0.141 | 0.004 | 0.388 | -0.141 | 0.14106 | 0.3 | 0.3 | NOT OK
Outer diameter of the flanges
| Theoretical value |  | Measured value |  | Tolerance
| f |  | f |  | fmax | fmin
V1 |  |  | 73.43 |  | 73.45 | 73.35 | OK
V2 |  |  | 73.43 |  | 73.45 | 73.35 | OK
Perpendicularity of the flanges
| Theoretical value |  | Measured value |  | Toler.
| Angle |  | Angle |  | Angle
V1 | 0 |  | 2.99 |  | 4 | OK
V2 | 0 |  | 3.58 |  | 4 | OK
| Position of V1 flange |  |  |  | Position of V2 flange
|  | +Z |  |  |  | +Z
+X |  |  |  | +X
| o |  |  |  | o
To overview
more info
To overview
more info

## survey
Survey Data
(all dimensions in mm)
Theoretical Coordinate System with origin on Connection Side End Plate
Vertical Position of the Tubes V1 and V2 measured at the Longitudinal Position of the Cold Feet Pads
| Longitudinal Position | z_V1 | z_V2 | z_average
Connection | 2180 | -0.023388 | 0.42975 | 0.20318
Center | 7580 | -0.20192 | -0.14362 | -0.17277
Lyre | 12980 | 0.31508 | 0.11104 | 0.21306
Longitudinal Axis
(origin on CS end-plate)
Vertical
or Z- Axis
To overview

## statistics
Statistical Data
(all dimensions in mm)
FALSE
Position of Tube Ends
Local Coordinate System: Rotated End-Cover Connection or Lyra Side
Where:
X=Transversal Axis
Y=Longitudinal Axis
Z=Vertical Axis
|  | V1 | V2
Dx_conn_side_v1 |  | -0.198 | Dx_lyra_side_v1 | 0.403
Dz_conn_side_v1 |  | 0.001 | Dz_lyra_side_v1 | -0.26
Dx_conn_side_v2 |  | -0.34 | Dx_lyra_side_v2 | 0.388
Dz_conn_side_v2 |  | -0.046 | Dz_lyra_side_v2 | -0.141
Max, Min and RMS of Deviation on shape V1 and V2
Rotated Theoretical Coordinate System
(X=Transversal Axis Y=Longitudinal Axis Z=Vertical Axis)
Max Dx V1 |  | 1.0822 | Max Dx V2 | 1.0824
Max Dz V1 |  | 0.627 | Max Dz V2 | 0.584
Min Dx V1 |  | -0.63907 | Min Dx v2 | -0.73186
Min Dz V1 |  | -0.474 | Min Dz v2 | -0.439
|  | RMS dx V1 | 0.45401
|  | RMS dx V2 | 0.54696
|  | RMS dz V1 | 0.25418
|  | RMS dz V2 | 0.27281
Z
X
Y
To overview

## data shape
pointID | x | y_meas | z_meas | x__theor | z_theor | +tol_x | -tol_x | +tol_z | -tol_z | offset | x_m-x_th | y_twist | twist | tw-av | av(tw) | +tol_tw-av | -tol_tw-av | x_meas_null | theor_null | tol+_null | tol-_null
ext1 | -97.146 | -26.779 | 0.229 | -97.192 | 0 | -96.192 | -98.192 | 1 | -1 | 0.23358 | 0.046031 | -26.779 | -0.097676 | -0.1635 | 0.06582 | 3.0658 | -2.9342 | 0.114 | 0.067969 | 1.068 | -0.93203
ext2 | -97.431 | 491.414 | 0.319 | -98.5122 | 0 | -97.5122 | -99.5122 | 1 | -1 | 1.1273 | 1.0812 | 491.414 | -0.95106 | -1.0169 | 0.06582 | 3.0658 | -2.9342 | -0.171 | -1.2522 | -0.25219 | -2.2522
ext3 | -97.464 | 504.908 | 0.245 | -98.5462 | 0 | -97.5462 | -99.5462 | 1 | -1 | 1.1096 | 1.0822 | 504.908 | 1.933 | 1.8671 | 0.06582 | 3.0658 | -2.9342 | -0.204 | -1.2862 | -0.28617 | -2.2862
ext4 | -98.859 | 982.026 | 0.002 | -99.706 | 0 | -98.706 | -100.706 | 1 | -1 | 0.847 | 0.847 | 982.026 | 0.14908 | 0.083265 | 0.06582 | 3.0658 | -2.9342 | -1.599 | -2.446 | -1.446 | -3.446
ext5 | -99.012 | 1018.046 | -0.082 | -99.7903 | 0 | -98.7903 | -100.7903 | 1 | -1 | 0.78258 | 0.77827 | 1018.046 | -1.3623 | -1.4281 | 0.06582 | 3.0658 | -2.9342 | -1.752 | -2.5303 | -1.5303 | -3.5303
ext6 | -100.329 | 1476.157 | 0.063 | -100.8219 | 0 | -99.8219 | -101.8219 | 1 | -1 | 0.49686 | 0.49285 | 1476.157 | -0.83796 | -0.90378 | 0.06582 | 3.0658 | -2.9342 | -3.069 | -3.5619 | -2.5619 | -4.5619
ext7 | -100.424 | 1529.137 | 0.098 | -100.9363 | 0 | -99.9363 | -101.9363 | 1 | -1 | 0.52163 | 0.51234 | 1529.137 | -1.6708 | -1.7366 | 0.06582 | 3.0658 | -2.9342 | -3.164 | -3.6763 | -2.6763 | -4.6763
ext8 | -101.742 | 1967.25 | 0.116 | -101.8448 | 0 | -100.8448 | -102.8448 | 1 | -1 | 0.15502 | 0.10283 | 1967.25 | -2.4059 | -2.4717 | 0.06582 | 3.0658 | -2.9342 | -4.482 | -4.5848 | -3.5848 | -5.5848
ext9 | -101.928 | 2041.325 | 0.063 | -101.9917 | 0 | -100.9917 | -102.9917 | 1 | -1 | 0.089586 | 0.063691 | 2041.325 | -2.1694 | -2.2353 | 0.06582 | 3.0658 | -2.9342 | -4.668 | -4.7317 | -3.7317 | -5.7317
ext10 | -102.914 | 2458.693 | -0.197 | -102.7827 | 0 | -101.7827 | -103.7827 | 1 | -1 | 0.23675 | -0.13131 | 2458.693 | -3.177 | -3.2429 | 0.06582 | 3.0658 | -2.9342 | -5.654 | -5.5227 | -4.5227 | -6.5227
ext11 | -103.156 | 2551.563 | -0.183 | -102.9503 | 0 | -101.9503 | -103.9503 | 1 | -1 | 0.27534 | -0.20572 | 2551.563 | -3.5215 | -3.5873 | 0.06582 | 3.0658 | -2.9342 | -5.896 | -5.6903 | -4.6903 | -6.6903
ext12 | -103.827 | 2950.563 | -0.009 | -103.6354 | 0 | -102.6354 | -104.6354 | 1 | -1 | 0.19183 | -0.19162 | 2950.563 | -2.4882 | -2.554 | 0.06582 | 3.0658 | -2.9342 | -6.567 | -6.3754 | -5.3754 | -7.3754
ext13 | -103.952 | 3062.541 | 0.139 | -103.8175 | 0 | -102.8175 | -104.8175 | 1 | -1 | 0.19344 | -0.13452 | 3062.541 | 1.0076 | 0.94179 | 0.06582 | 3.0658 | -2.9342 | -6.692 | -6.5575 | -5.5575 | -7.5575
ext14 | -104.412 | 3443.697 | -0.018 | -104.4039 | 0 | -103.4039 | -105.4039 | 1 | -1 | 0.01974 | -0.0081044 | 3443.697 | 0.32901 | 0.2632 | 0.06582 | 3.0658 | -2.9342 | -7.152 | -7.1439 | -6.1439 | -8.1439
ext15 | -104.602 | 3573.281 | 0.214 | -104.5915 | 0 | -103.5915 | -105.5915 | 1 | -1 | 0.21426 | -0.010502 | 3573.281 | 0.29303 | 0.22721 | 0.06582 | 3.0658 | -2.9342 | -7.342 | -7.3315 | -6.3315 | -8.3315
ext16 | -105.128 | 3935.04 | -0.086 | -105.0836 | 0 | -104.0836 | -106.0836 | 1 | -1 | 0.096774 | -0.044376 | 3935.04 | -1.4343 | -1.5001 | 0.06582 | 3.0658 | -2.9342 | -7.868 | -7.8236 | -6.8236 | -8.8236
ext17 | -105.442 | 4084.107 | 0.192 | -105.2729 | 0 | -104.2729 | -106.2729 | 1 | -1 | 0.25587 | -0.16913 | 4084.107 | 0.92021 | 0.85439 | 0.06582 | 3.0658 | -2.9342 | -8.182 | -8.0129 | -7.0129 | -9.0129
ext18 | -105.877 | 4425.951 | -0.084 | -105.677 | 0 | -104.677 | -106.677 | 1 | -1 | 0.2169 | -0.19997 | 4425.951 | -0.8174 | -0.88322 | 0.06582 | 3.0658 | -2.9342 | -8.617 | -8.417 | -7.417 | -9.417
ext19 | -106.134 | 4596.366 | 0.078 | -105.863 | 0 | -104.863 | -106.863 | 1 | -1 | 0.28202 | -0.27102 | 4596.366 | 0.83796 | 0.77214 | 0.06582 | 3.0658 | -2.9342 | -8.874 | -8.603 | -7.603 | -9.603
ext20 | -106.497 | 4915.653 | -0.055 | -106.1836 | 0 | -105.1836 | -107.1836 | 1 | -1 | 0.3182 | -0.31341 | 4915.653 | -0.046268 | -0.11209 | 0.06582 | 3.0658 | -2.9342 | -9.237 | -8.9236 | -7.9236 | -9.9236
ext21 | -106.718 | 5109.513 | -0.151 | -106.3606 | 0 | -105.3606 | -107.3606 | 1 | -1 | 0.38802 | -0.35743 | 5109.513 | 0.53465 | 0.46883 | 0.06582 | 3.0658 | -2.9342 | -9.458 | -9.1006 | -8.1006 | -10.1006
ext22 | -106.883 | 5407.343 | -0.163 | -106.6064 | 0 | -105.6064 | -107.6064 | 1 | -1 | 0.32103 | -0.27658 | 5407.343 | 1.023 | 0.95721 | 0.06582 | 3.0658 | -2.9342 | -9.623 | -9.3464 | -8.3464 | -10.3464
ext23 | -107.103 | 5619.201 | -0.113 | -106.7621 | 0 | -105.7621 | -107.7621 | 1 | -1 | 0.35913 | -0.34089 | 5619.201 | 1.2287 | 1.1628 | 0.06582 | 3.0658 | -2.9342 | -9.843 | -9.5021 | -8.5021 | -10.5021
ext24 | -107.42 | 5891.764 | -0.092 | -106.9389 | 0 | -105.9389 | -107.9389 | 1 | -1 | 0.48978 | -0.48106 | 5891.764 | 0.65289 | 0.58707 | 0.06582 | 3.0658 | -2.9342 | -10.16 | -9.6789 | -8.6789 | -10.6789
ext25 | -107.711 | 6130.14 | -0.223 | -107.0719 | 0 | -106.0719 | -108.0719 | 1 | -1 | 0.67686 | -0.63907 | 6130.14 | -0.26218 | -0.328 | 0.06582 | 3.0658 | -2.9342 | -10.451 | -9.8119 | -8.8119 | -10.8119
ext26 | -107.769 | 6384.062 | -0.253 | -107.1914 | 0 | -106.1914 | -108.1914 | 1 | -1 | 0.6306 | -0.57762 | 6384.062 | 0.89965 | 0.83383 | 0.06582 | 3.0658 | -2.9342 | -10.509 | -9.9314 | -8.9314 | -10.9314
ext27 | -107.763 | 6639.66 | -0.081 | -107.2885 | 0 | -106.2885 | -108.2885 | 1 | -1 | 0.48141 | -0.47455 | 6639.66 | 1.0796 | 1.0138 | 0.06582 | 3.0658 | -2.9342 | -10.503 | -10.0285 | -9.0285 | -11.0285
ext28 | -107.573 | 6875.849 | -0.111 | -107.3575 | 0 | -106.3575 | -108.3575 | 1 | -1 | 0.2424 | -0.21549 | 6875.849 | 0.55007 | 0.48425 | 0.06582 | 3.0658 | -2.9342 | -10.313 | -10.0975 | -9.0975 | -11.0975
ext29 | -107.593 | 7148.167 | -0.134 | -107.4125 | 0 | -106.4125 | -108.4125 | 1 | -1 | 0.2248 | -0.18049 | 7148.167 | 0.14394 | 0.078124 | 0.06582 | 3.0658 | -2.9342 | -10.333 | -10.1525 | -9.1525 | -11.1525
ext30 | -107.574 | 7364.849 | -0.207 | -107.4374 | 0 | -106.4374 | -108.4374 | 1 | -1 | 0.24799 | -0.13657 | 7364.849 | -0.14394 | -0.20976 | 0.06582 | 3.0658 | -2.9342 | -10.314 | -10.1774 | -9.1774 | -11.1774
ext31 | -107.768 | 7661.187 | -0.2 | -107.4445 | 0 | -106.4445 | -108.4445 | 1 | -1 | 0.38034 | -0.32351 | 7661.187 | 0.43183 | 0.36601 | 0.06582 | 3.0658 | -2.9342 | -10.508 | -10.1845 | -9.1845 | -11.1845
ext32 | -107.753 | 7858.205 | -0.099 | -107.4319 | 0 | -106.4319 | -108.4319 | 1 | -1 | 0.33601 | -0.3211 | 7858.205 | -0.27761 | -0.34343 | 0.06582 | 3.0658 | -2.9342 | -10.493 | -10.1719 | -9.1719 | -11.1719
ext33 | -107.805 | 8171.362 | -0.129 | -107.3835 | 0 | -106.3835 | -108.3835 | 1 | -1 | 0.44081 | -0.42151 | 8171.362 | 0.2262 | 0.16038 | 0.06582 | 3.0658 | -2.9342 | -10.545 | -10.1235 | -9.1235 | -11.1235
ext34 | -107.732 | 8350.203 | -0.209 | -107.3402 | 0 | -106.3402 | -108.3402 | 1 | -1 | 0.44406 | -0.3918 | 8350.203 | -0.20049 | -0.26631 | 0.06582 | 3.0658 | -2.9342 | -10.472 | -10.0802 | -9.0802 | -11.0802
ext35 | -107.721 | 8680.902 | -0.228 | -107.2302 | 0 | -106.2302 | -108.2302 | 1 | -1 | 0.54118 | -0.49081 | 8680.902 | -0.66831 | -0.73413 | 0.06582 | 3.0658 | -2.9342 | -10.461 | -9.9702 | -8.9702 | -10.9702
ext36 | -107.6 | 8846.076 | -0.228 | -107.1607 | 0 | -106.1607 | -108.1607 | 1 | -1 | 0.49496 | -0.43932 | 8846.076 | -1.5217 | -1.5875 | 0.06582 | 3.0658 | -2.9342 | -10.34 | -9.9007 | -8.9007 | -10.9007
ext37 | -107.509 | 9190.737 | -0.359 | -106.9844 | 0 | -105.9844 | -107.9844 | 1 | -1 | 0.63568 | -0.5246 | 9190.737 | -1.5731 | -1.6389 | 0.06582 | 3.0658 | -2.9342 | -10.249 | -9.7244 | -8.7244 | -10.7244
ext38 | -107.285 | 9342.649 | -0.474 | -106.8933 | 0 | -105.8933 | -107.8933 | 1 | -1 | 0.61491 | -0.39171 | 9342.649 | -0.67859 | -0.74441 | 0.06582 | 3.0658 | -2.9342 | -10.025 | -9.6333 | -8.6333 | -10.6333
ext39 | -107.17 | 9699.985 | -0.381 | -106.6466 | 0 | -105.6466 | -107.6466 | 1 | -1 | 0.64736 | -0.52337 | 9699.985 | 0.29817 | 0.23235 | 0.06582 | 3.0658 | -2.9342 | -9.91 | -9.3866 | -8.3866 | -10.3866
ext40 | -107.066 | 9836.416 | -0.394 | -106.5405 | 0 | -105.5405 | -107.5405 | 1 | -1 | 0.65682 | -0.52552 | 9836.416 | -0.89965 | -0.96547 | 0.06582 | 3.0658 | -2.9342 | -9.806 | -9.2805 | -8.2805 | -10.2805
ext41 | -106.733 | 10211.368 | -0.17 | -106.2147 | 0 | -105.2147 | -107.2147 | 1 | -1 | 0.54551 | -0.51835 | 10211.368 | 0.78141 | 0.71559 | 0.06582 | 3.0658 | -2.9342 | -9.473 | -8.9547 | -7.9547 | -9.9547
ext42 | -106.453 | 10332.563 | -0.191 | -106.0986 | 0 | -105.0986 | -107.0986 | 1 | -1 | 0.40255 | -0.35436 | 10332.563 | 0.64261 | 0.57679 | 0.06582 | 3.0658 | -2.9342 | -9.193 | -8.8386 | -7.8386 | -9.8386
ext43 | -105.94 | 10722.262 | -0.168 | -105.6902 | 0 | -104.6902 | -106.6902 | 1 | -1 | 0.30101 | -0.24977 | 10722.262 | 0.94592 | 0.8801 | 0.06582 | 3.0658 | -2.9342 | -8.68 | -8.4302 | -7.4302 | -9.4302
ext44 | -105.694 | 10828.502 | -0.268 | -105.5695 | 0 | -104.5695 | -106.5695 | 1 | -1 | 0.2955 | -0.12448 | 10828.502 | 0.23134 | 0.16552 | 0.06582 | 3.0658 | -2.9342 | -8.434 | -8.3095 | -7.3095 | -9.3095
ext45 | -105.209 | 11233.786 | -0.276 | -105.0722 | 0 | -104.0722 | -106.0722 | 1 | -1 | 0.30805 | -0.13682 | 11233.786 | 0.020563 | -0.045256 | 0.06582 | 3.0658 | -2.9342 | -7.949 | -7.8122 | -6.8122 | -8.8122
ext46 | -105.026 | 11323.825 | -0.252 | -104.9538 | 0 | -103.9538 | -105.9538 | 1 | -1 | 0.26215 | -0.072236 | 11323.825 | -0.071972 | -0.13779 | 0.06582 | 3.0658 | -2.9342 | -7.766 | -7.6938 | -6.6938 | -8.6938
ext47 | -104.489 | 11744.787 | 0.296 | -104.3619 | 0 | -103.3619 | -105.3619 | 1 | -1 | 0.32215 | -0.12713 | 11744.787 | 2.5601 | 2.4943 | 0.06582 | 3.0658 | -2.9342 | -7.229 | -7.1019 | -6.1019 | -8.1019
ext48 | -104.334 | 11814.545 | 0.275 | -104.2577 | 0 | -103.2577 | -105.2577 | 1 | -1 | 0.28539 | -0.076298 | 11814.545 | 0.85852 | 0.7927 | 0.06582 | 3.0658 | -2.9342 | -7.074 | -6.9977 | -5.9977 | -7.9977
ext49 | -103.61 | 12256.059 | 0.084 | -103.5583 | 0 | -102.5583 | -104.5583 | 1 | -1 | 0.098656 | -0.051739 | 12256.059 | 0.29303 | 0.22721 | 0.06582 | 3.0658 | -2.9342 | -6.35 | -6.2983 | -5.2983 | -7.2983
ext50 | -103.454 | 12301.44 | 0.09 | -103.4824 | 0 | -102.4824 | -104.4824 | 1 | -1 | 0.094387 | 0.02844 | 12301.44 | -0.44211 | -0.50793 | 0.06582 | 3.0658 | -2.9342 | -6.194 | -6.2224 | -5.2224 | -7.2224
ext51 | -102.381 | 12765.802 | 0.366 | -102.6645 | 0 | -101.6645 | -103.6645 | 1 | -1 | 0.46297 | 0.28352 | 12765.802 | 1.6759 | 1.6101 | 0.06582 | 3.0658 | -2.9342 | -5.121 | -5.4045 | -4.4045 | -6.4045
ext52 | -102.356 | 12794.238 | 0.332 | -102.6119 | 0 | -101.6119 | -103.6119 | 1 | -1 | 0.4192 | 0.25594 | 12794.238 | 1.1567 | 1.0909 | 0.06582 | 3.0658 | -2.9342 | -5.096 | -5.3519 | -4.3519 | -6.3519
ext53 | -101.255 | 13277.286 | 0.288 | -101.6749 | 0 | -100.6749 | -102.6749 | 1 | -1 | 0.50915 | 0.41987 | 13277.286 | 1.2132 | 1.1474 | 0.06582 | 3.0658 | -2.9342 | -3.995 | -4.4149 | -3.4149 | -5.4149
ext54 | -101.234 | 13284.133 | 0.233 | -101.661 | 0 | -100.661 | -102.661 | 1 | -1 | 0.48642 | 0.42699 | 13284.133 | 0.19535 | 0.12953 | 0.06582 | 3.0658 | -2.9342 | -3.974 | -4.401 | -3.401 | -5.401
ext55 | -100.078 | 13774.622 | 0.557 | -100.6234 | 0 | -99.6234 | -101.6234 | 1 | -1 | 0.77955 | 0.54538 | 13774.622 | 1.9792 | 1.9134 | 0.06582 | 3.0658 | -2.9342 | -2.818 | -3.3634 | -2.3634 | -4.3634
ext56 | -100.056 | 13789.836 | 0.627 | -100.5898 | 0 | -99.5898 | -101.5898 | 1 | -1 | 0.82347 | 0.53383 | 13789.836 | 1.5474 | 1.4816 | 0.06582 | 3.0658 | -2.9342 | -2.796 | -3.3298 | -2.3298 | -4.3298
ext57 | -98.703 | 14263.003 | 0.42 | -99.5052 | 0 | -98.5052 | -100.5052 | 1 | -1 | 0.90554 | 0.80225 | 14263.003 | 0.030845 | -0.034975 | 0.06582 | 3.0658 | -2.9342 | -1.443 | -2.2452 | -1.2452 | -3.2452
ext58 | -98.669 | 14300.787 | 0.492 | -99.4152 | 0 | -98.4152 | -100.4152 | 1 | -1 | 0.89381 | 0.74621 | 14300.787 | 1.2132 | 1.1474 | 0.06582 | 3.0658 | -2.9342 | -1.409 | -2.1552 | -1.1552 | -3.1552
ext59 | -97.376 | 14754.641 | 0.316 | -98.294 | 0 | -97.294 | -99.294 | 1 | -1 | 0.97086 | 0.91799 | 14754.641 | -0.14394 | -0.20976 | 0.06582 | 3.0658 | -2.9342 | -0.116 | -1.034 | -0.033993 | -2.034
ext60 | -97.365 | 14811.85 | 0.457 | -98.1481 | 0 | -97.1481 | -99.1481 | 1 | -1 | 0.9067 | 0.78311 | 14811.85 | 4.2515 | 4.1856 | 0.06582 | 3.0658 | -2.9342 | -0.105 | -0.88811 | 0.11189 | -1.8881
ext61 | -97.093 | 15228.883 | 0.023 | -97.0847 | 0 | -96.0847 | -98.0847 | 1 | -1 | 0.024461 | -0.0083264 | 15228.883 | -0.25704 | -0.32286 | 0.06582 | 3.0658 | -2.9342 | 0.167 | 0.17533 | 1.1753 | -0.82467
int1 | 97.281 | 20.791 | 0.248 | 97.2073 | 0 | 98.2073 | 96.2073 | 1 | -1 | 0.25872 | 0.073697 | [6 empty] | 0.021 | -0.052697 | 0.9473 | -1.0527
int2 | 97.495 | 190.453 | 0.504 | 96.7747 | 0 | 97.7747 | 95.7747 | 1 | -1 | 0.87915 | 0.72034 | [6 empty] | 0.235 | -0.48534 | 0.51466 | -1.4853
int3 | 97.011 | 499.643 | -0.131 | 95.9877 | 0 | 96.9877 | 94.9877 | 1 | -1 | 1.0316 | 1.0233 | [6 empty] | -0.249 | -1.2723 | -0.27228 | -2.2723
int4 | 96.624 | 679.136 | -0.027 | 95.5416 | 0 | 96.5416 | 94.5416 | 1 | -1 | 1.0828 | 1.0824 | [6 empty] | -0.636 | -1.7184 | -0.71844 | -2.7184
int5 | 95.728 | 1008.93 | 0.183 | 94.7517 | 0 | 95.7517 | 93.7517 | 1 | -1 | 0.99335 | 0.97635 | [6 empty] | -1.532 | -2.5083 | -1.5083 | -3.5083
int6 | 95.421 | 1165.923 | 0.226 | 94.3892 | 0 | 95.3892 | 93.3892 | 1 | -1 | 1.0562 | 1.0318 | [6 empty] | -1.839 | -2.8708 | -1.8708 | -3.8708
int7 | 94.336 | 1519.218 | 0.423 | 93.6057 | 0 | 94.6057 | 92.6057 | 1 | -1 | 0.844 | 0.73035 | [6 empty] | -2.924 | -3.6543 | -2.6543 | -4.6543
int8 | 94.121 | 1650.928 | 0.584 | 93.3249 | 0 | 94.3249 | 92.3249 | 1 | -1 | 0.98734 | 0.7961 | [6 empty] | -3.139 | -3.9351 | -2.9351 | -4.9351
int9 | 92.912 | 2030.298 | 0.485 | 92.5507 | 0 | 93.5507 | 91.5507 | 1 | -1 | 0.60479 | 0.36132 | [6 empty] | -4.348 | -4.7093 | -3.7093 | -5.7093
int10 | 92.684 | 2136.384 | 0.421 | 92.3433 | 0 | 93.3433 | 91.3433 | 1 | -1 | 0.54156 | 0.34066 | [6 empty] | -4.576 | -4.9167 | -3.9167 | -5.9167
int11 | 91.758 | 2540.31 | 0.502 | 91.5905 | 0 | 92.5905 | 90.5905 | 1 | -1 | 0.52921 | 0.1675 | [6 empty] | -5.502 | -5.6695 | -4.6695 | -6.6695
int12 | 91.711 | 2624.117 | 0.475 | 91.4416 | 0 | 92.4416 | 90.4416 | 1 | -1 | 0.54609 | 0.26943 | [6 empty] | -5.549 | -5.8184 | -4.8184 | -6.8184
int13 | 90.705 | 3053.003 | -0.057 | 90.7185 | 0 | 91.7185 | 89.7185 | 1 | -1 | 0.058576 | -0.013497 | [6 empty] | -6.555 | -6.5415 | -5.5415 | -7.5415
int14 | 90.604 | 3110.92 | -0.082 | 90.6259 | 0 | 91.6259 | 89.6259 | 1 | -1 | 0.084865 | -0.021865 | [6 empty] | -6.656 | -6.6341 | -5.6341 | -7.6341
int15 | 89.575 | 3562.667 | 0.157 | 89.9443 | 0 | 90.9443 | 88.9443 | 1 | -1 | 0.40127 | -0.36928 | [6 empty] | -7.685 | -7.3157 | -6.3157 | -8.3157
int16 | 89.614 | 3600.866 | 0.193 | 89.89 | 0 | 90.89 | 88.89 | 1 | -1 | 0.33676 | -0.27597 | [6 empty] | -7.646 | -7.37 | -6.37 | -8.37
int17 | 88.82 | 4073.901 | 0.013 | 89.2605 | 0 | 90.2605 | 88.2605 | 1 | -1 | 0.44066 | -0.44047 | [6 empty] | -8.44 | -7.9995 | -6.9995 | -8.9995
int18 | 88.91 | 4089.018 | 0.075 | 89.2417 | 0 | 90.2417 | 88.2417 | 1 | -1 | 0.34004 | -0.33166 | [6 empty] | -8.35 | -8.0183 | -7.0183 | -9.0183
int19 | 88.357 | 4571.439 | -0.085 | 88.6842 | 0 | 89.6842 | 87.6842 | 1 | -1 | 0.33807 | -0.32721 | [6 empty] | -8.903 | -8.5758 | -7.5758 | -9.5758
int20 | 88.251 | 4583.74 | -0.046 | 88.6711 | 0 | 89.6711 | 87.6711 | 1 | -1 | 0.42259 | -0.42007 | [6 empty] | -9.009 | -8.5889 | -7.5889 | -9.5889
int21 | 87.964 | 5056.393 | -0.255 | 88.2072 | 0 | 89.2072 | 87.2072 | 1 | -1 | 0.3524 | -0.24323 | [6 empty] | -9.296 | -9.0528 | -8.0528 | -10.0528
int22 | 87.837 | 5094.074 | -0.362 | 88.1737 | 0 | 89.1737 | 87.1737 | 1 | -1 | 0.49436 | -0.33667 | [6 empty] | -9.423 | -9.0863 | -8.0863 | -10.0863
int23 | 87.501 | 5541.487 | -0.352 | 87.8138 | 0 | 88.8138 | 86.8138 | 1 | -1 | 0.47089 | -0.31278 | [6 empty] | -9.759 | -9.4462 | -8.4462 | -10.4462
int24 | 87.387 | 5604.297 | -0.219 | 87.769 | 0 | 88.769 | 86.769 | 1 | -1 | 0.44028 | -0.38195 | [6 empty] | -9.873 | -9.491 | -8.491 | -10.491
int25 | 86.945 | 6026.445 | -0.172 | 87.5041 | 0 | 88.5041 | 86.5041 | 1 | -1 | 0.58493 | -0.55907 | [6 empty] | -10.315 | -9.7559 | -8.7559 | -10.7559
int26 | 86.725 | 6114.406 | -0.428 | 87.4569 | 0 | 88.4569 | 86.4569 | 1 | -1 | 0.84782 | -0.73186 | [6 empty] | -10.535 | -9.8031 | -8.8031 | -10.8031
int27 | 86.689 | 6511.073 | -0.291 | 87.2781 | 0 | 88.2781 | 86.2781 | 1 | -1 | 0.65707 | -0.58911 | [6 empty] | -10.571 | -9.9819 | -8.9819 | -10.9819
int28 | 86.586 | 6623.334 | -0.218 | 87.2377 | 0 | 88.2377 | 86.2377 | 1 | -1 | 0.68718 | -0.65169 | [6 empty] | -10.674 | -10.0223 | -9.0223 | -11.0223
int29 | 86.618 | 6997.016 | -0.162 | 87.1354 | 0 | 88.1354 | 86.1354 | 1 | -1 | 0.54217 | -0.5174 | [6 empty] | -10.642 | -10.1246 | -9.1246 | -11.1246
int30 | 86.544 | 7135.411 | -0.179 | 87.1101 | 0 | 88.1101 | 86.1101 | 1 | -1 | 0.59374 | -0.56611 | [6 empty] | -10.716 | -10.1499 | -9.1499 | -11.1499
int31 | 86.744 | 7486.132 | -0.284 | 87.0765 | 0 | 88.0765 | 86.0765 | 1 | -1 | 0.43731 | -0.33254 | [6 empty] | -10.516 | -10.1835 | -9.1835 | -11.1835
int32 | 86.614 | 7645.942 | -0.045 | 87.0757 | 0 | 88.0757 | 86.0757 | 1 | -1 | 0.46393 | -0.46174 | [6 empty] | -10.646 | -10.1843 | -9.1843 | -11.1843
int33 | 86.599 | 7962.658 | -0.173 | 87.101 | 0 | 88.101 | 86.101 | 1 | -1 | 0.53098 | -0.502 | [6 empty] | -10.661 | -10.159 | -9.159 | -11.159
int34 | 86.511 | 8156.024 | -0.17 | 87.134 | 0 | 88.134 | 86.134 | 1 | -1 | 0.64574 | -0.62296 | [6 empty] | -10.749 | -10.126 | -9.126 | -11.126
int35 | 86.664 | 8441.933 | -0.098 | 87.2071 | 0 | 88.2071 | 86.2071 | 1 | -1 | 0.55182 | -0.54305 | [6 empty] | -10.596 | -10.0529 | -9.0529 | -11.0529
int36 | 86.639 | 8666.34 | 0.068 | 87.2848 | 0 | 88.2848 | 86.2848 | 1 | -1 | 0.64935 | -0.64578 | [6 empty] | -10.621 | -9.9752 | -8.9752 | -10.9752
int37 | 86.845 | 8924.176 | -0.053 | 87.3962 | 0 | 88.3962 | 86.3962 | 1 | -1 | 0.55374 | -0.5512 | [6 empty] | -10.415 | -9.8638 | -8.8638 | -10.8638
int38 | 86.986 | 9179.867 | -0.342 | 87.53 | 0 | 88.53 | 86.53 | 1 | -1 | 0.6426 | -0.54403 | [6 empty] | -10.274 | -9.73 | -8.73 | -10.73
int39 | 87.294 | 9408.352 | -0.439 | 87.6693 | 0 | 88.6693 | 86.6693 | 1 | -1 | 0.57755 | -0.37529 | [6 empty] | -9.966 | -9.5907 | -8.5907 | -10.5907
int40 | 87.376 | 9685.719 | -0.219 | 87.8633 | 0 | 88.8633 | 86.8633 | 1 | -1 | 0.53423 | -0.48728 | [6 empty] | -9.884 | -9.3967 | -8.3967 | -10.3967
int41 | 87.594 | 9889.736 | -0.322 | 88.0234 | 0 | 89.0234 | 87.0234 | 1 | -1 | 0.53675 | -0.42944 | [6 empty] | -9.666 | -9.2366 | -8.2366 | -10.2366
int42 | 87.827 | 10196.016 | -0.316 | 88.2917 | 0 | 89.2917 | 87.2917 | 1 | -1 | 0.56193 | -0.46466 | [6 empty] | -9.433 | -8.9683 | -7.9683 | -9.9683
int43 | 88.175 | 10370.917 | -0.352 | 88.4598 | 0 | 89.4598 | 87.4598 | 1 | -1 | 0.45278 | -0.28479 | [6 empty] | -9.085 | -8.8002 | -7.8002 | -9.8002
int44 | 88.476 | 10706.884 | -0.313 | 88.8133 | 0 | 89.8133 | 87.8133 | 1 | -1 | 0.46012 | -0.33726 | [6 empty] | -8.784 | -8.4467 | -7.4467 | -9.4467
int45 | 88.734 | 10854.12 | -0.28 | 88.9808 | 0 | 89.9808 | 87.9808 | 1 | -1 | 0.37325 | -0.24682 | [6 empty] | -8.526 | -8.2792 | -7.2792 | -9.2792
int46 | 89.184 | 11216.658 | -0.238 | 89.4262 | 0 | 90.4262 | 88.4262 | 1 | -1 | 0.3396 | -0.24225 | [6 empty] | -8.076 | -7.8338 | -6.8338 | -8.8338
int47 | 89.475 | 11335.512 | -0.202 | 89.5824 | 0 | 90.5824 | 88.5824 | 1 | -1 | 0.2288 | -0.10745 | [6 empty] | -7.785 | -7.6776 | -6.6776 | -8.6776
int48 | 89.987 | 11726.304 | 0.108 | 90.1314 | 0 | 91.1314 | 89.1314 | 1 | -1 | 0.18036 | -0.14445 | [6 empty] | -7.273 | -7.1286 | -6.1286 | -8.1286
int49 | 90.206 | 11820.62 | 0.027 | 90.2721 | 0 | 91.2721 | 89.2721 | 1 | -1 | 0.071384 | -0.066081 | [6 empty] | -7.054 | -6.9879 | -5.9879 | -7.9879
int50 | 90.947 | 12236.237 | 0.176 | 90.9295 | 0 | 91.9295 | 89.9295 | 1 | -1 | 0.17687 | 0.017519 | [6 empty] | -6.313 | -6.3305 | -5.3305 | -7.3305
int51 | 91.116 | 12303.347 | 0.04 | 91.0414 | 0 | 92.0414 | 90.0414 | 1 | -1 | 0.084655 | 0.074609 | [6 empty] | -6.144 | -6.2186 | -5.2186 | -7.2186
int52 | 91.997 | 12744.268 | 0.107 | 91.8165 | 0 | 92.8165 | 90.8165 | 1 | -1 | 0.20985 | 0.18052 | [6 empty] | -5.263 | -5.4435 | -4.4435 | -6.4435
int53 | 92.15 | 12788.073 | 0.052 | 91.8973 | 0 | 92.8973 | 90.8973 | 1 | -1 | 0.25803 | 0.25274 | [6 empty] | -5.11 | -5.3627 | -4.3627 | -6.3627
int54 | 93.214 | 13252.901 | 0.195 | 92.7965 | 0 | 93.7965 | 91.7965 | 1 | -1 | 0.46082 | 0.41753 | [6 empty] | -4.046 | -4.4635 | -3.4635 | -5.4635
int55 | 93.364 | 13272.301 | 0.172 | 92.8357 | 0 | 93.8357 | 91.8357 | 1 | -1 | 0.55562 | 0.52833 | [6 empty] | -3.896 | -4.4243 | -3.4243 | -5.4243
int56 | 94.663 | 13757.95 | 0.326 | 93.8606 | 0 | 94.8606 | 92.8606 | 1 | -1 | 0.86612 | 0.80243 | [6 empty] | -2.597 | -3.3994 | -2.3994 | -4.3994
int57 | 94.587 | 13759.914 | 0.414 | 93.8649 | 0 | 94.8649 | 92.8649 | 1 | -1 | 0.83237 | 0.72211 | [6 empty] | -2.673 | -3.3951 | -2.3951 | -4.3951
int58 | 95.925 | 14238.556 | 0.256 | 94.9574 | 0 | 95.9574 | 93.9574 | 1 | -1 | 1.0009 | 0.96761 | [6 empty] | -1.335 | -2.3026 | -1.3026 | -3.3026
int59 | 95.944 | 14268.27 | 0.344 | 95.0279 | 0 | 96.0279 | 94.0279 | 1 | -1 | 0.97856 | 0.9161 | [6 empty] | -1.316 | -2.2321 | -1.2321 | -3.2321
int60 | 97.089 | 14718.235 | -0.37 | 96.134 | 0 | 97.134 | 95.134 | 1 | -1 | 1.0242 | 0.955 | [6 empty] | -0.171 | -1.126 | -0.126 | -2.126
int61 | 97.137 | 14777.325 | 0.073 | 96.2845 | 0 | 97.2845 | 95.2845 | 1 | -1 | 0.85564 | 0.85252 | [6 empty] | -0.123 | -0.97552 | 0.024478 | -1.9755
int62 | 97.289 | 15136.797 | 0.088 | 97.2011 | 0 | 98.2011 | 96.2011 | 1 | -1 | 0.12436 | 0.087866 | [6 empty] | 0.029 | -0.058866 | 0.94113 | -1.0589
BACK

## info_cm
Points measured:
the theoretical and measured values are expressed in a local coordinate system created
as follows:
Point1
Point2
Point3
Point4
outer sextupole magnet
inner sextupole magnet
Point1
Point2
outer decapole magnet
inner decapole magnet
BACK
sextupole: lyre side
theoretical coordinate system with origin on the end-plate, obtained after transformation and analysis of the mid-plane measurements and then translated over +Y to have its origin on the lyre side end-plate and then rotated around the z-axis over -2.5mrad
deca/octopole: connection side
theoretical coordinate system with origin on the end-plate, obtained after transformation and analysis of the mid-plane measurements and then rotated around the z-axis over +2.5mrad

## info_ec
D9,D10,D11: |  |  |  | Sign convention for angles:
on the end covers
Plane C = plane containing D9, D10 and D11 on the Connection Side
Plane L = plane containing D9, D10 and D11 on the Lyre Side
Theoretical Values and Coordinate systems
the theoretical and measured values are expressed in a local coordinate system created as follows:
connexion side
theoretical coordinate system, obtained after transformation and analysis of the mid-plane measurements
translated to have its origin at the intersection of the C-plane and the theoretical V1-V2-average line
and then rotated around the z-axis over +2.5mrad
lyre side
theoretical coordinate system with origin on the end-cover, obtained after transformation and analysis of the mid-plane measurements
translated to have its origin at the intersection of the L-plane and the theoretical V1-V2-average line
and then rotated around the z-axis over -2.5mrad
Tolerances:
Tolerances Connection Side (same for Lyre Side):
BACK
BACK

## info_cf
Theoretical values and Coordinate system:
Top view of cold mass and it's cold feet pads, showing the coordinate system used
The coordinate system is based on the theoretical system (obtained after transformation and analysis of the mid-plane measurements)
but has been translated to have its origin in the center of the central support cold feet pad.
Tolerances:
Nominal value and tolerances of distance between feet:
Nominal Value and tolerances of vertical position of feet:
Tolerance on parallelism between plane of feet pad and plane V1-V2:
| Length of cold feet pad=360mm. Tolerance of parrallelism becomes: |  | angle <= 0.5/360 mrad = 1.38 mrad for the central support pad
angle <=1/360 mrad = 2.76 mrad for the external ones
| Width of cold feet pad=300mm. Tolerance of parrallelism becomes: |  | angle <= 0.5/300 mrad = 1.67 mrad for the central support pad
angle <= 1/300 mrad = 3.34 mrad for the external ones
BACK

## info_tl
Tolerances:
Nominal Value and Tolerance of Total Length:
BACK

## info_sh
Theoretical values and Coordinate system:
The coordinate system used is the theoretical system, obtained after transformation and analysis of the mid-plane measurements
The (x=0) of the theoretical coordinate system lies on the (outside of) the end-plate of the connection side
Tolerances:
theoretic shape of the cold bore tubes and the tolerances imposed (all dimensions in mm)
BACK

## info_te
Theoretical values and Coordinate systems
the theoretical and measured values are expressed in a local coordinate system created as follows:
Connection side
theoretical coordinate system with origin on the end-cover, obtained after transformation and analysis of the mid-plane measurements
then translated to have its origin at the intersection of the C-plane and the theoretical V1-V2-average line
and rotated around the z-axis over +2.5mrad
Lyre side
theoretical coordinate system with origin on the end-cover, obtained after transformation and analysis of the mid-plane measurements
then translated to have its origin at the intersection of the L-plane and the theoretical V1-V2-average line
and rotated around the z-axis over -2.5mrad
Tolerances:
The total offset of each tube extremity must be <= 0.3 mm
(Total Offset = (Horizontal Offset)2 + (Vertical Offset)2 )
BACK
BACK