## 1.Cold Mass
Cold Mass
Identification |  |  |  |  | Properties |  |  | Step 1 (): Electrical check | [6 empty] | Step 1: Non-Conformities |  | Properties |  | Step 2 (): Warm magnetic measurements | [6 empty] | Step 2: Non-Conformities |  | Properties | [39 empty] | Step 3 (): Geometrical test | [6 empty] | Step 3: Non-Conformities |  | Properties | [19 empty] | Sub-Equipments |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Delivery date | Stacking factor (ferrom.) | Length (ferrom. part) | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Res.20°C | Induct. 10Hz | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | b2_straight_A1 | b3_straight_A1 | b4_straight_A1 | b5_straight_A1 | b7_straight_A1 | a1_straight_A1 | a2_straight_A1 | a3_straight_A1 | a4_straight_A1 | b2_straight_A2 | b3_straight_A2 | b4_straight_A2 | b5_straight_A2 | b7_straight_A2 | a1_straight_A2 | a2_straight_A2 | a3_straight_A2 | a4_straight_A2 | b2_integrated_A1 | b3_integrated_A1 | b4_integrated_A1 | b5_integrated_A1 | b7_integrated_A1 | a1_integrated_A1 | a2_integrated_A1 | a3_integrated_A1 | a4_integrated_A1 | transf_func_integ_A1 | mag_length_integ_A1 | b2_integrated_A2 | b3_integrated_A2 | b4_integrated_A2 | b5_integrated_A2 | b7_integrated_A2 | a1_integrated_A2 | a2_integrated_A2 | a3_integrated_A2 | a4_integrated_A2 | transf_func_integ_A2 | mag_length_integ_A2 | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Max_dx_v1 | Max_dz_v1 | Max_dx_v2 | Max_dz_v2 | Min_dx_v1 | Min_dz_v1 | Min_dx_v2 | Min_dz_v2 | RMS_dx_v1 | RMS_dx_v2 | RMS_dz_v1 | RMS_dz_v2 | dx_conn_side_v1 | dz_conn_side_v1 | dx_conn_side_v2 | dz_conn_side_v2 | dx_lyra_side_v1 | dz_lyra_side_v1 | dx_lyra_side_v2 | dz_lyra_side_v2 | Collared Coil | Magnet Assembly | Doc. Number | Type
[5 empty] | [] | [%] | [mm] | [9 empty] | [mOhm] | [mH] | [9 empty] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [9 empty] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | 1 | 2
(CERN ID) | [96 empty] | 1 | 1
M05M | HCMBB_A001 |  |  |  | P1802 | P1771 | P1770 | MTF000869 | [7 empty] | 2 | P1755 | P316 | MTF000870 | [7 empty] | 40 | P302 | P303 | P304 | P305 | P322 | P323 | P324 | P325 | P336 | P320 | P318 | P319 | P337 | P360 | P361 | P362 | P363 | P364 | P366 | P367 | P368 | P369 | P370 | P371 | P372 | P373 | P374 | P375 | P314 | P376 | P377 | P378 | P379 | P380 | P381 | P382 | P383 | P384 | P385 | P334 | MTF000871 | [7 empty] | 20 | P1772 | P1773 | P1774 | P1775 | P1821 | P1822 | P1823 | P1824 | P1776 | P1777 | P1778 | P1779 | P1762 | P1763 | P1764 | P1765 | P1766 | P1767 | P1768 | P1769 | HCMB__A001 | HCMCSMG001
| 3 | 3 | 2
HCMB__A001

## 2.Collared Coil
Collared Coil
Identification |  |  |  |  | Step 1 (): Delivery | [6 empty] | Step 1: Non-Conformities |  | Step 2 (cc-21): Perform collaring | [6 empty] | Step 2: Non-Conformities |  | Properties | Step 3 (ITP9): Perform electrical check | [6 empty] | Step 3: Non-Conformities |  | Properties |  | Step 4 (ITP10): Perform Mechanical measurement | [6 empty] | Step 4: Non-Conformities |  | Properties | [19 empty] | Step 5 (ITP11): Warm magnetic Measurement | [6 empty] | Step 5: Non-Conformities |  | Properties | [39 empty] | Step 6 (ITP11): Magnetic Length control | [6 empty] | Step 6: Non-Conformities |  | Properties |  | Sub-Equipments | [8 empty] | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Max. collaring pressure | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Res.20°C | Induct. 10Hz | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | A1up.i.l. shim side | A1up.i.l. shim central | A1up.o.l. shim side | A1up.o.l. shim central | A1low.i.l.shim side | A1low.i.l.shim central | A1.low.o.l.shim side | A1.low.o.l.shim central | A2up.i.l. shim side | A2up.i.l. shim central | A2up.o.l. shim side | A2up.o.l. shim central | A2low.i.l. shim side | A2low.i.l. shim central | A2low.o.l. shim side | A2low.o.l. shim central | Coll.size 2 straight sec | Coll.size 4 straight sec | Coll.size 6 straight sec | Coll.size 8 straight sec | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | b2_straight_A1 | b3_straight_A1 | b4_straight_A1 | b5_straight_A1 | b7_straight_A1 | a1_straight_A1 | a2_straight_A1 | a3_straight_A1 | a4_straight_A1 | coil_pos_straight_A1 | b2_straight_A2 | b3_straight_A2 | b4_straight_A2 | b5_straight_A2 | b7_straight_A2 | a1_straight_A2 | a2_straight_A2 | a3_straight_A2 | a4_straight_A2 | coil_pos_straight_A2 | b2_integrated_A1 | b3_integrated_A1 | b4_integrated_A1 | b5_integrated_A1 | b7_integrated_A1 | a1_integrated_A1 | a2_integrated_A1 | a3_integrated_A1 | a4_integrated_A1 | transf_func_integ_A1 | b2_integrated_A2 | b3_integrated_A2 | b4_integrated_A2 | b5_integrated_A2 | b7_integrated_A2 | a1_integrated_A2 | a2_integrated_A2 | a3_integrated_A2 | a4_integrated_A2 | transf_func_integ_A2 | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | mag_length_integ_A1 | mag_length_integ_A2 | Collars A Type 1 | Collars A Type 2 | Collars B Type 1 | Collars B Type 2 | Collars C Type 1 | Collars C Type 2 | Ground Insulation Sheet | Aperture | Aperture | Doc. Number | Type
[23 empty] | [MPa] | [9 empty] | [mOhm] | [mH] | [9 empty] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [mm] | [9 empty] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [µm] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [µm] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [9 empty] | [] | [] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 8
(CERN ID) | [123 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
M05G | HCMB__A001 |  |  |  | MTF000811 | [7 empty] | 0 | MTF000795 | [7 empty] | 1 | P1757 | MTF000796 | [7 empty] | 2 | P1755 | P316 | MTF000797 | [7 empty] | 20 | P1741 | P1742 | P1743 | P1744 | P1745 | P1746 | P1747 | P1748 | P1749 | P1750 | P1751 | P1752 | P1753 | P1754 | P1850 | P1851 | P1758 | P1759 | P1760 | P1761 | MTF000798 | [7 empty] | 40 | P302 | P303 | P304 | P305 | P322 | P323 | P324 | P325 | P336 | P300 | P320 | P318 | P319 | P337 | P360 | P361 | P362 | P363 | P364 | P365 | P366 | P367 | P368 | P369 | P370 | P371 | P372 | P373 | P374 | P375 | P376 | P377 | P378 | P379 | P380 | P381 | P382 | P383 | P384 | P385 | MTF000799 | [7 empty] | 2 | P314 | P334 | HCMB__A099 | HCMB__A100 | HCMB__A102 | HCMB__A103 | HCMB__A105 | HCMB__A106 | HCMB__A020 | HCMB__A009 | HCMB__A009
| 0 | 6 | 9
HCMB__A001-02000021 | 2021 | Ansaldo | Accepted |  | Done | ok | 1 | [6 empty] | Done | ok | 2 | 2002-12-10 | Ansaldo | Collaring_M021.xls | MA024914 |  |  | 700 | Done | ok | 3 | 2002-12-13 | Ansaldo | Collared_coilsM021.xls | MA025109 |  |  | 6082.06 | 87.1 | Done | ok | 4 | 2002-12-16 | Ansaldo | M021(Dimensionale).xls | MA025134 |  |  | 0.2 | 0.2 | 0.8 | 0.8 | 0.2 | 0.2 | 0.8 | 0.8 | 0.2 | 0.2 | 0.8 | 0.8 | 0.2 | 0.2 | 0.8 | 0.8 | 184.27 | 184.31 | 184.33 | 184.25 | Done | ok | 5 | 2002-12-20 | Cern | HCMB__A001-02000021_cc.xls |  | none |  | -0.073025 | -0.56408 | -0.026231 | -0.088931 | 0.99301 | -0.20507 | -0.27777 | -0.37401 | 0.20071 | 13.7554 | -0.14756 | -1.1028 | -0.025918 | -0.14221 | 0.97795 | -0.3501 | 0.1178 | -0.44232 | 0.14797 | 16.1232 | -0.1813 | -0.015175 | -0.074989 | -0.44369 | 0.99687 | -7.4159e-15 | 0.066186 | -0.3154 | 0.2619 | 0.5952 | -0.19611 | -0.29711 | -0.090903 | -0.44862 | 0.98274 | -5.1167e-13 | 0.44896 | -0.39224 | 0.21761 | 0.59516 | Done | ok | 5 | 2002-12-20 | Cern | HCMB__A001-02000021_cc.xls |  |  |  | 14448.59 | 14450.418 | HCMB__A099-MA020059 | HCMB__A100-MA020059 | HCMB__A102-MA020059 | HCMB__A103-MA020059 | HCMB__A105-MA020059 | HCMB__A106-MA020059 |  | HCMB__A009-02000041 | HCMB__A009-02000042

## 3.Collars A Type 1
Collars A Type 1
Identification |  |  |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Doc. Number | Type
(CERN ID)
M05R | HCMB__A099
| 0 | 0
HCMB__A099-MA020059 | MAL20059 | ERNESTO_MALVESTITI_SPA | Installed

## 4.Collars A Type 2
Identification |  |  |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Doc. Number | Type
(CERN ID)
M05R | HCMB__A100
| 0 | 0
HCMB__A100-MA020059 | MAL20059 | ERNESTO_MALVESTITI_SPA | Installed

## 5.Collars B Type 1
Collars B Type 1
Identification |  |  |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Doc. Number | Type
(CERN ID)
M05R | HCMB__A102
| 0 | 0
HCMB__A102-MA020059 | MAL20059 | ERNESTO_MALVESTITI_SPA | Installed

## 6.Collars B Type 2
Collars B Type 2
Identification |  |  |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Doc. Number | Type
(CERN ID)
M05R | HCMB__A103
| 0 | 0
HCMB__A103-MA020059 | MAL20059 | ERNESTO_MALVESTITI_SPA | Installed

## 7.Collars C Type 1
Collars C Type 1
Identification |  |  |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Doc. Number | Type
(CERN ID)
M05R | HCMB__A105
| 0 | 0
HCMB__A105-MA020059 | MAL20059 | ERNESTO_MALVESTITI_SPA | Installed

## 8.Collars C Type 2
Collars C Type 2
Identification |  |  |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Doc. Number | Type
(CERN ID)
M05R | HCMB__A106
| 0 | 0
HCMB__A106-MA020059 | MAL20059 | ERNESTO_MALVESTITI_SPA | Installed

## 9.Ground Insulation Sheet
Ground Insulation Sheet
Identification |  |  |  |  | Properties |  |  |  | Step 1 (): Delivery to Manufacturer | [6 empty] | Step 1: Non-Conformities |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Contract Number | Permeability | Thickness | Raw Material Certificate | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Doc. Number | Type
[5 empty] | [] | [] | [mm] | []
(CERN ID)
M05B | HCMB__A020 |  |  |  | P578 | P607 | P608 | P597 | MTF000808 | [7 empty] | 0
| 4 | 1

## 10.Aperture
Aperture
Identification |  |  |  |  | Properties | Sub-Equipments | [12 empty] | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Aperture number | Quench Heater | Quench Heater | Quench Heater | Quench Heater | Cold Bore Tube | Pole | Pole | Shims | Shims | Shims | Shims | Shim Retainers | Shim Retainers | Doc. Number | Type
[5 empty] | [] | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5
(CERN ID) | [5 empty] | 1 | 2 | 3 | 4 | 1 | 1 | 2 | 1 | 2 | 3 | 4 | 1 | 2
M05L | HCMB__A009 |  |  |  | P399 | HCMB__A025 | HCMB__A025 | HCMB__A025 | HCMB__A025 | HCVCC__001 | HCMB__A010 | HCMB__A010 | HCMB__A119 | HCMB__A119 | HCMB__A119 | HCMB__A119 | HCMB__A120 | HCMB__A120
| 1 | 0 | 13
HCMB__A009-02000041 |  | Ansaldo | Installed |  | 1 | HCMB__A025-10004867 | HCMB__A025-10004881 | HCMB__A025-10004899 | HCMB__A025-10004880 | HCVCC__001-DM010039 | HCMB__A010-02000082 | HCMB__A010-02000083
HCMB__A009-02000042 |  | Ansaldo | Installed |  | 2 | HCMB__A025-10004889 | HCMB__A025-10004604 | HCMB__A025-10004909 | HCMB__A025-10004922 | HCVCC__001-DM010075 | HCMB__A010-02000084 | HCMB__A010-02000085

## 11.Quench Heater
Quench Heater
Identification |  |  |  |  | Step 1 (): Manufacturer checks | [6 empty] | Step 1: Non-Conformities |  | Step 2 (): Delivery at CERN | [6 empty] | Step 2: Non-Conformities |  | Properties | Step 3 (): CERN checks | [6 empty] | Step 3: Non-Conformities |  | Properties | [11 empty] | Step 4 (): Returning to Manufacturer | [6 empty] | Step 4: Non-Conformities |  | Properties | Step 5 (): Sending to Magnet Integrator | [6 empty] | Step 5: Non-Conformities |  | Properties | Step 6 (): Magnet Integrator Checks | [6 empty] | Step 6: Non-Conformities |  | Step 7 (): Reception from Magnet Integrator | [6 empty] | Step 7: Non-Conformities |  | Properties | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Delivered at CERN on | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Checked at CERN on | Length | Temperature | Humidity | First strip end | First strip start | Second strip end | Second strip start | Strip O. Thick cont. | Strip O. Thick glue | Poly. O. Thick cont. | Poly. O. Thick glue | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Returned to Manuf. On | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Sent to Mag.Int. on | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Received from Mag.Int. on | Doc. Number | Type
[23 empty] | [] | [9 empty] | [] | [mm] | [°C] | [%] | [mm] | [mm] | [mm] | [mm] | [] | [] | [] | [] | [9 empty] | [] | [9 empty] | [] | [18 empty] | []
(CERN ID) | [33 empty] | 14557 | 25 | 50
M05Q | HCMB__A025 |  |  |  | MTF000775 | [7 empty] | 0 | MTF000778 | [7 empty] | 1 | P570 | MTF000776 | [7 empty] | 12 | P571 | P577 | 25 | 50 | P563 | P562 | P565 | P564 | P566 | P567 | P568 | P569 | MTF000780 | [7 empty] | 1 | P576 | MTF000779 | [7 empty] | 1 | P572 | MTF000777 | [7 empty] | 0 | MTF000781 | [7 empty] | 1 | P574
| 0 | 7 | [32 empty] | 25 | 50
HCMB__A025-10004604 | 10004604 | Axon | Installed |  | Done | ok | 1 | 2001-07-23 | Axon |  |  |  |  | Done | ok | 2 | [7 empty] | Done | ok | 3 | 2002-04-08 | F. Bourgeois |  |  |  |  | 2002-04-08 | 14557 | 23 | 34 | 5.84 | 5.76 | 29.99 | 29.85 |  |  |  |  | Cancelled | [9 empty] | Done | ok | 5 | 2002-04-09 | A. Sajous |  | EP1059869 |  |  | 2002-04-09 | Done | ok | 6 | 2002-04-18 | Ansaldo |  | MA0211632
HCMB__A025-10004867 | 10004867 | Axon | Installed |  | Done | ok | 1 | 2001-09-21 | Axon |  |  |  |  | Done | ok | 2 | [7 empty] | Done | ok | 3 | 2002-04-08 | F. Bourgeois |  |  |  |  | 2002-04-08 | 14557 | 23 | 35 | 5.78 | 5.74 | 29.79 | 29.77 |  |  |  |  | Cancelled | [9 empty] | Done | ok | 5 | 2002-04-09 | A. Sajous |  | EP1059869 |  |  | 2002-04-09 | Done | ok | 6 | 2002-04-18 | Ansaldo |  | MA0211632
HCMB__A025-10004899 | 10004899 | Axon | Installed |  | Done | ok | 1 | 2001-10-03 | Axon |  |  |  |  | Done | ok | 2 | [7 empty] | Done | ok | 3 | 2002-04-08 | F. Bourgeois |  |  |  |  | 2002-04-08 | 14557 | 20 | 34 | 5.91 | 5.89 | 30 | 30.01 |  |  |  |  | Cancelled | [9 empty] | Done | ok | 5 | 2002-04-09 | A. Sajous |  | EP1059869 |  |  | 2002-04-09 | Done | ok | 6 | 2002-04-18 | Ansaldo |  | MA0211632
HCMB__A025-10004880 | 10004880 | Axon | Installed |  | Done | ok | 1 | 2001-09-21 | Axon |  |  |  |  | Done | ok | 2 | [7 empty] | Done | ok | 3 | 2002-04-08 | F. Bourgeois |  |  |  |  | 2002-04-08 | 14557 | 22 | 34 | 5.76 | 5.75 | 29.73 | 29.76 |  |  |  |  | Cancelled | [9 empty] | Done | ok | 5 | 2002-04-09 | A. Sajous |  | EP1059869 |  |  | 2002-04-09 | Done | ok | 6 | 2002-04-18 | Ansaldo |  | MA0211632
HCMB__A025-10004881 | 10004881 | Axon | Installed |  | Done | ok | 1 | 2001-09-21 | Axon |  |  |  |  | Done | ok | 2 | [7 empty] | Done | ok | 3 | 2002-04-08 | F. Bourgeois |  |  |  |  | 2002-04-08 | 14557 | 22 | 34 | 5.71 | 5.75 | 29.79 | 29.75 |  |  |  |  | Cancelled | [9 empty] | Done | ok | 5 | 2002-04-09 | A. Sajous |  | EP1059869 |  |  | 2002-04-09 | Done | ok | 6 | 2002-04-18 | Ansaldo |  | MA0211632
HCMB__A025-10004889 | 10004889 | Axon | Installed |  | Done | ok | 1 | 2001-09-21 | Axon |  |  |  |  | Done | ok | 2 | [7 empty] | Done | ok | 3 | 2002-04-08 | F. Bourgeois |  |  |  |  | 2002-04-08 | 14557 | 22 | 35 | 5.91 | 5.9 | 29.94 | 29.97 |  |  |  |  | Cancelled | [9 empty] | Done | ok | 5 | 2002-04-09 | A. Sajous |  | EP1059869 |  |  | 2002-04-09 | Done | ok | 6 | 2002-04-18 | Ansaldo |  | MA0211632
HCMB__A025-10004909 | 10004909 | Axon | Installed |  | Done | ok | 1 | 04.19.01 | Axon |  |  |  |  | Done | ok | 2 | [7 empty] | Done | ok | 3 | 2002-04-08 | F. Bourgeois |  |  |  |  | 2002-04-08 | 14557 | 20 | 34 | 5.71 | 5.69 | 29.73 | 29.79 |  |  |  |  | Cancelled | [9 empty] | Done | ok | 5 | 2002-04-09 | A. Sajous |  | EP1059869 |  |  | 2002-04-09 | Done | ok | 6 | 2002-04-18 | Ansaldo |  | MA0211632
HCMB__A025-10004922 | 10004922 | Axon | Installed |  | Done | ok | 1 | 2001-10-02 | Axon |  |  |  |  | Done | ok | 2 | [7 empty] | Done | ok | 3 | 2002-04-08 | F. Bourgeois |  |  |  |  | 2002-04-08 | 14557 | 23 | 37 | 5.9 | 5.88 | 30.84 | 30.48 |  |  |  |  | Cancelled | [9 empty] | Done | ok | 5 | 2002-04-09 | A. Sajous |  | EP1059869 |  |  | 2002-04-09 | Done | ok | 6 | 2002-04-18 | Ansaldo |  | MA0211632

## 12.Cold Bore Tube
Cold Bore Tube
Identification |  |  |  |  | Properties | [7 empty] | Step 1 (): Cleaning | [6 empty] | Step 1: Non-Conformities |  | Properties | Step 2 (): Insulation | [6 empty] | Step 2: Non-Conformities |  | Properties | Step 3 (): Delivery to Manufacturer | [6 empty] | Step 3: Non-Conformities |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Contract Number | External diameter | Heat Number | Heat Treatment | Raw Material Certificate | Wall Thickness | Room Temp Pressure Test | Leak Test | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Cleaning Procedure | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Insulation Test | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Doc. Number | Type
[5 empty] | [] | [mm] | [] | [] | [] | [mm] | [] | [] | [9 empty] | [] | [9 empty] | [GOhm]
(CERN ID)
M059 | HCVCC__001 |  |  |  | P578 | P603 | P600 | P596 | P597 | P602 | P598 | P599 | MTF000805 | [7 empty] | 1 | P601 | Done | [7 empty] | 1 | P604 | MTF000804 | [7 empty] | 0
| 8 | 3 | [20 empty] | Done
HCVCC__001-DM010039 | MB-CBT0039 | DMV_Stainless_Italy | Accepted |  | F-302/LHC/LHC | ok | 180076 |  | 2001032663 | ok |  |  | Done | ok | 1 |  | Cern |  |  |  |  | Done | Done | ok | 2 | 2002-04-05 | Cern |  |  |  |  | ok | Done | ok | 3 | 2002-04-09 | Sajous |  | EP1059869
HCVCC__001-DM010075 | MB-CBT0075 | DMV_Stainless_Italy | Accepted |  | F-302/LHC/LHC | ok | 180076 |  | 2001032663 | ok |  |  | Done | ok | 1 |  | Cern |  |  |  |  | Done | Done | ok | 2 | 2002-04-05 | Cern |  |  |  |  | ok | Done | ok | 3 | 2002-04-09 | Sajous |  | EP1059869

## 13.Pole
Pole
Identification |  |  |  |  | Properties |  |  | Step 1 (ITP 6 - cc-13): Poles Assembly | [6 empty] | Step 1: Non-Conformities |  | Step 2 (ITP 7): Perform electrical tests | [6 empty] | Step 2: Non-Conformities |  | Properties | [7 empty] | Step 3 (ITP 8): Perform Mechanical measurements | [6 empty] | Step 3: Non-Conformities |  | Properties |  |  | Step 4 (cc-16): Insulate aperture to the Ground | [6 empty] | Step 4: Non-Conformities |  | Sub-Equipments |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Contract Number | Assembly Line number | Pole position | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | R[DC] | I for R[DC] | R[DC] of splice | I for R[DC] of splice | Inductance [10 KHz] | Inductance [100 Hz] | Inductance [1000 Hz] | Insulation Resistance | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | S 100 | Displacement at 40 MPa | Displacement at 80 MPa | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Inner Layer | Outer Layer | Doc. Number | Type
[5 empty] | [] | [] | [] | [18 empty] | [mOhm] | [A] | [µOhm] | [A] | [mH] | [mH] | [mH] | [MOhm] | [9 empty] | [mm] | [mm] | [mm] | [9 empty] | 1 | 2
(CERN ID) | [54 empty] | 1 | 1
M05F | HCMB__A010 |  |  |  | P578 | P606 | P398 | MTF000791 | [7 empty] | 0 | MTF000792 | [7 empty] | 8 | P625 | P350 | P626 | P351 | P621 | P622 | P623 | P624 | MTF000793 | [7 empty] | 3 | P631 | P629 | P630 | MTF000794 | [7 empty] | 0 | HCMB__A011 | HCMB__A012
| 3 | 4 | 2
HCMB__A010-02000082 | P082 | Ansaldo | Installed |  |  |  | A1_upper | Done | ok | 1 | 2002-10-30 | Ansaldo |  | MA024457 |  |  | Done | ok | 2 | 2002-11-16 | Ansaldo | P082.xls | MA024702 |  |  | 1554 | 1 | 65.76 | 30 | 13.62 | 13.51 | 12.77 | 59000 | Cancelled |  | 3 | [9 empty] | Done | ok | 4 |  | Ansaldo |  |  |  |  | HCMB__A011-02000085 | HCMB__A012-02000085
HCMB__A010-02000083 | P083 | Ansaldo | Installed |  |  |  | A1_lower | Done | ok | 1 | 2002-10-22 | Ansaldo |  | MA024339 |  |  | Done | ok | 2 | 2002-11-29 | Ansaldo | P083.xls | MA024876 |  |  | 1542.91 | 1 | 60.79 | 30 | 13.7 | 13.57 | 12.82 | 9250 | Cancelled |  | 3 | [9 empty] | Done | ok | 4 |  | Ansaldo |  |  |  |  | HCMB__A011-02000086 | HCMB__A012-02000086
HCMB__A010-02000084 | P084 | Ansaldo | Installed |  |  |  | A2_upper | Done | ok | 1 | 2002-11-04 | Ansaldo |  | MA024514 |  |  | Done | ok | 2 | 2002-11-25 | Ansaldo | P084.xls | MA024802 |  |  | 1537.24 | 1 | 67.9 | 30 | 13.69 | 13.58 | 12.84 | 21800 | Cancelled |  | 3 | [9 empty] | Done | ok | 4 |  | Ansaldo |  |  |  |  | HCMB__A011-02000087 | HCMB__A012-02000087
HCMB__A010-02000085 | P085 | Ansaldo | Installed |  |  |  | A2_lower | Done | ok | 1 | 2002-11-06 | Ansaldo |  | MA024532 |  |  | Done | ok | 2 | 2002-11-18 | Ansaldo | P085.xls | MA024704 |  |  | 1563.06 | 1 | 56.98 | 30 | 13.65 | 13.53 | 12.78 | 106000 | Cancelled |  | 3 | [9 empty] | Done | ok | 4 |  | Ansaldo |  |  |  |  | HCMB__A011-02000088 | HCMB__A012-02000088

## 14.Inner Layer
Inner Layer
Identification |  |  |  |  | Properties |  |  | Step 1 (): Delivery to manufacturer | [6 empty] | Step 1: Non-Conformities |  | Step 2 (cc-05 - cc-06): Wind layer | [6 empty] | Step 2: Non-Conformities |  | Step 3 (cc-07 - cc-08): Cure Layer | [6 empty] | Step 3: Non-Conformities |  | Step 4 (ITP3): Electrical Test after curing | [6 empty] | Step 4: Non-Conformities |  | Properties | [6 empty] | Step 5 (cc-11 - cc-12): Surfacing Heads of layer | [6 empty] | Step 5: Non-Conformities |  | Step 6 (ITP4 - ITP5): Perform Dimensional Meas. | [6 empty] | Step 6: Non-Conformities |  | Properties |  |  | Sub-Equipments | [5 empty] | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Contract Number | Date of Delivery | Winding Line | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Inductance [10 KHz] | Inductance [100 Hz] | Inductance [1000 Hz] | Insulation Test | R[DC] | Discharge with strain | Discharge without strain | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Displacement at 40 MPa | Displacement at 80 MPa | S 100 | Stabilizer End Cable | SC Isolated Type 1 | End Spacers Inner Layer | Cu Wedges Isolated T1 | Cu Wedges Isolated T2 | Cu Wedges Isolated T3 | Doc. Number | Type
[5 empty] | [] | [] | [] | [36 empty] | [mH] | [mH] | [mH] | [GOhm] | [mOhm] | [µs] | [µs] | [18 empty] | [mm] | [mm] | [mm] | 1 | 2 | 3 | 4 | 5 | 6
(CERN ID) | bar: 1 to 6
M05E | HCMB__A011 |  |  |  | P578 | P581 | P605 | MTF000810 | [7 empty] | 0 | MTF000786 | [7 empty] | 0 | MTF000787 | [7 empty] | 0 | MTF000788 | [7 empty] | 7 | P621 | P622 | P623 | P604 | P625 | P628 | Not Available | MTF000789 | [7 empty] | 0 | MTF000790 | [7 empty] | 3 | P629 | P630 | P631 | HCMB__A050 | HCMB__AI46 | HCMB__A059 | HCMB__A051 | HCMB__A053 | HCMB__A055
| 3 | 6 | 6 | [46 empty] | Not Available
HCMB__A011-02000085 | I085 | Ansaldo | Installed |  |  |  |  | Done | ok | 1 | [6 empty] | Done | ok | 2 | 2002-08-20 | Ansaldo |  | MA023507 |  |  | Done | ok | 3 | 2002-08-22 | Ansaldo |  | MA023511 |  |  | Done | ok | 4 | 2002-09-02 | Ansaldo | I085.xls | MA023609 |  |  | 1.87 | 1.86 | 1.81 | 75 | 491.658 | 393 | 390 | Done | ok | 5 | 2002-09-03 | Ansaldo |  | MA023610 |  |  | Done | ok | 6 | 2002-09-02 | Ansaldo | DI085.xls | MA023621 | [5 empty] | HCMB__A050-TR000002 | HCMB__AI46-1B10104F | HCMB__A059-TO000049 | HCMB__A051-SE000014 | HCMB__A053-SE000014 | HCMB__A055-SE000014
HCMB__A011-02000085 | [71 empty] | 3: HCMB__A059-TO000050
HCMB__A011-02000086 | I086 | Ansaldo | Installed |  |  |  |  | Done | ok | 1 | [6 empty] | Done | ok | 2 | 2002-08-22 | Ansaldo |  | MA023514 |  |  | Done | ok | 3 | 2002-08-26 | Ansaldo |  | MA023526 |  |  | Done | ok | 4 | 2002-10-14 | Ansaldo | I086.xls | MA024208 |  |  | 1.87 | 1.87 | 1.82 | 68 | 496.29 | 394 | 392 | Done | ok | 5 | 2002-10-14 | Ansaldo |  | MA024210 |  |  | Cancelled |  | 6 | [9 empty] | HCMB__A050-TR000002 | HCMB__AI46-1B10104E | HCMB__A059-TO000049 | HCMB__A051-SE000014 | HCMB__A053-SE000014 | HCMB__A055-SE000014
HCMB__A011-02000086 | [71 empty] | 3: HCMB__A059-TO000050
HCMB__A011-02000087 | I087 | Ansaldo | Installed |  |  |  |  | Done | ok | 1 | [6 empty] | Done | ok | 2 | 2002-08-26 | Ansaldo |  | MA023520 |  |  | Done | ok | 3 | 2002-08-28 | Ansaldo |  | MA023535 |  |  | Done | ok | 4 | 2002-10-29 | Ansaldo | I087.xls | MA024428 |  |  | 1.85 | 1.84 | 1.82 | 87 | 492.87 | 394 | 392 | Done | ok | 5 | 2002-10-29 | Ansaldo |  | MA024429 |  |  | Cancelled |  | 6 | [9 empty] | HCMB__A050-TR000002 | HCMB__AI46-1B10105A | HCMB__A059-TO000049 | HCMB__A051-SE000014 | HCMB__A053-SE000014 | HCMB__A055-SE000014
HCMB__A011-02000087 | [71 empty] | 3: HCMB__A059-TO000050
HCMB__A011-02000088 | I088 | Ansaldo | Installed |  |  |  |  | Done | ok | 1 | [6 empty] | Done | ok | 2 | 2002-08-29 | Ansaldo |  | MA023546 |  |  | Done | ok | 3 | 2002-08-30 | Ansaldo |  | MA023605 |  |  | Done | ok | 4 | 2002-10-30 | Ansaldo | I088.xls | MA024460 |  |  | 1.88 | 1.87 | 1.82 | 59 | 494.12 | 390 | 392 | Done | ok | 5 | 2002-10-30 | Ansaldo |  | MA024462 |  |  | Cancelled |  | 6 | [9 empty] | HCMB__A050-TR000002 | HCMB__AI46-1B10105B | HCMB__A059-TO000049 | HCMB__A051-SE000014 | HCMB__A053-SE000014 | HCMB__A055-SE000014
HCMB__A011-02000088 | [71 empty] | 3: HCMB__A059-TO000050

## 15.Outer Layer
Outer Layer
Identification |  |  |  |  | Properties |  |  | Step 1 (): Delivery to manufacturer | [6 empty] | Step 1: Non-Conformities |  | Step 2 (cc-05 - cc-06): Wind layer | [6 empty] | Step 2: Non-Conformities |  | Step 3 (cc-07 - cc-08): Cure Layer | [6 empty] | Step 3: Non-Conformities |  | Step 4 (ITP3): Electrical Test after curing | [6 empty] | Step 4: Non-Conformities |  | Properties | [6 empty] | Step 5 (cc-11 - cc-12): Surfacing Heads of layer | [6 empty] | Step 5: Non-Conformities |  | Step 6 (ITP4 - ITP5): Perform Dimensional Meas. | [6 empty] | Step 6: Non-Conformities |  | Properties |  |  | Sub-Equipments |  |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Contract Number | Date of Delivery | Winding Line | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Inductance [10 KHz] | Inductance [100 Hz] | Inductance [1000 Hz] | Insulation Test | R[DC] | Discharge with strain | Discharge without strain | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Displacement at 40 MPa | Displacement at 80 MPa | S 100 | Stabilizer End Cable | SC Isolated Type 2 | End Spacers Outer Layer | Cu Wedges Isolated T4 | Doc. Number | Type
[5 empty] | [] | [] | [] | [36 empty] | [mH] | [mH] | [mH] | [GOhm] | [mOhm] | [µs] | [µs] | [18 empty] | [mm] | [mm] | [mm] | 1 | 2 | 3 | 4
(CERN ID) | [71 empty] | 1 | 1 | 1 | 1
M05E | HCMB__A012 |  |  |  | P578 | P581 | P605 | MTF000812 | [7 empty] | 0 | MTF000813 | [7 empty] | 0 | MTF000814 | [7 empty] | 0 | MTF000815 | [7 empty] | 7 | P621 | P622 | P623 | P604 | P625 | P628 | P627 | MTF000816 | [7 empty] | 0 | MTF000817 | [7 empty] | 3 | P629 | P630 | P631 | HCMB__A050 | HCMB__AI47 | HCMB__A076 | HCMB__A057
| 3 | 6 | 4
HCMB__A012-02000085 | E085 | Ansaldo | Installed |  |  |  |  | Done | ok | 1 |  | Ansaldo |  |  |  |  | Done | ok | 2 | 2002-07-25 | Ansaldo |  | MA023046 |  |  | Done | ok | 3 | 2002-07-30 | Ansaldo |  | MA023112 |  |  | Done | ok | 4 | 2002-09-09 | Ansaldo | E085.xls | MA023701 |  |  | 6.63 | 6.6 | 6.53 | 69 | 1037.176 | 748 | 744 | Done | ok | 5 | 2002-09-09 | Ansaldo |  | MA023703 |  |  | Done | ok | 6 | 2002-09-09 | Ansaldo | DE085.xls | MA023715 | none |  |  |  |  | HCMB__A050-TR000002 | HCMB__AI47-2K04701C | HCMB__A080-TO000047 | HCMB__A057-SE000002
HCMB__A012-02000085 | [73 empty] | HCMB__A080-TO000048
HCMB__A012-02000085 | [73 empty] | HCMB__A080-TO000051
HCMB__A012-02000085 | [73 empty] | HCMB__A080-TO000052
HCMB__A012-02000086 | E086 | Ansaldo | Installed |  |  |  |  | Done | ok | 1 |  | Ansaldo |  |  |  |  | Done | ok | 2 | 2002-07-26 | Ansaldo |  | MA023060 |  |  | Done | ok | 3 | 2002-07-30 | Ansaldo |  | MA023120 |  |  | Done | ok | 4 | 2002-10-21 | Ansaldo | E086.xls | MA024314 |  |  | 6.69 | 6.65 | 6.59 | 79 | 1043.17 | 744 | 748 | Done | ok | 5 | 2002-10-21 | Ansaldo |  | MA024315 |  |  | Cancelled |  | 6 | [9 empty] | HCMB__A050-TR000002 | HCMB__AI47-2K04701B | HCMB__A080-TO000047 | HCMB__A057-SE000002
HCMB__A012-02000086 | [73 empty] | HCMB__A080-TO000048
HCMB__A012-02000086 | [73 empty] | HCMB__A080-TO000051
HCMB__A012-02000086 | [73 empty] | HCMB__A080-TO000052
HCMB__A012-02000087 | E087 | Ansaldo | Installed |  |  |  |  | Done | ok | 1 |  | Ansaldo |  |  |  |  | Done | ok | 2 | 2002-07-30 | Ansaldo |  | MA023110 |  |  | Done | ok | 3 | 2002-07-31 | Ansaldo |  | MA023136 |  |  | Done | ok | 4 | 2002-10-30 | Ansaldo | E087.xls | MA024447 |  |  | 6.79 | 6.72 | 6.64 | 76 | 1042.53 | 750 | 755 | Done | ok | 5 | 2002-10-30 | Ansaldo |  | MA024449 |  |  | Cancelled |  | 6 | [9 empty] | HCMB__A050-TR000002 | HCMB__AI47-2K04702A | HCMB__A080-TO000047 | HCMB__A057-SE000002
HCMB__A012-02000087 | [73 empty] | HCMB__A080-TO000048
HCMB__A012-02000087 | [73 empty] | HCMB__A080-TO000051
HCMB__A012-02000087 | [73 empty] | HCMB__A080-TO000052
HCMB__A012-02000088 | E088 | Ansaldo | Installed |  |  |  |  | Done | ok | 1 |  | Ansaldo |  |  |  |  | Done | ok | 2 | 2002-07-31 | Ansaldo |  | MA023126 |  |  | Done | ok | 3 | 2002-08-05 | Ansaldo |  | MA023202 |  |  | Done | ok | 4 | 2002-11-04 | Ansaldo | E088.xls | MA024506 |  |  | 6.63 | 6.6 | 6.53 | 59 | 1040.91 | 743 | 732 | Done | ok | 5 | 2002-11-04 | Ansaldo |  | MA024504 |  |  | Cancelled |  | 6 | [9 empty] | HCMB__A050-TR000002 | HCMB__AI47-2K04701A | HCMB__A080-TO000047 | HCMB__A057-SE000002
HCMB__A012-02000088 | [73 empty] | HCMB__A080-TO000048
HCMB__A012-02000088 | [73 empty] | HCMB__A080-TO000051
HCMB__A012-02000088 | [73 empty] | HCMB__A080-TO000052

## 16.Stabilizer End Cable
Stabilizer End Cable
Identification |  |  |  |  | Properties |  |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Contract Number | Date of Delivery | Destination Firm | Drawing number | Doc. Number | Type
[5 empty] | [] | [] | [] | []
(CERN ID)
M057 | HCMB__A050 |  |  |  | P578 | P581 | P580 | P579
| 4 | 0
HCMB__A050-TR000002 | Trefimetaux 0_2 | Trefimetaux | Installed |  | CA/1168503(1) | 2000-05-03 | Ansaldo | LHCMB_A0049/50

## 17.SC Isolated Type 1
SC Isolated Type 1
Identification |  |  |  |  | Properties |  | Step 1 (cc-01b): Insulate SC Inner Layer | [6 empty] | Step 1: Non-Conformities |  | Step 2 (ITP2): Electrical Test during Cable Insulation | [6 empty] | Step 2: Non-Conformities |  | Step 3 (): Delivery to Manufacturer | [6 empty] | Step 3: Non-Conformities |  | Sub-Equipments |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Cable Visual Inspection | Contract Number | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Polymide Tape P1 | Cable Supra Type 1 | Polymide Tape A1 | Doc. Number | Type
[5 empty] | [] | [] | [27 empty] | 1 | 2 | 3
(CERN ID) | [33 empty] | 1 | 1 | 1
M05C | HCMB__AI46 |  |  |  | P594 | P578 | MTF000782 | [7 empty] | 0 | MTF000785 | [7 empty] | 0 | MTF000809 | [7 empty] | 0 | HCMB__A109 | HCMB__A046 | HCMB__A110
| 2 | 3 | 3
HCMB__AI46-1B10104F | 01B10104F | Selva | Installed |  | ok |  | Done | ok | 1 | 2002-07-03 | Selva |  | 655/02 |  |  | Done | ok | 2 | 2002-07-03 | Selva |  | 655/02 |  |  | Done | ok | 3 | [6 empty] | 20080474 | HCMB__A046-1B10104F | 32810038
HCMB__AI46-1B10104F | [33 empty] | 20080472 |  | 32810036
HCMB__AI46-1B10104F | [35 empty] | 3281003Y
HCMB__AI46-1B10104E | 01B10104E | Selva | Installed |  | ok |  | Done | ok | 1 | 2002-07-03 | Selva |  | 655/02 |  |  | Done | ok | 2 | 2002-07-03 | Selva |  | 655/02 |  |  | Done | ok | 3 | [6 empty] | 20080474 | HCMB__A046-1B10104E | 32810038
HCMB__AI46-1B10104E | [33 empty] | 20080472 |  | 32810036
HCMB__AI46-1B10104E | [35 empty] | 3281003Y
HCMB__AI46-1B10105A | 01B10105A | Selva | Installed |  | ok |  | Done | ok | 1 | 2002-07-03 | Selva |  | 655/02 |  |  | Done | ok | 2 | 2002-07-03 | Selva |  | 655/02 |  |  | Done | ok | 3 | [6 empty] | 20080474 | HCMB__A046-1B10105A | 32810038
HCMB__AI46-1B10105A | [33 empty] | 20080472 |  | 32810036
HCMB__AI46-1B10105A | [35 empty] | 3281003Y
HCMB__AI46-1B10105B | 01B10105B | Selva | Installed |  | ok |  | Done | ok | 1 | 2002-07-03 | Selva |  | 655/02 |  |  | Done | ok | 2 | 2002-07-03 | Selva |  | 655/02 |  |  | Done | ok | 3 | [6 empty] | 20080474 | HCMB__A046-1B10105B | 32810038
HCMB__AI46-1B10105B | [33 empty] | 20080472 |  | 32810036
HCMB__AI46-1B10105B | [35 empty] | 3281003Y

## 18.SC Isolated Type 2
SC Isolated Type 2
Identification |  |  |  |  | Properties |  | Step 1 (cc-01b): Insulate SC Inner Layer | [6 empty] | Step 1: Non-Conformities |  | Step 2 (ITP2): Electrical Test during Cable Insulation | [6 empty] | Step 2: Non-Conformities |  | Step 3 (): Delivery to Manufacturer | [6 empty] | Step 3: Non-Conformities |  | Sub-Equipments |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Cable Visual Inspection | Contract Number | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Polymide Tape P1 | Cable Supra Type 2 | Polymide Tape A1 | Doc. Number | Type
[5 empty] | [] | [] | [27 empty] | 1 | 2 | 3
(CERN ID) | [33 empty] | 1 | 1 | 1
M05C | HCMB__AI47 |  |  |  | P594 | P578 | MTF000827 | [7 empty] | 0 | MTF000828 | [7 empty] | 0 | MTF000829 | [7 empty] | 0 | HCMB__A109 | HCMB__A047 | HCMB__A110
| 2 | 3 | 3
HCMB__AI47-2K04701C | 02K04701C | Selva | Installed |  | ok |  | Done | ok | 1 | 2002-07-06 | Selva |  | 660/02 |  |  | Done | ok | 2 | 2002-07-06 | Selva |  | 660/02 |  |  | Done | ok | 3 | [6 empty] | 20080472 | HCMB__A047-2K04701C | 33110053
HCMB__AI47-2K04701B | 02K04701B | Selva | Installed |  | ok |  | Done | ok | 1 | 2002-07-06 | Selva |  | 660/02 |  |  | Done | ok | 2 | 2002-07-06 | Selva |  | 660/02 |  |  | Done | ok | 3 | [6 empty] | 20080474 | HCMB__A047-2K04701B | 33110053
HCMB__AI47-2K04701B | [35 empty] | 3281003Y
HCMB__AI47-2K04702A | 02K04702A | Selva | Installed |  | ok |  | Done | ok | 1 | 2002-07-06 | Selva |  | 660/02 |  |  | Done | ok | 2 | 2002-07-06 | Selva |  | 660/02 |  |  | Done | ok | 3 | [6 empty] | 20080472 | HCMB__A047-2K04702A | 33110053
HCMB__AI47-2K04702A | [33 empty] | 20080474
HCMB__AI47-2K04701A | 02K04701A | Selva | Installed |  | ok |  | Done | ok | 1 | 2002-07-06 | Selva |  | 660/02 |  |  | Done | ok | 2 | 2002-07-06 | Selva |  | 660/02 |  |  | Done | ok | 3 | [6 empty] | 20080474 | HCMB__A047-2K04701A | 3281003Y

## 19.Polymide Tape P1
Polymide Tape P1
Identification | [5 empty] | Properties |  |  |  | Step 1 (): Delivery of Tape to firm | [6 empty] | Step 1: Non-Conformities |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Quantity | Comment | Contract Number | Date of Delivery | Destination Firm | Drawing number | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Doc. Number | Type
[6 empty] | [] | [] | [] | []
(CERN ID)
M052 | HCMB__A109 |  |  | MTFBATOT |  | P578 | P581 | P580 | P579 | MTF000826 | [7 empty] | 0
| 5 | 1
HCMB__A109-20080472 | 20080474 | Kaneka | Installed |  |  |  |  | Selva |  | Done | ok | 1
HCMB__A109-20080475 | 20080472 | Kaneka | Installed |  |  |  |  | Selva |  | Done | ok | 1
HCMB__A109-20041471 | 20041471 | Kaneka | Installed |  |  |  |  | Selva |  | Done | ok | 1
HCMB__A109-20041475 | 20041475 | Kaneka | Installed |  |  |  |  | Selva |  | Done | ok | 1

## 20.Polymide Tape A1
Polymide Tape A1
Identification | [5 empty] | Properties |  |  |  | Step 1 (): Delivery of Tape to firm | [6 empty] | Step 1: Non-Conformities |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Quantity | Comment | Contract Number | Date of Delivery | Destination Firm | Drawing number | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Doc. Number | Type
[6 empty] | [] | [] | [] | []
(CERN ID)
M052 | HCMB__A110 |  |  | MTFBATOT |  | P578 | P581 | P580 | P579 | MTF000801 | [7 empty] | 0
| 5 | 1
HCMB__A110-32810038 | 32810038 | Kaneka | Installed |  |  |  |  | Selva |  | Done | ok | 1
HCMB__A110-32810036 | 32810036 | Kaneka | Installed |  |  |  |  | Selva |  | Done | ok | 1
HCMB__A110-3281003Y | 3281003Y | Kaneka | Installed |  |  |  |  | Selva |  | Done | ok | 1
HCMB__A110-33110056 | 33110056 | Kaneka | Installed |  |  |  |  | Selva |  | Done | ok | 1
HCMB__A110-33110053 | 33110053 | Kaneka | Installed |  |  |  |  | Selva |  | Done | ok | 1

## 21.Cable Supra Type 1
Cable Supra Type 1
Identification |  |  |  |  | Properties | [13 empty] | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Average Keystone | Average Mid-Thickness | Average Width | Cable Bend Test | Cable Ic at 4.2 K | Field for Ic | Cable Length | Cable Visual Inspection | Heat Treatment | Heat Treatment temp. | Stack Mid-Thickness | Transposition Direction | Transposition Pitch | Comment on cable quality | Doc. Number | Type
[5 empty] | [] | [mm] | [mm] | [] | [A] | [T] | [m] | [] | [] | [°C] | [] | [] | [] | []
(CERN ID)
M050 | HCMB__A046 |  |  |  | P589 | P588 | P587 | P593 | P595 | P633 | P586 | P594 | P596 | P632 | P590 | P591 | P592 | P559
| 14 | 0
HCMB__A046-1B10104F | 01B10104F | Alstom | Installed |  | 1.253 | 1.8995 | 15.0901 | ok | 539 |  | 531 | ok | 2h31mn | 200 | 1.9 | left | 117
HCMB__A046-1B10104E | 01B10104E | Alstom | Installed |  | 1.256 | 1.9001 | 15.0889 | ok | 539 |  | 463 | ok | 2h31mn | 200 | 1.9 | left | 117
HCMB__A046-1B10105A | 01B10105A | Alstom | Installed |  | 1.255 | 1.8995 | 15.0885 | ok | 522 |  | 465 | ok | 2h31mn | 200 | 1.8996 | left | 117
HCMB__A046-1B10105B | 01B10105B | Alstom | Installed |  | 1.257 | 1.8996 | 15.0902 | ok | 522 |  | 463 | ok | 2h31mn | 200 | 1.8996 | left | 117

## 22.Cable Supra Type 2
Cable Supra Type 2
Identification |  |  |  |  | Properties | [13 empty] | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Average Keystone | Average Mid-Thickness | Average Width | Cable Bend Test | Cable Ic at 4.2 K | Field for Ic | Cable Length | Cable Visual Inspection | Heat Treatment | Heat Treatment temp. | Stack Mid-Thickness | Transposition Direction | Transposition Pitch | Comment on cable quality | Doc. Number | Type
[5 empty] | [] | [mm] | [mm] | [] | [A] | [T] | [m] | [] | [] | [°C] | [] | [] | [] | []
(CERN ID)
M050 | HCMB__A047 |  |  |  | P589 | P588 | P587 | P593 | P595 | P633 | P586 | P594 | P596 | P632 | P590 | P591 | P592 | P559
| 14 | 0
HCMB__A047-2K04701C | 02K04701C | Furukawa | Installed |  | 0.88 | 1.4791 | 15.0911 | ok | 402.4 |  | 754 | ok | 5h | 200 | 1.4791 | left | 101.1
HCMB__A047-2K04701B | 02K04701B | Furukawa | Installed |  | 0.881 | 1.4789 | 15.09 | ok | 402.4 |  | 754 | ok | 5h | 200 | 1.4791 | left | 101.1
HCMB__A047-2K04702A | 02K04702A | Furukawa | Installed |  | 0.88 | 1.4791 | 15.0919 | ok | 395.5 |  | 755 | ok | 5h | 200 | 1.4791 | left | 100.9
HCMB__A047-2K04701A | 02K04701A | Furukawa | Installed |  | 0.881 | 1.4795 | 15.0902 | ok | 402.4 |  | 754 | ok | 5h | 200 | 1.4791 | left | 101.1

## 23.End Spacers Inner Layer
End Spacers Inner Layer
Identification | [5 empty] | Properties | Step 1 (): Delivery of end spacers | [6 empty] | Step 1: Non-Conformities |  | Sub-Equipments | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Chips and Wedges tips | Doc. Number | Type
[6 empty] | [] | [9 empty] | 1
(CERN ID) | [15 empty] | 1
M054 | HCMB__A059 |  |  | MTFBATOT |  | P578 | MTF000802 | [7 empty] | 0 | HCMB__A069
| 1 | 1 | 1
HCMB__A059-TO000049 | Tosti_Batch49 | Tosti | Installed |  |  |  | Done | ok | 1
HCMB__A059-TO000050 | Tosti_Batch50 | Tosti | Installed |  |  |  | Done | ok | 1

## 24.End Spacers Outer Layer
End Spacers Outer Layer
Identification | [5 empty] | Properties | [7 empty] | Step 1: Non-Conformities |  | Sub-Equipments | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Chips and Wedges tips | Doc. Number | Type
[6 empty] | [] | [9 empty] | 1
(CERN ID) | [15 empty] | 1
M054 | HCMB__A076 |  |  | MTFBATOT |  | P578 | MTF000825 | [7 empty] | 0 | HCMB__A069
| 1 | 1 | 1
HCMB__A080-TO000047 | TOSTI_Batch47 | Tosti | Installed |  |  |  | Done | ok | 1
HCMB__A080-TO000048 | TOSTI_Batch48 | Tosti | Installed |  |  |  | Done | ok | 1
HCMB__A080-TO000051 | TOSTI_Batch51 | Tosti | Installed |  |  |  | Done | ok | 1
HCMB__A080-TO000052 | TOSTI_Batch52 | Tosti | Installed |  |  |  | Done | ok | 1

## 25.Chips and Wedges tips
Identification | [5 empty] | Properties | Step 1 (): Delivery of chips and wedge tips | [6 empty] | Step 1: Non-Conformities |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Doc. Number | Type
[]
(CERN ID)
M055 | HCMB__A069 |  |  | MTFBATOT |  | P578 | MTF000803 | [7 empty] | 0
| 1 | 1

## 26.Cu Wedges Isolated T1
Cu Wedges Isolated T1
Identification | [5 empty] | Properties |  |  |  | Step 1 (cc-02b): Copper wedge Insulation | [6 empty] | Step 1: Non-Conformities |  | Sub-Equipments |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Comment on Delivery | Date of Delivery | Insulation Test | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Polymide Tape P1 | Copper Wedges Type 1 | Polymide Tape A1 | Doc. Number | Type
[6 empty] | [] | [] | [] | [GOhm] | [9 empty] | 1 | 2 | 3
(CERN ID) | [18 empty] | 1 | 1 | 1
M05D | HCMB__A051 |  |  | MTFBATOT |  | P578 | P585 | P581 | P604 | MTF000783 | [7 empty] | 0 | HCMB__A109 | HCMB__A052 | HCMB__A110
| 4 | 1 | 3
HCMB__A051-SE000014 | Outokumpu Batch 14 | Selva | Installed | 321 | [5 empty] | Done | ok | 1 | 21.12.01 | Selva |  | 1331/01 |  |  | 20041471 | HCMB__A052-OU000014 | 033110056
20041475

## 27.Cu Wedges Isolated T2
Cu Wedges Isolated T2
Identification | [5 empty] | Properties |  |  |  | Step 1 (cc-02b): Copper wedge Insulation | [6 empty] | Step 1: Non-Conformities |  | Sub-Equipments |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Comment on Delivery | Date of Delivery | Insulation Test | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Polymide Tape P1 | Copper Wedges Type 2 | Polymide Tape A1 | Doc. Number | Type
[6 empty] | [] | [] | [] | [GOhm] | [9 empty] | 1 | 2 | 3
(CERN ID) | [18 empty] | 1 | 1 | 1
M05D | HCMB__A053 |  |  | MTFBATOT |  | P578 | P585 | P581 | P604 | MTF000819 | [7 empty] | 0 | HCMB__A109 | HCMB__A054 | HCMB__A110
| 4 | 1 | 3
HCMB__A053-SE000014 | Outokumpu Batch 14 | Selva | Installed | 321 | [5 empty] | Done | ok | 1 | 21.12.01 | Selva |  | 1331/01 |  |  | 20041471 | HCMB__A054-OU000014 | 033110056
20041475

## 28.Cu Wedges Isolated T3
Cu Wedges Isolated T3
Identification | [5 empty] | Properties |  |  |  | Step 1 (cc-02b): Copper wedge Insulation | [6 empty] | Step 1: Non-Conformities |  | Sub-Equipments |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Comment on Delivery | Date of Delivery | Insulation Test | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Polymide Tape P1 | Copper Wedges Type 3 | Polymide Tape A1 | Doc. Number | Type
[6 empty] | [] | [] | [] | [GOhm] | [9 empty] | 1 | 2 | 3
(CERN ID) | [18 empty] | 1 | 1 | 1
M05D | HCMB__A055 |  |  | MTFBATOT |  | P578 | P585 | P581 | P604 | MTF000821 | [7 empty] | 0 | HCMB__A109 | HCMB__A056 | HCMB__A110
| 4 | 1 | 3
HCMB__A055-SE000014 | Outokumpu Batch 14 | Selva | Installed | 321 | [5 empty] | Done | ok | 1 | 21.12.01 | Selva |  | 1331/01 |  |  | 20041471 | HCMB__A056-OU000014 | 033110056
20041475

## 29.Cu Wedges Isolated T4
Cu Wedges Isolated T4
Identification | [5 empty] | Properties |  |  |  | Step 1 (cc-02b): Copper wedge Insulation | [6 empty] | Step 1: Non-Conformities |  | Sub-Equipments |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Comment on Delivery | Date of Delivery | Insulation Test | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Polymide Tape P1 | Copper Wedges Type 4 | Polymide Tape A1 | Doc. Number | Type
[6 empty] | [] | [] | [] | [GOhm] | [9 empty] | 1 | 2 | 3
(CERN ID) | [18 empty] | 1 | 1 | 1
M05D | HCMB__A057 |  |  | MTFBATOT |  | P578 | P585 | P581 | P604 | MTF000823 | [7 empty] | 0 | HCMB__A109 | HCMB__A058 | HCMB__A110
| 4 | 1 | 3
HCMB__A057-SE000002 | Outokumpu_Batch2 | Selva | Installed | 321 | [5 empty] | Done | ok | 1 | 2002-01-31 | Selva |  | 93/02 |  |  | 20041471 | HCMB__A058-OU000002

## 30.Copper Wedges Type 1
Copper Wedges Type 1
Identification | [5 empty] | Properties | [16 empty] | Step 1 (cc-04 a): Clean-up Cu Wedges | [6 empty] | Step 1: Non-Conformities |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Angle [A] (Beg) | BCH (Beg) | BCV (Beg) | Length [AB] (Beg) | Length [AC] (Beg) | Angle A (Mid) | BCH (Mid) | BCV (Mid) | Length [AB] (Mid) | Length [BC] (Mid) | Angle A (End) | BCH (End) | BCV (End) | Length [AB] (End) | Length [BC] (End) | Raw Material Certificate | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Doc. Number | Type
[6 empty] | [] | [°] | [mm] | [mm] | [mm] | [mm] | [°] | [mm] | [mm] | [mm] | [mm] | [°] | [mm] | [mm] | [mm] | [mm] | []
(CERN ID)
M051 | HCMB__A052 |  |  | MTFBATOT |  | P578 | P582 | P609 | P610 | P583 | P584 | P613 | P612 | P611 | P615 | P614 | P618 | P617 | P616 | P620 | P619 | P597 | MTF000800 | [7 empty] | 0
| 17 | 1
HCMB__A052-OU000014 | Outokumpo_Batch14 | Outokumpu | Installed | 321 | [18 empty] | Done | ok | 1

## 31.Copper Wedges Type 2
Copper Wedges Type 2
Identification | [5 empty] | Properties | [16 empty] | Step 1 (cc-04 a): Clean-up Cu Wedges | [6 empty] | Step 1: Non-Conformities |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Angle [A] (Beg) | BCH (Beg) | BCV (Beg) | Length [AB] (Beg) | Length [AC] (Beg) | Angle A (Mid) | BCH (Mid) | BCV (Mid) | Length [AB] (Mid) | Length [BC] (Mid) | Angle A (End) | BCH (End) | BCV (End) | Length [AB] (End) | Length [BC] (End) | Raw Material Certificate | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Doc. Number | Type
[6 empty] | [] | [°] | [mm] | [mm] | [mm] | [mm] | [°] | [mm] | [mm] | [mm] | [mm] | [°] | [mm] | [mm] | [mm] | [mm] | []
(CERN ID)
M051 | HCMB__A054 |  |  | MTFBATOT |  | P578 | P582 | P609 | P610 | P583 | P584 | P613 | P612 | P611 | P615 | P614 | P618 | P617 | P616 | P620 | P619 | P597 | MTF000820 | [7 empty] | 0
| 17 | 1
HCMB__A054-OU000014 | Outokumpo_Batch14 | Outokumpu | Installed | 321 | [18 empty] | Done | ok | 1

## 32.Copper Wedges Type 3
Copper Wedges Type 3
Identification | [5 empty] | Properties | [16 empty] | Step 1 (cc-04 a): Clean-up Cu Wedges | [6 empty] | Step 1: Non-Conformities |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Angle [A] (Beg) | BCH (Beg) | BCV (Beg) | Length [AB] (Beg) | Length [AC] (Beg) | Angle A (Mid) | BCH (Mid) | BCV (Mid) | Length [AB] (Mid) | Length [BC] (Mid) | Angle A (End) | BCH (End) | BCV (End) | Length [AB] (End) | Length [BC] (End) | Raw Material Certificate | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Doc. Number | Type
[6 empty] | [] | [°] | [mm] | [mm] | [mm] | [mm] | [°] | [mm] | [mm] | [mm] | [mm] | [°] | [mm] | [mm] | [mm] | [mm] | []
(CERN ID)
M051 | HCMB__A056 |  |  | MTFBATOT |  | P578 | P582 | P609 | P610 | P583 | P584 | P613 | P612 | P611 | P615 | P614 | P618 | P617 | P616 | P620 | P619 | P597 | MTF000822 | [7 empty] | 0
| 17 | 1
HCMB__A056-OU000014 | Outokumpo_Batch14 | Outokumpu | Installed | 321 | [18 empty] | Done | ok | 1

## 33.Copper Wedges Type 4
Copper Wedges Type 4
Identification | [5 empty] | Properties | [16 empty] | Step 1 (cc-04 a): Clean-up Cu Wedges | [6 empty] | Step 1: Non-Conformities |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Contract Number | Angle [A] (Beg) | BCH (Beg) | BCV (Beg) | Length [AB] (Beg) | Length [AC] (Beg) | Angle A (Mid) | BCH (Mid) | BCV (Mid) | Length [AB] (Mid) | Length [BC] (Mid) | Angle A (End) | BCH (End) | BCV (End) | Length [AB] (End) | Length [BC] (End) | Raw Material Certificate | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Doc. Number | Type
[6 empty] | [] | [°] | [mm] | [mm] | [mm] | [mm] | [°] | [mm] | [mm] | [mm] | [mm] | [°] | [mm] | [mm] | [mm] | [mm] | []
(CERN ID)
M051 | HCMB__A058 |  |  | MTFBATOT |  | P578 | P582 | P609 | P610 | P583 | P584 | P613 | P612 | P611 | P615 | P614 | P618 | P617 | P616 | P620 | P619 | P597 | MTF000824 | [7 empty] | 0
| 17 | 1
HCMB__A058-OU000002 | Outokumpu_Batch2 | Outokumpu | Installed | 321 | [18 empty] | Done | ok | 1

## 34.Shims
Shims
Identification | [5 empty] | Properties |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Thickness | Permeability | Doc. Number | Type
[6 empty] | [mm] | []
(CERN ID)
M05J | HCMB__A119 |  |  | MTFBATOT |  | P608 | P607
| 2 | 0

## 35.Shim Retainers
Shim Retainers
Identification | [5 empty] | Properties |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Units in batch | Comment | Thickness | Permeability | Doc. Number | Type
[6 empty] | [mm] | []
(CERN ID)
M05K | HCMB__A120 |  |  | MTFBATOT |  | P608 | P607
| 2 | 0

## 36.Magnet Assembly
Magnet Assembly
Identification |  |  |  |  | Properties | [119 empty] | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Manufacturer drawing ID | CDD drawing ID | I leak (4K,BT) | I leak (4K,AT) | R dc (4K,BT) | R dc (4K,AT) | I leak (300K,BT) | I leak (300K,AT) | R dc (300K,BT) | R dc (300K,AT) | L 1kHz (300K,BT) | L 1kHz (300K,AT) | L 100Hz (300K,BT) | L 100Hz (300K,AT) | Quench Current 1 (tr.) | Quench Current 2 (tr.) | Quench Current 3 (tr.) | Quench Current 4 (tr.) | Quench Current 5 (tr.) | Quench Current 6 (tr.) | Quench Current 7 (tr.) | Quench Current 8 (tr.) | Quench Current 9 (tr.) | Quench Current 10 (tr.) | Quench Current 11 (tr.) | Quench Current 12 (tr.) | Quench Current 13 (tr.) | Quench Current 14 (tr.) | Quench Current 15 (tr.) | Quench Current 16 (tr.) | Quench Current 17 (tr.) | Quench Current 18 (tr.) | Quench Current 19 (tr.) | Quench Current 20 (tr.) | b1 (300K,BT) | a1 (300K,BT) | b2 (300K,BT) | a2 (300K,BT) | b3 (300K,BT) | a3 (300K,BT) | b4 (300K,BT) | a4 (300K,BT) | b5 (300K,BT) | a5 (300K,BT) | b6 (300K,BT) | a6 (300K,BT) | b7 (300K,BT) | a7 (300K,BT) | b8 (300K,BT) | a8 (300K,BT) | b9 (300K,BT) | a9 (300K,BT) | b10 (300K,BT) | a10 (300K,BT) | b11 (300K,BT) | a11 (300K,BT) | b12 (300K,BT) | a12 (300K,BT) | b13 (300K,BT) | a13 (300K,BT) | b14 (300K,BT) | a14 (300K,BT) | b15 (300K,BT) | a15 (300K,BT) | dx (300K,BT) | dy (300K,BT) | dT (300K,BT) | Quench Current 1 (re-tr.) | Quench Current 2 (re-tr.) | Quench Current 3 (re-tr.) | Quench Current 4 (re-tr.) | Quench Current 5 (re-tr.) | Quench Current 6 (re-tr.) | Quench Current 7 (re-tr.) | Quench Current 8 (re-tr.) | Quench Current 9 (re-tr.) | Quench Current 10(re-tr.) | Quench Current 11(re-tr.) | Quench Current 12(re-tr.) | Quench Current 13(re-tr.) | Quench Current 14(re-tr.) | Quench Current 15(re-tr.) | Quench Current 16(re-tr.) | Quench Current 17(re-tr.) | Quench Current 18(re-tr.) | Quench Current 19(re-tr.) | Quench Current 20(re-tr.) | b1 (300K,AT) | a1 (300K,AT) | b2 (300K,AT) | a2 (300K,AT) | b3 (300K,AT) | a3 (300K,AT) | b4 (300K,AT) | a4 (300K,AT) | b5 (300K,AT) | a5 (300K,AT) | b6 (300K,AT) | a6 (300K,AT) | b7 (300K,AT) | a7 (300K,AT) | b8 (300K,AT) | a8 (300K,AT) | b9 (300K,AT) | a9 (300K,AT) | b10 (300K,AT) | a10 (300K,AT) | b11 (300K,AT) | a11 (300K,AT) | b12 (300K,AT) | a12 (300K,AT) | b13 (300K,AT) | a13 (300K,AT) | b14 (300K,AT) | a14 (300K,AT) | b15 (300K,AT) | a15 (300K,AT) | dx (300K,AT) | dy (300K,AT) | dT (300K,AT) | Doc. Number | Type
[5 empty] | [] | [] | [µA] | [µA] | [nOhm] | [nOhm] | [µA] | [µA] | [Ohm] | [Ohm] | [µH] | [µH] | [µH] | [µH] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [mm] | [mm] | [mrad] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [mm] | [mm] | [mrad]
(CERN ID)
M060 | HCMCSMG001 |  |  |  | P639 | P672 | P674 | P946 | P638 | P952 | P680 | P932 | P656 | P935 | P658 | P938 | P661 | P941 | P820 | P821 | P822 | P823 | P824 | P825 | P826 | P827 | P828 | P829 | P830 | P831 | P832 | P833 | P834 | P835 | P836 | P837 | P838 | P839 | P860 | P861 | P862 | P863 | P864 | P865 | P866 | P867 | P868 | P869 | P870 | P871 | P872 | P873 | P874 | P875 | P876 | P877 | P878 | P879 | P880 | P881 | P882 | P883 | P884 | P885 | P886 | P887 | P888 | P889 | P890 | P891 | P892 | P840 | P841 | P842 | P843 | P844 | P845 | P846 | P847 | P848 | P849 | P850 | P851 | P852 | P853 | P854 | P855 | P856 | P857 | P858 | P859 | P893 | P894 | P895 | P896 | P897 | P898 | P899 | P900 | P901 | P902 | P903 | P904 | P905 | P906 | P907 | P908 | P909 | P910 | P911 | P912 | P913 | P914 | P915 | P916 | P917 | P918 | P919 | P920 | P921 | P922 | P923 | P924 | P925
| 120 | 0

## 37.Magnet Assembly
Magnet Assembly
Identification |  |  |  |  | Step 1 (): Delivery Information | [6 empty] | Step 1: Non-Conformities |  | Properties |  | Step 2 (): LHeT Tests Training | [6 empty] | Step 2: Non-Conformities |  | Properties | [21 empty] | Step 3 (): RT Tests Before Training | [6 empty] | Step 3: Non-Conformities |  | Properties | [36 empty] | Step 4 (): RT Tests After Training | [6 empty] | Step 4: Non-Conformities |  | Properties | [36 empty] | Step 5 (): LHeT Tests Re-Training | [6 empty] | Step 5: Non-Conformities |  | Properties | [21 empty] | Sub-Equipments |  |  |  | Equipment Non-Conformities
Equipment ID | Other ID | Manufacturer | Status | Comment | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | Manufacturer drawing ID | CDD drawing ID | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | I leak (4K,BT) | R dc (4K,BT) | Quench Current 1 (tr.) | Quench Current 2 (tr.) | Quench Current 3 (tr.) | Quench Current 4 (tr.) | Quench Current 5 (tr.) | Quench Current 6 (tr.) | Quench Current 7 (tr.) | Quench Current 8 (tr.) | Quench Current 9 (tr.) | Quench Current 10 (tr.) | Quench Current 11 (tr.) | Quench Current 12 (tr.) | Quench Current 13 (tr.) | Quench Current 14 (tr.) | Quench Current 15 (tr.) | Quench Current 16 (tr.) | Quench Current 17 (tr.) | Quench Current 18 (tr.) | Quench Current 19 (tr.) | Quench Current 20 (tr.) | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | I leak (300K,BT) | R dc (300K,BT) | L 1kHz (300K,BT) | L 100Hz (300K,BT) | b1 (300K,BT) | a1 (300K,BT) | b2 (300K,BT) | a2 (300K,BT) | b3 (300K,BT) | a3 (300K,BT) | b4 (300K,BT) | a4 (300K,BT) | b5 (300K,BT) | a5 (300K,BT) | b6 (300K,BT) | a6 (300K,BT) | b7 (300K,BT) | a7 (300K,BT) | b8 (300K,BT) | a8 (300K,BT) | b9 (300K,BT) | a9 (300K,BT) | b10 (300K,BT) | a10 (300K,BT) | b11 (300K,BT) | a11 (300K,BT) | b12 (300K,BT) | a12 (300K,BT) | b13 (300K,BT) | a13 (300K,BT) | b14 (300K,BT) | a14 (300K,BT) | b15 (300K,BT) | a15 (300K,BT) | dx (300K,BT) | dy (300K,BT) | dT (300K,BT) | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | I leak (300K,AT) | R dc (300K,AT) | L 1kHz (300K,AT) | L 100Hz (300K,AT) | b1 (300K,AT) | a1 (300K,AT) | b2 (300K,AT) | a2 (300K,AT) | b3 (300K,AT) | a3 (300K,AT) | b4 (300K,AT) | a4 (300K,AT) | b5 (300K,AT) | a5 (300K,AT) | b6 (300K,AT) | a6 (300K,AT) | b7 (300K,AT) | a7 (300K,AT) | b8 (300K,AT) | a8 (300K,AT) | b9 (300K,AT) | a9 (300K,AT) | b10 (300K,AT) | a10 (300K,AT) | b11 (300K,AT) | a11 (300K,AT) | b12 (300K,AT) | a12 (300K,AT) | b13 (300K,AT) | a13 (300K,AT) | b14 (300K,AT) | a14 (300K,AT) | b15 (300K,AT) | a15 (300K,AT) | dx (300K,AT) | dy (300K,AT) | dT (300K,AT) | Status | Result | Standard Step ID | Completed On | Executed by | Results doc. | Comments | Doc. Number | Type | I leak (4K,AT) | R dc (4K,AT) | Quench Current 1 (re-tr.) | Quench Current 2 (re-tr.) | Quench Current 3 (re-tr.) | Quench Current 4 (re-tr.) | Quench Current 5 (re-tr.) | Quench Current 6 (re-tr.) | Quench Current 7 (re-tr.) | Quench Current 8 (re-tr.) | Quench Current 9 (re-tr.) | Quench Current 10(re-tr.) | Quench Current 11(re-tr.) | Quench Current 12(re-tr.) | Quench Current 13(re-tr.) | Quench Current 14(re-tr.) | Quench Current 15(re-tr.) | Quench Current 16(re-tr.) | Quench Current 17(re-tr.) | Quench Current 18(re-tr.) | Quench Current 19(re-tr.) | Quench Current 20(re-tr.) | Protection Resistor | Magnetic Shield | Shield End Cap | Magnet Module | Doc. Number | Type
[14 empty] | [] | [] | [9 empty] | [µA] | [nOhm] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [9 empty] | [µA] | [Ohm] | [µH] | [µH] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [mm] | [mm] | [mrad] | [9 empty] | [µA] | [Ohm] | [µH] | [µH] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [mm] | [mm] | [mrad] | [9 empty] | [µA] | [nOhm] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | [] | 1 | 2 | 3 | 4
(CERN ID) | [169 empty] | 1 | 1 | 1 | 1
M060 | HCMCSMH001 |  |  |  | MTF000848 | [7 empty] | 2 | P639 | P672 | MTF000849 | [7 empty] | 22 | P674 | P638 | P820 | P821 | P822 | P823 | P824 | P825 | P826 | P827 | P828 | P829 | P830 | P831 | P832 | P833 | P834 | P835 | P836 | P837 | P838 | P839 | MTF000850 | [7 empty] | 37 | P680 | P656 | P658 | P661 | P860 | P861 | P862 | P863 | P864 | P865 | P866 | P867 | P868 | P869 | P870 | P871 | P872 | P873 | P874 | P875 | P876 | P877 | P878 | P879 | P880 | P881 | P882 | P883 | P884 | P885 | P886 | P887 | P888 | P889 | P890 | P891 | P892 | MTF000894 | [7 empty] | 37 | P932 | P935 | P938 | P941 | P893 | P894 | P895 | P896 | P897 | P898 | P899 | P900 | P901 | P902 | P903 | P904 | P905 | P906 | P907 | P908 | P909 | P910 | P911 | P912 | P913 | P914 | P915 | P916 | P917 | P918 | P919 | P920 | P921 | P922 | P923 | P924 | P925 | MTF000895 | [7 empty] | 22 | P946 | P952 | P840 | P841 | P842 | P843 | P844 | P845 | P846 | P847 | P848 | P849 | P850 | P851 | P852 | P853 | P854 | P855 | P856 | P857 | P858 | P859 | HCMCSMH017 | HCMCSMH008 | HCMCSMH007 | HCMCSMH002
| 0 | 5 | 4

## 38.Standard Steps
Standard Steps
MB Cold Mass - Cold Mass
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000869 |  | 1 | Electrical check | Manufacturer | CERN
MTF000870 |  | 2 | Warm magnetic measurements | Manufacturer | CERN
MTF000871 |  | 3 | Geometrical test | Manufacturer | CERN
Collared Coil - Collared Coil
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000811 |  | 1 | Delivery
MTF000795 | cc-21 | 2 | Perform collaring |  |  |  | LHC-MB-CI-0006 (ver.1) | 6.4.2
MTF000796 | ITP9 | 3 | Perform electrical check |  |  |  | LHC-MB-CI-0006 (ver.1) | Annex B10
MTF000797 | ITP10 | 4 | Perform Mechanical measurement |  |  |  | LHC-MB-CI-0006 (ver.1) | Annex B9
MTF000798 | ITP11 | 5 | Warm magnetic Measurement |  |  |  | LHC-MB-CI-0006 (ver.1) | Annex B18
MTF000799 | ITP11 | 6 | Magnetic Length control |  |  |  | LHC-MB-CI-0006 (ver.1) | Annex B19
MB Collars - Collars A Type 1
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MB Collars - Collars A Type 2
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MB Collars - Collars B Type 1
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MB Collars - Collars B Type 2
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MB Collars - Collars C Type 1
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MB Collars - Collars C Type 2
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
Ground Insulation Sheet - Ground Insulation Sheet
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000808 |  | 1 | Delivery to Manufacturer |  | Manufacturer
Aperture - Aperture
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MB Quench Heater - Quench Heater
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000775 |  | 1 | Manufacturer checks | Manufacturer | Manufacturer | Francois J. | LHC-DQH-CI-0001 (ver.1)
MTF000778 |  | 2 | Delivery at CERN | Manufacturer | CERN | Desebe O.
MTF000776 |  | 3 | CERN checks | CERN | CERN | Desebe O. | LHC-DQH-CI-0001 (ver.1)
MTF000780 |  | 4 | Returning to Manufacturer | CERN | Manufacturer
MTF000779 |  | 5 | Sending to Magnet Integrator | CERN | Magnet Integrator | Desebe O.
MTF000777 |  | 6 | Magnet Integrator Checks | Magnet Integrator | CERN
MTF000781 |  | 7 | Reception from Magnet Integrator | CERN | CERN
Cold Bore Tube - Cold Bore Tube
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000805 |  | 1 | Cleaning
MTF000806 |  | 2 | Insulation
MTF000804 |  | 3 | Delivery to Manufacturer |  | Manufacturer
Pole - Pole
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000791 | ITP 6 - cc-13 | 1 | Poles Assembly |  |  |  | LHC-MB-CI-0006 (ver.1) | 6.2.6
MTF000792 | ITP 7 | 2 | Perform electrical tests |  |  |  | LHC-MB-CI-0006 (ver.1) | 6.2.7 | See also Annex B10
MTF000793 | ITP 8 | 3 | Perform Mechanical measurements |  |  |  | LHC-MB-CI-0006 (ver.1) | Annex B9
MTF000794 | cc-16 | 4 | Insulate aperture to the Ground |  |  |  | LHC-MB-CI-0006 (ver.1) | Annex B10
Layer - Inner Layer
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000810 |  | 1 | Delivery to manufacturer |  | Manufacturer
MTF000786 | cc-05 - cc-06 | 2 | Wind layer |  |  |  | LHC-MB-CI-0006 (ver.1) | 6.2.3
MTF000787 | cc-07 - cc-08 | 3 | Cure Layer |  |  |  | LHC-MB-CI-0006 (ver.1) | 6.2.4
MTF000788 | ITP3 | 4 | Electrical Test after curing |  |  |  | LHC-MB-CI-0006 (ver.1) | Annex B10
MTF000789 | cc-11 - cc-12 | 5 | Surfacing Heads of layer |  |  |  | LHC-MB-CI-0006 (ver.1) | 6.2.5 | See also annex B8
MTF000790 | ITP4 - ITP5 | 6 | Perform Dimensional Meas. |  |  |  | LHC-MB-CI-0006 (ver.1) | Annex B9
Layer - Outer Layer
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000812 |  | 1 | Delivery to manufacturer |  | Manufacturer
MTF000813 | cc-05 - cc-06 | 2 | Wind layer |  |  |  | LHC-MB-CI-0006 (ver.1) | 6.2.3
MTF000814 | cc-07 - cc-08 | 3 | Cure Layer |  |  |  | LHC-MB-CI-0006 (ver.1) | 6.2.4
MTF000815 | ITP3 | 4 | Electrical Test after curing |  |  |  | LHC-MB-CI-0006 (ver.1) | Annex B10
MTF000816 | cc-11 - cc-12 | 5 | Surfacing Heads of layer |  |  |  | LHC-MB-CI-0006 (ver.1) | 6.2.5 | See also annex B8
MTF000817 | ITP4 - ITP5 | 6 | Perform Dimensional Meas. |  |  |  | LHC-MB-CI-0006 (ver.1) | Annex B9
Stabilizer - Stabilizer End Cable
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
SC Isolated - SC Isolated Type 1
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000782 | cc-01b | 1 | Insulate SC Inner Layer |  |  |  | LHC-MB-CI-0006 (ver.1) | B4
MTF000785 | ITP2 | 2 | Electrical Test during Cable Insulation |  |  |  | LHC-MB-CI-0006 (ver.1) | B7
MTF000809 |  | 3 | Delivery to Manufacturer |  | Manufacturer
SC Isolated - SC Isolated Type 2
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000827 | cc-01b | 1 | Insulate SC Inner Layer |  |  |  | LHC-MB-CI-0006 (ver.1) | B4
MTF000828 | ITP2 | 2 | Electrical Test during Cable Insulation |  |  |  | LHC-MB-CI-0006 (ver.1) | B7
MTF000829 |  | 3 | Delivery to Manufacturer |  | Manufacturer
Polymide Tape - Polymide Tape P1
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000826 |  | 1 | Delivery of Tape to firm |  |  | Hans Kummer
Polymide Tape - Polymide Tape A1
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000801 |  | 1 | Delivery of Tape to firm |  |  | Hans Kummer
Cable Supra - Cable Supra Type 1
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
Cable Supra - Cable Supra Type 2
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
End Spacers - End Spacers Inner Layer
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000802 |  | 1 | Delivery of end spacers | TOSTI | Manufacturer | Paolo Fessia | LHC-MB__A-CI-0003 (ver.1)
End Spacers - End Spacers Outer Layer
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000825 |  | 1 | Delivery of end spacers | TOSTI | Manufacturer | Paolo Fessia | LHC-MB__A-CI-0003 (ver.1)
Chips and Wedges Tips - Chips and Wedges tips
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000803 |  | 1 | Delivery of chips and wedge tips | TOSTI | Manufacturer | Paolo Fessia | LHC-MB__A-CI-0003 (ver.1)
Isolated Cu Wedges - Cu Wedges Isolated T1
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000783 | cc-02b | 1 | Copper wedge Insulation |  |  |  | LHC-MB-CI-0006 (ver.1) | B5
Isolated Cu Wedges - Cu Wedges Isolated T2
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000819 | cc-02b | 1 | Copper wedge Insulation |  |  |  | LHC-MB-CI-0006 (ver.1) | B5
Isolated Cu Wedges - Cu Wedges Isolated T3
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000821 | cc-02b | 1 | Copper wedge Insulation |  |  |  | LHC-MB-CI-0006 (ver.1) | B5
Isolated Cu Wedges - Cu Wedges Isolated T4
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000823 | cc-02b | 1 | Copper wedge Insulation |  |  |  | LHC-MB-CI-0006 (ver.1) | B5
Copper Wedges - Copper Wedges Type 1
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000800 | cc-04 a | 1 | Clean-up Cu Wedges | OUTOKUMPU |  | Diego Perini | LHC-MB-CI-0006 (ver.1) | Annex B5
Copper Wedges - Copper Wedges Type 2
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000820 | cc-04 a | 1 | Clean-up Cu Wedges | OUTOKUMPU |  | Diego Perini | LHC-MB-CI-0006 (ver.1) | Annex B5
Copper Wedges - Copper Wedges Type 3
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000822 | cc-04 a | 1 | Clean-up Cu Wedges | OUTOKUMPU |  | Diego Perini | LHC-MB-CI-0006 (ver.1) | Annex B5
Copper Wedges - Copper Wedges Type 4
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000824 | cc-04 a | 1 | Clean-up Cu Wedges | OUTOKUMPU |  | Diego Perini | LHC-MB-CI-0006 (ver.1) | Annex B5
Shims - Shims
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
Shim Retainers - Shim Retainers
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
Magnet Assembly - Magnet Assembly
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
Magnet Assembly - Magnet Assembly
Standard Step ID | Other identifier | Sequence Number | Description | Provided by | ExpectedBy | Responsible | Aplicable standard | Chapter | Comment
MTF000848 |  | 1 | Delivery Information
MTF000849 |  | 2 | LHeT Tests Training
MTF000850 |  | 3 | RT Tests Before Training
MTF000894 |  | 4 | RT Tests After Training
MTF000895 |  | 5 | LHeT Tests Re-Training

## 39.Properties
Properties
Description | Code | Unit | Type | Category | Default | Comment
Delivery date | P1802 |  | CHAR
Res.20°C | P1755 | mOhm | NUM |  |  | Resistance at 20°C
Induct. 10Hz | P316 | mH | NUM |  |  | Inductance at 10Hz (after assembly)
Stacking factor (ferrom.) | P1771 | % | NUM
Length (ferrom. part) | P1770 | mm | NUM
b2_straight_A1 | P302 |  | NUM
b3_straight_A1 | P303 |  | NUM
b4_straight_A1 | P304 |  | NUM
b5_straight_A1 | P305 |  | NUM
b7_straight_A1 | P322 |  | NUM
a1_straight_A1 | P323 |  | NUM
a2_straight_A1 | P324 |  | NUM
a3_straight_A1 | P325 |  | NUM
a4_straight_A1 | P336 |  | NUM
b2_straight_A2 | P320 |  | NUM |  |  | Resistance at 20°C (after collaring) for Aperture 2
b3_straight_A2 | P318 |  | NUM
b4_straight_A2 | P319 |  | NUM
b5_straight_A2 | P337 |  | NUM
b7_straight_A2 | P360 |  | NUM
a1_straight_A2 | P361 |  | NUM
a2_straight_A2 | P362 |  | NUM
a3_straight_A2 | P363 |  | NUM
a4_straight_A2 | P364 |  | NUM
b2_integrated_A1 | P366 |  | NUM
b3_integrated_A1 | P367 |  | NUM
b4_integrated_A1 | P368 |  | NUM
b5_integrated_A1 | P369 |  | NUM
b7_integrated_A1 | P370 |  | NUM
a1_integrated_A1 | P371 |  | NUM
a2_integrated_A1 | P372 |  | NUM
a3_integrated_A1 | P373 |  | NUM
a4_integrated_A1 | P374 |  | NUM
transf_func_integ_A1 | P375 |  | CHAR |  |  | transfer function intergated A1
mag_length_integ_A1 | P314 |  | NUM |  |  | Magnetic length integrated A1
b2_integrated_A2 | P376 |  | NUM
b3_integrated_A2 | P377 |  | NUM
b4_integrated_A2 | P378 |  | NUM
b5_integrated_A2 | P379 |  | NUM
b7_integrated_A2 | P380 |  | NUM
a1_integrated_A2 | P381 |  | NUM
a2_integrated_A2 | P382 |  | NUM
a3_integrated_A2 | P383 |  | NUM
a4_integrated_A2 | P384 |  | NUM
transf_func_integ_A2 | P385 |  | CHAR |  |  | transfer function intergated A2
mag_length_integ_A2 | P334 |  | NUM |  |  | Magnetic length integrated A2
Max_dx_v1 | P1772 |  | NUM
Max_dz_v1 | P1773 |  | NUM
Max_dx_v2 | P1774 |  | NUM
Max_dz_v2 | P1775 |  | NUM
Min_dx_v1 | P1821 |  | NUM
Min_dz_v1 | P1822 |  | NUM
Min_dx_v2 | P1823 |  | NUM
Min_dz_v2 | P1824 |  | NUM
RMS_dx_v1 | P1776 |  | NUM
RMS_dx_v2 | P1777 |  | NUM
RMS_dz_v1 | P1778 |  | NUM
RMS_dz_v2 | P1779 |  | NUM
dx_conn_side_v1 | P1762 |  | NUM
dz_conn_side_v1 | P1763 |  | NUM
dx_conn_side_v2 | P1764 |  | NUM
dz_conn_side_v2 | P1765 |  | NUM
dx_lyra_side_v1 | P1766 |  | NUM
dz_lyra_side_v1 | P1767 |  | NUM
dx_lyra_side_v2 | P1768 |  | NUM
dz_lyra_side_v2 | P1769 |  | NUM
A1up.i.l. shim side | P1741 | mm | NUM |  |  | A1-upper inner layer pole shim side
A1up.i.l. shim central | P1742 | mm | NUM |  |  | A1-upper inner layer pole shim central
A1up.o.l. shim side | P1743 | mm | NUM |  |  | A1-upper outer layer pole shim side
A1up.o.l. shim central | P1744 | mm | NUM |  |  | A1-upper outer layer pole shim central
A1low.i.l.shim side | P1745 | mm | NUM |  |  | A1-lower inner layer pole shim side
A1low.i.l.shim central | P1746 | mm | NUM |  |  | A1-lower inner layer pole shim side
A1.low.o.l.shim side | P1747 | mm | NUM |  |  | A1-lower outer layer pole shim side
A1.low.o.l.shim central | P1748 | mm | NUM |  |  | A1-lower outer layer pole shim central
A2up.i.l. shim side | P1749 | mm | NUM |  |  | A2-upper inner layer pole shim side
A2up.i.l. shim central | P1750 | mm | NUM |  |  | A2-upper inner layer pole shim side
A2up.o.l. shim side | P1751 | mm | NUM |  |  | A2-upper outer layer pole shim side
A2up.o.l. shim central | P1752 | mm | NUM |  |  | A2-upper outer layer pole shim central
A2low.i.l. shim side | P1753 | mm | NUM |  |  | A2-lower inner layer pole shim side
A2low.i.l. shim central | P1754 | mm | NUM |  |  | A2-lower inner layer pole shim side
A2low.o.l. shim side | P1850 | mm | NUM
A2low.o.l. shim central | P1851 | mm | NUM
Max. collaring pressure | P1757 | MPa | NUM |  |  | Maximum collaring pressure
Coll.size 2 straight sec | P1758 | mm | NUM |  |  | Collar size 2 (straight section)
Coll.size 4 straight sec | P1759 | mm | NUM |  |  | Collar size 4 (straight section)
Coll.size 6 straight sec | P1760 | mm | NUM |  |  | Collar size 6 (straight section)
Coll.size 8 straight sec | P1761 | mm | NUM |  |  | Collar size 8 (straight section)
coil_pos_straight_A1 | P300 | µm | NUM |  |  | Coil positioning straight A1
coil_pos_straight_A2 | P365 | µm | NUM
Contract Number | P578 |  | CHAR
Permeability | P607 |  | NUM
Thickness | P608 | mm | NUM
Raw Material Certificate | P597 |  | CHAR
Aperture number | P399 |  | CHAR
Delivered at CERN on | P570 |  | CHAR
Checked at CERN on | P571 |  | CHAR
Length | P577 | mm | NUM | Quench Heater | 14557
Temperature | P560 | °C | NUM | Quench Heater | 25
Humidity | P561 | % | NUM | Quench Heater | 50
First strip end | P563 | mm | NUM
First strip start | P562 | mm | NUM
Second strip end | P565 | mm | NUM
Second strip start | P564 | mm | NUM
Strip O. Thick cont. | P566 |  | CHAR
Strip O. Thick glue | P567 |  | CHAR
Poly. O. Thick cont. | P568 |  | CHAR
Poly. O. Thick glue | P569 |  | CHAR
Returned to Manuf. On | P576 |  | CHAR
Sent to Mag.Int. on | P572 |  | CHAR
Received from Mag.Int. on | P574 |  | CHAR
Cleaning Procedure | P601 |  | CHAR |  |  | OK/NOT OK
External diameter | P603 | mm | NUM
Heat Number | P600 |  | NUM
Heat Treatment | P596 |  | NUM
Wall Thickness | P602 | mm | NUM
Insulation Test | P604 | GOhm | NUM
Room Temp Pressure Test | P598 |  | CHAR |  |  | Passed/Failed
Leak Test | P599 |  | CHAR |  |  | Passed/Failed
Assembly Line number | P606 |  | NUM
Pole position | P398 |  | CHAR
R[DC] | P625 | mOhm | NUM
I for R[DC] | P350 | A | NUM
R[DC] of splice | P626 | µOhm | NUM
I for R[DC] of splice | P351 | A | NUM
Inductance [10 KHz] | P621 | mH | NUM
Inductance [100 Hz] | P622 | mH | NUM
Inductance [1000 Hz] | P623 | mH | NUM
Insulation Resistance | P624 | MOhm | NUM
S 100 | P631 | mm | NUM |  |  | Coil size at 100MPa
Displacement at 40 MPa | P629 | mm | NUM
Displacement at 80 MPa | P630 | mm | NUM
Date of Delivery | P581 |  | CHAR
Winding Line | P605 |  | NUM
Discharge with strain | P628 | µs | NUM
Discharge without strain | P627 | µs | NUM
Destination Firm | P580 |  | CHAR
Drawing number | P579 |  | CHAR
Cable Visual Inspection | P594 |  | CHAR |  |  | Passed/Failed
Average Keystone | P589 |  | NUM
Average Mid-Thickness | P588 | mm | NUM
Average Width | P587 | mm | NUM
Cable Bend Test | P593 |  | CHAR |  |  | Yes/No
Cable Ic at 4.2 K | P595 | A | NUM
Field for Ic | P633 | T | NUM
Cable Length | P586 | m | NUM
Heat Treatment temp. | P632 | °C | NUM
Stack Mid-Thickness | P590 |  | NUM
Transposition Direction | P591 |  | CHAR |  |  | Left/Right
Transposition Pitch | P592 |  | NUM
Comment on cable quality | P559 |  | CHAR
Comment on Delivery | P585 |  | CHAR
Angle [A] (Beg) | P582 | ° | NUM
BCH (Beg) | P609 | mm | NUM
BCV (Beg) | P610 | mm | NUM
Length [AB] (Beg) | P583 | mm | NUM
Length [AC] (Beg) | P584 | mm | NUM
Angle A (Mid) | P613 | ° | NUM
BCH (Mid) | P612 | mm | NUM
BCV (Mid) | P611 | mm | NUM
Length [AB] (Mid) | P615 | mm | NUM
Length [BC] (Mid) | P614 | mm | NUM
Angle A (End) | P618 | ° | NUM
BCH (End) | P617 | mm | NUM
BCV (End) | P616 | mm | NUM
Length [AB] (End) | P620 | mm | NUM
Length [BC] (End) | P619 | mm | NUM
Manufacturer drawing ID | P639 |  | CHAR |  |  | Drawing ID
CDD drawing ID | P672 |  | CHAR |  |  | CDD drawing ID
I leak (4K,BT) | P674 | µA | NUM |  |  | Leakage current - before training
I leak (4K,AT) | P946 | µA | NUM |  |  | Leakage current - training
R dc (4K,BT) | P638 | nOhm | NUM |  |  | DC resistance - before training
R dc (4K,AT) | P952 | nOhm | NUM |  |  | DC resistance - training
I leak (300K,BT) | P680 | µA | NUM |  |  | Leakage current (RT) - before training
I leak (300K,AT) | P932 | µA | NUM |  |  | Leakage current (RT) - training
R dc (300K,BT) | P656 | Ohm | CHAR |  |  | DC resistance (Ohms) - before training
R dc (300K,AT) | P935 | Ohm | CHAR |  |  | DC resistance (RT) - training
L 1kHz (300K,BT) | P658 | µH | NUM |  |  | Inductance at 1 kHz (RT) - before training
L 1kHz (300K,AT) | P938 | µH | NUM |  |  | Inductance at 1 kHz (RT) - training
L 100Hz (300K,BT) | P661 | µH | NUM |  |  | Inductance at 100Hz (RT) - before training
L 100Hz (300K,AT) | P941 | µH | NUM |  |  | Inductance at 100Hz (RT) - training
Quench Current 1 (tr.) | P820 |  | NUM |  |  | Quench Current 1 (Training)
Quench Current 2 (tr.) | P821 |  | NUM |  |  | Quench Current 2 (Training)
Quench Current 3 (tr.) | P822 |  | NUM |  |  | Quench Current 3 (Training)
Quench Current 4 (tr.) | P823 |  | NUM
Quench Current 5 (tr.) | P824 |  | NUM
Quench Current 6 (tr.) | P825 |  | NUM
Quench Current 7 (tr.) | P826 |  | NUM
Quench Current 8 (tr.) | P827 |  | NUM
Quench Current 9 (tr.) | P828 |  | NUM
Quench Current 10 (tr.) | P829 |  | NUM
Quench Current 11 (tr.) | P830 |  | NUM
Quench Current 12 (tr.) | P831 |  | NUM
Quench Current 13 (tr.) | P832 |  | NUM
Quench Current 14 (tr.) | P833 |  | NUM
Quench Current 15 (tr.) | P834 |  | NUM
Quench Current 16 (tr.) | P835 |  | NUM
Quench Current 17 (tr.) | P836 |  | NUM
Quench Current 18 (tr.) | P837 |  | NUM
Quench Current 19 (tr.) | P838 |  | NUM
Quench Current 20 (tr.) | P839 |  | NUM
b1 (300K,BT) | P860 |  | CHAR
a1 (300K,BT) | P861 |  | CHAR
b2 (300K,BT) | P862 |  | CHAR
a2 (300K,BT) | P863 |  | CHAR
b3 (300K,BT) | P864 |  | CHAR
a3 (300K,BT) | P865 |  | CHAR
b4 (300K,BT) | P866 |  | CHAR
a4 (300K,BT) | P867 |  | CHAR
b5 (300K,BT) | P868 |  | CHAR
a5 (300K,BT) | P869 |  | CHAR
b6 (300K,BT) | P870 |  | CHAR
a6 (300K,BT) | P871 |  | CHAR
b7 (300K,BT) | P872 |  | CHAR
a7 (300K,BT) | P873 |  | CHAR
b8 (300K,BT) | P874 |  | CHAR
a8 (300K,BT) | P875 |  | CHAR
b9 (300K,BT) | P876 |  | CHAR
a9 (300K,BT) | P877 |  | CHAR
b10 (300K,BT) | P878 |  | CHAR
a10 (300K,BT) | P879 |  | CHAR
b11 (300K,BT) | P880 |  | CHAR
a11 (300K,BT) | P881 |  | CHAR
b12 (300K,BT) | P882 |  | CHAR
a12 (300K,BT) | P883 |  | CHAR
b13 (300K,BT) | P884 |  | CHAR
a13 (300K,BT) | P885 |  | CHAR
b14 (300K,BT) | P886 |  | CHAR
a14 (300K,BT) | P887 |  | CHAR
b15 (300K,BT) | P888 |  | CHAR
a15 (300K,BT) | P889 |  | CHAR
dx (300K,BT) | P890 | mm | CHAR
dy (300K,BT) | P891 | mm | CHAR
dT (300K,BT) | P892 | mrad | CHAR
Quench Current 1 (re-tr.) | P840 |  | NUM
Quench Current 2 (re-tr.) | P841 |  | NUM
Quench Current 3 (re-tr.) | P842 |  | NUM
Quench Current 4 (re-tr.) | P843 |  | NUM
Quench Current 5 (re-tr.) | P844 |  | NUM
Quench Current 6 (re-tr.) | P845 |  | NUM
Quench Current 7 (re-tr.) | P846 |  | NUM
Quench Current 8 (re-tr.) | P847 |  | NUM
Quench Current 9 (re-tr.) | P848 |  | NUM
Quench Current 10(re-tr.) | P849 |  | NUM
Quench Current 11(re-tr.) | P850 |  | NUM
Quench Current 12(re-tr.) | P851 |  | NUM
Quench Current 13(re-tr.) | P852 |  | NUM
Quench Current 14(re-tr.) | P853 |  | NUM
Quench Current 15(re-tr.) | P854 |  | NUM
Quench Current 16(re-tr.) | P855 |  | NUM
Quench Current 17(re-tr.) | P856 |  | NUM
Quench Current 18(re-tr.) | P857 |  | NUM
Quench Current 19(re-tr.) | P858 |  | NUM
Quench Current 20(re-tr.) | P859 |  | NUM
b1 (300K,AT) | P893 |  | CHAR
a1 (300K,AT) | P894 |  | CHAR
b2 (300K,AT) | P895 |  | CHAR
a2 (300K,AT) | P896 |  | CHAR
b3 (300K,AT) | P897 |  | CHAR
a3 (300K,AT) | P898 |  | CHAR
b4 (300K,AT) | P899 |  | CHAR
a4 (300K,AT) | P900 |  | CHAR
b5 (300K,AT) | P901 |  | CHAR
a5 (300K,AT) | P902 |  | CHAR
b6 (300K,AT) | P903 |  | CHAR
a6 (300K,AT) | P904 |  | CHAR
b7 (300K,AT) | P905 |  | CHAR
a7 (300K,AT) | P906 |  | CHAR
b8 (300K,AT) | P907 |  | CHAR
a8 (300K,AT) | P908 |  | CHAR
b9 (300K,AT) | P909 |  | CHAR
a9 (300K,AT) | P910 |  | CHAR
b10 (300K,AT) | P911 |  | CHAR
a10 (300K,AT) | P912 |  | CHAR
b11 (300K,AT) | P913 |  | CHAR
a11 (300K,AT) | P914 |  | CHAR
b12 (300K,AT) | P915 |  | CHAR
a12 (300K,AT) | P916 |  | CHAR
b13 (300K,AT) | P917 |  | CHAR
a13 (300K,AT) | P918 |  | CHAR
b14 (300K,AT) | P919 |  | CHAR
a14 (300K,AT) | P920 |  | CHAR
b15 (300K,AT) | P921 |  | CHAR
a15 (300K,AT) | P922 |  | CHAR
dx (300K,AT) | P923 | mm | CHAR
dy (300K,AT) | P924 | mm | CHAR
dT (300K,AT) | P925 | mrad | CHAR

## Personal Information
Personal Information
EDMSlogin
EDMSGroup
Created On