## Wtable (hidden)
13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Weld V1 V2 | VAC test V1 V2 | Weld E line | VAC test E | Soldering Main Bus bars | Insulation Main bus bars | Us weld spool | Insulate spool | PAQ | weld Y line | weld X line | VAC test X line | weld C' line | weld M3 | weld K1,K2 | VAC test K1, K2, C' line | weld M1,M2 | insert N line | cabling N line | AIV 1 | US weld N line | AIV 2 | Weld N | insulation N TIG, M1,M2, N | Close W | VAC final test
8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 5.714% | 0% | 14.29% | 0% | 2.857% | 5.714% | 5.714% | 0%
THE LINE ABOVE IT TO TRANSFER THE VALUES FROM THE TABLE BELOW TO THE EVALUATION SHEET
TABLE TO EVALUATE WEIGHT OF DIFFERENT INTERCONNECT PHASES
| Fabbrication phases | VAC test | Elecectrical test | %
Weld V1 V2 | 3 |  |  | 8.571% | Weld V1 V2 | 3
VAC test V1 V2 |  |  |  | 0% | VAC test V1 V2
Weld E line | 1.5 |  |  | 4.286% | Weld E line | 1.5
VAC test E |  |  |  | 0% | VAC test E
Soldering Main Bus bars | 4 |  |  | 11.43% | Soldering Main Bus bars | 4
Insulation Main bus bars | 1 |  |  | 2.857% | Insulation Main bus bars | 1
Us weld spool | 2 |  |  | 5.714% | Us weld spool | 2
Insulate spool | 1 |  |  | 2.857% | Insulate spool | 1
PAQ |  |  |  | 0% | PAQ
weld Y line | 0.25 |  |  | 0.7143% | weld Y line | 0.25
weld X line | 1.5 |  |  | 4.286% | weld X line | 1.5
VAC test X line |  |  |  | 0% | VAC test X line
weld C' line | 1 |  |  | 2.857% | weld C' line | 1
weld M3 | 1 |  |  | 2.857% | weld M3 | 1.5
weld K1,K2 | 1.25 |  |  | 3.571% | weld K1,K2 | 2
VAC test K1, K2, C' line |  |  |  | 0% | VAC test K1, K2, C' line
weld M1,M2 | 2.5 |  |  | 7.143% | weld M1,M2 | 3
insert N line | 3 |  |  | 8.571% | insert N line | 3
cabling N line | 2 |  |  | 5.714% | cabling N line | 2
AIV 1 |  |  |  | 0% | AIV 1
US weld N line | 5 |  |  | 14.29% | US weld N line | 5
AIV 2 |  |  |  | 0% | AIV 2
Weld N | 1 |  |  | 2.857% | Weld N | 1
insulation N TIG, M1,M2, N | 2 |  |  | 5.714% | insulation N TIG, M1,M2, N | 2
Close W | 2 |  |  | 5.714% | Close W | 2
VAC final test |  |  |  |  | VAC final test
TOTAL | 35 | 0 | 0 | 100%

## TS database
https://edms.cern.ch/asbuilt/plsql/mtf_equip.eqp_main_top?cookie=&p_rec_id=
DCUM | IC Type | IC Name | IC MTF | UP Type | UP MTF | DOWN Type | DOWN MTF
20255.3214 | QDQI_018 | QDQI.7R7 | HCQDQI_018-IE000002 | DFBAN |  | LQTAC
20263.0664 | QQBI_012 | QQBI.A8R7 | HCQQBI_012-IE000030 | LQTAC |  | LBARA | HCLBARA000-IN003026
20278.7264 | QBBI_004 | QBBI.8R7 | HCQBBI_004-IE000579 | LBARA | HCLBARA000-IN003026 | LBBRB | HCLBBRB000-IN001031
20294.3864 | QBQI_000 | QBQI.8R7 | HCQBQI_000-IE000145 | LBBRB | HCLBBRB000-IN001031 | LQTBB
20302.1314 | QQBI_012 | QQBI.8R7 | HCQQBI_012-IE000022 | LQTBB |  | LBARA | HCLBARA000-IN003050
20317.7914 | QBBI_004 | QBBI.9R7 | HCQBBI_004-IE000580 | LBARA | HCLBARA000-IN003050 | LBBRC | HCLBBRC000-IN001044
20333.4514 | QBQI_001 | QBQI.9R7 | HCQBQI_001-IE000078 | LBBRC | HCLBBRC000-IN001044 | LQTEC
20342.5964 | QQBI_012 | QQBI.9R7 | HCQQBI_012-IE000023 | LQTEC |  | LBARA | HCLBARA000-IN001052
20358.2564 | QBBI_004 | QBBI.10R7 | HCQBBI_004-IE000581 | LBARA | HCLBARA000-IN001052 | LBBRB | HCLBBRB000-IN001032
20373.9164 | QBQI_000 | QBQI.10R7 | HCQBQI_000-IE000146 | LBBRB | HCLBBRB000-IN001032 | LQTBB
20381.6614 | QQBI_012 | QQBI.10R7 | HCQQBI_012-IE000024 | LQTBB |  | LBARA | HCLBARA000-IN003022
20397.3214 | QBBI_004 | QBBI.11R7 | HCQBBI_004-IE000582 | LBARA | HCLBARA000-IN003022 | LBBRA | HCLBBRA000-IN001034
20412.9814 | QBEI_008 | QBEI.11R7 | HCQBEI_008-IE000007 | LBBRA | HCLBBRA000-IN001034 | LEDR | HCLEDR_000-CR000001
20426.6981 | QEQI_013 | QEQI.11R7 | HCQEQI_013-IE000001 | LEDR | HCLEDR_000-CR000001 | LQTCH
20434.4431 | QQBI_012 | QQBI.11R7 | HCQQBI_012-IE000025 | LQTCH |  | LBARA | HCLBARA000-IN002018
20450.1031 | QBBI_004 | QBBI.A12R7 | HCQBBI_004-IE000583 | LBARA | HCLBARA000-IN002018 | LBBRA | HCLBBRA000-IN001010
20465.7631 | QBBI_004 | QBBI.B12R7 | HCQBBI_004-IE000584 | LBBRA | HCLBBRA000-IN001010 | LBARB | HCLBARB000-IN002039
20481.4231 | QBQI_000 | QBQI.12R7 | HCQBQI_000-IE000147 | LBARB | HCLBARB000-IN002039 | LQATH | HCLQATH001-CR000245
20487.8931 | QQBI_002 | QQBI.12R7 | HCQQBI_012-IE000026 | LQATH | HCLQATH001-CR000245 | LBBRA | HCLBBRA000-IN003041
20503.5531 | QBBI_004 | QBBI.A13R7 | HCQBBI_004-IE000585 | LBBRA | HCLBBRA000-IN003041 | LBARA | HCLBARA000-IN001054
20519.2131 | QBBI_004 | QBBI.B13R7 | HCQBBI_004-IE000586 | LBARA | HCLBARA000-IN001054 | LBBRC | HCLBBRC000-IN003019
20534.8731 | QBQI_001 | QBQI.13R7 | HCQBQI_001-IE000079 | LBBRC | HCLBBRC000-IN003019 | LQATM | HCLQATM001-CR000019
20541.3431 | QQBI_002 | QQBI.13R7 | HCQQBI_002-IE000271 | LQATM | HCLQATM001-CR000019 | LBARA | HCLBARA000-IN003030
20557.0031 | QBBI_004 | QBBI.A14R7 | HCQBBI_004-IE000587 | LBARA | HCLBARA000-IN003030 | LBBRA | HCLBBRA000-IN001004
20572.6631 | QBBI_004 | QBBI.B14R7 | HCQBBI_004-IE000588 | LBBRA | HCLBBRA000-IN001004 | LBARB | HCLBARB000-IN002015
20588.3231 | QBQI_000 | QBQI.14R7 | HCQBQI_000-IE000148 | LBARB | HCLBARB000-IN002015 | LQATH | HCLQATH001-CR000037
20594.7931 | QQBI_002 | QQBI.14R7 | HCQQBI_002-IE000272 | LQATH | HCLQATH001-CR000037 | LBBRA | HCLBBRA000-IN003020
20610.4531 | QBBI_004 | QBBI.A15R7 | HCQBBI_004-IE000589 | LBBRA | HCLBBRA000-IN003020 | LBARA | HCLBARA000-IN003010
20626.1131 | QBBI_004 | QBBI.B15R7 | HCQBBI_004-IE000590 | LBARA | HCLBARA000-IN003010 | LBBRC | HCLBBRC000-IN001022
20641.7731 | QBQI_001 | QBQI.15R7 | HCQBQI_001-IE000080 | LBBRC | HCLBBRC000-IN001022 | LQATQ
20648.2431 | QQBI_002 | QQBI.15R7 | HCQQBI_002-IE000273 | LQATQ |  | LBARA | HCLBARA000-IN003279
20663.9031 | QBBI_004 | QBBI.A16R7 | HCQBBI_004-IE000591 | LBARA | HCLBARA000-IN003279 | LBBRA | HCLBBRA000-IN001008
20679.5631 | QBBI_004 | QBBI.B16R7 | HCQBBI_004-IE000592 | LBBRA | HCLBBRA000-IN001008 | LBARB | HCLBARB000-IN003028
20695.2231 | QBQI_000 | QBQI.16R7 | HCQBQI_000-IE000149 | LBARB | HCLBARB000-IN003028 | LQATH | HCLQATH001-CR000041
20701.6931 | QQBI_002 | QQBI.16R7 | HCQQBI_002-IE000274 | LQATH | HCLQATH001-CR000041 | LBBRA | HCLBBRA000-IN002008
20717.3531 | QBBI_004 | QBBI.A17R7 | HCQBBI_004-IE000593 | LBBRA | HCLBBRA000-IN002008 | LBARA | HCLBARA000-IN003055
20733.0131 | QBBI_004 | QBBI.B17R7 | HCQBBI_004-IE000594 | LBARA | HCLBARA000-IN003055 | LBBRC | HCLBBRC000-IN001035
20748.6731 | QBQI_001 | QBQI.17R7 | HCQBQI_001-IE000081 | LBBRC | HCLBBRC000-IN001035 | LQATM | HCLQATM001-CR000039
20755.1431 | QQBI_002 | QQBI.17R7 | HCQQBI_002-IE000275 | LQATM | HCLQATM001-CR000039 | LBARA | HCLBARA000-IN003006
20770.8031 | QBBI_004 | QBBI.A18R7 | HCQBBI_004-IE000595 | LBARA | HCLBARA000-IN003006 | LBBRA | HCLBBRA000-IN001021
20786.4631 | QBBI_004 | QBBI.B18R7 | HCQBBI_004-IE000596 | LBBRA | HCLBBRA000-IN001021 | LBARB | HCLBARB000-IN002029
20802.1231 | QBQI_000 | QBQI.18R7 | HCQBQI_000-IE000150 | LBARB | HCLBARB000-IN002029 | LQATH | HCLQATH001-CR000031
20808.5931 | QQBI_002 | QQBI.18R7 | HCQQBI_002-IE000276 | LQATH | HCLQATH001-CR000031 | LBBRA | HCLBBRA000-IN002004
20824.2531 | QBBI_004 | QBBI.A19R7 | HCQBBI_004-IE000597 | LBBRA | HCLBBRA000-IN002004 | LBARA | HCLBARA000-IN001045
20839.9131 | QBBI_004 | QBBI.B19R7 | HCQBBI_004-IE000598 | LBARA | HCLBARA000-IN001045 | LBBRC | HCLBBRC000-IN002009
20855.5731 | QBQI_001 | QBQI.19R7 | HCQBQI_001-IE000082 | LBBRC | HCLBBRC000-IN002009 | LQATQ
20862.0431 | QQBI_002 | QQBI.19R7 | HCQQBI_002-IE000277 | LQATQ |  | LBARA | HCLBARA000-IN003054
20877.7031 | QBBI_004 | QBBI.A20R7 | HCQBBI_004-IE000599 | LBARA | HCLBARA000-IN003054 | LBBRA | HCLBBRA000-IN002002
20893.3631 | QBBI_004 | QBBI.B20R7 | HCQBBI_004-IE000600 | LBBRA | HCLBBRA000-IN002002 | LBARB | HCLBARB000-IN003043
20909.0231 | QBQI_000 | QBQI.20R7 | HCQBQI_000-IE000151 | LBARB | HCLBARB000-IN003043 | LQATH | HCLQATH001-CR000249
20915.4931 | QQBI_002 | QQBI.20R7 | HCQQBI_002-IE000278 | LQATH | HCLQATH001-CR000249 | LBBRA | HCLBBRA000-IN003014
20931.1531 | QBBI_004 | QBBI.A21R7 | HCQBBI_004-IE000601 | LBBRA | HCLBBRA000-IN003014 | LBARA | HCLBARA000-IN001012
20946.8131 | QBBI_004 | QBBI.B21R7 | HCQBBI_004-IE000602 | LBARA | HCLBARA000-IN001012 | LBBRC | HCLBBRC000-IN001024
20962.4731 | QBQI_001 | QBQI.21R7 | HCQBQI_001-IE000083 | LBBRC | HCLBBRC000-IN001024 | LQATM | HCLQATM001-CR000040
20968.9431 | QQBI_002 | QQBI.21R7 | HCQQBI_002-IE000279 | LQATM | HCLQATM001-CR000040 | LBARA | HCLBARA000-IN003007
20984.6031 | QBBI_004 | QBBI.A22R7 | HCQBBI_004-IE000603 | LBARA | HCLBARA000-IN003007 | LBBRA | HCLBBRA000-IN001023
21000.2631 | QBBI_004 | QBBI.B22R7 | HCQBBI_004-IE000604 | LBBRA | HCLBBRA000-IN001023 | LBARB | HCLBARB000-IN002020
21015.9231 | QBQI_000 | QBQI.22R7 | HCQBQI_000-IE000152 | LBARB | HCLBARB000-IN002020 | LQOAG | HCLQOAG001-CR000002
21022.3931 | QQBI_002 | QQBI.22R7 | HCQQBI_002-IE000280 | LQOAG | HCLQOAG001-CR000002 | LBBRA | HCLBBRA000-IN003042
21038.0531 | QBBI_004 | QBBI.A23R7 | HCQBBI_004-IE000605 | LBBRA | HCLBBRA000-IN003042 | LBARA | HCLBARA000-IN001014
21053.7131 | QBBI_004 | QBBI.B23R7 | HCQBBI_004-IE000606 | LBARA | HCLBARA000-IN001014 | LBBRC | HCLBBRC000-IN001039
21069.3731 | QBQI_001 | QBQI.23R7 | HCQBQI_001-IE000084 | LBBRC | HCLBBRC000-IN001039 | LQASE
21075.8431 | QQBI_002 | QQBI.23R7 | HCQQBI_002-IE000281 | LQASE |  | LBARA | HCLBARA000-IN003027
21091.5031 | QBBI_004 | QBBI.A24R7 | HCQBBI_004-IE000607 | LBARA | HCLBARA000-IN003027 | LBBRA | HCLBBRA000-IN001020
21107.1631 | QBBI_004 | QBBI.B24R7 | HCQBBI_004-IE000608 | LBBRA | HCLBBRA000-IN001020 | LBARB | HCLBARB000-IN003008
21122.8231 | QBQI_000 | QBQI.24R7 | HCQBQI_000-IE000153 | LBARB | HCLBARB000-IN003008 | LQOAG | HCLQOAG001-CR000016
21129.2931 | QQBI_002 | QQBI.24R7 | HCQQBI_002-IE000282 | LQOAG | HCLQOAG001-CR000016 | LBBRA | HCLBBRA000-IN002012
21144.9531 | QBBI_004 | QBBI.A25R7 | HCQBBI_004-IE000609 | LBBRA | HCLBBRA000-IN002012 | LBARA | HCLBARA000-IN001051
21160.6131 | QBBI_004 | QBBI.B25R7 | HCQBBI_004-IE000610 | LBARA | HCLBARA000-IN001051 | LBBRC | HCLBBRC000-IN001006
21176.2731 | QBQI_001 | QBQI.25R7 | HCQBQI_001-IE000085 | LBBRC | HCLBBRC000-IN001006 | LQOAR | HCLQOAR001-CR000003
21182.7431 | QQBI_002 | QQBI.25R7 | HCQQBI_002-IE000283 | LQOAR | HCLQOAR001-CR000003 | LBARA | HCLBARA000-IN001053
21198.4031 | QBBI_004 | QBBI.A26R7 | HCQBBI_004-IE000611 | LBARA | HCLBARA000-IN001053 | LBBRA | HCLBBRA000-IN001038
21214.0631 | QBBI_004 | QBBI.B26R7 | HCQBBI_004-IE000612 | LBBRA | HCLBBRA000-IN001038 | LBARB | HCLBARB000-IN001055
21229.7231 | QBQI_000 | QBQI.26R7 | HCQBQI_000-IE000154 | LBARB | HCLBARB000-IN001055 | LQOAG | HCLQOAG001-CR000017
21236.1931 | QQBI_002 | QQBI.26R7 | HCQQBI_002-IE000284 | LQOAG | HCLQOAG001-CR000017 | LBBRA | HCLBBRA000-IN003039
21251.8531 | QBBI_004 | QBBI.A27R7 | HCQBBI_004-IE000613 | LBBRA | HCLBBRA000-IN003039 | LBARA | HCLBARA000-IN003024
21267.5131 | QBBI_004 | QBBI.B27R7 | HCQBBI_004-IE000614 | LBARA | HCLBARA000-IN003024 | LBBRC | HCLBBRC000-IN001049
21283.1731 | QBQI_001 | QBQI.27R7 | HCQBQI_001-IE000086 | LBBRC | HCLBBRC000-IN001049 | LQASE | HCLQASE001-CR000078
21289.6431 | QQBI_002 | QQBI.27R7 | HCQQBI_002-IE000285 | LQASE | HCLQASE001-CR000078 | LBARA | HCLBARA000-IN002034
21305.3031 | QBBI_004 | QBBI.A28R7 | HCQBBI_004-IE000615 | LBARA | HCLBARA000-IN002034 | LBBRA | HCLBBRA000-IN002048
21320.9631 | QBBI_004 | QBBI.B28R7 | HCQBBI_004-IE000616 | LBBRA | HCLBBRA000-IN002048 | LBARB | HCLBARB000-IN002011
21336.6231 | QBQI_000 | QBQI.28R7 | HCQBQI_000-IE000155 | LBARB | HCLBARB000-IN002011 | LQOAG | HCLQOAG001-CR000023
21343.0931 | QQBI_002 | QQBI.28R7 | HCQQBI_002-IE000286 | LQOAG | HCLQOAG001-CR000023 | LBBRA | HCLBBRA000-IN001042
21358.7531 | QBBI_004 | QBBI.A29R7 | HCQBBI_004-IE000617 | LBBRA | HCLBBRA000-IN001042 | LBARA | HCLBARA000-IN001013
21374.4131 | QBBI_004 | QBBI.B29R7 | HCQBBI_004-IE000618 | LBARA | HCLBARA000-IN001013 | LBBRC | HCLBBRC000-IN003017
21390.0731 | QBQI_001 | QBQI.29R7 | HCQBQI_001-IE000087 | LBBRC | HCLBBRC000-IN003017 | LQOBF | HCLQOBF001-CR000014
21396.5431 | QQBI_002 | QQBI.29R7 | HCQQBI_002-IE000287 | LQOBF | HCLQOBF001-CR000014 | LBARA | HCLBARA000-IN002019
21412.2031 | QBBI_004 | QBBI.A30R7 | HCQBBI_004-IE000619 | LBARA | HCLBARA000-IN002019 | LBBRA | HCLBBRA000-IN001007
21427.8631 | QBBI_004 | QBBI.B30R7 | HCQBBI_004-IE000620 | LBBRA | HCLBBRA000-IN001007 | LBARB | HCLBARB000-IN002027
21443.5231 | QBQI_000 | QBQI.30R7 | HCQBQI_000-IE000156 | LBARB | HCLBARB000-IN002027 | LQOAM | HCLQOAM001-CR000008
21449.9931 | QQBI_002 | QQBI.30R7 | HCQQBI_002-IE000288 | LQOAM | HCLQOAM001-CR000008 | LBBRA | HCLBBRA000-IN001041
21465.6531 | QBBI_004 | QBBI.A31R7 | HCQBBI_004-IE000621 | LBBRA | HCLBBRA000-IN001041 | LBARA | HCLBARA000-IN002026
21481.3131 | QBBI_004 | QBBI.B31R7 | HCQBBI_004-IE000622 | LBARA | HCLBARA000-IN002026 | LBBRC | HCLBBRC000-IN001028
21496.9731 | QBQI_001 | QBQI.31R7 | HCQBQI_001-IE000088 | LBBRC | HCLBBRC000-IN001028 | LQOAV | HCLQOAV001-CR000076
21503.4431 | QQBI_002 | QQBI.31R7 | HCQQBI_002-IE000289 | LQOAV | HCLQOAV001-CR000076 | LBARA | HCLBARA000-IN003052
21519.1031 | QBBI_004 | QBBI.A32R7 | HCQBBI_004-IE000623 | LBARA | HCLBARA000-IN003052 | LBBRA | HCLBBRA000-IN002052
21534.7631 | QBBI_004 | QBBI.B32R7 | HCQBBI_004-IE000624 | LBBRA | HCLBBRA000-IN002052 | LBARB | HCLBARB000-IN002005
21550.4231 | QBQI_000 | QBQI.32R7 | HCQBQI_000-IE000157 | LBARB | HCLBARB000-IN002005 | LQOAG | HCLQOAG001-CR000001
21556.8931 | QQBI_002 | QQBI.32R7 | HCQQBI_002-IE000290 | LQOAG | HCLQOAG001-CR000001 | LBBRA | HCLBBRA000-IN001016
21572.5531 | QBBI_004 | QBBI.A33R7 | HCQBBI_004-IE000625 | LBBRA | HCLBBRA000-IN001016 | LBARA | HCLBARA000-IN003023
21588.2131 | QBBI_004 | QBBI.B33R7 | HCQBBI_004-IE000626 | LBARA | HCLBARA000-IN003023 | LBBRC | HCLBBRC000-IN002041
21603.8731 | QBQI_001 | QBQI.33R7 | HCQBQI_001-IE000089 | LBBRC | HCLBBRC000-IN002041 | LQOBJ | HCLQOBJ001-CR000009
21610.3431 | QQBI_002 | QQBI.33R7 | HCQQBI_002-IE000291 | LQOBJ | HCLQOBJ001-CR000009 | LBARA | HCLBARA000-IN002016
21626.0031 | QBBI_004 | QBBI.A34R7 | HCQBBI_004-IE000627 | LBARA | HCLBARA000-IN002016 | LBBRA | HCLBBRA000-IN001003
21641.6631 | QBBI_004 | QBBI.B34R7 | HCQBBI_004-IE000628 | LBBRA | HCLBBRA000-IN001003 | LBARB | HCLBARB000-IN003025
21657.3231 | QBQI_000 | QBQI.34R7 | HCQBQI_000-IE000158 | LBARB | HCLBARB000-IN003025 | LQOAM | HCLQOAM001-CR000012
21663.7931 | QQBI_002 | QQBI.34L8 | HCQQBI_002-IE000293 | LQOAM | HCLQOAM001-CR000012 | LBBRA | HCLBBRA000-IN001025
21679.4531 | QBBI_004 | QBBI.B34L8 | HCQBBI_004-IE000629 | LBBRA | HCLBBRA000-IN001025 | LBARA | HCLBARA000-IN002017
21695.1131 | QBBI_004 | QBBI.A34L8 | HCQBBI_004-IE000630 | LBARA | HCLBARA000-IN002017 | LBBRC | HCLBBRC000-IN003005
21710.773090 | QBQI_001 | QBQI.34L8 | HCQBQI_001-IE000098 | LBBRC | HCLBBRC000-IN003005 | LQOBF | HCLQOBF001-CR000026
21717.2431 | QQBI_002 | QQBI.33L8 | HCQQBI_002-IE000294 | LQOBF | HCLQOBF001-CR000026 | LBARA | HCLBARA000-IN003021
21732.9031 | QBBI_004 | QBBI.B33L8 | HCQBBI_004-IE000631 | LBARA | HCLBARA000-IN003021 | LBBRA | HCLBBRA000-IN002050
21748.5631 | QBBI_004 | QBBI.A33L8 | HCQBBI_004-IE000632 | LBBRA | HCLBBRA000-IN002050 | LBARB | HCLBARB000-IN002523
21764.2231 | QBQI_000 | QBQI.33L8 | HCQBQI_001-IE000090 | LBARB | HCLBARB000-IN002523 | LQOAM | HCLQOAM001-CR000021
21770.6931 | QQBI_002 | QQBI.32L8 | HCQQBI_002-IE000295 | LQOAM | HCLQOAM001-CR000021 | LBBRA | HCLBBRA000-IN001027
21786.3531 | QBBI_004 | QBBI.B32L8 | HCQBBI_004-IE000633 | LBBRA | HCLBBRA000-IN001027 | LBARA | HCLBARA000-IN001139
21802.0131 | QBBI_004 | QBBI.A32L8 | HCQBBI_004-IE000634 | LBARA | HCLBARA000-IN001139 | LBBRC | HCLBBRC000-IN001033
21817.6731 | QBQI_001 | QBQI.32L8 | HCQBQI_000-IE000159 | LBBRC | HCLBBRC000-IN001033 | LQOAV | HCLQOAV001-CR000077
21824.1431 | QQBI_002 | QQBI.31L8 | HCQQBI_002-IE000296 | LQOAV | HCLQOAV001-CR000077 | LBARA | HCLBARA000-IN003064
21839.8031 | QBBI_004 | QBBI.B31L8 | HCQBBI_004-IE000635 | LBARA | HCLBARA000-IN003064 | LBBRA | HCLBBRA000-IN002044
21855.4631 | QBBI_004 | QBBI.A31L8 | HCQBBI_004-IE000636 | LBBRA | HCLBBRA000-IN002044 | LBARB | HCLBARB000-IN001140
21871.1231 | QBQI_000 | QBQI.31L8 | HCQBQI_001-IE000091 | LBARB | HCLBARB000-IN001140 | LQOAG | HCLQOAG001-CR000015
21877.5931 | QQBI_002 | QQBI.30L8 | HCQQBI_002-IE000297 | LQOAG | HCLQOAG001-CR000015 | LBBRA | HCLBBRA000-IN003018
21893.2531 | QBBI_004 | QBBI.B30L8 | HCQBBI_004-IE000637 | LBBRA | HCLBBRA000-IN003018 | LBARA | HCLBARA000-IN001066
21908.9131 | QBBI_004 | QBBI.A30L8 | HCQBBI_004-IE000638 | LBARA | HCLBARA000-IN001066 | LBBRC | HCLBBRC000-IN003011
21924.5731 | QBQI_001 | QBQI.30L8 | HCQBQI_000-IE000160 | LBBRC | HCLBBRC000-IN003011 | LQOBF | HCLQOBF001-CR000007
21931.0431 | QQBI_002 | QQBI.29L8 | HCQQBI_002-IE000298 | LQOBF | HCLQOBF001-CR000007 | LBARA | HCLBARA000-IN002033
21946.7031 | QBBI_004 | QBBI.B29L8 | HCQBBI_004-IE000639 | LBARA | HCLBARA000-IN002033 | LBBRA | HCLBBRA000-IN001009
21962.3631 | QBBI_004 | QBBI.A29L8 | HCQBBI_004-IE000640 | LBBRA | HCLBBRA000-IN001009 | LBARB | HCLBARB000-IN001136
21978.0231 | QBQI_000 | QBQI.29L8 | HCQBQI_001-IE000092 | LBARB | HCLBARB000-IN001136 | LQOAM | HCLQOAM001-CR000013
21984.4931 | QQBI_002 | QQBI.28L8 | HCQQBI_002-IE000299 | LQOAM | HCLQOAM001-CR000013 | LBBRA | HCLBBRA000-IN003015
22000.1531 | QBBI_004 | QBBI.B28L8 | HCQBBI_004-IE000641 | LBBRA | HCLBBRA000-IN003015 | LBARA | HCLBARA000-IN002038
22015.8131 | QBBI_004 | QBBI.A28L8 | HCQBBI_004-IE000642 | LBARA | HCLBARA000-IN002038 | LBBRC | HCLBBRC000-IN003013
22031.4731 | QBQI_001 | QBQI.28L8 | HCQBQI_000-IE000161 | LBBRC | HCLBBRC000-IN003013 | LQASE | HCLQASE001-CR000082
22037.9431 | QQBI_002 | QQBI.27L8 | HCQQBI_002-IE000300 | LQASE | HCLQASE001-CR000082 | LBARA | HCLBARA000-IN003057
22053.6031 | QBBI_004 | QBBI.B27L8 | HCQBBI_004-IE000643 | LBARA | HCLBARA000-IN003057 | LBBRA | HCLBBRA000-IN001018
22069.2631 | QBBI_004 | QBBI.A27L8 | HCQBBI_004-IE000644 | LBBRA | HCLBBRA000-IN001018 | LBARB | HCLBARB000-IN002030
22084.9231 | QBQI_000 | QBQI.27L8 | HCQBQI_001-IE000093 | LBARB | HCLBARB000-IN002030 | LQOAG | HCLQOAG001-CR000020
22091.3931 | QQBI_002 | QQBI.26L8 | HCQQBI_002-IE000301 | LQOAG | HCLQOAG001-CR000020 | LBBRA | HCLBBRA000-IN001040
22107.0531 | QBBI_004 | QBBI.B26L8 | HCQBBI_004-IE000645 | LBBRA | HCLBBRA000-IN001040 | LBARA | HCLBARA000-IN003044
22122.7131 | QBBI_004 | QBBI.A26L8 | HCQBBI_004-IE000646 | LBARA | HCLBARA000-IN003044 | LBBRC | HCLBBRC000-IN003259
22138.3731 | QBQI_001 | QBQI.26L8 | HCQBQI_000-IE000162 | LBBRC | HCLBBRC000-IN003259 | LQOBN | HCLQOBN001-CR000029
22144.8431 | QQBI_002 | QQBI.25L8 | HCQQBI_002-IE000302 | LQOBN | HCLQOBN001-CR000029 | LBARA | HCLBARA000-IN001135
22160.5031 | QBBI_004 | QBBI.B25L8 | HCQBBI_004-IE000647 | LBARA | HCLBARA000-IN001135 | LBBRA | HCLBBRA000-IN002010
22176.1631 | QBBI_004 | QBBI.A25L8 | HCQBBI_004-IE000648 | LBBRA | HCLBBRA000-IN002010 | LBARB | HCLBARB000-IN002037
22191.8231 | QBQI_000 | QBQI.25L8 | HCQBQI_001-IE000094 | LBARB | HCLBARB000-IN002037 | LQOAG | HCLQOAG001-CR000018
22198.2931 | QQBI_002 | QQBI.24L8 | HCQQBI_002-IE000303 | LQOAG | HCLQOAG001-CR000018 | LBBRA | HCLBBRA000-IN003037
22213.9531 | QBBI_004 | QBBI.B24L8 | HCQBBI_004-IE000649 | LBBRA | HCLBBRA000-IN003037 | LBARA | HCLBARA000-IN001141
22229.6131 | QBBI_004 | QBBI.A24L8 | HCQBBI_004-IE000650 | LBARA | HCLBARA000-IN001141 | LBBRD | HCLBBRD000-IN002021
22245.2731 | QBQI_005 | QBQI.24L8 | HCQBQI_000-IE000163 | LBBRD | HCLBBRD000-IN002021 | LQASF | HCLQASF001-CR000083
22251.7431 | QQBI_002 | QQBI.23L8 | HCQQBI_002-IE000304 | LQASF | HCLQASF001-CR000083 | LBARA | HCLBARA000-IN001137
22267.4031 | QBBI_004 | QBBI.B23L8 | HCQBBI_004-IE000651 | LBARA | HCLBARA000-IN001137 | LBBRA | HCLBBRA000-IN002022
22283.0631 | QBBI_004 | QBBI.A23L8 | HCQBBI_004-IE000652 | LBBRA | HCLBBRA000-IN002022 | LBARB | HCLBARB000-IN001138
22298.7231 | QBQI_000 | QBQI.23L8 | HCQBQI_005-IE000065 | LBARB | HCLBARB000-IN001138 | LQOAG | HCLQOAG001-CR000004
22305.1931 | QQBI_002 | QQBI.22L8 | HCQQBI_002-IE000305 | LQOAG | HCLQOAG001-CR000004 | LBBRA | HCLBBRA000-IN002065
22320.8531 | QBBI_004 | QBBI.B22L8 | HCQBBI_004-IE000653 | LBBRA | HCLBBRA000-IN002065 | LBARA | HCLBARA000-IN003046
22336.5131 | QBBI_004 | QBBI.A22L8 | HCQBBI_004-IE000654 | LBARA | HCLBARA000-IN003046 | LBBRD | HCLBBRD000-IN003263
22352.1731 | QBQI_005 | QBQI.22L8 | HCQBQI_000-IE000164 | LBBRD | HCLBBRD000-IN003263 | LQATK | HCLQATK001-CR000048
22358.6431 | QQBI_002 | QQBI.21L8 | HCQQBI_002-IE000306 | LQATK | HCLQATK001-CR000048 | LBARA | HCLBARA000-IN001142
22374.3031 | QBBI_004 | QBBI.B21L8 | HCQBBI_004-IE000655 | LBARA | HCLBARA000-IN001142 | LBBRA | HCLBBRA000-IN002007
22389.9631 | QBBI_004 | QBBI.A21L8 | HCQBBI_004-IE000656 | LBBRA | HCLBBRA000-IN002007 | LBARB | HCLBARB000-IN002036
22405.6231 | QBQI_000 | QBQI.21L8 | HCQBQI_005-IE000066 | LBARB | HCLBARB000-IN002036 | LQATH | HCLQATH001-CR000011
22412.0931 | QQBI_002 | QQBI.20L8 | HCQQBI_002-IE000307 | LQATH | HCLQATH001-CR000011 | LBBRA | HCLBBRA000-IN001015
22427.7531 | QBBI_004 | QBBI.B20L8 | HCQBBI_004-IE000657 | LBBRA | HCLBBRA000-IN001015 | LBARA | HCLBARA000-IN002028
22443.4131 | QBBI_004 | QBBI.A20L8 | HCQBBI_004-IE000658 | LBARA | HCLBARA000-IN002028 | LBBRD | HCLBBRD000-IN001029
22459.0731 | QBQI_005 | QBQI.20L8 | HCQBQI_000-IE000165 | LBBRD | HCLBBRD000-IN001029 | LQATO | HCLQATO001-CR000084
22465.5431 | QQBI_002 | QQBI.19L8 | HCQQBI_002-IE000308 | LQATO | HCLQATO001-CR000084 | LBARA | HCLBARA000-IN003048
22481.2031 | QBBI_004 | QBBI.B19L8 | HCQBBI_004-IE000659 | LBARA | HCLBARA000-IN003048 | LBBRA | HCLBBRA000-IN003270
22496.8631 | QBBI_004 | QBBI.A19L8 | HCQBBI_004-IE000660 | LBBRA | HCLBBRA000-IN003270 | LBARB | HCLBARB000-IN003061
22512.5231 | QBQI_000 | QBQI.19L8 | HCQBQI_005-IE000067 | LBARB | HCLBARB000-IN003061 | LQATH | HCLQATH001-CR000044
22518.9931 | QQBI_002 | QQBI.18L8 | HCQQBI_002-IE000309 | LQATH | HCLQATH001-CR000044 | LBBRA | HCLBBRA000-IN001036
22534.6531 | QBBI_004 | QBBI.B18L8 | HCQBBI_004-IE000661 | LBBRA | HCLBBRA000-IN001036 | LBARA | HCLBARA000-IN003049
22550.3131 | QBBI_004 | QBBI.A18L8 | HCQBBI_004-IE000662 | LBARA | HCLBARA000-IN003049 | LBBRD | HCLBBRD000-IN003012
22565.9731 | QBQI_005 | QBQI.18L8 | HCQBQI_000-IE000166 | LBBRD | HCLBBRD000-IN003012 | LQATK | HCLQATK001-CR000042
22572.4431 | QQBI_002 | QQBI.17L8 | HCQQBI_002-IE000310 | LQATK | HCLQATK001-CR000042 | LBARA | HCLBARA000-IN002042
22588.1031 | QBBI_004 | QBBI.B17L8 | HCQBBI_004-IE000663 | LBARA | HCLBARA000-IN002042 | LBBRA | HCLBBRA000-IN002006
22603.7631 | QBBI_004 | QBBI.A17L8 | HCQBBI_004-IE000664 | LBBRA | HCLBBRA000-IN002006 | LBARB | HCLBARB000-IN002056
22619.4231 | QBQI_000 | QBQI.17L8 | HCQBQI_005-IE000068 | LBARB | HCLBARB000-IN002056 | LQATH | HCLQATH001-CR000046
22625.8931 | QQBI_002 | QQBI.16L8 | HCQQBI_002-IE000311 | LQATH | HCLQATH001-CR000046 | LBBRA | HCLBBRA000-IN003003
22641.5531 | QBBI_004 | QBBI.B16L8 | HCQBBI_004-IE000665 | LBBRA | HCLBBRA000-IN003003 | LBARA | HCLBARA000-IN003063
22657.2131 | QBBI_004 | QBBI.A16L8 | HCQBBI_004-IE000666 | LBARA | HCLBARA000-IN003063 | LBBRD | HCLBBRD000-IN003504
22672.8731 | QBQI_005 | QBQI.16L8 | HCQBQI_000-IE000167 | LBBRD | HCLBBRD000-IN003504 | LQATO | HCLQATO001-CR000049
22679.3431 | QQBI_002 | QQBI.15L8 | HCQQBI_002-IE000312 | LQATO | HCLQATO001-CR000049 | LBARA | HCLBARA000-IN003009
22695.0031 | QBBI_004 | QBBI.B15L8 | HCQBBI_004-IE000667 | LBARA | HCLBARA000-IN003009 | LBBRA | HCLBBRA000-IN002014
22710.6631 | QBBI_004 | QBBI.A15L8 | HCQBBI_004-IE000668 | LBBRA | HCLBBRA000-IN002014 | LBARB | HCLBARB000-IN003058
22726.3231 | QBQI_000 | QBQI.15L8 | HCQBQI_005-IE000069 | LBARB | HCLBARB000-IN003058 | LQATH | HCLQATH001-CR000045
22732.7931 | QQBI_002 | QQBI.14L8 | HCQQBI_002-IE000313 | LQATH | HCLQATH001-CR000045 | LBBRA | HCLBBRA000-IN001519
22748.4531 | QBBI_004 | QBBI.B14L8 | HCQBBI_004-IE000669 | LBBRA | HCLBBRA000-IN001519 | LBARA | HCLBARA000-IN002031
22764.1131 | QBBI_004 | QBBI.A14L8 | HCQBBI_004-IE000670 | LBARA | HCLBARA000-IN002031 | LBBRD | HCLBBRD000-IN003038
22779.7731 | QBQI_005 | QBQI.14L8 | HCQBQI_000-IE000168 | LBBRD | HCLBBRD000-IN003038 | LQATK | HCLQATK001-CR000349
22786.2431 | QQBI_002 | QQBI.13L8 | HCQQBI_002-IE000314 | LQATK | HCLQATK001-CR000349 | LBARA | HCLBARA000-IN003065
22801.9031 | QBBI_004 | QBBI.B13L8 | HCQBBI_004-IE000671 | LBARA | HCLBARA000-IN003065 | LBBRA | HCLBBRA000-IN003002
22817.5631 | QBBI_004 | QBBI.A13L8 | HCQBBI_004-IE000672 | LBBRA | HCLBBRA000-IN003002 | LBARB | HCLBARB000-IN003029
22833.2231 | QBQI_000 | QBQI.13L8 | HCQBQI_005-IE000070 | LBARB | HCLBARB000-IN003029 | LQATH | HCLQATH001-CR000043
22839.6931 | QQBI_002 | QQBI.12L8 | HCQQBI_002-IE000315 | LQATH | HCLQATH001-CR000043 | LBBRA | HCLBBRA000-IN001017
22855.3531 | QBBI_004 | QBBI.B12L8 | HCQBBI_004-IE000673 | LBBRA | HCLBBRA000-IN001017 | LBARA | HCLBARA000-IN001133
22871.0131 | QBBI_004 | QBBI.A12L8 | HCQBBI_004-IE000674 | LBARA | HCLBARA000-IN001133 | LBBRD | HCLBBRD000-IN003034
22886.6731 | QBQI_005 | QBQI.12L8 | HCQBQI_000-IE000169 | LBBRD | HCLBBRD000-IN003034 | LQTCG
22894.4181 | QQEI_006 | QQEI.11L8 | HCQQEI_006-IE000007 | LQTCG |  | LEBR | HCLEBR_000-CR000001
22907.1928 | QEBI_007 | QEBI.11L8 | HCQEBI_007-IE000007 | LEBR | HCLEBR_000-CR000001 | LBARA | HCLBARA000-IN003066
22922.8528 | QBBI_004 | QBBI.11L8 | HCQBBI_004-IE000675 | LBARA | HCLBARA000-IN003066 | LBBRP | HCLBBRP000-IN003264
22938.5128 | QBQI_010 | QBQI.11L8 | HCQBQI_005-IE000071 | LBBRP | HCLBBRP000-IN003264 | LQNCE | HCLQNCE001-CR000602
22946.2578 | QQBI_102 | QQBI.10L8 | HCQQBI_102-IE000008 | LQNCE | HCLQNCE001-CR000602 | LBARE | HCLBARE000-IN003053
22961.9178 | QBBI_104 | QBBI.10L8 | HCQBBI_104-IE000008 | LBARE | HCLBARE000-IN003053 | LBBRG | HCLBBRG000-IN001030
22977.5778 | QBQI_025 | QBQI.10L8 | HCQBQI_010-IE000004 | LBBRG | HCLBBRG000-IN001030 | LQNJF | HCLQNJF001-CR000613
22986.7228 | QQBI_092 | QQBI.9L8 | HCQQBI_092-IE000010 | LQNJF | HCLQNJF001-CR000613 | LBARE | HCLBARE000-IN003062
23002.3828 | QBBI_094 | QBBI.9L8 | HCQBBI_094-IE000010 | LBARE | HCLBARE000-IN003062 | LBBRF | HCLBBRF000-IN003036
23018.0428 | QBQI_030 | QBQI.9L8 | HCQBQI_025-IE000002 | LBBRF | HCLBBRF000-IN003036 | LQNCE | HCLQNCE001-CR000601
23025.7878 | QQBI_082 | QQBI.8L8 | HCQQBI_082-IE000006 | LQNCE | HCLQNCE001-CR000601 | LBARE | HCLBARE000-IN003051
23041.4478 | QBBI_084 | QBBI.8L8 | HCQBBI_084-IE000010 | LBARE | HCLBARE000-IN003051 | LBBRQ | HCLBBRQ000-IN003016
23057.1078 | QBQI_041 | QBQI.8L8 | HCQBQI_030-IE000005 | LBBRQ | HCLBBRQ000-IN003016 | LQNFI | HCLQNFI001-CR000604
23067.2278 | QQDI_015 | QQDI.7L8 | HCQQDI_015-IE000003 | LQNFI | HCLQNFI001-CR000604 | DFBAO
23183.4498 | QQBM_043 | QQBM.4L8 | HCQQBM_043-IE000002 | LQYEB | HCLQYEB001-CR000607 | LBRCC | HCLBRCC001-BL000002
23257.5678 | QBDI_001 | QBDI.3L8 | HCQBDI_001-IE000001 | LBXA | HCLBX__001-BL000002 | DFBXG
23260.4208 | QDQI_004 | QDQI.3L8 | HCQDQI_004-IE000001 | DFBXG |  | LQXAF | HCLQXC_001-FL000003
23270.9608 | QQQI_002 | QQQI.2L8 | HCQQQI_002-IE000003 | LQXAF | HCLQXC_001-FL000003 | LQXBB | HCLQXB_001-FL000004
23284.6948 | QQQI_001 | QQQI.1L8 | HCQQQI_001-IE000003 | LQXBB | HCLQXB_001-FL000004 | LQXAB | HCLQXA_001-FL000001
13298.8336 | QQQI_001 | QQQI.1L5 | HCQQQI_001-IE000001 | LQXBB |  | LQXAB

## IC
INTERCONNECTIONS AVAILABILITY IN SECTOR 7-8
| MAGNETS | [8 empty] | INTERCONNECTIONS
SUB SECTOR | FUNCTIONAL POSITION NAME | MTF PART ID - ALLOCATED BY MED | ALLOCATION | DCUM RING START | DCUM RING END |  | QRL AVAILABILITY | MAGNET IN PLACE | INITIAL ALIGNEMENT + SMOOTHING (TS/SU web site) | DCUM RING START | FUNCTIONAL POSITION NAME (2006-01-18) | AVAILABILITY for preinspection
I | [10 empty] | QDQI.7R7
| LQTAC.7R7 | 0 | MQ .7R7 | 20255.3214 | 20263.0664 | 5 | 1 | 0 |  |  | QQBI.A8R7
| LBARA.8R7 | HCLBARA000-IN003026 | MB A.8R7 | 20263.0664 | 20278.7264 | 0 | 1 | 1 |  |  | QBBI.8R7
| LBBRB.8R7 | HCLBBRB000-IN001031 | MB B.8R7 | 20278.7264 | 20294.3864 | 0 | 1 | 1 |  |  | QBQI.8R7
H | LQTBB.8R7 |  | MQ .8R7 | 20294.3864 | 20302.1314 | 4 | 1 | 0 |  |  | QQBI.8R7
| LBARA.9R7 | HCLBARA000-IN003050 | MB A.9R7 | 20302.1314 | 20317.7914 | 0 | 1 | 1 |  |  | QBBI.9R7
| LBBRC.9R7 | HCLBBRC000-IN001044 | MB B.9R7 | 20317.7914 | 20333.4514 | 0 | 1 | 1 |  |  | QBQI.9R7
| LQTEC.9R7 |  | MQ .9R7 | 20333.4514 | 20342.5964 | 3 | 1 | 0 |  |  | QQBI.9R7
| LBARA.10R7 | HCLBARA000-IN001052 | MB A10R7 | 20342.5964 | 20358.2564 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBBI.10R7 | QBBI.10R7
| LBBRB.10R7 | HCLBBRB000-IN001032 | MB B10R7 | 20358.2564 | 20373.9164 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBQI.10R7
| LQTBB.10R7 |  | MQ 10R7 | 20373.9164 | 20381.6614 | 2 | 1 | 0 |  |  | QQBI.10R7
| LBARA.11R7 | HCLBARA000-IN003022 | MB A11R7 | 20381.6614 | 20397.3214 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBBI.11R7 | QBBI.11R7
| LBBRA.11R7 | HCLBBRA000-IN001034 | MB B11R7 | 20397.3214 | 20412.9814 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBEI.11R7
| LEDR..11R7 | HCLEDR_000-CR000001 | MB C11R7 | 20412.9814 | 20426.6981 | 0 | 1 | 1 |  |  | QEQI.11R7
| LQTCH.11R7 |  | MQ 11R7 | 20426.6981 | 20434.4431 | 0 | 1 | 1 |  |  | QQBI.11R7
| LBARA.12R7 | HCLBARA000-IN002018 | MB A12R7 | 20434.4431 | 20450.1031 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBBI.A12R7 | QBBI.A12R7
| LBBRA.12R7 | HCLBBRA000-IN001010 | MB B12R7 | 20450.1031 | 20465.7631 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBBI.B12R7 | QBBI.B12R7
| LBARB.12R7 | HCLBARB000-IN002039 | MB C12R7 | 20465.7631 | 20481.4231 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBQI.12R7 | QBQI.12R7
| LQATH.12R7 | HCLQATH001-CR000245 | MQ 12R7 | 20481.4231 | 20487.8931 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QQBI.12R7 | QQBI.12R7
| LBBRA.13R7 | HCLBBRA000-IN003041 | MB A13R7 | 20487.8931 | 20503.5531 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBBI.A13R7 | QBBI.A13R7
| LBARA.13R7 | HCLBARA000-IN001054 | MB B13R7 | 20503.5531 | 20519.2131 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBBI.B13R7 | QBBI.B13R7
| LBBRC.13R7 | HCLBBRC000-IN003019 | MB C13R7 | 20519.2131 | 20534.8731 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBQI.13R7 | QBQI.13R7
| LQATM.13R7 | HCLQATM001-CR000019 | MQ 13R7 | 20534.8731 | 20541.3431 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QQBI.13R7 | QQBI.13R7
| LBARA.14R7 | HCLBARA000-IN003030 | MB A14R7 | 20541.3431 | 20557.0031 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBBI.A14R7 | QBBI.A14R7
| LBBRA.14R7 | HCLBBRA000-IN001004 | MB B14R7 | 20557.0031 | 20572.6631 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBBI.B14R7 | QBBI.B14R7
| LBARB.14R7 | HCLBARB000-IN002015 | MB C14R7 | 20572.6631 | 20588.3231 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBQI.14R7 | QBQI.14R7
| LQATH.14R7 | HCLQATH001-CR000037 | MQ 14R7 | 20588.3231 | 20594.7931 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QQBI.14R7 | QQBI.14R7
| LBBRA.15R7 | HCLBBRA000-IN003020 | MB A15R7 | 20594.7931 | 20610.4531 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBBI.A15R7 | QBBI.A15R7
| LBARA.15R7 | HCLBARA000-IN003010 | MB B15R7 | 20610.4531 | 20626.1131 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBBI.B15R7 | QBBI.B15R7
| LBBRC.15R7 | HCLBBRC000-IN001022 | MB C15R7 | 20626.1131 | 20641.7731 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QBQI.15R7 | QBQI.15R7
| LQATQ.15R7 |  | MQ 15R7 | 20641.7731 | 20648.2431 | 0 | 1 | 1 | 2006-03-10 | 2006-03-10 | QQBI.15R7 | QQBI.15R7
| LBARA.16R7 | HCLBARA000-IN003279 | MB A16R7 | 20648.2431 | 20663.9031 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.A16R7 | QBBI.A16R7
| LBBRA.16R7 | HCLBBRA000-IN001008 | MB B16R7 | 20663.9031 | 20679.5631 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B16R7 | QBBI.B16R7
| LBARB.16R7 | HCLBARB000-IN003028 | MB C16R7 | 20679.5631 | 20695.2231 | 0 | 1 | 1 | 2006-04-27 |  | QBQI.16R7 | QBQI.16R7
| LQATH.16R7 | HCLQATH001-CR000041 | MQ 16R7 | 20695.2231 | 20701.6931 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.16R7 | QQBI.16R7
G | LBBRA.17R7 | HCLBBRA000-IN002008 | MB A17R7 | 20701.6931 | 20717.3531 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.A17R7 | QBBI.A17R7
| LBARA.17R7 | HCLBARA000-IN003055 | MB B17R7 | 20717.3531 | 20733.0131 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B17R7 | QBBI.B17R7
| LBBRC.17R7 | HCLBBRC000-IN001035 | MB C17R7 | 20733.0131 | 20748.6731 | 0 | 1 | 1 | 2006-04-27 |  | QBQI.17R7 | QBQI.17R7
| LQATM.17R7 | HCLQATM001-CR000039 | MQ 17R7 | 20748.6731 | 20755.1431 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.17R7 | QQBI.17R7
| LBARA.18R7 | HCLBARA000-IN003006 | MB A18R7 | 20755.1431 | 20770.8031 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.A18R7 | QBBI.A18R7
| LBBRA.18R7 | HCLBBRA000-IN001021 | MB B18R7 | 20770.8031 | 20786.4631 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B18R7 | QBBI.B18R7
| LBARB.18R7 | HCLBARB000-IN002029 | MB C18R7 | 20786.4631 | 20802.1231 | 0 | 1 | 1 | 2006-04-27 |  | QBQI.18R7 | QBQI.18R7
| LQATH.18R7 | HCLQATH001-CR000031 | MQ 18R7 | 20802.1231 | 20808.5931 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.18R7 | QQBI.18R7
| LBBRA.19R7 | HCLBBRA000-IN002004 | MB A19R7 | 20808.5931 | 20824.2531 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.A19R7 | QBBI.A19R7
| LBARA.19R7 | HCLBARA000-IN001045 | MB B19R7 | 20824.2531 | 20839.9131 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B19R7 | QBBI.B19R7
| LBBRC.19R7 | HCLBBRC000-IN002009 | MB C19R7 | 20839.9131 | 20855.5731 | 0 | 1 | 1 | 2006-04-27 |  | QBQI.19R7 | QBQI.19R7
| LQATQ.19R7 |  | MQ 19R7 | 20855.5731 | 20862.0431 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.19R7 | QQBI.19R7
| LBARA.20R7 | HCLBARA000-IN003054 | MB A20R7 | 20862.0431 | 20877.7031 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.A20R7 | QBBI.A20R7
| LBBRA.20R7 | HCLBBRA000-IN002002 | MB B20R7 | 20877.7031 | 20893.3631 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B20R7 | QBBI.B20R7
| LBARB.20R7 | HCLBARB000-IN003043 | MB C20R7 | 20893.3631 | 20909.0231 | 0 | 1 | 1 | 2006-04-27 |  | QBQI.20R7 | QBQI.20R7
| LQATH.20R7 | HCLQATH001-CR000249 | MQ 20R7 | 20909.0231 | 20915.4931 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.20R7 | QQBI.20R7
| LBBRA.21R7 | HCLBBRA000-IN003014 | MB A21R7 | 20915.4931 | 20931.1531 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.A21R7 | QBBI.A21R7
| LBARA.21R7 | HCLBARA000-IN001012 | MB B21R7 | 20931.1531 | 20946.8131 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B21R7 | QBBI.B21R7
| LBBRC.21R7 | HCLBBRC000-IN001024 | MB C21R7 | 20946.8131 | 20962.4731 | 0 | 1 | 1 | 2006-05-04 |  | QBQI.21R7 | QBQI.21R7
| LQATM.21R7 | HCLQATM001-CR000040 | MQ 21R7 | 20962.4731 | 20968.9431 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.21R7 | QQBI.21R7
| LBARA.22R7 | HCLBARA000-IN003007 | MB A22R7 | 20968.9431 | 20984.6031 | 0 | 1 | 1 | 2006-05-12 |  | QBBI.A22R7 | QBBI.A22R7
| LBBRA.22R7 | HCLBBRA000-IN001023 | MB B22R7 | 20984.6031 | 21000.2631 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B22R7 | QBBI.B22R7
| LBARB.22R7 | HCLBARB000-IN002020 | MB C22R7 | 21000.2631 | 21015.9231 | 0 | 1 | 1 | 2006-04-27 |  | QBQI.22R7 | QBQI.22R7
| LQOAG.22R7 | HCLQOAG001-CR000002 | MQ 22R7 | 21015.9231 | 21022.3931 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.22R7 | QQBI.22R7
| LBBRA.23R7 | HCLBBRA000-IN003042 | MB A23R7 | 21022.3931 | 21038.0531 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.A23R7 | QBBI.A23R7
| LBARA.23R7 | HCLBARA000-IN001014 | MB B23R7 | 21038.0531 | 21053.7131 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B23R7 | QBBI.B23R7
| LBBRC.23R7 | HCLBBRC000-IN001039 | MB C23R7 | 21053.7131 | 21069.3731 | 0 | 1 | 1 | 2006-04-27 |  | QBQI.23R7 | QBQI.23R7
| LQASE.23R7 |  | MQ 23R7 | 21069.3731 | 21075.8431 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.23R7 | QQBI.23R7
| LBARA.24R7 | HCLBARA000-IN003027 | MB A24R7 | 21075.8431 | 21091.5031 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.A24R7 | QBBI.A24R7
| LBBRA.24R7 | HCLBBRA000-IN001020 | MB B24R7 | 21091.5031 | 21107.1631 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B24R7 | QBBI.B24R7
| LBARB.24R7 | HCLBARB000-IN003008 | MB C24R7 | 21107.1631 | 21122.8231 | 0 | 1 | 1 | 2006-04-27 |  | QBQI.24R7 | QBQI.24R7
| LQOAG.24R7 | HCLQOAG001-CR000016 | MQ 24R7 | 21122.8231 | 21129.2931 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.24R7 | QQBI.24R7
F | LBBRA.25R7 | HCLBBRA000-IN002012 | MB A25R7 | 21129.2931 | 21144.9531 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.A25R7 | QBBI.A25R7
| LBARA.25R7 | HCLBARA000-IN001051 | MB B25R7 | 21144.9531 | 21160.6131 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B25R7 | QBBI.B25R7
| LBBRC.25R7 | HCLBBRC000-IN001006 | MB C25R7 | 21160.6131 | 21176.2731 | 0 | 1 | 1 | 2006-04-27 |  | QBQI.25R7 | QBQI.25R7
| LQOAR.25R7 | HCLQOAR001-CR000003 | MQ 25R7 | 21176.2731 | 21182.7431 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.25R7 | QQBI.25R7
| LBARA.26R7 | HCLBARA000-IN001053 | MB A26R7 | 21182.7431 | 21198.4031 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.A26R7 | QBBI.A26R7
| LBBRA.26R7 | HCLBBRA000-IN001038 | MB B26R7 | 21198.4031 | 21214.0631 | 0 | 1 | 1 | 2006-04-27 |  | QBBI.B26R7 | QBBI.B26R7
| LBARB.26R7 | HCLBARB000-IN001055 | MB C26R7 | 21214.0631 | 21229.7231 | 0 | 1 | 1 | 2006-05-04 |  | QBQI.26R7 | QBQI.26R7
| LQOAG.26R7 | HCLQOAG001-CR000017 | MQ 26R7 | 21229.7231 | 21236.1931 | 0 | 1 | 1 | 2006-04-27 |  | QQBI.26R7 | QQBI.26R7
| LBBRA.27R7 | HCLBBRA000-IN003039 | MB A27R7 | 21236.1931 | 21251.8531 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBBI.A27R7 | QBBI.A27R7
| LBARA.27R7 | HCLBARA000-IN003024 | MB B27R7 | 21251.8531 | 21267.5131 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBBI.B27R7 | QBBI.B27R7
| LBBRC.27R7 | HCLBBRC000-IN001049 | MB C27R7 | 21267.5131 | 21283.1731 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBQI.27R7 | QBQI.27R7
| LQASE.27R7 | HCLQASE001-CR000078 | MQ 27R7 | 21283.1731 | 21289.6431 | 0 | 1 | 1 | 2006-05-17 | 2006-03-31 | QQBI.27R7 | QQBI.27R7
| LBARA.28R7 | HCLBARA000-IN002034 | MB A28R7 | 21289.6431 | 21305.3031 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBBI.A28R7 | QBBI.A28R7
| LBBRA.28R7 | HCLBBRA000-IN002048 | MB B28R7 | 21305.3031 | 21320.9631 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBBI.B28R7 | QBBI.B28R7
| LBARB.28R7 | HCLBARB000-IN002011 | MB C28R7 | 21320.9631 | 21336.6231 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBQI.28R7 | QBQI.28R7
| LQOAG.28R7 | HCLQOAG001-CR000023 | MQ 28R7 | 21336.6231 | 21343.0931 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QQBI.28R7 | QQBI.28R7
| LBBRA.29R7 | HCLBBRA000-IN001042 | MB A29R7 | 21343.0931 | 21358.7531 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBBI.A29R7 | QBBI.A29R7
| LBARA.29R7 | HCLBARA000-IN001013 | MB B29R7 | 21358.7531 | 21374.4131 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBBI.B29R7 | QBBI.B29R7
| LBBRC.29R7 | HCLBBRC000-IN003017 | MB C29R7 | 21374.4131 | 21390.0731 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBQI.29R7 | QBQI.29R7
| LQOBF.29R7 | HCLQOBF001-CR000014 | MQ 29R7 | 21390.0731 | 21396.5431 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QQBI.29R7 | QQBI.29R7
| LBARA.30R7 | HCLBARA000-IN002019 | MB A30R7 | 21396.5431 | 21412.2031 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBBI.A30R7 | QBBI.A30R7
| LBBRA.30R7 | HCLBBRA000-IN001007 | MB B30R7 | 21412.2031 | 21427.8631 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBBI.B30R7 | QBBI.B30R7
| LBARB.30R7 | HCLBARB000-IN002027 | MB C30R7 | 21427.8631 | 21443.5231 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBQI.30R7 | QBQI.30R7
| LQOAM.30R7 | HCLQOAM001-CR000008 | MQ 30R7 | 21443.5231 | 21449.9931 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QQBI.30R7 | QQBI.30R7
| LBBRA.31R7 | HCLBBRA000-IN001041 | MB A31R7 | 21449.9931 | 21465.6531 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBBI.A31R7 | QBBI.A31R7
| LBARA.31R7 | HCLBARA000-IN002026 | MB B31R7 | 21465.6531 | 21481.3131 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBBI.B31R7 | QBBI.B31R7
| LBBRC.31R7 | HCLBBRC000-IN001028 | MB C31R7 | 21481.3131 | 21496.9731 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBQI.31R7 | QBQI.31R7
| LQOAV.31R7 | HCLQOAV001-CR000076 | MQ 31R7 | 21496.9731 | 21503.4431 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QQBI.31R7 | QQBI.31R7
| LBARA.32R7 | HCLBARA000-IN003052 | MB A32R7 | 21503.4431 | 21519.1031 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.A32R7 | QBBI.A32R7
| LBBRA.32R7 | HCLBBRA000-IN002052 | MB B32R7 | 21519.1031 | 21534.7631 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.B32R7 | QBBI.B32R7
| LBARB.32R7 | HCLBARB000-IN002005 | MB C32R7 | 21534.7631 | 21550.4231 | 0 | 1 | 1 | 2006-05-04 |  | QBQI.32R7 | QBQI.32R7
| LQOAG.32R7 | HCLQOAG001-CR000001 | MQ 32R7 | 21550.4231 | 21556.8931 | 0 | 1 | 1 | 2006-05-04 |  | QQBI.32R7 | QQBI.32R7
E | LBBRA.33R7 | HCLBBRA000-IN001016 | MB A33R7 | 21556.8931 | 21572.5531 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.A33R7 | QBBI.A33R7
| LBARA.33R7 | HCLBARA000-IN003023 | MB B33R7 | 21572.5531 | 21588.2131 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.B33R7 | QBBI.B33R7
| LBBRC.33R7 | HCLBBRC000-IN002041 | MB C33R7 | 21588.2131 | 21603.8731 | 0 | 1 | 1 | 2006-05-04 |  | QBQI.33R7 | QBQI.33R7
| LQOBJ.33R7 | HCLQOBJ001-CR000009 | MQ 33R7 | 21603.8731 | 21610.3431 | 0 | 1 | 1 | 2006-05-04 |  | QQBI.33R7 | QQBI.33R7
| LBARA.34R7 | HCLBARA000-IN002016 | MB A34R7 | 21610.3431 | 21626.0031 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.A34R7 | QBBI.A34R7
| LBBRA.34R7 | HCLBBRA000-IN001003 | MB B34R7 | 21626.0031 | 21641.6631 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.B34R7 | QBBI.B34R7
| LBARB.34R7 | HCLBARB000-IN003025 | MB C34R7 | 21641.6631 | 21657.3231 | 0 | 1 | 1 | 2006-05-04 |  | QBQI.34R7 | QBQI.34R7
| LQOAM.34R7 | HCLQOAM001-CR000012 | MQ 34R7 | 21657.3231 | 21663.7931 | 0 | 1 | 1 | 2006-05-04 |  | QQBI.34L8 | QQBI.34L8
| LBBRA.34L8 | HCLBBRA000-IN001025 | MB C34L8 | 21663.7931 | 21679.4531 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.B34L8 | QBBI.B34L8
| LBARA.34L8 | HCLBARA000-IN002017 | MB B34L8 | 21679.4531 | 21695.1131 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.A34L8 | QBBI.A34L8
| LBBRC.34L8 | HCLBBRC000-IN003005 | MB A34L8 | 21695.1131 | 21710.7731 | 0 | 1 | 1 | 2006-05-04 |  | QBQI.34L8 | QBQI.34L8
| LQOBF.33L8 | HCLQOBF001-CR000026 | MQ 33L8 | 21710.7731 | 21717.2431 | 0 | 1 | 1 | 2006-05-04 |  | QQBI.33L8 | QQBI.33L8
| LBARA.33L8 | HCLBARA000-IN003021 | MB C33L8 | 21717.2431 | 21732.9031 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.B33L8 | QBBI.B33L8
| LBBRA.33L8 | HCLBBRA000-IN002050 | MB B33L8 | 21732.9031 | 21748.5631 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.A33L8 | QBBI.A33L8
| LBARB.33L8 | HCLBARB000-IN002523 | MB A33L8 | 21748.5631 | 21764.2231 | 0 | 1 | 1 | 2006-05-04 |  | QBQI.33L8 | QBQI.33L8
D | LQOAM.32L8 | HCLQOAM001-CR000021 | MQ 32L8 | 21764.2231 | 21770.6931 | 0 | 1 | 1 | 2006-05-04 |  | QQBI.32L8 | QQBI.32L8
| LBBRA.32L8 | HCLBBRA000-IN001027 | MB C32L8 | 21770.6931 | 21786.3531 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.B32L8 | QBBI.B32L8
| LBARA.32L8 | HCLBARA000-IN001139 | MB B32L8 | 21786.3531 | 21802.0131 | 0 | 1 | 1 | 2006-05-04 |  | QBBI.A32L8 | QBBI.A32L8
| LBBRC.32L8 | HCLBBRC000-IN001033 | MB A32L8 | 21802.0131 | 21817.6731 | 0 | 1 | 1 | 2006-05-04 |  | QBQI.32L8 | QBQI.32L8
| LQOAV.31L8 | HCLQOAV001-CR000077 | MQ 31L8 | 21817.6731 | 21824.1431 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QQBI.31L8 | QQBI.31L8
| LBARA.31L8 | HCLBARA000-IN003064 | MB C31L8 | 21824.1431 | 21839.8031 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBBI.B31L8 | QBBI.B31L8
| LBBRA.31L8 | HCLBBRA000-IN002044 | MB B31L8 | 21839.8031 | 21855.4631 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBBI.A31L8 | QBBI.A31L8
| LBARB.31L8 | HCLBARB000-IN001140 | MB A31L8 | 21855.4631 | 21871.1231 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBQI.31L8 | QBQI.31L8
| LQOAG.30L8 | HCLQOAG001-CR000015 | MQ 30L8 | 21871.1231 | 21877.5931 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QQBI.30L8 | QQBI.30L8
| LBBRA.30L8 | HCLBBRA000-IN003018 | MB C30L8 | 21877.5931 | 21893.2531 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBBI.B30L8 | QBBI.B30L8
| LBARA.30L8 | HCLBARA000-IN001066 | MB B30L8 | 21893.2531 | 21908.9131 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBBI.A30L8 | QBBI.A30L8
| LBBRC.30L8 | HCLBBRC000-IN003011 | MB A30L8 | 21908.9131 | 21924.5731 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBQI.30L8 | QBQI.30L8
| LQOBF.29L8 | HCLQOBF001-CR000007 | MQ 29L8 | 21924.5731 | 21931.0431 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QQBI.29L8 | QQBI.29L8
| LBARA.29L8 | HCLBARA000-IN002033 | MB C29L8 | 21931.0431 | 21946.7031 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBBI.B29L8 | QBBI.B29L8
| LBBRA.29L8 | HCLBBRA000-IN001009 | MB B29L8 | 21946.7031 | 21962.3631 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBBI.A29L8 | QBBI.A29L8
| LBARB.29L8 | HCLBARB000-IN001136 | MB A29L8 | 21962.3631 | 21978.0231 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBQI.29L8 | QBQI.29L8
| LQOAM.28L8 | HCLQOAM001-CR000013 | MQ 28L8 | 21978.0231 | 21984.4931 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QQBI.28L8 | QQBI.28L8
| LBBRA.28L8 | HCLBBRA000-IN003015 | MB C28L8 | 21984.4931 | 22000.1531 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBBI.B28L8 | QBBI.B28L8
| LBARA.28L8 | HCLBARA000-IN002038 | MB B28L8 | 22000.1531 | 22015.8131 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBBI.A28L8 | QBBI.A28L8
| LBBRC.28L8 | HCLBBRC000-IN003013 | MB A28L8 | 22015.8131 | 22031.4731 | 0 | 1 | 1 | 2006-01-26 | 2006-01-26 | QBQI.28L8 | QBQI.28L8
| LQASE.27L8 | HCLQASE001-CR000082 | MQ 27L8 | 22031.4731 | 22037.9431 | 0 | 1 | 1 | 2006-05-04 |  | QQBI.27L8 | QQBI.27L8
| LBARA.27L8 | HCLBARA000-IN003057 | MB C27L8 | 22037.9431 | 22053.6031 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBBI.B27L8 | QBBI.B27L8
| LBBRA.27L8 | HCLBBRA000-IN001018 | MB B27L8 | 22053.6031 | 22069.2631 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBBI.A27L8 | QBBI.A27L8
| LBARB.27L8 | HCLBARB000-IN002030 | MB A27L8 | 22069.2631 | 22084.9231 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBQI.27L8 | QBQI.27L8
| LQOAG.26L8 | HCLQOAG001-CR000020 | MQ 26L8 | 22084.9231 | 22091.3931 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QQBI.26L8 | QQBI.26L8
| LBBRA.26L8 | HCLBBRA000-IN001040 | MB C26L8 | 22091.3931 | 22107.0531 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBBI.B26L8 | QBBI.B26L8
| LBARA.26L8 | HCLBARA000-IN003044 | MB B26L8 | 22107.0531 | 22122.7131 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBBI.A26L8 | QBBI.A26L8
| LBBRC.26L8 | HCLBBRC000-IN003259 | MB A26L8 | 22122.7131 | 22138.3731 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBQI.26L8 | QBQI.26L8
| LQOBN.25L8 | HCLQOBN001-CR000029 | MQ 25L8 | 22138.3731 | 22144.8431 | 0 | 1 | 1 | 2006-03-17 | 2006-03-17 | QQBI.25L8 | QQBI.25L8
| LBARA.25L8 | HCLBARA000-IN001135 | MB C25L8 | 22144.8431 | 22160.5031 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBBI.B25L8 | QBBI.B25L8
| LBBRA.25L8 | HCLBBRA000-IN002010 | MB B25L8 | 22160.5031 | 22176.1631 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBBI.A25L8 | QBBI.A25L8
| LBARB.25L8 | HCLBARB000-IN002037 | MB A25L8 | 22176.1631 | 22191.8231 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBQI.25L8 | QBQI.25L8
C | LQOAG.24L8 | HCLQOAG001-CR000018 | MQ 24L8 | 22191.8231 | 22198.2931 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QQBI.24L8 | QQBI.24L8
| LBBRA.24L8 | HCLBBRA000-IN003037 | MB C24L8 | 22198.2931 | 22213.9531 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBBI.B24L8 | QBBI.B24L8
| LBARA.24L8 | HCLBARA000-IN001141 | MB B24L8 | 22213.9531 | 22229.6131 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBBI.A24L8 | QBBI.A24L8
| LBBRD.24L8 | HCLBBRD000-IN002021 | MB A24L8 | 22229.6131 | 22245.2731 | 0 | 1 | 1 | 2006-01-20 | 2006-01-20 | QBQI.24L8 | QBQI.24L8
| LQASF.23L8 | HCLQASF001-CR000083 | MQ 23L8 | 22245.2731 | 22251.7431 | 0 | 1 | 1 | 2006-02-16 | 2006-02-16 | QQBI.23L8 | QQBI.23L8
| LBARA.23L8 | HCLBARA000-IN001137 | MB C23L8 | 22251.7431 | 22267.4031 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QBBI.B23L8 | QBBI.B23L8
| LBBRA.23L8 | HCLBBRA000-IN002022 | MB B23L8 | 22267.4031 | 22283.0631 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QBBI.A23L8 | QBBI.A23L8
| LBARB.23L8 | HCLBARB000-IN001138 | MB A23L8 | 22283.0631 | 22298.7231 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QBQI.23L8 | QBQI.23L8
| LQOAG.22L8 | HCLQOAG001-CR000004 | MQ 22L8 | 22298.7231 | 22305.1931 | 0 | 1 | 1 | 2006-02-16 | 2006-02-16 | QQBI.22L8 | QQBI.22L8
| LBBRA.22L8 | HCLBBRA000-IN002065 | MB C22L8 | 22305.1931 | 22320.8531 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QBBI.B22L8 | QBBI.B22L8
| LBARA.22L8 | HCLBARA000-IN003046 | MB B22L8 | 22320.8531 | 22336.5131 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QBBI.A22L8 | QBBI.A22L8
| LBBRD.22L8 | HCLBBRD000-IN003263 | MB A22L8 | 22336.5131 | 22352.1731 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QBQI.22L8 | QBQI.22L8
| LQATK.21L8 | HCLQATK001-CR000048 | MQ 21L8 | 22352.1731 | 22358.6431 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QQBI.21L8 | QQBI.21L8
| LBARA.21L8 | HCLBARA000-IN001142 | MB C21L8 | 22358.6431 | 22374.3031 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QBBI.B21L8 | QBBI.B21L8
| LBBRA.21L8 | HCLBBRA000-IN002007 | MB B21L8 | 22374.3031 | 22389.9631 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QBBI.A21L8 | QBBI.A21L8
| LBARB.21L8 | HCLBARB000-IN002036 | MB A21L8 | 22389.9631 | 22405.6231 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QBQI.21L8 | QBQI.21L8
| LQATH.20L8 | HCLQATH001-CR000011 | MQ 20L8 | 22405.6231 | 22412.0931 | 0 | 1 | 1 | 2006-02-16 | 2006-02-16 | QQBI.20L8 | QQBI.20L8
| LBBRA.20L8 | HCLBBRA000-IN001015 | MB C20L8 | 22412.0931 | 22427.7531 | 0 | 1 | 1 | 2006-02-16 | 2006-02-16 | QBBI.B20L8 | QBBI.B20L8
| LBARA.20L8 | HCLBARA000-IN002028 | MB B20L8 | 22427.7531 | 22443.4131 | 0 | 1 | 1 | 2006-02-03 | 2006-02-03 | QBBI.A20L8 | QBBI.A20L8
| LBBRD.20L8 | HCLBBRD000-IN001029 | MB A20L8 | 22443.4131 | 22459.0731 | 0 | 1 | 1 | 2006-02-16 | 2006-02-16 | QBQI.20L8 | QBQI.20L8
| LQATO.19L8 | HCLQATO001-CR000084 | MQ 19L8 | 22459.0731 | 22465.5431 | 0 | 1 | 1 | 2006-02-16 | 2006-02-16 | QQBI.19L8 | QQBI.19L8
| LBARA.19L8 | HCLBARA000-IN003048 | MB C19L8 | 22465.5431 | 22481.2031 | 0 | 1 | 1 | 2005-12-16 | 2005-12-16 | QBBI.B19L8 | QBBI.B19L8
| LBBRA.19L8 | HCLBBRA000-IN003270 | MB B19L8 | 22481.2031 | 22496.8631 | 0 | 1 | 1 | 2005-12-16 | 2005-12-16 | QBBI.A19L8 | QBBI.A19L8
| LBARB.19L8 | HCLBARB000-IN003061 | MB A19L8 | 22496.8631 | 22512.5231 | 0 | 1 | 1 | 2005-12-16 | 2005-12-16 | QBQI.19L8 | QBQI.19L8
| LQATH.18L8 | HCLQATH001-CR000044 | MQ 18L8 | 22512.5231 | 22518.9931 | 0 | 1 | 1 | 2005-12-16 | 2005-12-16 | QQBI.18L8 | QQBI.18L8
| LBBRA.18L8 | HCLBBRA000-IN001036 | MB C18L8 | 22518.9931 | 22534.6531 | 0 | 1 | 1 | 2005-12-16 | 2005-12-16 | QBBI.B18L8 | QBBI.B18L8
| LBARA.18L8 | HCLBARA000-IN003049 | MB B18L8 | 22534.6531 | 22550.3131 | 0 | 1 | 1 | 2005-12-09 | 2005-12-09 | QBBI.A18L8 | QBBI.A18L8
| LBBRD.18L8 | HCLBBRD000-IN003012 | MB A18L8 | 22550.3131 | 22565.9731 | 0 | 1 | 1 | 2005-12-09 | 2005-12-09 | QBQI.18L8 | QBQI.18L8
| LQATK.17L8 | HCLQATK001-CR000042 | MQ 17L8 | 22565.9731 | 22572.4431 | 0 | 1 | 1 | 2005-12-09 | 2005-12-09 | QQBI.17L8 | QQBI.17L8
| LBARA.17L8 | HCLBARA000-IN002042 | MB C17L8 | 22572.4431 | 22588.1031 | 0 | 1 | 1 | 2005-12-09 | 2005-12-09 | QBBI.B17L8 | QBBI.B17L8
| LBBRA.17L8 | HCLBBRA000-IN002006 | MB B17L8 | 22588.1031 | 22603.7631 | 0 | 1 | 1 | 2005-12-09 | 2005-12-09 | QBBI.A17L8 | QBBI.A17L8
| LBARB.17L8 | HCLBARB000-IN002056 | MB A17L8 | 22603.7631 | 22619.4231 | 0 | 1 | 1 | 2005-12-09 | 2005-12-09 | QBQI.17L8 | QBQI.17L8
B | LQATH.16L8 | HCLQATH001-CR000046 | MQ 16L8 | 22619.4231 | 22625.8931 | 0 | 1 | 1 | 2005-12-09 | 2005-12-09 | QQBI.16L8 | QQBI.16L8
| LBBRA.16L8 | HCLBBRA000-IN003003 | MB C16L8 | 22625.8931 | 22641.5531 | 0 | 1 | 1 | 2005-12-09 | 2005-12-09 | QBBI.B16L8 | QBBI.B16L8
| LBARA.16L8 | HCLBARA000-IN003063 | MB B16L8 | 22641.5531 | 22657.2131 | 0 | 1 | 1 | 2005-12-09 | 2005-12-09 | QBBI.A16L8 | QBBI.A16L8
| LBBRD.16L8 | HCLBBRD000-IN003504 | MB A16L8 | 22657.2131 | 22672.8731 | 0 | 1 | 1 | 2005-12-09 | 2005-12-09 | QBQI.16L8 | QBQI.16L8
| LQATO.15L8 | HCLQATO001-CR000049 | MQ 15L8 | 22672.8731 | 22679.3431 | 0 | 1 | 1 | 2005-12-05 | 2005-12-05 | QQBI.15L8 | QQBI.15L8
| LBARA.15L8 | HCLBARA000-IN003009 | MB C15L8 | 22679.3431 | 22695.0031 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBBI.B15L8 | QBBI.B15L8
| LBBRA.15L8 | HCLBBRA000-IN002014 | MB B15L8 | 22695.0031 | 22710.6631 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBBI.A15L8 | QBBI.A15L8
| LBARB.15L8 | HCLBARB000-IN003058 | MB A15L8 | 22710.6631 | 22726.3231 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBQI.15L8 | QBQI.15L8
| LQATH.14L8 | HCLQATH001-CR000045 | MQ 14L8 | 22726.3231 | 22732.7931 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QQBI.14L8 | QQBI.14L8
| LBBRA.14L8 | HCLBBRA000-IN001519 | MB C14L8 | 22732.7931 | 22748.4531 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBBI.B14L8 | QBBI.B14L8
| LBARA.14L8 | HCLBARA000-IN002031 | MB B14L8 | 22748.4531 | 22764.1131 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBBI.A14L8 | QBBI.A14L8
| LBBRD.14L8 | HCLBBRD000-IN003038 | MB A14L8 | 22764.1131 | 22779.7731 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBQI.14L8 | QBQI.14L8
| LQATK.13L8 | HCLQATK001-CR000349 | MQ 13L8 | 22779.7731 | 22786.2431 | 0 | 1 | 1 | 2005-12-02 | 2005-12-02 | QQBI.13L8 | QQBI.13L8
| LBARA.13L8 | HCLBARA000-IN003065 | MB C13L8 | 22786.2431 | 22801.9031 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBBI.B13L8 | QBBI.B13L8
| LBBRA.13L8 | HCLBBRA000-IN003002 | MB B13L8 | 22801.9031 | 22817.5631 | 0 | 1 | 1 | 2005-12-19 | 2005-12-19 | QBBI.A13L8 | QBBI.A13L8
| LBARB.13L8 | HCLBARB000-IN003029 | MB A13L8 | 22817.5631 | 22833.2231 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBQI.13L8 | QBQI.13L8
| LQATH.12L8 | HCLQATH001-CR000043 | MQ 12L8 | 22833.2231 | 22839.6931 | 0 | 1 | 1 | 2005-12-05 | 2005-12-05 | QQBI.12L8 | QQBI.12L8
| LBBRA.12L8 | HCLBBRA000-IN001017 | MB C12L8 | 22839.6931 | 22855.3531 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBBI.B12L8 | QBBI.B12L8
| LBARA.12L8 | HCLBARA000-IN001133 | MB B12L8 | 22855.3531 | 22871.0131 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBBI.A12L8 | QBBI.A12L8
| LBBRD.12L8 | HCLBBRD000-IN003034 | MB A12L8 | 22871.0131 | 22886.6731 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBQI.12L8 | QBQI.12L8
| LQTCG.11L8 |  | MQ 11L8 | 22886.6731 | 22894.4181 | 0 | 1 | 1 | 2006-05-04 |  | QQEI.11L8 | QQEI.11L8
| LEBR..11L8 | HCLEBR_000-CR000001 | MB C11L8 | 22894.4181 | 22907.1928 | 0 | 1 | 1 | 2006-05-04 |  | QEBI.11L8 | QEBI.11L8
| LBARA.11L8 | HCLBARA000-IN003066 | MB B11L8 | 22907.1928 | 22922.8528 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBBI.11L8 | QBBI.11L8
| LBBRP.11L8 | HCLBBRP000-IN003264 | MB A11L8 | 22922.8528 | 22938.5128 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBQI.11L8 | QBQI.11L8
| LQNCE.10L8 | HCLQNCE001-CR000602 | MQ 10L8 | 22938.5128 | 22946.2578 | 0 | 1 | 1 | 2006-03-22 | 2006-03-22 | QQBI.10L8 | QQBI.10L8
| LBARE.10L8 | HCLBARE000-IN003053 | MB B10L8 | 22946.2578 | 22961.9178 | 0 | 1 | 1 | 2005-11-15 | 2005-11-15 | QBBI.10L8 | QBBI.10L8
| LBBRG.10L8 | HCLBBRG000-IN001030 | MB A10L8 | 22961.9178 | 22977.5778 | 0 | 1 | 1 | 2006-03-22 | 2006-03-22 | QBQI.10L8 | QBQI.10L8
| LQNJF.9L8 | HCLQNJF001-CR000613 | MQ .9L8 | 22977.5778 | 22986.7228 | 0 | 1 | 1 | 2006-03-22 | 2006-03-22 | QQBI.9L8 | QQBI.9L8
| LBARE.9L8 | HCLBARE000-IN003062 | MB B.9L8 | 22986.7228 | 23002.3828 | 0 | 1 | 1 | 2006-03-22 | 2006-03-22 | QBBI.9L8 | QBBI.9L8
| LBBRF.9L8 | HCLBBRF000-IN003036 | MB A.9L8 | 23002.3828 | 23018.0428 | 0 | 1 | 1 | 2006-03-22 | 2006-03-22 | QBQI.9L8 | QBQI.9L8
| LQNCE.8L8 | HCLQNCE001-CR000601 | MQ .8L8 | 23018.0428 | 23025.7878 | 0 | 1 | 1 | 2006-03-22 | 2006-03-22 | QQBI.8L8 | QQBI.8L8
A | LBARE.8L8 | HCLBARE000-IN003051 | MB B.8L8 | 23025.7878 | 23041.4478 | 0 | 1 | 1 | 2006-03-22 | 2006-03-22 | QBBI.8L8 | QBBI.8L8
| LBBRQ.8L8 | HCLBBRQ000-IN003016 | MB A.8L8 | 23041.4478 | 23057.1078 | 0 | 1 | 1 | 2006-03-31 | 2006-03-31 | QBQI.8L8 | QBQI.8L8
| LQNFI.7L8 | HCLQNFI001-CR000604 | MQ .7L8 | 23057.1078 | 23067.2278 | 0 | 1 | 1 | 2006-03-22 | 2006-03-22 | QQDI.7L8
| Total | 202 | 211 |  |  |  | 211 | 207 | 201 | 131 | 211 | 198

## CRI
https://edms.cern.ch/document/
SUB SECTOR | DCUM RING START | magnet down | Interconnect number | magnet up | Available for pre inspection | Magnet OPEN non conformities affecting interconnect | clickable Magnet Non conformity | Pre inspection date | Pre inspection NCR | clickable pre inspection Non conformity | pre inspection ok | Comments (not locked)
A
| 20255.3214 | 0 | QQBI.A8R7 | HCLBARA000-IN003026 | 0 |  | Click here for NCR |  |  | Click here for NCR
| 20263.0664 | HCLBARA000-IN003026 | QBBI.8R7 | HCLBBRB000-IN001031 | 0 |  | Click here for NCR |  |  | Click here for NCR
57 | 20278.7264 | HCLBBRB000-IN001031 | QBQI.8R7 | 0 | 0 |  | Click here for NCR |  |  | Click here for NCR
| 20294.3864 | 0 | QQBI.8R7 | HCLBARA000-IN003050 | 0 |  | Click here for NCR |  |  | Click here for NCR
| 20302.1314 | HCLBARA000-IN003050 | QBBI.9R7 | HCLBBRC000-IN001044 | 0 |  | Click here for NCR |  |  | Click here for NCR | 2006-07-07
| 20317.7914 | HCLBBRC000-IN001044 | QBQI.9R7 | 0 | 0 |  | Click here for NCR |  |  | Click here for NCR
| 20333.4514 | 0 | QQBI.9R7 | HCLBARA000-IN001052 | 0 |  | Click here for NCR |  |  | Click here for NCR
| 20342.5964 | HCLBARA000-IN001052 | QBBI.10R7 | HCLBBRB000-IN001032 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-05-18
| 20358.2564 | HCLBBRB000-IN001032 | QBQI.10R7 | 0 | 38786 |  | Click here for NCR |  |  | Click here for NCR
| 20373.9164 | 0 | QQBI.10R7 | HCLBARA000-IN003022 | 0 |  | Click here for NCR |  |  | Click here for NCR
| 20381.6614 | HCLBARA000-IN003022 | QBBI.11R7 | HCLBBRA000-IN001034 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-05-18
| 20397.3214 | HCLBBRA000-IN001034 | QBEI.11R7 | HCLEDR_000-CR000001 | 38786 |  | Click here for NCR | 2006-06-20 |  | Click here for NCR | 2006-06-27
| 20412.9814 | HCLEDR_000-CR000001 | QEQI.11R7 | 0 | 0 |  | Click here for NCR | 2006-06-20 |  | Click here for NCR | 2006-06-27
| 20426.6981 | 0 | QQBI.11R7 | HCLBARA000-IN002018 | 0 |  | Click here for NCR | 2006-06-20 |  | Click here for NCR | 2006-06-27
| 20434.4431 | HCLBARA000-IN002018 | QBBI.A12R7 | HCLBBRA000-IN001010 | 38786 |  | Click here for NCR | 2006-04-16 |  | Click here for NCR | 2006-05-04
| 20450.1031 | HCLBBRA000-IN001010 | QBBI.B12R7 | HCLBARB000-IN002039 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-05-04
| 20465.7631 | HCLBARB000-IN002039 | QBQI.12R7 | HCLQATH001-CR000245 | 38786 |  | Click here for NCR | 2006-04-16 |  | Click here for NCR | 2006-05-04
| 20481.4231 | HCLQATH001-CR000245 | QQBI.12R7 | HCLBBRA000-IN003041 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-04-16
| 20487.8931 | HCLBBRA000-IN003041 | QBBI.A13R7 | HCLBARA000-IN001054 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-04-16
| 20503.5531 | HCLBARA000-IN001054 | QBBI.B13R7 | HCLBBRC000-IN003019 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-05-04
| 20519.2131 | HCLBBRC000-IN003019 | QBQI.13R7 | HCLQATM001-CR000019 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-05-04
| 20534.8731 | HCLQATM001-CR000019 | QQBI.13R7 | HCLBARA000-IN003030 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-04-16
| 20541.3431 | HCLBARA000-IN003030 | QBBI.A14R7 | HCLBBRA000-IN001004 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-07-07
| 20557.0031 | HCLBBRA000-IN001004 | QBBI.B14R7 | HCLBARB000-IN002015 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-07-07
| 20572.6631 | HCLBARB000-IN002015 | QBQI.14R7 | HCLQATH001-CR000037 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-06-02
| 20588.3231 | HCLQATH001-CR000037 | QQBI.14R7 | HCLBBRA000-IN003020 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-06-02
| 20594.7931 | HCLBBRA000-IN003020 | QBBI.A15R7 | HCLBARA000-IN003010 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-04-16
| 20610.4531 | HCLBARA000-IN003010 | QBBI.B15R7 | HCLBBRC000-IN001022 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-04-16
| 20626.1131 | HCLBBRC000-IN001022 | QBQI.15R7 | 0 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-04-16
| 20641.7731 | 0 | QQBI.15R7 | HCLBARA000-IN003279 | 38786 |  | Click here for NCR | 2006-04-15 |  | Click here for NCR | 2006-04-16
| 20648.2431 | HCLBARA000-IN003279 | QBBI.A16R7 | HCLBBRA000-IN001008 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 20663.9031 | HCLBBRA000-IN001008 | QBBI.B16R7 | HCLBARB000-IN003028 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 20679.5631 | HCLBARB000-IN003028 | QBQI.16R7 | HCLQATH001-CR000041 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
C | 20695.2231 | HCLQATH001-CR000041 | QQBI.16R7 | HCLBBRA000-IN002008 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 20701.6931 | HCLBBRA000-IN002008 | QBBI.A17R7 | HCLBARA000-IN003055 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-06-21
| 20717.3531 | HCLBARA000-IN003055 | QBBI.B17R7 | HCLBBRC000-IN001035 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 20733.0131 | HCLBBRC000-IN001035 | QBQI.17R7 | HCLQATM001-CR000039 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-06-02
| 20748.6731 | HCLQATM001-CR000039 | QQBI.17R7 | HCLBARA000-IN003006 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-06-02
| 20755.1431 | HCLBARA000-IN003006 | QBBI.A18R7 | HCLBBRA000-IN001021 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 20770.8031 | HCLBBRA000-IN001021 | QBBI.B18R7 | HCLBARB000-IN002029 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 20786.4631 | HCLBARB000-IN002029 | QBQI.18R7 | HCLQATH001-CR000031 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 20802.1231 | HCLQATH001-CR000031 | QQBI.18R7 | HCLBBRA000-IN002004 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 20808.5931 | HCLBBRA000-IN002004 | QBBI.A19R7 | HCLBARA000-IN001045 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-06-21
| 20824.2531 | HCLBARA000-IN001045 | QBBI.B19R7 | HCLBBRC000-IN002009 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-06-21
| 20839.9131 | HCLBBRC000-IN002009 | QBQI.19R7 | 0 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-08
| 20855.5731 | 0 | QQBI.19R7 | HCLBARA000-IN003054 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-08
| 20862.0431 | HCLBARA000-IN003054 | QBBI.A20R7 | HCLBBRA000-IN002002 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 20877.7031 | HCLBBRA000-IN002002 | QBBI.B20R7 | HCLBARB000-IN003043 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 20893.3631 | HCLBARB000-IN003043 | QBQI.20R7 | HCLQATH001-CR000249 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-08
| 20909.0231 | HCLQATH001-CR000249 | QQBI.20R7 | HCLBBRA000-IN003014 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-08
| 20915.4931 | HCLBBRA000-IN003014 | QBBI.A21R7 | HCLBARA000-IN001012 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-08
| 20931.1531 | HCLBARA000-IN001012 | QBBI.B21R7 | HCLBBRC000-IN001024 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-08
| 20946.8131 | HCLBBRC000-IN001024 | QBQI.21R7 | HCLQATM001-CR000040 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-08
| 20962.4731 | HCLQATM001-CR000040 | QQBI.21R7 | HCLBARA000-IN003007 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-08
| 20968.9431 | HCLBARA000-IN003007 | QBBI.A22R7 | HCLBBRA000-IN001023 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-08
| 20984.6031 | HCLBBRA000-IN001023 | QBBI.B22R7 | HCLBARB000-IN002020 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 21000.2631 | HCLBARB000-IN002020 | QBQI.22R7 | HCLQOAG001-CR000002 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-04
| 21015.9231 | HCLQOAG001-CR000002 | QQBI.22R7 | HCLBBRA000-IN003042 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-04
| 21022.3931 | HCLBBRA000-IN003042 | QBBI.A23R7 | HCLBARA000-IN001014 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 21038.0531 | HCLBARA000-IN001014 | QBBI.B23R7 | HCLBBRC000-IN001039 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-04
| 21053.7131 | HCLBBRC000-IN001039 | QBQI.23R7 | 0 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 21069.3731 | 0 | QQBI.23R7 | HCLBARA000-IN003027 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 21075.8431 | HCLBARA000-IN003027 | QBBI.A24R7 | HCLBBRA000-IN001020 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-04
| 21091.5031 | HCLBBRA000-IN001020 | QBBI.B24R7 | HCLBARB000-IN003008 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-04
| 21107.1631 | HCLBARB000-IN003008 | QBQI.24R7 | HCLQOAG001-CR000016 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-04
D | 21122.8231 | HCLQOAG001-CR000016 | QQBI.24R7 | HCLBBRA000-IN002012 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-04
| 21129.2931 | HCLBBRA000-IN002012 | QBBI.A25R7 | HCLBARA000-IN001051 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-04
| 21144.9531 | HCLBARA000-IN001051 | QBBI.B25R7 | HCLBBRC000-IN001006 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-04
| 21160.6131 | HCLBBRC000-IN001006 | QBQI.25R7 | HCLQOAR001-CR000003 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-06-02
| 21176.2731 | HCLQOAR001-CR000003 | QQBI.25R7 | HCLBARA000-IN001053 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-06-02
| 21182.7431 | HCLBARA000-IN001053 | QBBI.A26R7 | HCLBBRA000-IN001038 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 21198.4031 | HCLBBRA000-IN001038 | QBBI.B26R7 | HCLBARB000-IN001055 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 21214.0631 | HCLBARB000-IN001055 | QBQI.26R7 | HCLQOAG001-CR000017 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 21229.7231 | HCLQOAG001-CR000017 | QQBI.26R7 | HCLBBRA000-IN003039 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 21236.1931 | HCLBBRA000-IN003039 | QBBI.A27R7 | HCLBARA000-IN003024 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-12
| 21251.8531 | HCLBARA000-IN003024 | QBBI.B27R7 | HCLBBRC000-IN001049 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-12
| 21267.5131 | HCLBBRC000-IN001049 | QBQI.27R7 | HCLQASE001-CR000078 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-12
| 21283.1731 | HCLQASE001-CR000078 | QQBI.27R7 | HCLBARA000-IN002034 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-12
| 21289.6431 | HCLBARA000-IN002034 | QBBI.A28R7 | HCLBBRA000-IN002048 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-12
| 21305.3031 | HCLBBRA000-IN002048 | QBBI.B28R7 | HCLBARB000-IN002011 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-12
| 21320.9631 | HCLBARB000-IN002011 | QBQI.28R7 | HCLQOAG001-CR000023 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-12
| 21336.6231 | HCLQOAG001-CR000023 | QQBI.28R7 | HCLBBRA000-IN001042 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-12
| 21343.0931 | HCLBBRA000-IN001042 | QBBI.A29R7 | HCLBARA000-IN001013 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-12
| 21358.7531 | HCLBARA000-IN001013 | QBBI.B29R7 | HCLBBRC000-IN003017 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-12
| 21374.4131 | HCLBBRC000-IN003017 | QBQI.29R7 | HCLQOBF001-CR000014 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-06
| 21390.0731 | HCLQOBF001-CR000014 | QQBI.29R7 | HCLBARA000-IN002019 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-06
| 21396.5431 | HCLBARA000-IN002019 | QBBI.A30R7 | HCLBBRA000-IN001007 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-06
| 21412.2031 | HCLBBRA000-IN001007 | QBBI.B30R7 | HCLBARB000-IN002027 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-06
| 21427.8631 | HCLBARB000-IN002027 | QBQI.30R7 | HCLQOAM001-CR000008 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-06
| 21443.5231 | HCLQOAM001-CR000008 | QQBI.30R7 | HCLBBRA000-IN001041 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-06
| 21449.9931 | HCLBBRA000-IN001041 | QBBI.A31R7 | HCLBARA000-IN002026 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-06
| 21465.6531 | HCLBARA000-IN002026 | QBBI.B31R7 | HCLBBRC000-IN001028 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-06
| 21481.3131 | HCLBBRC000-IN001028 | QBQI.31R7 | HCLQOAV001-CR000076 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-04-06
| 21496.9731 | HCLQOAV001-CR000076 | QQBI.31R7 | HCLBARA000-IN003052 | 38807 |  | Click here for NCR | 2006-04-01 |  | Click here for NCR | 2006-05-19
| 21503.4431 | HCLBARA000-IN003052 | QBBI.A32R7 | HCLBBRA000-IN002052 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 21519.1031 | HCLBBRA000-IN002052 | QBBI.B32R7 | HCLBARB000-IN002005 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 21534.7631 | HCLBARB000-IN002005 | QBQI.32R7 | HCLQOAG001-CR000001 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-06-02
E | 21550.4231 | HCLQOAG001-CR000001 | QQBI.32R7 | HCLBBRA000-IN001016 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-06-02
| 21556.8931 | HCLBBRA000-IN001016 | QBBI.A33R7 | HCLBARA000-IN003023 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 21572.5531 | HCLBARA000-IN003023 | QBBI.B33R7 | HCLBBRC000-IN002041 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21588.2131 | HCLBBRC000-IN002041 | QBQI.33R7 | HCLQOBJ001-CR000009 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21603.8731 | HCLQOBJ001-CR000009 | QQBI.33R7 | HCLBARA000-IN002016 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21610.3431 | HCLBARA000-IN002016 | QBBI.A34R7 | HCLBBRA000-IN001003 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21626.0031 | HCLBBRA000-IN001003 | QBBI.B34R7 | HCLBARB000-IN003025 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21641.6631 | HCLBARB000-IN003025 | QBQI.34R7 | HCLQOAM001-CR000012 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21657.3231 | HCLQOAM001-CR000012 | QQBI.34L8 | HCLBBRA000-IN001025 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21663.7931 | HCLBBRA000-IN001025 | QBBI.B34L8 | HCLBARA000-IN002017 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-19
| 21679.4531 | HCLBARA000-IN002017 | QBBI.A34L8 | HCLBBRC000-IN003005 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21695.1131 | HCLBBRC000-IN003005 | QBQI.34L8 | HCLQOBF001-CR000026 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21710.7731 | HCLQOBF001-CR000026 | QQBI.33L8 | HCLBARA000-IN003021 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21717.2431 | HCLBARA000-IN003021 | QBBI.B33L8 | HCLBBRA000-IN002050 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21732.9031 | HCLBBRA000-IN002050 | QBBI.A33L8 | HCLBARB000-IN002523 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
F | 21748.5631 | HCLBARB000-IN002523 | QBQI.33L8 | HCLQOAM001-CR000021 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21764.2231 | HCLQOAM001-CR000021 | QQBI.32L8 | HCLBBRA000-IN001027 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21770.6931 | HCLBBRA000-IN001027 | QBBI.B32L8 | HCLBARA000-IN001139 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21786.3531 | HCLBARA000-IN001139 | QBBI.A32L8 | HCLBBRC000-IN001033 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21802.0131 | HCLBBRC000-IN001033 | QBQI.32L8 | HCLQOAV001-CR000077 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-17
| 21817.6731 | HCLQOAV001-CR000077 | QQBI.31L8 | HCLBARA000-IN003064 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 21824.1431 | HCLBARA000-IN003064 | QBBI.B31L8 | HCLBBRA000-IN002044 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 21839.8031 | HCLBBRA000-IN002044 | QBBI.A31L8 | HCLBARB000-IN001140 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 21855.4631 | HCLBARB000-IN001140 | QBQI.31L8 | HCLQOAG001-CR000015 | 38743 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 21871.1231 | HCLQOAG001-CR000015 | QQBI.30L8 | HCLBBRA000-IN003018 | 38743 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 21877.5931 | HCLBBRA000-IN003018 | QBBI.B30L8 | HCLBARA000-IN001066 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 21893.2531 | HCLBARA000-IN001066 | QBBI.A30L8 | HCLBBRC000-IN003011 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 21908.9131 | HCLBBRC000-IN003011 | QBQI.30L8 | HCLQOBF001-CR000007 | 38743 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 21924.5731 | HCLQOBF001-CR000007 | QQBI.29L8 | HCLBARA000-IN002033 | 38743 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 21931.0431 | HCLBARA000-IN002033 | QBBI.B29L8 | HCLBBRA000-IN001009 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 21946.7031 | HCLBBRA000-IN001009 | QBBI.A29L8 | HCLBARB000-IN001136 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 21962.3631 | HCLBARB000-IN001136 | QBQI.29L8 | HCLQOAM001-CR000013 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 21978.0231 | HCLQOAM001-CR000013 | QQBI.28L8 | HCLBBRA000-IN003015 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 21984.4931 | HCLBBRA000-IN003015 | QBBI.B28L8 | HCLBARA000-IN002038 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22000.1531 | HCLBARA000-IN002038 | QBBI.A28L8 | HCLBBRC000-IN003013 | 38743 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22015.8131 | HCLBBRC000-IN003013 | QBQI.28L8 | HCLQASE001-CR000082 | 38743 |  | Click here for NCR | 2006-03-15 |  | Click here for NCR | 2006-04-06
| 22031.4731 | HCLQASE001-CR000082 | QQBI.27L8 | HCLBARA000-IN003057 | 0 |  | Click here for NCR | 2006-03-15 |  | Click here for NCR | 2006-04-06
| 22037.9431 | HCLBARA000-IN003057 | QBBI.B27L8 | HCLBBRA000-IN001018 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22053.6031 | HCLBBRA000-IN001018 | QBBI.A27L8 | HCLBARB000-IN002030 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22069.2631 | HCLBARB000-IN002030 | QBQI.27L8 | HCLQOAG001-CR000020 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22084.9231 | HCLQOAG001-CR000020 | QQBI.26L8 | HCLBBRA000-IN001040 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22091.3931 | HCLBBRA000-IN001040 | QBBI.B26L8 | HCLBARA000-IN003044 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22107.0531 | HCLBARA000-IN003044 | QBBI.A26L8 | HCLBBRC000-IN003259 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22122.7131 | HCLBBRC000-IN003259 | QBQI.26L8 | HCLQOBN001-CR000029 | 38737 |  | Click here for NCR | 2006-03-15 |  | Click here for NCR | 2006-04-06
| 22138.3731 | HCLQOBN001-CR000029 | QQBI.25L8 | HCLBARA000-IN001135 | 38793 |  | Click here for NCR | 2006-03-15 |  | Click here for NCR | 2006-04-06
| 22144.8431 | HCLBARA000-IN001135 | QBBI.B25L8 | HCLBBRA000-IN002010 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22160.5031 | HCLBBRA000-IN002010 | QBBI.A25L8 | HCLBARB000-IN002037 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
G | 22176.1631 | HCLBARB000-IN002037 | QBQI.25L8 | HCLQOAG001-CR000018 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22191.8231 | HCLQOAG001-CR000018 | QQBI.24L8 | HCLBBRA000-IN003037 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22198.2931 | HCLBBRA000-IN003037 | QBBI.B24L8 | HCLBARA000-IN001141 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22213.9531 | HCLBARA000-IN001141 | QBBI.A24L8 | HCLBBRD000-IN002021 | 38737 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22229.6131 | HCLBBRD000-IN002021 | QBQI.24L8 | HCLQASF001-CR000083 | 38737 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22245.2731 | HCLQASF001-CR000083 | QQBI.23L8 | HCLBARA000-IN001137 | 38764 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22251.7431 | HCLBARA000-IN001137 | QBBI.B23L8 | HCLBBRA000-IN002022 | 38751 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22267.4031 | HCLBBRA000-IN002022 | QBBI.A23L8 | HCLBARB000-IN001138 | 38751 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22283.0631 | HCLBARB000-IN001138 | QBQI.23L8 | HCLQOAG001-CR000004 | 38751 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22298.7231 | HCLQOAG001-CR000004 | QQBI.22L8 | HCLBBRA000-IN002065 | 38764 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22305.1931 | HCLBBRA000-IN002065 | QBBI.B22L8 | HCLBARA000-IN003046 | 38751 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22320.8531 | HCLBARA000-IN003046 | QBBI.A22L8 | HCLBBRD000-IN003263 | 38751 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22336.5131 | HCLBBRD000-IN003263 | QBQI.22L8 | HCLQATK001-CR000048 | 38751 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22352.1731 | HCLQATK001-CR000048 | QQBI.21L8 | HCLBARA000-IN001142 | 38751 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22358.6431 | HCLBARA000-IN001142 | QBBI.B21L8 | HCLBBRA000-IN002007 | 38751 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22374.3031 | HCLBBRA000-IN002007 | QBBI.A21L8 | HCLBARB000-IN002036 | 38751 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22389.9631 | HCLBARB000-IN002036 | QBQI.21L8 | HCLQATH001-CR000011 | 38751 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22405.6231 | HCLQATH001-CR000011 | QQBI.20L8 | HCLBBRA000-IN001015 | 38764 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22412.0931 | HCLBBRA000-IN001015 | QBBI.B20L8 | HCLBARA000-IN002028 | 38764 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22427.7531 | HCLBARA000-IN002028 | QBBI.A20L8 | HCLBBRD000-IN001029 | 38751 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22443.4131 | HCLBBRD000-IN001029 | QBQI.20L8 | HCLQATO001-CR000084 | 38764 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22459.0731 | HCLQATO001-CR000084 | QQBI.19L8 | HCLBARA000-IN003048 | 38764 |  | Click here for NCR | 2006-03-20 |  | Click here for NCR | 2006-03-21
| 22465.5431 | HCLBARA000-IN003048 | QBBI.B19L8 | HCLBBRA000-IN003270 | 38702 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22481.2031 | HCLBBRA000-IN003270 | QBBI.A19L8 | HCLBARB000-IN003061 | 38702 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22496.8631 | HCLBARB000-IN003061 | QBQI.19L8 | HCLQATH001-CR000044 | 38702 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22512.5231 | HCLQATH001-CR000044 | QQBI.18L8 | HCLBBRA000-IN001036 | 38702 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22518.9931 | HCLBBRA000-IN001036 | QBBI.B18L8 | HCLBARA000-IN003049 | 38702 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22534.6531 | HCLBARA000-IN003049 | QBBI.A18L8 | HCLBBRD000-IN003012 | 38695 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22550.3131 | HCLBBRD000-IN003012 | QBQI.18L8 | HCLQATK001-CR000042 | 38695 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22565.9731 | HCLQATK001-CR000042 | QQBI.17L8 | HCLBARA000-IN002042 | 38695 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22572.4431 | HCLBARA000-IN002042 | QBBI.B17L8 | HCLBBRA000-IN002006 | 38695 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22588.1031 | HCLBBRA000-IN002006 | QBBI.A17L8 | HCLBARB000-IN002056 | 38695 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
H | 22603.7631 | HCLBARB000-IN002056 | QBQI.17L8 | HCLQATH001-CR000046 | 38695 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22619.4231 | HCLQATH001-CR000046 | QQBI.16L8 | HCLBBRA000-IN003003 | 38695 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22625.8931 | HCLBBRA000-IN003003 | QBBI.B16L8 | HCLBARA000-IN003063 | 38695 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22641.5531 | HCLBARA000-IN003063 | QBBI.A16L8 | HCLBBRD000-IN003504 | 38695 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22657.2131 | HCLBBRD000-IN003504 | QBQI.16L8 | HCLQATO001-CR000049 | 38695 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22672.8731 | HCLQATO001-CR000049 | QQBI.15L8 | HCLBARA000-IN003009 | 38691 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22679.3431 | HCLBARA000-IN003009 | QBBI.B15L8 | HCLBBRA000-IN002014 | 38671 |  | Click here for NCR | 2005-11-30 |  | Click here for NCR | 2005-12-01
| 22695.0031 | HCLBBRA000-IN002014 | QBBI.A15L8 | HCLBARB000-IN003058 | 38671 |  | Click here for NCR | 2005-11-30 |  | Click here for NCR | 2005-12-01
| 22710.6631 | HCLBARB000-IN003058 | QBQI.15L8 | HCLQATH001-CR000045 | 38671 |  | Click here for NCR | 2005-11-30 |  | Click here for NCR | 2005-12-01
| 22726.3231 | HCLQATH001-CR000045 | QQBI.14L8 | HCLBBRA000-IN001519 | 38671 |  | Click here for NCR | 2005-11-30 |  | Click here for NCR | 2005-12-01
| 22732.7931 | HCLBBRA000-IN001519 | QBBI.B14L8 | HCLBARA000-IN002031 | 38671 |  | Click here for NCR | 2005-11-30 |  | Click here for NCR | 2005-12-01
| 22748.4531 | HCLBARA000-IN002031 | QBBI.A14L8 | HCLBBRD000-IN003038 | 38671 |  | Click here for NCR | 2005-11-30 |  | Click here for NCR | 2005-12-01
| 22764.1131 | HCLBBRD000-IN003038 | QBQI.14L8 | HCLQATK001-CR000349 | 38671 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22779.7731 | HCLQATK001-CR000349 | QQBI.13L8 | HCLBARA000-IN003065 | 38688 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22786.2431 | HCLBARA000-IN003065 | QBBI.B13L8 | HCLBBRA000-IN003002 | 38671 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22801.9031 | HCLBBRA000-IN003002 | QBBI.A13L8 | HCLBARB000-IN003029 | 38705 |  | Click here for NCR | 2006-02-15 |  | Click here for NCR | 2006-02-16
| 22817.5631 | HCLBARB000-IN003029 | QBQI.13L8 | HCLQATH001-CR000043 | 38671 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22833.2231 | HCLQATH001-CR000043 | QQBI.12L8 | HCLBBRA000-IN001017 | 38691 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-01-11
| 22839.6931 | HCLBBRA000-IN001017 | QBBI.B12L8 | HCLBARA000-IN001133 | 38671 |  | Click here for NCR | 2005-11-30 |  | Click here for NCR | 2005-12-01
| 22855.3531 | HCLBARA000-IN001133 | QBBI.A12L8 | HCLBBRD000-IN003034 | 38671 |  | Click here for NCR | 2005-11-30 |  | Click here for NCR | 2005-12-01
| 22871.0131 | HCLBBRD000-IN003034 | QBQI.12L8 | 0 | 38671 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 22886.6731 | 0 | QQEI.11L8 | HCLEBR_000-CR000001 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 22894.4181 | HCLEBR_000-CR000001 | QEBI.11L8 | HCLBARA000-IN003066 | 0 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 22907.1928 | HCLBARA000-IN003066 | QBBI.11L8 | HCLBBRP000-IN003264 | 38671 |  | Click here for NCR | 2005-11-30 |  | Click here for NCR | 2005-12-01
| 22922.8528 | HCLBBRP000-IN003264 | QBQI.11L8 | HCLQNCE001-CR000602 | 38671 |  | Click here for NCR | 2006-01-05 |  | Click here for NCR | 2006-03-29
| 22938.5128 | HCLQNCE001-CR000602 | QQBI.10L8 | HCLBARE000-IN003053 | 38798 |  | Click here for NCR | 2006-01-06 |  | Click here for NCR | 2006-03-29
| 22946.2578 | HCLBARE000-IN003053 | QBBI.10L8 | HCLBBRG000-IN001030 | 38671 |  | Click here for NCR | 2006-01-07 |  | Click here for NCR | 2006-03-29
| 22961.9178 | HCLBBRG000-IN001030 | QBQI.10L8 | HCLQNJF001-CR000613 | 38798 |  | Click here for NCR | 2006-01-08 |  | Click here for NCR | 2006-03-29
| 22977.5778 | HCLQNJF001-CR000613 | QQBI.9L8 | HCLBARE000-IN003062 | 38798 |  | Click here for NCR | 2006-01-09 |  | Click here for NCR | 2006-04-02
| 22986.7228 | HCLBARE000-IN003062 | QBBI.9L8 | HCLBBRF000-IN003036 | 38798 |  | Click here for NCR | 2006-01-10 |  | Click here for NCR | 2006-04-02
| 23002.3828 | HCLBBRF000-IN003036 | QBQI.9L8 | HCLQNCE001-CR000601 | 38798 |  | Click here for NCR | 2006-01-11 |  | Click here for NCR | 2006-03-29
I | 23018.0428 | HCLQNCE001-CR000601 | QQBI.8L8 | HCLBARE000-IN003051 | 38798 |  | Click here for NCR | 2006-01-12 |  | Click here for NCR | 2006-03-29
| 23025.7878 | HCLBARE000-IN003051 | QBBI.8L8 | HCLBBRQ000-IN003016 | 38798 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-05-18
| 23041.4478 | HCLBBRQ000-IN003016 | QBQI.8L8 | HCLQNFI001-CR000604 | 38807 |  | Click here for NCR | 2006-05-09 |  | Click here for NCR | 2006-06-13
| TOTAL |  |  |  | 0 | 0 |  | 201 | 0 |  | 202 | 0
9
Formulas:
Pre inspection date = [pre inspection ok]-1

## general
SUB SEC. | dcum ring start | mag. Left |  | IC number | mag. Right | Weld V1 V2 | VAC test V1 V2 | RF test | Weld E | VAC test E | Solder Main BB | Insulate Main BB | US weld Spools | Insulate spools | PAQ | solder Y | weld X | VAC test X | weld C' | weld M3 | weld K1,K2 | VAC test circuit K1K2C' | weld M1,M2 | insert N | Tack Weld N (not qbq) | cable N | Test HVQN | AIV 1 | US weld N (cables) | AIV 2 | Weld N (sleeve) | insulate N Weld M2N | Close W | VAC final test | Vacuum sector | SUB SECTOR | DCUM RING START | Interconnect number | VAC test V1 V2 | VAC test E | PAQ | VAC test X line | VAC test C' line | AIV 1 | AIV 2 | VAC final test
|  |  | 0 | QQBI.A8R7 | 3026 | [31 empty] | 0 | QQBI.A8R7
I |  | 3026 | 0 | QBBI.8R7 | 1031 | [29 empty] | VACSEC.A7R4 | A | 0 | QBBI.8R7
| 20255.3214 | 1031 | 0 | QBQI.8R7 | [32 empty] | 20255.3214 | QBQI.8R7
H | 20263.0664 |  | 0 | QQBI.8R7 | 3050 | [31 empty] | 20263.0664 | QQBI.8R7
| 20278.7264 | 3050 | 2006-07-07 | QBBI.9R7 | 1044 | [30 empty] | B | 20278.7264 | QBBI.9R7
| 20294.3864 | 1044 | 0 | QBQI.9R7 | [32 empty] | 20294.3864 | QBQI.9R7
| 20302.1314 |  | 0 | QQBI.9R7 | 1052 | [31 empty] | 20302.1314 | QQBI.9R7
| 20317.7914 | 1052 | 2006-05-18 | QBBI.10R7 | 1032 | 2006-05-22 |  |  | 2006-05-22 |  | 2006-05-23 | 2006-05-30 | 2006-05-24 | 2006-06-08 |  | 2006-05-29 |  |  | 2006-07-03 | [17 empty] | 20317.7914 | QBBI.10R7
| 20333.4514 | 1032 | 0 | QBQI.10R7 | [32 empty] | 20333.4514 | QBQI.10R7
| 20342.5964 |  | 0 | QQBI.10R7 | 3022 | [31 empty] | 20342.5964 | QQBI.10R7
| 20358.2564 | 3022 | 2006-05-18 | QBBI.11R7 | 1034 | 2006-05-23 |  |  | 2006-05-23 |  | 2006-05-23 | 2006-05-30 | 2006-05-24 | 2006-06-15 |  | 2006-05-29 |  |  | 2006-06-29 | [17 empty] | 20358.2564 | QBBI.11R7
| 20373.9164 | 1034 | 2006-06-27 | QBEI.11R7 | 0001 | 2006-06-28 |  |  | 2006-06-28 |  | 2006-06-29 | 2006-06-29 | [24 empty] | 20373.9164 | QBEI.11R7
| 20381.6614 | 0001 | 2006-06-27 | QEQI.11R7 |  |  |  |  | 2006-06-28 | [27 empty] | 20381.6614 | QEQI.11R7
| 20397.3214 |  | 2006-06-27 | QQBI.11R7 | 2018 |  |  |  | 2006-06-29 |  | 2006-06-28 | 2006-06-29 | 2006-06-29 | 2006-07-03 | [22 empty] | 20397.3214 | QQBI.11R7
| 20412.9814 | 2018 | 2006-05-04 | QBBI.A12R7 | 1010 | 2006-05-22 |  |  | 2006-05-22 |  | 2006-05-22 | 2006-05-30 | 2006-05-23 | 2006-06-15 |  | 2006-05-17 | [20 empty] | 20412.9814 | QBBI.A12R7
| 20426.6981 | 1010 | 2006-05-04 | QBBI.B12R7 | 2039 | 2006-05-18 |  |  | 2006-06-13 |  | 2006-05-11 | 2006-05-11 | 2006-05-11 | 2006-06-15 |  | 2006-05-17 | [18 empty] | VACSEC.A11R4 |  | 20426.6981 | QBBI.B12R7
| 20434.4431 | 2039 | 2006-05-04 | QBQI.12R7 | 0245 | 2006-05-17 |  |  | 2006-05-17 | [6 empty] | 2006-05-18 | 2006-06-21 | [19 empty] | 20434.4431 | QBQI.12R7
| 20450.1031 | 0245 | 2006-04-16 | QQBI.12R7 | 3041 | 2006-05-09 |  |  | 2006-05-09 |  | 2006-05-11 | 2006-05-11 | 2006-05-11 | 2006-05-18 | 2006-07-11 | 2006-05-18 | 2006-06-21 |  | 2006-07-03 | [17 empty] | 20450.1031 | QQBI.12R7
| 20465.7631 | 3041 | 2006-04-16 | QBBI.A13R7 | 1054 | 2006-06-26 |  |  | 2006-06-15 |  | 2006-06-13 | 2006-06-14 | 2006-06-19 | 2006-06-19 | 2006-07-11 | 2006-05-22 | 2006-06-21 |  | 2006-07-03 | [17 empty] | 20465.7631 | QBBI.A13R7
| 20481.4231 | 1054 | 2006-05-04 | QBBI.B13R7 | 3019 | 2006-06-12 |  |  | 2006-06-12 |  | 2006-05-10 | 2006-05-10 | 2006-05-11 | 2006-05-18 | 2006-07-11 | 2006-05-22 |  |  | 2006-07-05 | [17 empty] | 20481.4231 | QBBI.B13R7
| 20487.8931 | 3019 | 2006-05-04 | QBQI.13R7 | 0019 | [10 empty] | 2006-05-10 | [20 empty] | 20487.8931 | QBQI.13R7
| 20503.5531 | 0019 | 2006-04-16 | QQBI.13R7 | 3030 | 2006-05-05 |  |  | 2006-06-15 |  | 2006-05-09 | 2006-05-09 | 2006-05-10 | 2006-05-18 |  | 2006-05-18 |  |  | 2006-07-05 | [17 empty] | 20503.5531 | QQBI.13R7
| 20519.2131 | 3030 | 2006-07-07 | QBBI.A14R7 | 1004 | [31 empty] | 20519.2131 | QBBI.A14R7
| 20534.8731 | 1004 | 2006-07-07 | QBBI.B14R7 | 2015 | [31 empty] | 20534.8731 | QBBI.B14R7
| 20541.3431 | 2015 | 2006-06-02 | QBQI.14R7 | 0037 | 2006-06-12 |  |  | 2006-06-12 | [6 empty] | 2006-06-12 | [20 empty] | 20541.3431 | QBQI.14R7
| 20557.0031 | 0037 | 2006-06-02 | QQBI.14R7 | 3020 | 2006-06-13 |  |  | 2006-06-13 |  | 2006-06-12 | 2006-06-14 | 2006-06-15 | 2006-06-21 | 2006-07-11 | 2006-06-12 |  |  | 2006-07-05 | [17 empty] | 20557.0031 | QQBI.14R7
| 20572.6631 | 3020 | 2006-04-16 | QBBI.A15R7 | 3010 | 2006-05-05 |  |  | 2006-06-19 |  | 2006-05-05 | 2006-05-05 | 2006-05-09 | 2006-06-14 | 2006-07-11 | 2006-05-10 | 2006-07-05 |  | 2006-07-05 | [17 empty] | 20572.6631 | QBBI.A15R7
| 20588.3231 | 3010 | 2006-04-16 | QBBI.B15R7 | 1022 | 2006-05-09 |  |  | 2006-05-09 |  | 2006-05-05 | 2006-05-05 | 2006-05-05 | 2006-06-14 | 2006-07-11 | 2006-05-10 | 2006-07-05 |  | 2006-07-05 | [17 empty] | 20588.3231 | QBBI.B15R7
| 20594.7931 | 1022 | 2006-04-16 | QBQI.15R7 | 019. | 2006-05-05 |  |  | 2006-05-09 | [6 empty] | 2006-05-22 | 2006-06-21 | [19 empty] | 20594.7931 | QBQI.15R7
| 20610.4531 | 019. | 2006-04-16 | QQBI.15R7 | 3279 | 2006-05-05 |  |  | 2006-05-09 |  | 2006-05-04 | 2006-05-04 | 2006-05-05 | 2006-06-08 | ncrMEL | 2006-05-10 | 2006-06-21 |  | 2006-07-05 | [17 empty] | 20610.4531 | QQBI.15R7
| 20626.1131 | 3279 | 2006-05-18 | QBBI.A16R7 | 1008 | 2006-05-23 |  |  | 2006-05-23 |  | 2006-05-24 | 2006-05-30 | 2006-05-24 | 2006-06-08 | ncrMEL | 2006-05-22 | 2006-06-21 |  | 2006-07-05 | [17 empty] | 20626.1131 | QBBI.A16R7
| 20641.7731 | 1008 | 2006-05-18 | QBBI.B16R7 | 3028 | 2006-05-23 |  |  | 2006-05-23 |  | 2006-05-24 | 2006-05-31 | 2006-05-29 | 2006-06-08 | ncrMEL | 2006-05-22 | 2006-06-26 |  | 2006-07-05 | [15 empty] | VACSEC.A15R4 |  | 20641.7731 | QBBI.B16R7
| 20648.2431 | 3028 | 2006-05-18 | QBQI.16R7 | 0041 | 2006-05-24 |  |  | 2006-05-24 | [6 empty] | 2006-05-22 | [20 empty] | 20648.2431 | QBQI.16R7
| 20663.9031 | 0041 | 2006-05-18 | QQBI.16R7 | 2008 | 2006-05-24 |  |  | 2006-05-24 |  | 2006-05-29 | 2006-05-31 | 2006-05-29 | 2006-06-14 | 2006-07-11 | 2006-05-29 | 2006-06-26 | [19 empty] | 20663.9031 | QQBI.16R7
G | 20679.5631 | 2008 | 2006-06-21 | QBBI.A17R7 | 3055 | 2006-06-27 |  |  | 2006-06-27 |  | 2006-06-28 | 2006-06-28 | 2006-06-29 | 2006-06-29 | 2006-07-11 | 2006-06-26 | 2006-07-05 | [19 empty] | 20679.5631 | QBBI.A17R7
| 20695.2231 | 3055 | 2006-05-18 | QBBI.B17R7 | 1035 | 2006-05-24 |  |  | 2006-05-24 |  | 2006-05-29 | 2006-05-31 | 2006-05-30 | 2006-06-14 | 2006-07-11 | 2006-05-22 | 2006-06-27 | [18 empty] | C | 20695.2231 | QBBI.B17R7
| 20701.6931 | 1035 | 2006-06-02 | QBQI.17R7 | 0039 | [10 empty] | 2006-06-12 | [20 empty] | 20701.6931 | QBQI.17R7
| 20717.3531 | 0039 | 2006-06-02 | QQBI.17R7 | 3006 | 2006-06-14 |  |  | 2006-06-14 |  | 2006-06-12 | 2006-06-14 | 2006-06-15 | 2006-06-21 |  | 2006-06-12 | 2006-06-27 | [19 empty] | 20717.3531 | QQBI.17R7
| 20733.0131 | 3006 | 2006-05-19 | QBBI.A18R7 | 1021 | 2006-05-29 |  |  | 2006-05-29 |  | 2006-05-30 | 2006-05-31 | 2006-05-31 | 2006-06-21 |  | 2006-06-12 | 2006-06-27 | [19 empty] | 20733.0131 | QBBI.A18R7
| 20748.6731 | 1021 | 2006-05-18 | QBBI.B18R7 | 2029 | 2006-05-29 |  |  | 2006-05-29 |  | 2006-05-30 | 2006-05-31 | 2006-05-31 | 2006-06-13 |  | 2006-05-22 | 2006-06-27 | [19 empty] | 20748.6731 | QBBI.B18R7
| 20755.1431 | 2029 | 2006-05-18 | QBQI.18R7 | 0031 | 2006-05-30 |  |  | 2006-05-30 | [6 empty] | 2006-05-29 | [20 empty] | 20755.1431 | QBQI.18R7
| 20770.8031 | 0031 | 2006-05-18 | QQBI.18R7 | 2004 | 2006-05-30 |  |  | 2006-05-30 |  | 2006-05-31 | 2006-06-08 | 2006-06-01 | 2006-06-13 |  | 2006-05-29 | 2006-06-27 | [19 empty] | 20770.8031 | QQBI.18R7
| 20786.4631 | 2004 | 2006-06-21 | QBBI.A19R7 | 1045 |  |  |  | 2006-06-27 |  | 2006-06-27 | 2006-06-27 | 2006-06-28 | 2006-06-29 |  | 2006-06-26 | [20 empty] | 20786.4631 | QBBI.A19R7
| 20802.1231 | 1045 | 2006-06-21 | QBBI.B19R7 | 2009 |  |  |  | 2006-06-28 |  | 2006-06-27 | 2006-06-28 | 2006-06-28 | 2006-06-29 |  | 2006-06-26 | [20 empty] | 20802.1231 | QBBI.B19R7
| 20808.5931 | 2009 | 2006-05-08 | QBQI.19R7 | 060. | 2006-05-31 |  |  | 2006-05-31 | [6 empty] | 2006-05-29 | [20 empty] | 20808.5931 | QBQI.19R7
| 20824.2531 | 060. | 2006-05-08 | QQBI.19R7 | 3054 | 2006-06-14 |  |  | 2006-06-19 |  | 2006-05-31 | 2006-06-08 | 2006-06-01 | 2006-06-13 | 2006-07-06 | 2006-05-29 | 2006-06-27 | [19 empty] | 20824.2531 | QQBI.19R7
| 20839.9131 | 3054 | 2006-05-19 | QBBI.A20R7 | 2002 | 2006-05-31 |  |  | 2006-05-31 |  | 2006-06-01 | 2006-06-08 | 2006-06-01 | 2006-06-19 | 2006-07-06 | 2006-05-29 | 2006-06-28 | [19 empty] | 20839.9131 | QBBI.A20R7
| 20855.5731 | 2002 | 2006-05-19 | QBBI.B20R7 | 3043 | 2006-06-01 |  |  | 2006-06-01 |  | 2006-06-01 | 2006-06-06 | 2006-06-06 | 2006-06-19 | 2006-07-06 | 2006-05-29 | 2006-06-28 | [17 empty] | VACSEC.A19R4 |  | 20855.5731 | QBBI.B20R7
| 20862.0431 | 3043 | 2006-05-08 | QBQI.20R7 | 0249 | 2006-06-01 |  |  | 2006-06-15 | [6 empty] | 2006-05-29 | [20 empty] | 20862.0431 | QBQI.20R7
| 20877.7031 | 0249 | 2006-05-08 | QQBI.20R7 | 3014 | 2006-06-01 |  |  | 2006-06-01 |  | 2006-06-06 | 2006-06-08 | 2006-06-07 | 2006-06-12 | ncrMEL | 2006-05-29 | 2006-06-28 | [19 empty] | 20877.7031 | QQBI.20R7
| 20893.3631 | 3014 | 2006-05-08 | QBBI.A21R7 | 1012 | 2006-06-06 |  |  | 2006-06-06 |  | 2006-05-18 | 2006-05-18 | 2006-06-07 | 2006-06-19 | ncrMEL | 2006-05-10 | 2006-07-05 | [19 empty] | 20893.3631 | QBBI.A21R7
| 20909.0231 | 1012 | 2006-05-08 | QBBI.B21R7 | 1024 | 2006-05-22 |  |  | 2006-05-18 |  | 2006-05-22 | 2006-06-08 | 2006-06-06 | 2006-06-19 | ncrMEL | 2006-05-10 | 2006-07-05 | [19 empty] | 20909.0231 | QBBI.B21R7
| 20915.4931 | 1024 | 2006-05-08 | QBQI.21R7 | 0040 | [10 empty] | 2006-05-29 | [20 empty] | 20915.4931 | QBQI.21R7
| 20931.1531 | 0040 | 2006-05-08 | QQBI.21R7 | 3007 | 2006-05-11 |  |  | 2006-05-12 |  | 2006-05-11 | 2006-05-11 | 2006-05-12 | 2006-06-08 | ncrMEL | 2006-05-29 | 2006-07-06 | [19 empty] | 20931.1531 | QQBI.21R7
| 20946.8131 | 3007 | 2006-05-08 | QBBI.A22R7 | 1023 | 2006-05-12 |  |  | 2006-05-12 |  | 2006-05-12 | 2006-05-12 | 2006-05-15 | 2006-06-08 | ncrMEL | 2006-05-29 | 2006-07-06 | [19 empty] | 20946.8131 | QBBI.A22R7
| 20962.4731 | 1023 | 2006-05-19 | QBBI.B22R7 | 2020 | ncrREPLACE |  |  | 2006-06-14 |  | 2006-06-06 | 2006-06-08 | 2006-06-09 | 2006-06-21 | ncrMEL | 2006-06-06 | [20 empty] | 20962.4731 | QBBI.B22R7
| 20968.9431 | 2020 | 2006-05-04 | QBQI.22R7 | 0002 | 2006-05-11 |  |  | 2006-05-12 | [6 empty] | 2006-05-29 | [20 empty] | 20968.9431 | QBQI.22R7
| 20984.6031 | 0002 | 2006-05-04 | QQBI.22R7 | 3042 | 2006-05-11 |  |  | 2006-05-12 |  | 2006-05-12 | 2006-05-12 | 2006-05-15 | 2006-06-08 | 2006-07-06 | 2006-05-29 | [20 empty] | 20984.6031 | QQBI.22R7
| 21000.2631 | 3042 | 2006-05-19 | QBBI.A23R7 | 1014 | 2006-06-06 |  |  | 2006-06-06 |  | 2006-06-07 | 2006-06-08 | 2006-06-09 | 2006-06-21 | 2006-07-06 | 2006-06-12 | 2006-06-21 | [19 empty] | 21000.2631 | QBBI.A23R7
| 21015.9231 | 1014 | 2006-05-04 | QBBI.B23R7 | 1039 | 2006-05-11 |  |  | 2006-05-12 |  | 2006-05-11 | 2006-05-11 | 2006-05-16 | 2006-06-21 | 2006-07-06 | 2006-06-12 | 2006-06-21 | [19 empty] | 21015.9231 | QBBI.B23R7
| 21022.3931 | 1039 | 2006-05-19 | QBQI.23R7 |  | 2006-06-07 |  |  | 2006-06-07 | [6 empty] | 2006-06-06 | [20 empty] | 21022.3931 | QBQI.23R7
| 21038.0531 |  | 2006-05-19 | QQBI.23R7 | 3027 | 2006-06-07 |  |  | 2006-06-07 |  | 2006-06-07 | 2006-06-09 | 2006-06-09 | 2006-06-21 | ncrMEL | 2006-06-06 | 2006-06-21 | [19 empty] | 21038.0531 | QQBI.23R7
| 21053.7131 | 3027 | 2006-05-04 | QBBI.A24R7 | 1020 | 2006-05-12 |  |  | 2006-05-18 |  | 2006-05-15 | 2006-06-08 | 2006-05-16 | 2006-06-08 | ncrMEL | 2006-06-06 | [20 empty] | 21053.7131 | QBBI.A24R7
| 21069.3731 | 1020 | 2006-05-04 | QBBI.B24R7 | 3008 | 2006-05-15 |  |  | 2006-05-18 |  | 2006-05-15 | 2006-06-08 | 2006-05-17 | 2006-06-08 | ncrMEL | 2006-06-06 | [18 empty] | VACSEC.A23R4 |  | 21069.3731 | QBBI.B24R7
| 21075.8431 | 3008 | 2006-05-04 | QBQI.24R7 | 0016 | 2006-05-15 |  |  | 2006-05-15 | [6 empty] | 2006-06-20 | [20 empty] | 21075.8431 | QBQI.24R7
| 21091.5031 | 0016 | 2006-05-04 | QQBI.24R7 | 2012 | 2006-05-18 |  |  | 2006-06-19 |  | 2006-05-16 | 2006-06-08 | 2006-05-18 | 2006-06-08 | 2006-07-06 | 2006-06-20 | [20 empty] | 21091.5031 | QQBI.24R7
F | 21107.1631 | 2012 | 2006-05-04 | QBBI.A25R7 | 1051 | 2006-05-18 |  |  | 2006-05-17 |  | 2006-05-16 | 2006-06-08 | 2006-05-18 | 2006-06-08 | 2006-07-06 | 2006-06-20 | [20 empty] | 21107.1631 | QBBI.A25R7
| 21122.8231 | 1051 | 2006-05-04 | QBBI.B25R7 | 1006 | 2006-05-17 |  |  | 2006-05-17 |  | 2006-05-16 | 2006-06-08 | 2006-05-22 | 2006-06-08 | 2006-07-06 | 2006-06-20 | [19 empty] | D | 21122.8231 | QBBI.B25R7
| 21129.2931 | 1006 | 2006-06-02 | QBQI.25R7 | 0003 | [10 empty] | 2006-06-20 | [20 empty] | 21129.2931 | QBQI.25R7
| 21144.9531 | 0003 | 2006-06-02 | QQBI.25R7 | 1053 | 2006-06-15 |  |  | 2006-06-15 |  | 2006-06-13 | 2006-06-15 | 2006-06-14 | 2006-06-19 | ncrMEL | 2006-06-20 | [20 empty] | 21144.9531 | QQBI.25R7
| 21160.6131 | 1053 | 2006-05-19 | QBBI.A26R7 | 1038 | 2006-06-07 |  |  | 2006-06-07 |  | 2006-06-08 | 2006-06-12 | 2006-06-09 | 2006-06-12 | ncrMEL | 2006-06-20 | [20 empty] | 21160.6131 | QBBI.A26R7
| 21176.2731 | 1038 | 2006-05-18 | QBBI.B26R7 | 1055 | 2006-06-08 |  |  | 2006-06-08 |  | 2006-06-08 | 2006-06-14 | 2006-06-13 | 2006-06-14 | ncrMEL | 2006-06-20 | [20 empty] | 21176.2731 | QBBI.B26R7
| 21182.7431 | 1055 | 2006-05-18 | QBQI.26R7 | 0017 | 2006-06-08 |  |  | 2006-06-08 | [6 empty] | 2006-06-20 | [20 empty] | 21182.7431 | QBQI.26R7
| 21198.4031 | 0017 | 2006-05-18 | QQBI.26R7 | 3039 | 2006-06-09 |  |  | 2006-06-09 |  | 2006-06-09 | 2006-06-14 | 2006-06-13 | 2006-06-14 | 2006-06-30 | 2006-06-20 | [20 empty] | 21198.4031 | QQBI.26R7
| 21214.0631 | 3039 | 2006-04-12 | QBBI.A27R7 | 3024 | 2006-05-16 |  |  | 2006-06-15 |  | 2006-05-17 | 2006-05-17 | 2006-05-23 | 2006-06-19 | 2006-06-30 | 2006-05-09 | 2006-06-21 | [19 empty] | 21214.0631 | QBBI.A27R7
| 21229.7231 | 3024 | 2006-04-12 | QBBI.B27R7 | 1049 | 2006-05-03 |  |  | 2006-05-03 |  | 2006-05-04 | 2006-05-04 | 2006-06-14 | 2006-06-21 | 2006-06-30 | 2006-05-09 | 2006-06-21 | [19 empty] | 21229.7231 | QBBI.B27R7
| 21236.1931 | 1049 | 2006-04-12 | QBQI.27R7 | 0078 | 2006-06-09 |  |  | 2006-06-09 |  | 2006-07-05 | 2006-07-05 | ncr cern |  |  | 2006-07-03 | [20 empty] | 21236.1931 | QBQI.27R7
| 21251.8531 | 0078 | 2006-04-12 | QQBI.27R7 | 2034 | 2006-06-09 |  |  | 2006-06-19 |  | 2006-06-09 | 2006-06-14 | 2006-06-14 | 2006-06-21 | 2006-06-30 | 2006-06-20 | [20 empty] | 21251.8531 | QQBI.27R7
| 21267.5131 | 2034 | 2006-04-12 | QBBI.A28R7 | 2048 | ncr cern |  |  | 2006-05-03 |  | 2006-05-03 | 2006-05-03 | 2006-06-19 | 2006-06-26 | 2006-06-30 | 2006-05-09 | 2006-06-28 |  | 2006-06-26 | [17 empty] | 21267.5131 | QBBI.A28R7
| 21283.1731 | 2048 | 2006-04-12 | QBBI.B28R7 | 2011 | 2006-04-27 |  |  | 2006-06-12 |  | 2006-05-02 | 2006-05-02 | 2006-05-02 | 2006-06-26 | 2006-06-30 | 2006-05-09 | 2006-06-13 |  | ncr ieg | [15 empty] | VACSEC.A27R4 |  | 21283.1731 | QBBI.B28R7
| 21289.6431 | 2011 | 2006-04-12 | QBQI.28R7 | 0023 | 2006-05-02 |  |  | 2006-05-02 |  | 2006-07-06 | 2006-07-06 |  |  |  | 2006-05-09 | 2006-06-15 | [19 empty] | 21289.6431 | QBQI.28R7
| 21305.3031 | 0023 | 2006-04-12 | QQBI.28R7 | 1042 | 2006-05-02 |  |  | 2006-05-02 |  | 2006-05-02 | 2006-05-02 | 2006-05-03 | 2006-06-21 | 2006-06-30 | 2006-05-09 | 2006-06-15 |  | 2006-06-26 | [17 empty] | 21305.3031 | QQBI.28R7
| 21320.9631 | 1042 | 2006-04-12 | QBBI.A29R7 | 1013 | 2006-05-16 |  |  | 2006-05-17 |  | 2006-05-17 | 2006-05-17 | 2006-06-20 | 2006-06-26 | 2006-06-30 | 2006-06-13 | 2006-06-15 |  | 2006-06-26 | [17 empty] | 21320.9631 | QBBI.A29R7
| 21336.6231 | 1013 | 2006-04-12 | QBBI.B29R7 | 3017 | [5 empty] | 2006-06-14 | 2006-06-14 | 2006-06-19 | 2006-06-26 | 2006-06-30 | 2006-05-09 | 2006-06-13 |  | 2006-06-26 | [17 empty] | 21336.6231 | QBBI.B29R7
| 21343.0931 | 3017 | 2006-04-06 | QBQI.29R7 | 0014 | 2006-04-19 |  |  | 2006-04-19 | 2006-06-23 | 2006-07-05 | 2006-07-05 | 2006-07-06 |  |  | 2006-06-13 | 2006-06-13 |  | ncr ieg | [17 empty] | 21343.0931 | QBQI.29R7
| 21358.7531 | 0014 | 2006-04-06 | QQBI.29R7 | 2019 | 2006-04-20 |  |  | 2006-04-20 | 2006-06-23 | 2006-04-24 | 2006-04-24 | 2006-04-25 | 2006-06-21 | 2006-06-30 | 2006-06-13 | 2006-06-13 |  | 2006-06-27 | [17 empty] | 21358.7531 | QQBI.29R7
| 21374.4131 | 2019 | 2006-04-06 | QBBI.A30R7 | 1007 | 2006-04-24 |  |  | 2006-04-24 | 2006-06-23 | 2006-04-20 | 2006-06-13 | 2006-04-24 | 2006-06-21 | 2006-06-30 | 2006-06-13 | 2006-06-15 |  | 2006-06-27 | [17 empty] | 21374.4131 | QBBI.A30R7
| 21390.0731 | 1007 | 2006-04-06 | QBBI.B30R7 | 2027 | 2006-04-25 |  |  | 2006-05-10 | 2006-06-23 | 2006-04-24 | 2006-04-24 | 2006-04-25 | 2006-06-21 | 2006-06-30 | 2006-06-13 | 2006-06-15 |  | 2006-06-28 | [17 empty] | 21390.0731 | QBBI.B30R7
| 21396.5431 | 2027 | 2006-04-06 | QBQI.30R7 | 0008 | 2006-04-24 |  |  | 2006-05-11 | 2006-06-23 | 2006-07-05 |  | ncr ieg |  |  | 2006-06-13 | 2006-06-14 | [19 empty] | 21396.5431 | QBQI.30R7
| 21412.2031 | 0008 | 2006-04-06 | QQBI.30R7 | 1041 | ncr cern |  |  | 2006-05-11 | 2006-06-23 | 2006-04-18 | 2006-04-18 | 2006-04-19 | 2006-06-21 | ncrMEL | 2006-04-26 | 2006-06-14 |  | 2006-06-27 | [17 empty] | 21412.2031 | QQBI.30R7
| 21427.8631 | 1041 | 2006-04-06 | QBBI.A31R7 | 2026 | 2006-04-18 |  |  | 2006-04-18 | 2006-06-23 | 2006-04-19 | 2006-04-19 | 2006-04-19 | 2006-06-26 | ncrMEL | 2006-04-26 | 2006-06-14 |  | 2006-06-28 | [17 empty] | 21427.8631 | QBBI.A31R7
| 21443.5231 | 2026 | 2006-04-06 | QBBI.B31R7 | 1028 | 2006-04-18 |  |  | 2006-04-18 | 2006-06-23 | 2006-04-19 | 2006-04-19 | 2006-04-20 | 2006-06-26 | ncrMEL | 2006-04-26 | 2006-06-14 |  | 2006-07-03 | [17 empty] | 21443.5231 | QBBI.B31R7
| 21449.9931 | 1028 | 2006-04-06 | QBQI.31R7 | 0076 | 2006-04-19 |  |  | 2006-05-17 | 2006-06-23 | [5 empty] | 2006-04-26 | 2006-06-21 |  | 2006-06-29 | [17 empty] | 21449.9931 | QBQI.31R7
| 21465.6531 | 0076 | 2006-05-19 | QQBI.31R7 | 3052 | 2006-06-09 |  |  | 2006-06-09 | 2006-06-23 | 2006-06-12 | 2006-06-12 | 2006-06-15 | 2006-06-26 | ncrMEL | 2006-06-13 | 2006-06-21 |  | 2006-06-29 | [17 empty] | 21465.6531 | QQBI.31R7
| 21481.3131 | 3052 | 2006-05-19 | QBBI.A32R7 | 2052 | 2006-06-06 |  |  | 2006-06-06 | 2006-06-23 | 2006-06-07 | 2006-06-07 | 2006-06-08 | 2006-06-08 | ncrMEL | 2006-06-13 | 2006-06-21 |  | ncr ieg | [17 empty] | 21481.3131 | QBBI.A32R7
| 21496.9731 | 2052 | 2006-05-19 | QBBI.B32R7 | 2005 | 2006-06-06 |  |  | 2006-06-06 | 2006-06-23 | 2006-06-07 | 2006-06-07 | 2006-06-07 | 2006-06-07 | ncrMEL | 2006-06-13 | 2006-06-21 | [17 empty] | VACSEC.A31R4 |  | 21496.9731 | QBBI.B32R7
| 21503.4431 | 2005 | 2006-06-02 | QBQI.32R7 | 0001 | 2006-06-06 |  |  | 2006-06-06 | 2006-06-23 | [5 empty] | 2006-06-01 | 2006-06-15 | [19 empty] | 21503.4431 | QBQI.32R7
| 21519.1031 | 0001 | 2006-06-02 | QQBI.32R7 | 1016 | 2006-06-06 |  |  | 2006-06-06 | 2006-06-23 | 2006-06-06 | 2006-06-06 | 2006-06-07 | 2006-06-07 | ncrMEL | 2006-06-13 | 2006-06-15 |  | 2006-07-03 | [17 empty] | 21519.1031 | QQBI.32R7
E | 21534.7631 | 1016 | 2006-05-19 | QBBI.A33R7 | 3023 | 2006-06-09 |  |  | 2006-06-09 | 2006-06-23 | 2006-06-06 | 2006-06-06 | 2006-06-06 | 2006-06-26 | ncrMEL | 2006-06-01 | 2006-06-21 |  | 2006-07-03 | [17 empty] | 21534.7631 | QBBI.A33R7
| 21550.4231 | 3023 | 2006-05-17 | QBBI.B33R7 | 2041 | 2006-06-08 |  |  | 2006-06-08 | 2006-06-23 | 2006-06-01 | 2006-06-01 | 2006-06-06 | 2006-06-06 | ncrMEL | 2006-06-01 | 2006-06-21 |  | 2006-07-03 | [16 empty] | E | 21550.4231 | QBBI.B33R7
| 21556.8931 | 2041 | 2006-05-17 | QBQI.33R7 | 0009 | [10 empty] | 2006-06-01 | 2006-06-19 |  | 2006-07-03 | [17 empty] | 21556.8931 | QBQI.33R7
| 21572.5531 | 0009 | 2006-05-17 | QQBI.33R7 | 2016 | 2006-05-31 | 2006-06-13 |  | 2006-06-08 |  | 2006-06-15 | 2006-06-15 | 2006-06-21 | 2006-06-26 |  | 2006-06-01 | 2006-06-19 |  | 2006-07-03 | [17 empty] | 21572.5531 | QQBI.33R7
| 21588.2131 | 2016 | 2006-05-17 | QBBI.A34R7 | 1003 | 2006-05-31 | 2006-06-13 |  | 2006-06-08 |  | 2006-05-31 | 2006-05-31 | 2006-06-01 | 2006-06-21 |  | 2006-06-01 | 2006-06-19 |  | 2006-07-05 | [17 empty] | 21588.2131 | QBBI.A34R7
| 21603.8731 | 1003 | 2006-05-17 | QBBI.B34R7 | 3025 | 2006-05-30 | 2006-06-13 |  | 2006-05-30 |  | 2006-05-30 | 2006-05-30 | 2006-06-01 | 2006-06-21 |  | 2006-06-01 | 2006-06-19 |  | 2006-07-05 | [17 empty] | 21603.8731 | QBBI.B34R7
| 21610.3431 | 3025 | 2006-05-17 | QBQI.34R7 | 0012 | 2006-05-30 | 2006-06-13 |  | 2006-05-30 | [6 empty] | 2006-06-13 | 2006-06-14 | [19 empty] | 21610.3431 | QBQI.34R7
| 21626.0031 | 0012 | 2006-05-17 | QQBI.34L8 | 1025 | 2006-05-29 | 2006-06-13 |  | 2006-05-29 |  | ncr ieg |  | 2006-05-31 | 2006-06-27 |  | 2006-05-24 | 2006-06-14 |  | 2006-06-29 | [17 empty] | 21626.0031 | QQBI.34L8
| 21641.6631 | 1025 | 2006-05-19 | QBBI.B34L8 | 2017 | 2006-05-31 | ncr |  | 2006-05-31 |  | 2006-05-29 | 2006-05-29 | 2006-06-22 | 2006-06-27 |  | 2006-05-24 | 2006-06-14 |  | 2006-06-29 | [17 empty] | 21641.6631 | QBBI.B34L8
| 21657.3231 | 2017 | 2006-05-17 | QBBI.A34L8 | 3005 | 2006-05-24 | 2006-06-13 |  | 2006-05-24 |  | 2006-05-29 | 2006-05-29 | 2006-05-31 | 2006-06-27 |  | 2006-05-24 | 2006-06-14 |  | 2006-06-29 | [15 empty] | VACSEC.A31L5 |  | 21657.3231 | QBBI.A34L8
| 21663.7931 | 3005 | 2006-05-17 | QBQI.34L8 | 0026 | 2006-05-29 | 2006-06-13 |  | 2006-05-29 | [6 empty] | 2006-05-24 | 2006-06-14 |  | ncr ieg | [17 empty] | 21663.7931 | QBQI.34L8
| 21679.4531 | 0026 | 2006-05-17 | QQBI.33L8 | 3021 | 2006-05-24 | 2006-06-13 |  | 2006-05-24 |  | 2006-05-24 | 2006-06-13 | 2006-06-13 | 2006-06-27 |  | 2006-05-24 | 2006-06-14 |  | 2006-06-21 | [17 empty] | 21679.4531 | QQBI.33L8
| 21695.1131 | 3021 | 2006-05-17 | QBBI.B33L8 | 2050 | 2006-05-23 | 2006-06-13 |  | 2006-05-24 |  | 2006-05-24 | 2006-06-26 | 2006-05-31 | 2006-06-27 |  | 2006-06-13 | 2006-06-13 |  | 2006-06-21 | [17 empty] | 21695.1131 | QBBI.B33L8
| 21710.7731 | 2050 | 2006-05-17 | QBBI.A33L8 | 2523 | ncrREPLACE | 2006-06-13 |  | 2006-05-24 |  | 2006-05-24 | 2006-05-24 | 2006-05-29 | 2006-05-30 |  | 2006-05-24 | 2006-06-13 |  | 2006-06-21 | [17 empty] | 21710.7731 | QBBI.A33L8
| 21717.2431 | 2523 | 2006-05-17 | QBQI.33L8 | 0021 | ncrRETOUCHE | 2006-06-13 |  | 2006-05-24 | [6 empty] | 2006-05-24 | 2006-06-13 | [19 empty] | 21717.2431 | QBQI.33L8
D | 21732.9031 | 0021 | 2006-05-17 | QQBI.32L8 | 1027 | 2006-05-23 | 2006-06-13 |  | 2006-06-13 |  | 2006-05-23 | 2006-05-23 | 2006-06-08 |  |  | 2006-05-24 | 2006-06-13 |  | 2006-06-21 | [17 empty] | 21732.9031 | QQBI.32L8
| 21748.5631 | 1027 | 2006-05-17 | QBBI.B32L8 | 1139 | 2006-05-22 | 2006-06-13 |  | 2006-05-22 |  | 2006-05-23 | 2006-05-23 | 2006-05-29 | 2006-06-22 |  | 2006-06-13 | 2006-06-13 |  | 2006-06-21 | [16 empty] | F | 21748.5631 | QBBI.B32L8
| 21764.2231 | 1139 | 2006-05-17 | QBBI.A32L8 | 1033 | 2006-05-22 | 2006-06-13 |  | 2006-05-23 |  | 2006-05-22 | 2006-06-13 | 2006-05-24 | 2006-06-27 |  | 2006-06-13 | 2006-06-13 |  | 2006-06-21 | [17 empty] | 21764.2231 | QBBI.A32L8
| 21770.6931 | 1033 | 2006-05-17 | QBQI.32L8 | 0077 | [10 empty] | 2006-06-13 | 2006-06-28 |  | 2006-06-28 | [17 empty] | 21770.6931 | QBQI.32L8
| 21786.3531 | 0077 | 2006-02-16 | QQBI.31L8 | 3064 | 2006-02-14 | 2006-05-03 |  | 2006-03-16 | 2006-05-22 | 2006-02-15 | 2006-03-20 | 2006-02-22 | 2006-05-09 | 2006-06-21 | 2006-02-22 | 2006-03-21 |  | 2006-03-29 | 2006-07-08 | 2006-07-08 |  | 2006-07-08 | 2006-07-03 | [12 empty] | 21786.3531 | QQBI.31L8
| 21802.0131 | 3064 | 2006-02-16 | QBBI.B31L8 | 2044 | 2006-02-15 | 2006-05-03 |  | 2006-03-16 | 2006-05-22 | 2006-02-16 | 2006-03-20 | 2006-02-20 | 2006-04-27 | 2006-06-21 | 2006-02-22 | 2006-03-21 |  | 2006-06-21 | 2006-07-08 | 2006-07-08 |  | 2006-07-08 | 2006-07-03 | [12 empty] | 21802.0131 | QBBI.B31L8
| 21817.6731 | 2044 | 2006-02-16 | QBBI.A31L8 | 1140 | ncrREPLACE | 2006-05-03 |  | 2006-02-22 | 2006-05-22 | 2006-02-22 | 2006-03-20 | 2006-02-23 | 2006-04-27 | 2006-06-21 | 2006-02-22 | 2006-03-21 |  | 2006-03-30 | 2006-07-08 | 2006-07-08 |  | 2006-07-08 | 2006-07-03 | [10 empty] | VACSEC.A27L5 |  | 21817.6731 | QBBI.A31L8
| 21824.1431 | 1140 | 2006-03-21 | QBQI.31L8 | 0015 | 2006-04-10 | 2006-05-03 |  | 2006-04-26 | 2006-05-22 | 2006-06-13 | 2006-06-13 | 2006-06-27 |  |  | 2006-03-30 | 2006-06-29 |  |  | 2006-07-08 | [16 empty] | 21824.1431 | QBQI.31L8
| 21839.8031 | 0015 | 2006-03-21 | QQBI.30L8 | 3018 | 2006-04-05 | 2006-05-03 |  | 2006-04-26 | 2006-05-22 | 2006-04-06 | 2006-04-11 | 2006-04-10 | 2006-04-27 | 2006-06-07 | 2006-03-30 | 2006-05-30 |  | 2006-03-30 | 2006-07-07 | 2006-07-07 |  | 2006-07-07 | 2006-06-28 | 2006-07-05 | [11 empty] | 21839.8031 | QQBI.30L8
| 21855.4631 | 3018 | 2006-02-16 | QBBI.B30L8 | 1066 | 2006-02-15 | ncr |  | 2006-03-16 | 2006-05-22 | 2006-02-16 | 2006-03-20 | 2006-02-20 | 2006-05-04 | 2006-06-07 | 2006-02-22 | 2006-03-21 |  | 2006-03-30 | 2006-07-07 | 2006-07-07 |  | 2006-07-07 | 2006-06-28 | 2006-07-05 | [11 empty] | 21855.4631 | QBBI.B30L8
| 21871.1231 | 1066 | 2006-02-16 | QBBI.A30L8 | 3011 | ncrREPLACE | 2006-05-03 |  | 2006-02-22 | 2006-05-22 | 2006-02-23 | 2006-03-20 | 2006-02-27 | 2006-05-04 | 2006-06-07 | 2006-03-06 | 2006-03-21 |  | 2006-04-04 | 2006-07-07 | 2006-07-07 |  | 2006-07-07 | 2006-06-28 | 2006-07-05 | [11 empty] | 21871.1231 | QBBI.A30L8
| 21877.5931 | 3011 | 2006-03-21 | QBQI.30L8 | 0007 | 2006-04-10 | 2006-05-03 |  | 2006-05-16 | 2006-05-22 | 2006-06-13 |  | 2006-06-15 |  |  | 2006-04-26 | ncr ieg |  | 2006-03-29 | [17 empty] | 21877.5931 | QBQI.30L8
| 21893.2531 | 0007 | 2006-03-21 | QQBI.29L8 | 2033 | 2006-04-10 | 2006-05-03 |  | 2006-04-10 | 2006-05-22 | 2006-04-11 | 2006-04-11 | 2006-04-12 | 2006-05-09 | 2006-06-07 | 2006-03-30 | 2006-05-30 |  | 2006-03-28 | 2006-06-16 | 2006-06-17 |  | 2006-06-16 | 2006-06-28 | 2006-06-29 | [11 empty] | 21893.2531 | QQBI.29L8
| 21908.9131 | 2033 | 2006-02-16 | QBBI.B29L8 | 1009 | 2006-02-14 | 2006-03-17 |  | 2006-03-16 | 2006-05-22 | 2006-02-14 | 2006-03-20 | 2006-02-17 | 2006-04-20 | 2006-06-07 | 2006-03-02 | 2006-03-21 |  |  | 2006-06-16 | 2006-06-17 |  | 2006-06-16 | 2006-06-28 | 2006-06-29 | [11 empty] | 21908.9131 | QBBI.B29L8
| 21924.5731 | 1009 | 2006-02-16 | QBBI.A29L8 | 1136 | 2006-03-09 | 2006-03-17 |  | 2006-03-13 | 2006-05-22 | 2006-02-20 | 2006-03-20 | 2006-02-22 | 2006-04-27 | 2006-06-07 | 2006-02-21 | 2006-03-21 |  | 2006-04-04 | 2006-06-16 | 2006-06-17 |  | 2006-06-16 | 2006-06-28 | 2006-06-29 | [11 empty] | 21924.5731 | QBBI.A29L8
| 21931.0431 | 1136 | 2006-02-16 | QBQI.29L8 | 0013 | 2006-02-13 | 2006-03-17 |  | 2006-03-16 | 2006-05-22 | 2006-06-13 | 2006-06-13 | 2006-06-15 |  |  | 2006-03-02 | 2006-03-20 |  |  | 2006-07-07 | [16 empty] | 21931.0431 | QBQI.29L8
| 21946.7031 | 0013 | 2006-02-16 | QQBI.28L8 | 3015 | v1 coupe | ncr |  | 2006-03-16 | 2006-05-22 | 2006-02-20 | 2006-03-20 | 2006-02-21 | 2006-04-27 | 2006-06-07 | 2006-03-02 | 2006-03-20 |  | 2006-03-28 | 2006-07-06 | 2006-07-07 |  | 2006-07-06 | 2006-06-29 | 2006-07-05 | [11 empty] | 21946.7031 | QQBI.28L8
| 21962.3631 | 3015 | 2006-02-16 | QBBI.B28L8 | 2038 | v1 coupe | ncr v1 |  | 2006-03-16 | 2006-05-22 | 2006-01-13 | 2006-03-20 | 2006-02-16 | 2006-04-27 | 2006-06-07 | 2006-02-21 | 2006-03-20 |  | 2006-03-28 | 2006-06-16 | 2006-06-17 |  | 2006-06-16 | 2006-06-29 | 2006-07-05 | [11 empty] | 21962.3631 | QBBI.B28L8
| 21978.0231 | 2038 | 2006-02-16 | QBBI.A28L8 | 3013 | 2006-02-08 | 2006-03-17 |  | 2006-03-15 | 2006-05-22 | 2006-02-09 | 2006-04-10 | 2006-02-15 | 2006-04-27 | 2006-06-07 | 2006-02-21 | 2006-03-20 |  | 2006-03-28 | 2006-06-17 | 2006-06-17 |  | 2006-06-17 | 2006-06-29 | 2006-07-05 | [11 empty] | 21978.0231 | QBBI.A28L8
| 21984.4931 | 3013 | 2006-04-06 | QBQI.28L8 | 0082 | [5 empty] | 2006-06-28 | 2006-06-28 | 2006-06-29 |  |  | 2006-05-29 | 2006-06-13 |  | 2006-06-28 | 2006-07-06 | [16 empty] | 21984.4931 | QBQI.28L8
| 22000.1531 | 0082 | 2006-04-06 | QQBI.27L8 | 3057 | 2006-04-26 | 2006-05-15 |  | 2006-04-26 | 2006-05-15 | 2006-04-12 | 2006-04-12 | 2006-04-12 | 2006-04-27 | 2006-06-21 | 2006-04-26 | 2006-05-03 |  | 2006-05-03 | 2006-07-06 | 2006-07-06 |  | 2006-07-06 | 2006-06-29 | 2006-07-05 | [11 empty] | 22000.1531 | QQBI.27L8
| 22015.8131 | 3057 | 2006-02-16 | QBBI.B27L8 | 1018 | 2006-02-23 | 2006-05-15 |  | 2006-02-23 | 2006-05-15 | 2006-02-27 | 2006-04-10 | 2006-02-28 | 2006-04-27 | 2006-06-21 | 2006-03-02 | 2006-06-12 |  | 2006-03-27 | 2006-07-06 | 2006-07-06 |  | 2006-07-06 | 2006-06-29 | 2006-07-05 | [11 empty] | 22015.8131 | QBBI.B27L8
| 22031.4731 | 1018 | 2006-02-16 | QBBI.A27L8 | 2030 | 2006-04-26 | ncr lw |  | 2006-04-26 | 2006-05-15 | 2006-04-25 | 2006-04-25 | 2006-04-26 | 2006-04-27 | 2006-06-21 | 2006-03-06 | 2006-06-12 |  | 2006-05-03 | 2006-07-06 | 2006-07-06 |  | 2006-07-01 | 2006-06-29 | 2006-07-05 | [9 empty] | VACSEC.A23L5 |  | 22031.4731 | QBBI.A27L8
| 22037.9431 | 2030 | 2006-02-16 | QBQI.27L8 | 0020 | 2006-02-27 | 2006-05-15 |  | 2006-02-27 | 2006-05-15 | 2006-06-27 | 2006-06-27 | 2006-06-28 |  |  | 2006-03-02 | 2006-03-21 |  |  | 2006-07-06 | [16 empty] | 22037.9431 | QBQI.27L8
| 22053.6031 | 0020 | 2006-02-16 | QQBI.26L8 | 1040 | 2006-03-13 | 2006-05-15 |  | 2006-03-13 | 2006-05-15 | 2006-03-14 | 2006-04-10 | 2006-03-16 | 2006-04-27 | 2006-06-07 | 2006-03-06 | 2006-05-24 |  | 2006-03-27 | 2006-06-29 | 2006-06-29 |  | 2006-06-29 | 2006-06-28 | 2006-06-28 |  | 2006-07-11 | [9 empty] | 22053.6031 | QQBI.26L8
| 22069.2631 | 1040 | 2006-02-16 | QBBI.B26L8 | 3044 | 2006-02-23 | 2006-05-15 |  | 2006-02-23 | 2006-05-15 | 2006-02-27 | 2006-04-10 | 2006-02-28 | 2006-04-27 | 2006-06-07 | 2006-03-06 | 2006-03-21 |  | 2006-03-27 | 2006-06-29 | 2006-06-29 |  | 2006-06-29 | 2006-06-28 | 2006-06-28 |  | 2006-07-11 | [9 empty] | 22069.2631 | QBBI.B26L8
| 22084.9231 | 3044 | 2006-02-16 | QBBI.A26L8 | 3259 | 2006-04-25 | 2006-06-28 |  | 2006-04-25 | 2006-05-15 | 2006-04-13 | 2006-04-13 | 2006-04-18 | 2006-04-27 | 2006-06-07 | 2006-03-06 | 2006-04-26 |  | 2006-05-03 | 2006-06-29 | 2006-06-29 |  | 2006-06-29 | 2006-06-28 | 2006-06-28 |  | 2006-07-11 | [9 empty] | 22084.9231 | QBBI.A26L8
| 22091.3931 | 3259 | 2006-04-06 | QBQI.26L8 | 0029 | 2006-04-25 | 2006-06-28 |  | 2006-04-25 | 2006-05-15 | [5 empty] | 2006-04-26 | 2006-05-24 |  | 2006-05-02 | [17 empty] | 22091.3931 | QBQI.26L8
| 22107.0531 | 0029 | 2006-04-06 | QQBI.25L8 | 1135 | 2006-04-25 | 2006-05-15 |  | 2006-04-25 | 2006-05-15 | 2006-04-12 | 2006-04-12 | 2006-04-13 | 2006-04-27 | 2006-06-21 | 2006-04-26 | 2006-05-24 |  | 2006-05-02 | 2006-07-01 | 2006-07-01 |  | 2006-06-29 | 2006-06-27 | 2006-06-28 |  | 2006-07-11 | [9 empty] | 22107.0531 | QQBI.25L8
| 22122.7131 | 1135 | 2006-02-16 | QBBI.B25L8 | 2010 | 2006-02-01 | 2006-02-16 |  | 2006-03-13 | 2006-03-28 | 2006-02-08 | 2006-04-10 | 2006-02-14 | 2006-04-27 | 2006-06-21 | 2006-03-06 | 2006-03-21 |  | 2006-03-23 | 2006-06-29 | 2006-07-01 |  | 2006-06-29 | 2006-06-27 | 2006-06-28 |  | 2006-07-11 | [9 empty] | 22122.7131 | QBBI.B25L8
| 22138.3731 | 2010 | 2006-02-16 | QBBI.A25L8 | 2037 | 2006-02-01 | 2006-02-16 |  | 2006-03-13 | 2006-03-28 | 2006-02-17 | 2006-04-10 | 2006-02-22 | 2006-04-27 | 2006-06-21 | 2006-03-06 | 2006-03-22 |  | 2006-03-23 | 2006-06-29 | 2006-06-29 |  | 2006-06-29 | 2006-06-27 | 2006-06-28 |  | 2006-07-11 | [9 empty] | 22138.3731 | QBBI.A25L8
| 22144.8431 | 2037 | 2006-02-16 | QBQI.25L8 | 0018 | 2006-02-01 | 2006-02-16 |  | 2006-03-14 | 2006-03-28 | 2006-02-07 | 2006-06-26 | 2006-06-26 |  |  | 2006-03-08 | 2006-03-22 |  |  | 2006-07-01 | [16 empty] | 22144.8431 | QBQI.25L8
C | 22160.5031 | 0018 | 2006-02-16 | QQBI.24L8 | 3037 | 2006-01-31 | ncr |  | 2006-03-14 | 2006-03-28 | 2006-02-06 | 2006-04-10 | 2006-02-09 | 2006-04-27 | 2006-05-25 | 2006-03-08 | 2006-03-22 |  | 2006-03-23 | 2006-06-16 | 2006-06-17 |  | 2006-06-17 | 2006-06-06 | ok |  | 2006-07-11 | [9 empty] | 22160.5031 | QQBI.24L8
| 22176.1631 | 3037 | 2006-02-16 | QBBI.B24L8 | 1141 | 2006-01-31 | 2006-02-16 |  | 2006-03-15 | 2006-03-28 | 2006-02-03 | 2006-04-10 | 2006-02-08 | 2006-04-27 | 2006-05-25 | 2006-03-08 | 2006-03-23 |  | 2006-03-22 | 2006-06-17 | 2006-06-17 |  | 2006-06-17 | 2006-06-06 | ok |  | 2006-07-11 | [8 empty] | G | 22176.1631 | QBBI.B24L8
| 22191.8231 | 1141 | 2006-02-16 | QBBI.A24L8 | 2021 | 2006-01-30 | 2006-02-16 |  | 2006-02-27 | 2006-03-28 | 2006-02-02 | 2006-04-10 | 2006-02-08 | 2006-04-27 | 2006-05-25 | 2006-03-08 | 2006-03-23 |  | 2006-03-22 | 2006-06-17 | 2006-06-17 |  | 2006-06-17 | 2006-06-06 | ok |  | 2006-07-11 | [9 empty] | 22191.8231 | QBBI.A24L8
| 22198.2931 | 2021 | 2006-03-21 | QBQI.24L8 | 0083 | 2006-06-01 | 2006-06-13 |  | 2006-06-01 | 2006-06-16 | 2006-06-08 | 2006-06-28 | 2006-06-14 | [5 empty] | 2006-03-22 | 2006-07-01 | [16 empty] | 22198.2931 | QBQI.24L8
| 22213.9531 | 0083 | 2006-03-21 | QQBI.23L8 | 1137 | 2006-02-28 | 2006-03-07 |  | 2006-03-14 | 2006-03-28 | 2006-02-28 | 2006-04-10 | 2006-03-01 | 2006-04-25 | 2006-05-25 | 2006-03-08 | 2006-03-21 | 2006-03-28 | 2006-03-21 | 2006-06-21 | 2006-06-21 |  | 2006-06-17 | 2006-06-06 | 2006-06-14 |  | 2006-07-11 | [9 empty] | 22213.9531 | QQBI.23L8
| 22229.6131 | 1137 | 2006-02-16 | QBBI.B23L8 | 2022 | 2006-02-28 | 2006-03-07 |  | 2006-03-14 | 2006-03-28 | 2006-03-01 | 2006-04-10 | 2006-03-01 | 2006-04-25 | 2006-05-25 | 2006-03-08 | 2006-03-21 | 2006-03-28 | 2006-03-21 | 2006-06-15 | 2006-06-21 |  | 2006-06-15 | 2006-06-06 | 2006-06-14 |  | 2006-07-11 | [9 empty] | 22229.6131 | QBBI.B23L8
| 22245.2731 | 2022 | 2006-02-16 | QBBI.A23L8 | 1138 | 2006-03-01 | 2006-03-07 |  | 2006-03-01 | 2006-03-28 | 2006-03-01 | 2006-04-10 | 2006-03-02 | 2006-04-20 | 2006-05-25 | 2006-03-08 | 2006-03-21 | 2006-03-28 | 2006-03-22 | 2006-06-10 | 2006-06-15 |  | 2006-06-10 | 2006-06-06 | 2006-06-14 |  | 2006-07-11 | [7 empty] | VACSEC.A19L5 |  | 22245.2731 | QBBI.A23L8
| 22251.7431 | 1138 | 2006-03-21 | QBQI.23L8 | 0004 | 2006-03-01 | 2006-06-28 |  | 2006-03-01 | 2006-03-28 | 2006-06-08 | 2006-06-08 | 2006-06-14 |  |  | 2006-03-08 | 2006-03-20 | 2006-03-28 | [18 empty] | 22251.7431 | QBQI.23L8
| 22267.4031 | 0004 | 2006-03-21 | QQBI.22L8 | 2065 | 2006-03-02 | 2006-03-07 |  | 2006-03-02 | 2006-03-28 | 2006-03-02 | 2006-04-10 | 2006-03-06 | 2006-04-20 | 2006-05-23 | 2006-03-08 | 2006-03-20 | 2006-03-28 | 2006-06-28 | 2006-06-10 | 2006-06-10 |  | 2006-06-10 | 2006-05-23 | 2006-06-14 |  | 2006-05-15 | [9 empty] | 22267.4031 | QQBI.22L8
| 22283.0631 | 2065 | 2006-02-16 | QBBI.B22L8 | 3046 | 2006-03-02 | 2006-03-07 |  | 2006-03-02 | 2006-03-28 | 2006-03-02 | 2006-04-10 | 2006-03-06 | 2006-04-20 | 2006-05-23 | 2006-03-08 | 2006-03-16 | 2006-03-28 | 2006-03-20 | 2006-06-09 | 2006-06-09 |  | 2006-06-09 | 2006-05-23 | 2006-06-14 |  | 2006-05-15 | [9 empty] | 22283.0631 | QBBI.B22L8
| 22298.7231 | 3046 | 2006-02-16 | QBBI.A22L8 | 3263 | 2006-03-06 | 2006-03-07 |  | 2006-03-14 | 2006-03-28 | 2006-03-06 | 2006-04-10 | 2006-03-07 | 2006-04-20 | 2006-05-23 | 2006-03-08 | 2006-03-16 | 2006-03-28 | 2006-03-16 | 2006-06-09 | 2006-06-09 |  | 2006-06-09 | 2006-05-23 | 2006-06-14 |  | 2006-05-15 | [9 empty] | 22298.7231 | QBBI.A22L8
| 22305.1931 | 3263 | 2006-02-16 | QBQI.22L8 | 0048 | 2006-03-29 | ncrREPLACE |  | 2006-03-29 | 2006-04-21 | 2006-05-31 | 2006-05-31 | 2006-06-12 | [5 empty] | 2006-03-16 | 2006-07-07 | [5 empty] | 2006-06-08 | [10 empty] | 22305.1931 | QBQI.22L8
| 22320.8531 | 0048 | 2006-03-21 | QQBI.21L8 | 1142 | 2006-03-28 | 2006-04-21 |  | 2006-03-28 | 2006-04-21 | 2006-03-29 | 2006-03-30 | 2006-03-30 | 2006-04-25 | 2006-05-23 | 2006-04-25 | 2006-04-25 | 2006-05-15 | 2006-04-26 | 2006-06-08 | 2006-06-09 |  | 2006-06-08 | 2006-05-23 | ok |  | 2006-05-15 | 2006-07-11 |  |  | 2006-07-06 | [5 empty] | 22320.8531 | QQBI.21L8
| 22336.5131 | 1142 | 2006-03-21 | QBBI.B21L8 | 2007 | 2006-03-29 | ncr |  | 2006-03-29 | 2006-04-21 | 2006-03-29 | 2006-03-30 | 2006-04-03 | 2006-04-26 | 2006-05-23 | 2006-04-25 | 2006-04-25 | 2006-05-15 | 2006-04-26 | 2006-06-03 | 2006-06-03 |  | 2006-06-29 | 2006-05-23 | ok |  | 2006-05-15 | 2006-07-11 |  |  | 2006-07-06 | [5 empty] | 22336.5131 | QBBI.B21L8
| 22352.1731 | 2007 | 2006-02-16 | QBBI.A21L8 | 2036 | 2006-03-09 | 2006-04-21 |  | 2006-03-09 | 2006-04-21 | 2006-03-09 | 2006-04-19 | 2006-03-14 | 2006-04-19 | 2006-05-23 | 2006-03-08 | 2006-03-15 | 2006-05-15 | 2006-03-15 | 2006-06-03 | 2006-06-03 |  | 2006-06-03 | 2006-05-23 | 2006-06-21 |  | 2006-05-15 | 2006-07-11 |  |  | 2006-07-06 | [5 empty] | 22352.1731 | QBBI.A21L8
| 22358.6431 | 2036 | 2006-03-21 | QBQI.21L8 | 0011 | 2006-03-15 | 2006-04-21 |  | 2006-03-15 | 2006-04-21 | 2006-05-31 | 2006-05-31 | 2006-06-12 |  |  | 2006-03-08 | 2006-03-15 | 2006-05-15 |  | 2006-07-05 | [5 empty] | 2006-06-08 | [10 empty] | 22358.6431 | QBQI.21L8
| 22374.3031 | 0011 | 2006-03-21 | QQBI.20L8 | 1015 | 2006-03-08 | 2006-04-21 |  | 2006-03-08 | 2006-04-21 | 2006-03-09 | 2006-04-20 | 2006-03-09 | 2006-04-20 | 2006-05-23 | 2006-03-08 | 2006-03-15 | 2006-05-15 | 2006-03-15 | 2006-06-03 | 2006-06-03 |  | 2006-06-07 | 2006-05-22 | ok |  | 2006-05-15 | 20006-06-30 | [8 empty] | 22374.3031 | QQBI.20L8
| 22389.9631 | 1015 | 2006-03-21 | QBBI.B20L8 | 2028 | 2006-03-07 | 2006-04-21 |  | 2006-03-08 | 2006-04-21 | 2006-04-08 | 2006-04-19 | 2006-03-09 | 2006-04-19 | 2006-05-23 | 2006-03-08 | 2006-03-14 | 2006-05-15 | 2006-03-14 | 2006-06-03 | 2006-06-03 |  | 2006-06-03 | 2006-05-22 | ok |  | 2006-05-15 | 20006-06-30 | [8 empty] | 22389.9631 | QBBI.B20L8
| 22405.6231 | 2028 | 2006-03-21 | QBBI.A20L8 | 1029 | 2006-03-07 | 2006-04-21 |  | 2006-03-07 | 2006-04-21 | 2006-03-07 | 2006-04-19 | 2006-03-08 | 2006-04-19 | 2006-05-23 | 2006-03-08 | 2006-03-14 | 2006-05-15 | 2006-03-13 | 2006-06-03 | 2006-06-08 |  | 2006-06-03 | 2006-05-22 | 2006-06-21 |  | 2006-05-15 | 20006-06-30 | [8 empty] | 22405.6231 | QBBI.A20L8
| 22412.0931 | 1029 | 2006-03-21 | QBQI.20L8 | 0084 | [5 empty] | 2006-06-12 | 2006-06-12 | 2006-06-13 | [5 empty] | 2006-03-13 | 2006-07-05 | 2006-07-05 |  |  |  |  | 2006-06-08 |  |  | 2006-07-06 | [7 empty] | 22412.0931 | QBQI.20L8
| 22427.7531 | 0084 | 2006-03-21 | QQBI.19L8 | 3048 | 2006-03-06 | 2006-03-09 |  | 2006-03-15 | 2006-03-27 | 2006-03-07 | 2006-04-20 | 2006-03-07 | 2006-04-20 | 2006-05-23 | 2006-02-23 | 2006-02-23 | 2006-03-21 | 2006-03-13 | 2006-06-08 | 2006-06-09 |  | 2006-06-08 | 2006-05-22 | ok |  | 2006-05-15 | 2006-07-11 | [8 empty] | 22427.7531 | QQBI.19L8
| 22443.4131 | 3048 | 2006-02-16 | QBBI.B19L8 | 3270 | 2006-01-13 | ncr |  | 2006-01-23 | 2006-02-12 | 2006-01-18 | 2006-01-18 | 2006-01-18 | 2006-04-20 | 2006-05-23 | 2006-01-19 | 2006-02-07 | 2006-03-21 | 2006-02-07 | 2006-06-09 | 2006-06-09 |  | 2006-06-09 | 2006-05-22 | ok |  | 2006-05-15 | 2006-07-11 | [8 empty] | 22443.4131 | QBBI.B19L8
| 22459.0731 | 3270 | 2006-02-16 | QBBI.A19L8 | 3061 | 2006-01-12 | 2006-02-16 |  | 2006-01-23 | 2006-02-12 | 2006-01-16 | 2006-01-18 | 2006-01-17 | 2006-01-18 | 2006-05-23 | 2006-01-18 | 2006-02-07 | 2006-03-21 | 2006-02-07 | 2006-06-09 | 2006-06-10 |  | 2006-06-09 | 2006-05-22 | ok |  | 2006-05-15 | 2006-07-11 | [6 empty] | VACSEC.A15L5 |  | 22459.0731 | QBBI.A19L8
| 22465.5431 | 3061 | 2006-02-16 | QBQI.19L8 | 0044 | 2006-01-12 | 2006-03-09 |  | 2006-01-23 | 2006-02-12 | 2006-06-01 | 2006-06-01 | 2006-06-12 |  |  | 2006-01-18 | 2006-02-06 | 2006-03-21 |  | 2006-07-05 | [5 empty] | 2006-06-08 | [10 empty] | 22465.5431 | QBQI.19L8
| 22481.2031 | 0044 | 2006-02-16 | QQBI.18L8 | 1036 | 2006-01-11 | 2006-02-16 |  | 2006-01-18 | 2006-02-12 | 2006-01-13 | 2006-01-16 | 2006-01-16 | 2006-04-20 | 2006-04-28 | 2006-01-18 | 2006-02-06 | 2006-03-21 | 2006-02-07 | 2006-05-10 | 2006-05-24 | 2006-07-03 | 2006-05-10 | 2006-05-03 | 2006-05-04 |  | 2006-05-15 | 2006-07-11 | [8 empty] | 22481.2031 | QQBI.18L8
| 22496.8631 | 1036 | 2006-02-16 | QBBI.B18L8 | 3049 | 2006-01-10 | 2006-02-16 |  | 2006-01-18 | 2006-02-12 | 2006-01-12 | 2006-01-12 | 2006-01-16 | 2006-01-16 | 2006-04-28 | 2006-01-18 | 2006-02-06 | 2006-03-21 | 2006-02-07 | 2006-05-11 | 2006-05-12 | 2006-07-03 | 2006-05-11 | 2006-05-03 | 2006-05-04 |  | 2006-05-15 | 2006-07-11 | [8 empty] | 22496.8631 | QBBI.B18L8
| 22512.5231 | 3049 | 2006-01-11 | QBBI.A18L8 | 3012 | 2006-01-11 | 2006-02-16 |  | 2006-01-17 | 2006-02-12 | 2006-01-10 | 2006-01-12 | 2006-01-12 | 2006-04-04 | 2006-04-28 | 2006-01-17 | 2006-02-06 | 2006-03-21 | 2006-02-07 | 2006-05-09 | 2006-05-12 | 2006-07-03 | 2006-05-09 | 2006-05-03 | 2006-05-04 |  | 2006-05-15 | 2006-07-11 | [8 empty] | 22512.5231 | QBBI.A18L8
| 22518.9931 | 3012 | 2006-01-11 | QBQI.18L8 | 0042 | 2006-03-08 | ncr |  | 2006-01-30 | 2006-02-12 | 2006-04-18 | 2006-04-18 | 2006-04-18 | 2006-04-25 |  |  |  |  | 2006-02-09 | 2006-07-05 | 2006-06-26 | 2006-07-03 |  |  |  | 2006-05-04 | [10 empty] | 22518.9931 | QBQI.18L8
| 22534.6531 | 0042 | 2006-01-11 | QQBI.17L8 | 2042 | 2005-12-20 | 2006-03-21 |  | 2006-01-17 | 2006-02-12 | 2006-01-10 | 1900-03-30 | 2006-01-12 | 2006-01-12 | 2006-03-28 | 2006-01-06 | 2006-02-06 | 2006-03-21 | 2006-02-09 | 2006-04-12 | 2006-05-23 | 2006-07-03 | 2006-04-12 | 2006-05-03 | 2006-05-04 |  | 2006-05-15 | 2006-05-11 |  | 2006-05-17 | 2006-05-23 | [5 empty] | 22534.6531 | QQBI.17L8
| 22550.3131 | 2042 | 2006-01-11 | QBBI.B17L8 | 2006 | 2005-12-20 | 2006-02-16 |  | 2006-03-15 | 2006-03-27 | 2006-01-09 | 2006-01-10 | 2006-01-10 | 2006-01-10 | 2006-03-28 | 2006-01-12 | 2006-02-06 | 2006-03-21 | 2006-02-16 | 2006-05-17 | 2006-05-12 | 2006-07-03 | 2006-05-17 | 2006-05-03 | 2006-05-04 |  | 2006-05-15 | 2006-05-11 |  | 2006-05-17 | 2006-05-23 | [5 empty] | 22550.3131 | QBBI.B17L8
| 22565.9731 | 2006 | 2006-01-11 | QBBI.A17L8 | 2056 | 2005-12-19 | 2006-02-16 |  | 2006-01-17 | 2006-02-12 | 2006-01-09 | 2006-01-09 | 2006-01-09 | 2006-01-12 | 2006-03-28 | 2006-01-12 | 2006-02-06 | 2006-03-21 | 2006-02-16 | 2006-04-24 | 2006-05-12 | 2006-07-03 | 2006-04-24 | 2006-05-03 | 2006-05-04 |  | 2006-05-15 | 2006-05-11 |  | 2006-05-17 | 2006-05-23 | [5 empty] | 22565.9731 | QBBI.A17L8
| 22572.4431 | 2056 | 2006-01-11 | QBQI.17L8 | 0046 | 2005-12-19 | 2006-02-16 |  | 2006-01-17 | 2006-02-12 | 2006-04-13 | 2006-04-13 | 2006-04-18 | 2006-04-25 |  | 2006-01-12 | 2006-02-06 | 2006-03-21 |  | 2006-06-02 | [5 empty] | 2006-05-04 |  |  | 2006-05-12 | [7 empty] | 22572.4431 | QBQI.17L8
B | 22588.1031 | 0046 | 2006-01-11 | QQBI.16L8 | 3003 | 2005-12-15 | 2006-02-16 |  | 2006-01-17 | 2006-02-12 | 2006-01-05 | 2006-01-06 | 2006-01-06 | 2006-04-10 | 2006-04-01 | 2006-01-09 | 2006-02-06 | 2006-03-21 | 2006-02-16 | 2006-05-17 | 2006-05-23 | 2006-06-21 | 2006-05-17 | 2006-05-03 | 2006-05-04 |  | 2006-05-15 | 2006-05-20 |  | 2006-07-04 | 2006-06-15 | [5 empty] | 22588.1031 | QQBI.16L8
| 22603.7631 | 3003 | 2006-01-11 | QBBI.B16L8 | 3063 | 2006-06-08 | 2006-06-16 |  | 2006-01-16 | 2006-02-12 | 2005-12-20 | 2006-01-05 | 2006-01-05 | 2006-04-10 | 2006-04-01 | 2006-01-09 | 2006-02-06 | 2006-03-21 | 2006-02-16 | 2006-05-22 | 2006-06-07 | 2006-06-21 | 2006-05-22 | 2006-05-03 | 2006-05-04 |  | 2006-05-15 | 2006-05-20 |  | 2006-07-04 | 2006-06-15 |  |  |  |  | H | 22603.7631 | QBBI.B16L8
| 22619.4231 | 3063 | 2006-01-11 | QBBI.A16L8 | 3504 | 2005-12-15 | 2006-02-16 |  | 2006-01-16 | 2006-02-12 | 2005-12-19 | 2005-12-20 | 2005-12-20 | 2006-04-10 | 2006-04-01 | 2006-01-09 | 2006-02-06 | 2006-03-21 | 2006-02-16 | 2006-05-16 | 2006-05-23 | 2006-06-21 | 2006-05-16 | 2006-05-03 | 2006-05-04 |  | 2006-05-15 | 2006-05-20 |  | 2006-07-04 | 2006-06-15 | [5 empty] | 22619.4231 | QBBI.A16L8
| 22625.8931 | 3504 | 2006-01-11 | QBQI.16L8 | 0049 | 2005-12-14 | 2006-02-16 |  | 2006-05-03 | 2006-06-02 | 2005-12-16 | 2005-12-20 | 2005-12-19 | 2006-04-10 | 2006-04-01 |  |  |  | 2006-03-09 | 2006-06-01 | 2006-06-26 | 2006-07-04 |  |  |  | 2006-05-18 |  |  | 2006-06-21 | [7 empty] | 22625.8931 | QBQI.16L8
| 22641.5531 | 0049 | 2006-01-11 | QQBI.15L8 | 3009 | 2006-02-20 | 2006-03-21 |  | 2006-02-20 | 2006-03-27 | 2006-05-18 | 2006-05-18 | 2006-05-23 | 2006-05-31 |  | 2005-12-12 | 2006-02-06 | 2006-03-21 | 2006-02-20 | 2006-06-10 | 2006-06-10 | 2006-06-21 | 2006-06-10 | 2006-05-15 | 2006-05-16 |  | 2006-05-15 | 2006-06-13 |  | 2006-07-04 | 2006-06-15 | [5 empty] | 22641.5531 | QQBI.15L8
| 22657.2131 | 3009 | 2005-12-01 | QBBI.B15L8 | 2014 | 2005-11-22 | 2006-02-16 |  | 2005-12-01 | 2006-02-12 | 2005-11-23 | 2005-12-07 | 2005-12-06 | 2005-12-13 | 2006-03-28 | 2005-11-28 | 2005-12-02 | 2006-03-21 | 2006-02-21 | 2006-04-19 | 2006-05-15 | 2006-06-21 | 2006-04-19 | 2006-05-15 | 2006-05-16 |  | 2006-05-15 | 2006-06-13 |  | 2006-07-04 | 2006-06-19 | [5 empty] | 22657.2131 | QBBI.B15L8
| 22672.8731 | 2014 | 2005-12-01 | QBBI.A15L8 | 3058 | 2005-12-05 | 2006-02-16 |  | 2005-12-06 | 2006-02-12 | 2005-12-06 | 2005-12-08 | 2005-12-07 | 2005-12-13 | 2006-03-28 | 2005-12-06 | 2005-12-08 | 2006-03-21 | 2006-01-19 | 2006-04-20 | 2006-05-15 | 2006-06-21 | 2006-04-20 | 2006-05-15 | 2006-05-16 |  | 2006-05-15 | 2006-06-13 |  | 2006-07-04 | 2006-06-19 |  |  |  | VACSEC.A11L5 |  | 22672.8731 | QBBI.A15L8
| 22679.3431 | 3058 | 2005-12-01 | QBQI.15L8 | 0045 | 2005-11-21 | 2006-02-16 |  | 2005-12-01 | 2006-02-12 | 2005-11-23 | 2005-11-23 | 2005-12-01 | 2006-03-23 | 2006-03-28 | 2005-11-28 | 2005-12-02 | 2006-03-21 |  | 2006-04-24 | [5 empty] | 2006-06-06 |  |  | 2006-06-21 | [7 empty] | 22679.3431 | QBQI.15L8
| 22695.0031 | 0045 | 2005-12-01 | QQBI.14L8 | 1519 | 2005-11-21 | ncr |  | 2005-12-01 | 2006-02-12 | 2005-11-22 | 2005-12-07 | 2005-11-30 | 2005-12-12 | 2006-03-28 | 2005-11-28 | 2005-12-08 | 2006-03-21 | 2006-01-20 | 2006-05-18 | 2006-05-22 | 2006-06-21 | 2006-05-18 | 2006-05-15 | 2006-05-17 |  | 2006-05-15 | 2006-06-13 |  | 2006-07-06 | 2006-06-19 | [5 empty] | 22695.0031 | QQBI.14L8
| 22710.6631 | 1519 | 2005-12-01 | QBBI.B14L8 | 2031 | 2005-11-17 | ncr |  | 2005-11-30 | 2006-02-12 | 2005-11-21 | 2005-12-07 | 2005-11-29 | 2005-12-12 | 2006-03-28 | 2005-11-28 | 2005-12-06 | 2006-03-21 | 2006-01-09 | 2006-04-20 | 2006-05-15 | 2006-06-21 | 2006-04-20 | 2006-05-15 | 2006-05-17 |  | 2006-05-15 | 2006-06-13 |  | 2006-07-06 | 2006-06-19 | [5 empty] | 22710.6631 | QBBI.B14L8
| 22726.3231 | 2031 | 2005-12-01 | QBBI.A14L8 | 3038 | 2005-02-02 | 2006-02-16 |  | 2005-12-06 | 2006-02-12 | 2006-05-03 | 2006-05-03 | 2006-05-03 | 2006-05-23 |  | 2005-12-12 | 2006-02-02 | 2006-03-21 | 2006-02-21 | 2006-06-01 | 2006-06-01 | 2006-06-21 | 2006-06-07 | 2006-05-15 | 2006-05-17 |  | 2006-05-15 | 2006-06-13 |  | 2006-07-06 | 2006-06-19 | [5 empty] | 22726.3231 | QBBI.A14L8
| 22732.7931 | 3038 | 2006-01-11 | QBQI.14L8 | 0349 | 2005-12-07 | 2006-02-16 |  | 2006-01-16 | 2006-03-27 | 2005-12-08 | 2006-04-11 | 2005-12-12 | 2006-04-11 | 2006-03-28 |  |  |  | 2006-01-09 | 2006-06-01 | 2006-07-05 | 2006-07-07 |  |  |  | 2006-06-06 |  |  | 2006-06-21 | [7 empty] | 22732.7931 | QBQI.14L8
| 22748.4531 | 0349 | 2006-01-11 | QQBI.13L8 | 3065 | 2005-12-07 | 2006-02-16 |  | 2006-01-13 | 2006-03-27 | 2005-12-09 | 2005-12-14 | 2006-01-23 | 2006-04-10 | 2006-03-28 | 2006-01-09 | 2006-02-02 | 2006-03-21 | 2006-01-06 | 2006-05-18 | 2006-05-22 | 2006-06-21 | 2006-05-18 | 2006-05-16 | 2006-05-22 |  | 2006-05-15 | 2006-06-13 |  | 2006-07-11 | 2006-06-20 | [5 empty] | 22748.4531 | QQBI.13L8
| 22764.1131 | 3065 | 2006-02-16 | QBBI.B13L8 | 3002 | 2006-01-18 | 2006-02-16 |  | 2006-02-22 | 2006-03-27 | 2006-01-19 | 2006-01-19 | 2006-01-19 | 2006-04-20 | 2006-03-28 | 2006-01-23 | 2006-02-02 | 2006-03-21 | 2006-02-21 | 2006-05-23 | 2006-06-07 | 2006-06-21 | 2006-05-23 | 2006-05-16 | 2006-05-22 |  | 2006-05-15 | 2006-06-13 |  | 2006-07-11 | 2006-06-19 | [5 empty] | 22764.1131 | QBBI.B13L8
| 22779.7731 | 3002 | 2006-02-16 | QBBI.A13L8 | 3029 | 2006-02-21 | 2006-20-03 |  | 2006-02-21 | 2006-03-27 | 2006-02-21 | 2006-05-23 | 2006-05-04 | 2006-05-23 |  | 2006-02-21 | 2006-02-21 | 2006-03-21 | 2006-02-21 | 2006-06-01 | 2006-06-01 | 2006-06-21 | 2006-06-01 | 2006-05-16 | 2006-05-22 |  | 2006-05-15 | 2006-06-13 |  | 2006-07-11 | 2006-06-19 | [5 empty] | 22779.7731 | QBBI.A13L8
| 22786.2431 | 3029 | 2006-01-11 | QBQI.13L8 | 0043 | 2005-12-14 | 2006-02-16 |  | 2005-12-14 | 2006-02-12 | 2005-12-13 | 2006-03-23 | 2005-12-15 | 2006-03-23 | 2006-03-28 | 2006-01-16 | 2006-02-02 | 2006-03-21 |  | 2006-04-12 | [5 empty] | 2006-06-06 |  |  | 2006-06-15 | [7 empty] | 22786.2431 | QBQI.13L8
| 22801.9031 | 0043 | 2006-01-11 | QQBI.12L8 | 1017 | 2005-12-13 | 2006-02-16 |  | 2006-01-09 | 2006-02-12 | 2005-12-15 | 2005-12-08 | 2005-12-16 | 2006-01-13 | 2006-03-28 | 2006-01-17 | 2006-02-02 | 2006-03-21 | 2006-06-28 | 2006-04-19 | 2006-05-22 |  | 2006-04-19 | 2006-05-17 | 2006-05-22 |  | 2006-05-15 | [9 empty] | 22801.9031 | QQBI.12L8
| 22817.5631 | 1017 | 2005-12-01 | QBBI.B12L8 | 1133 | 2005-11-24 | ncr |  | 2005-11-30 | 2006-02-12 | 2005-11-30 | 2005-12-08 | 2005-12-05 | 2005-12-12 | 2006-03-28 | 2005-12-06 | 2005-12-08 | 2006-03-21 | 2006-01-06 | 2006-04-18 | 2006-05-05 |  | 2006-04-18 | 2006-05-17 | 2006-05-22 |  | 2006-05-15 | [9 empty] | 22817.5631 | QBBI.B12L8
| 22833.2231 | 1133 | 2005-12-01 | QBBI.A12L8 | 3034 | 2005-11-23 | 2006-02-16 |  | 2005-12-07 | 2006-02-12 | 2005-11-30 | 2005-12-08 | 2005-12-05 | 2005-12-12 | 2006-03-28 | 2005-12-01 | 2005-12-06 | 2006-03-21 | 2006-01-06 | 2006-04-18 | 2006-05-05 |  | 2006-04-18 | 2006-05-17 | 2006-05-22 |  | 2006-05-15 | [9 empty] | 22833.2231 | QBBI.A12L8
| 22839.6931 | 3034 | 2006-05-18 | QBQI.12L8 | [32 empty] | 22839.6931 | QBQI.12L8
| 22855.3531 |  | 2006-05-18 | QQEI.11L8 | 0001 | 2006-06-09 | 2006-06-21 |  | 2006-06-09 |  | 2006-06-09 | 2006-06-09 | 2006-06-13 | 2006-06-21 |  | 2006-06-28 | 2006-06-29 |  | 2006-06-22 | [17 empty] | 22855.3531 | QQEI.11L8
| 22871.0131 | 0001 | 2006-05-18 | QEBI.11L8 | 3066 | 2006-06-07 | 2006-06-21 |  | 2006-06-07 |  | 2006-06-09 | 2006-06-09 | 2006-06-13 | 2006-06-28 |  | 2006-06-19 | 2006-06-26 |  | 2006-06-26 | [17 empty] | 22871.0131 | QEBI.11L8
| 22886.6731 | 3066 | 2005-12-01 | QBBI.11L8 | 3264 | 2005-11-30 | 2006-05-03 |  | 2005-12-05 | 2006-05-15 | 2005-12-01 | 2005-12-08 | 2005-12-05 | 2005-12-05 |  | 2005-12-01 | 2005-12-05 |  | 2006-06-28 | [15 empty] | VACSEC.A7L5 |  | 22886.6731 | QBBI.11L8
| 22894.4181 | 3264 | 2006-03-29 | QBQI.11L8 | 0602 | 2006-04-04 | 2006-05-03 |  | 2006-04-04 | 2006-05-15 | [5 empty] | 2006-03-30 | 2006-06-28 | [19 empty] | 22894.4181 | QBQI.11L8
| 22907.1928 | 0602 | 2006-03-29 | QQBI.10L8 | 3053 | 2006-04-04 | 2006-05-03 |  | 2006-04-04 | 2006-05-15 | 2006-04-05 | 2006-04-11 | 2006-04-06 | 2006-04-11 | 2006-07-11 | 2006-03-30 | 2006-04-27 |  | 2006-05-02 | [17 empty] | 22907.1928 | QQBI.10L8
| 22922.8528 | 3053 | 2006-03-29 | QBBI.10L8 | 1030 | 2006-03-30 | 2006-05-03 |  | 2006-03-30 | 2006-05-15 | 2006-04-03 | 2006-04-03 | 2006-04-04 | 2006-04-11 | 2006-07-11 | 2006-03-30 | 2006-04-27 |  | 2006-05-02 | [17 empty] | 22922.8528 | QBBI.10L8
| 22938.5128 | 1030 | 2006-03-29 | QBQI.10L8 | 0613 | 2006-04-04 | ncr |  | 2006-04-04 | 2006-05-15 | [8 empty] | 2006-05-02 | [17 empty] | 22938.5128 | QBQI.10L8
| 22946.2578 | 0613 | 2006-04-02 | QQBI.9L8 | 3062 | ncrREPLACE | 2006-05-03 |  | 2006-04-03 | 2006-05-15 | 2006-04-05 | 2006-04-11 | 2006-04-05 | 2006-06-28 | 2006-07-11 | 2006-04-26 | 2006-04-27 | 2006-07-11 | 2006-05-02 | [17 empty] | 22946.2578 | QQBI.9L8
| 22961.9178 | 3062 | 2006-04-02 | QBBI.9L8 | 3036 | 2006-04-03 | 2006-05-03 |  | 2006-04-03 | 2006-05-15 | 2006-04-04 | 2006-04-11 | 2006-04-04 | 2006-06-28 | 2006-07-11 | 2006-04-26 | 2006-04-27 | 2006-07-11 | 2006-05-02 | [17 empty] | 22961.9178 | QBBI.9L8
| 22977.5778 | 3036 | 2006-03-29 | QBQI.9L8 | 0601 | 2006-03-30 | 2006-05-03 |  | 2006-04-27 | 2006-05-15 | 2006-04-03 | 2006-04-03 |  |  |  | 2006-04-26 | 2006-04-27 | 2006-07-11 | [18 empty] | 22977.5778 | QBQI.9L8
| 22986.7228 | 0601 | 2006-03-29 | QQBI.8L8 | 3051 | 2006-04-03 | 2006-05-03 |  | 2006-04-03 | 2006-05-15 | 2006-04-04 | 2006-04-11 | 2006-04-05 | 2006-04-11 |  | 2006-04-26 | 2006-04-27 | 2006-07-11 | 2006-04-27 | [17 empty] | 22986.7228 | QQBI.8L8
A | 23002.3828 | 3051 | 2006-05-18 | QBBI.8L8 | 3016 | 2006-06-12 | 2006-06-21 |  | 2006-06-12 |  | 2006-06-09 | 2006-06-09 | 2006-07-07 |  |  | 2006-06-27 | 2006-06-27 | 2006-07-11 | 2006-06-26 | [17 empty] | 23002.3828 | QBBI.8L8
| 23018.0428 | 3016 | 2006-06-13 | QBQI.8L8 | 0604 | 2006-06-22 |  |  | 2006-06-22 |  | 2006-06-29 | 2006-06-29 |  |  |  | 2006-06-19 | 2006-06-27 | 2006-07-11 | 2006-06-22 | [16 empty] | I | 23018.0428 | QBQI.8L8
| TOTAL |  |  | 202 | /210 | 175 | 89 | 0 | 189 | 102 | 171 | 169 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 47 | 10 | 45 | 24 | 6 | 15 | 18 | 0 | 0 | 0
[44 empty] | test | test

## JUMPER
QRL sector | Decum | Jumper | CY | VAC test CY | XB | Vac test XB | KD1 | Vac test KD1 | KD2 | Vac test KD2 | CC' | Vac test CC' | LD1 | Vac test LD1 | LD2 | Vac test LD2 | Thermal shield | Bellow | Jumper | performed operations | Percentage Jumper welds accomplished
A |  | Q7R7 | [16 empty] | Q7R7 | 0 | 0%
B |  | Q9R7 | [16 empty] | Q9R7 | 0 | 0%
B |  | Q11R7 | [16 empty] | Q11R7 | 0 | 0%
B |  | Q13R7 | [16 empty] | Q13R7 | 0 | 0%
B |  | Q15R7 | [16 empty] | Q15R7 | 0 | 0%
C |  | Q17R7 | [16 empty] | Q17R7 | 0 | 0%
C |  | Q19R7 | [16 empty] | Q19R7 | 0 | 0%
C |  | Q21R7 | [16 empty] | Q21R7 | 0 | 0%
C |  | Q23R7 | [16 empty] | Q23R7 | 0 | 0%
D |  | Q25R7 | [16 empty] | Q25R7 | 0 | 0%
D |  | Q27R7 | [16 empty] | Q27R7 | 0 | 0%
D |  | Q29R7 | [16 empty] | Q29R7 | 0 | 0%
D |  | Q31R7 | [16 empty] | Q31R7 | 0 | 0%
E |  | Q33R7 | [16 empty] | Q33R7 | 0 | 0%
E |  | Q33L8 | [16 empty] | Q33L8 | 0 | 0%
F |  | Q31L8 | [16 empty] | Q31L8 | 0 | 0%
F |  | Q29L8 | [16 empty] | Q29L8 | 0 | 0%
F |  | Q27L8 | [16 empty] | Q27L8 | 0 | 0%
F |  | Q25L8 | [16 empty] | Q25L8 | 0 | 0%
G |  | Q23L8 | 2006-05-30 | [15 empty] | Q23L8 | 1 | 11.11%
G |  | Q21L8 | 2006-05-30 |  | 2006-05-30 | [13 empty] | Q21L8 | 2 | 22.22%
G |  | Q19L8 | done? |  | 2006-05-30 | [13 empty] | Q19L8 | 1 | 11.11%
G |  | Q17L8 | 2006-05-30 | 2006-07-03 | 2006-05-30 | 2006-07-03 | done? |  | done? |  | done? | [7 empty] | Q17L8 | 2 | 22.22%
H |  | Q15L8 | [16 empty] | Q15L8 | 0 | 0%
H |  | Q13L8 | done? |  | done? | [13 empty] | Q13L8 | 0 | 0%
H |  | Q11L8 | [16 empty] | Q11L8 | 0 | 0%
H |  | Q9L8 | [16 empty] | Q9L8 | 0 | 0%
I |  | Q7L8 | [16 empty] | Q7L8 | 0 | 0%

## time-analysis pre int
week | start date (Monday) | end date (Sunday) | magnet in place | magnet aligned | pre inspection | cumulative magnet aligned | cumulative magnet pre-inspected
48 | 2005-09-01 | 2005-12-04 | 211 | 16 | 0 | 16 | 0
49 | 2005-12-05 | 2005-12-11 | 0 | 12 | 0 | 28 | 0
50 | 2005-12-12 | 2005-12-18 | -1 | 5 | 191 | 33 | 191
51 | 2005-12-19 | 2005-12-25 | 210 | 1 | 200 | 34 | 391
52 | 2005-12-26 | 2006-01-01 | COUNT(IC!H$2:H$216)-COUNTIF(IC!H$2:H$216;">04/12/05")-COUNTIF(IC!H$2:H$216;"<28/11/05") | 0 | 9 | 34 | 400
1 | 2006-01-02 | 2006-01-08 | 0 | 0 | 169 | 34 | 569
2 | 2006-01-09 | 2006-01-15 | -1 | 0 | -1 | 34 | 568
3 | 2006-01-16 | 2006-01-22 | 210 | 14 | 200 | 48 | 768
4 | 2006-01-23 | 2006-01-29 | 210 | 16 | 200 | 64 | 968
5 | 2006-01-30 | 2006-02-05 | 211 | 11 | 126 | 75 | 1094
6 | 2006-02-06 | 2006-02-12 | 0 | 0 | 3 | 75 | 1097
7 | 2006-02-13 | 2006-02-19 | 210 | 6 | 200 | 81 | 1297
8 | 2006-02-20 | 2006-02-26 | 210 | 0 | 200 | 81 | 1497
9 | 2006-02-27 | 2006-03-05 | 211 | 0 | 126 | 81 | 1623
10 | 2006-03-06 | 2006-03-12 | 0 | 20 | 3 | 101 | 1626
11 | 2006-03-13 | 2006-03-19 | 210 | 1 | 200 | 102 | 1826
12 | 2006-03-20 | 2006-03-26 | 210 | 8 | 200 | 110 | 2026
13 | 2006-03-27 | 2006-04-02 | 211 | 21 | 32 | 131 | 2058
14 | 2006-04-03 | 2006-04-09 | 0 | 0 | 133 | 131 | 2191
15 | 2006-04-10 | 2006-04-16 | -1 | 0 | -1 | 131 | 2190
16 | 2006-04-17 | 2006-04-23 | 210 | 0 | 200 | 131 | 2390
17 | 2006-04-24 | 2006-04-30 | 210 | 0 | 200 | 131 | 2590
18 | 2006-05-01 | 2006-05-07 | 0 | 0 | 192 | 131 | 2782
19 | 2006-05-08 | 2006-05-14 | -1 | 0 | -1 | 131 | 2781
20 | 2006-05-15 | 2006-05-21 | 210 | 0 | 200 | 131 | 2981
21 | 2006-05-22 | 2006-05-28 | 210 | 0 | 200 | 131 | 3181
22 | 2006-05-29 | 2006-06-04 | 211 | 0 | 108 | 131 | 3289
23 | 2006-06-05 | 2006-06-11 | 0 | 0 | 75 | 131 | 3364
24 | 2006-06-12 | 2006-06-18 | -1 | 0 | -1 | 131 | 3363
25 | 2006-06-19 | 2006-06-25 | 210 | 0 | 200 | 131 | 3563
26 | 2006-06-26 | 2006-07-02 | 211 | 0 | 32 | 131 | 3595
27 | 2006-07-03 | 2006-07-09 | 0 | 0 | 133 | 131 | 3728
28 | 2006-07-10 | 2006-07-16 | -1 | 0 | -1 | 131 | 3727
29 | 2006-07-17 | 2006-07-23 | 210 | 0 | 200 | 131 | 3927
30 | 2006-07-24 | 2006-07-30 | 210 | 0 | 200 | 131 | 4127
31 | 2006-07-31 | 2006-08-06 | 211 | 0 | 198 | 131 | 4325
32 | 2006-08-07 | 2006-08-13 | -1 | 0 | -1 | 131 | 4324
33 | 2006-08-14 | 2006-08-20 | 210 | 0 | 200 | 131 | 4524
34 | 2006-08-21 | 2006-08-27 | 210 | 0 | 200 | 131 | 4724
35 | 2006-08-28 | 2006-09-03 | 211 | 0 | 68 | 131 | 4792
36 | 2006-09-04 | 2006-09-10 | 0 | 0 | 93 | 131 | 4885
37 | 2006-09-11 | 2006-09-17 | -1 | 0 | -1 | 131 | 4884
38 | 2006-09-18 | 2006-09-24 | 210 | 0 | 200 | 131 | 5084
39 | 2006-09-25 | 2006-10-01 | 211 | 0 | 30 | 131 | 5114
40 | 2006-10-02 | 2006-10-08 | 0 | 0 | 169 | 131 | 5283
41 | 2006-10-09 | 2006-10-15 | -1 | 0 | -1 | 131 | 5282
42 | 2006-10-16 | 2006-10-22 | 210 | 0 | 200 | 131 | 5482
43 | 2006-10-23 | 2006-10-29 | 210 | 0 | 200 | 131 | 5682
44 | 2006-10-30 | 2006-11-05 | 211 | 0 | 198 | 131 | 5880
45 | 2006-11-06 | 2006-11-12 | 0 | 0 | 3 | 131 | 5883
46 | 2006-11-13 | 2006-11-19 | 211 | 0 | 201 | 131 | 6084
47 | 2006-11-20 | 2006-11-26 | 210 | 0 | 200 | 131 | 6284
48 | 2006-11-27 | 2006-12-03 | 211 | 0 | 68 | 131 | 6352
49 | 2006-12-04 | 2006-12-10 | 0 | 0 | 93 | 131 | 6445
50 | 2006-12-11 | 2006-12-17 | -1 | 0 | -1 | 131 | 6444
51 | 2006-12-18 | 2006-12-24 | 210 | 0 | 200 | 131 | 6644
52 | 2006-12-25 | 2006-12-31 | 210 | 0 | 200 | 131 | 6844
TOTAL |  |  | 7142 | 131 | 6844
Formulas:
end date (Sunday) = [start date (Monday), row below]-1
end date (Sunday) = [start date (Monday)]+6
start date (Monday) = [end date (Sunday)]-6
start date (Monday) = [end date (Sunday), row above]+1

## work status int
[5 empty] | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 5.714% | 0% | 14.29% | 0% | 2.857% | 5.714% | 5.714% | 0%
SUB SECTOR | DCUM RING START | magnet down | Interconnect number | magnet up | Weld V1 V2 | VAC test V1 V2 | Weld E | VAC test E | Solder Main BB | Insulate Main BB | US weld Spools | Insulate spools | PAQ | solder Y | weld X | VAC test X | weld C' | weld M3 | weld K1,K2 | VAC test circuit K1K2C' | weld M1,M2 | insert N | cable N | AIV 1 | US weld N (cables) | AIV 2 | Weld N (sleeve) | insulate N Weld M2N | Close W | VAC final test
A | 0 | HCLBBRB000-IN001031 | QBBI.8R7 | HCLBARA000-IN003026 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20255.3214 | 0 | QBQI.8R7 | HCLBBRB000-IN001031 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20263.0664 | HCLBARA000-IN003050 | QQBI.8R7 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
B | 20278.7264 | HCLBBRC000-IN001044 | QBBI.9R7 | HCLBARA000-IN003050 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20294.3864 | 0 | QBQI.9R7 | HCLBBRC000-IN001044 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20302.1314 | HCLBARA000-IN001052 | QQBI.9R7 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20317.7914 | HCLBBRB000-IN001032 | QBBI.10R7 | HCLBARA000-IN001052 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20333.4514 | 0 | QBQI.10R7 | HCLBBRB000-IN001032 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20342.5964 | HCLBARA000-IN003022 | QQBI.10R7 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20358.2564 | HCLBBRA000-IN001034 | QBBI.11R7 | HCLBARA000-IN003022 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20373.9164 | HCLEDR_000-CR000001 | QBEI.11R7 | HCLBBRA000-IN001034 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20381.6614 | 0 | QEQI.11R7 | HCLEDR_000-CR000001 | 0% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20397.3214 | HCLBARA000-IN002018 | QQBI.11R7 | 0 | 0% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20412.9814 | HCLBBRA000-IN001010 | QBBI.A12R7 | HCLBARA000-IN002018 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20426.6981 | HCLBARB000-IN002039 | QBBI.B12R7 | HCLBBRA000-IN001010 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20434.4431 | HCLQATH001-CR000245 | QBQI.12R7 | HCLBARB000-IN002039 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20450.1031 | HCLBBRA000-IN003041 | QQBI.12R7 | HCLQATH001-CR000245 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20465.7631 | HCLBARA000-IN001054 | QBBI.A13R7 | HCLBBRA000-IN003041 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20481.4231 | HCLBBRC000-IN003019 | QBBI.B13R7 | HCLBARA000-IN001054 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20487.8931 | HCLQATM001-CR000019 | QBQI.13R7 | HCLBBRC000-IN003019 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20503.5531 | HCLBARA000-IN003030 | QQBI.13R7 | HCLQATM001-CR000019 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20519.2131 | HCLBBRA000-IN001004 | QBBI.A14R7 | HCLBARA000-IN003030 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20534.8731 | HCLBARB000-IN002015 | QBBI.B14R7 | HCLBBRA000-IN001004 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20541.3431 | HCLQATH001-CR000037 | QBQI.14R7 | HCLBARB000-IN002015 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20557.0031 | HCLBBRA000-IN003020 | QQBI.14R7 | HCLQATH001-CR000037 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20572.6631 | HCLBARA000-IN003010 | QBBI.A15R7 | HCLBBRA000-IN003020 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20588.3231 | HCLBBRC000-IN001022 | QBBI.B15R7 | HCLBARA000-IN003010 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20594.7931 | 0 | QBQI.15R7 | HCLBBRC000-IN001022 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20610.4531 | HCLBARA000-IN003279 | QQBI.15R7 | 0 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20626.1131 | HCLBBRA000-IN001008 | QBBI.A16R7 | HCLBARA000-IN003279 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20641.7731 | HCLBARB000-IN003028 | QBBI.B16R7 | HCLBBRA000-IN001008 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20648.2431 | HCLQATH001-CR000041 | QBQI.16R7 | HCLBARB000-IN003028 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20663.9031 | HCLBBRA000-IN002008 | QQBI.16R7 | HCLQATH001-CR000041 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20679.5631 | HCLBARA000-IN003055 | QBBI.A17R7 | HCLBBRA000-IN002008 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | 20695.2231 | HCLBBRC000-IN001035 | QBBI.B17R7 | HCLBARA000-IN003055 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20701.6931 | HCLQATM001-CR000039 | QBQI.17R7 | HCLBBRC000-IN001035 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20717.3531 | HCLBARA000-IN003006 | QQBI.17R7 | HCLQATM001-CR000039 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20733.0131 | HCLBBRA000-IN001021 | QBBI.A18R7 | HCLBARA000-IN003006 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20748.6731 | HCLBARB000-IN002029 | QBBI.B18R7 | HCLBBRA000-IN001021 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20755.1431 | HCLQATH001-CR000031 | QBQI.18R7 | HCLBARB000-IN002029 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20770.8031 | HCLBBRA000-IN002004 | QQBI.18R7 | HCLQATH001-CR000031 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20786.4631 | HCLBARA000-IN001045 | QBBI.A19R7 | HCLBBRA000-IN002004 | 0% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20802.1231 | HCLBBRC000-IN002009 | QBBI.B19R7 | HCLBARA000-IN001045 | 0% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20808.5931 | 0 | QBQI.19R7 | HCLBBRC000-IN002009 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20824.2531 | HCLBARA000-IN003054 | QQBI.19R7 | 0 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20839.9131 | HCLBBRA000-IN002002 | QBBI.A20R7 | HCLBARA000-IN003054 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20855.5731 | HCLBARB000-IN003043 | QBBI.B20R7 | HCLBBRA000-IN002002 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20862.0431 | HCLQATH001-CR000249 | QBQI.20R7 | HCLBARB000-IN003043 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20877.7031 | HCLBBRA000-IN003014 | QQBI.20R7 | HCLQATH001-CR000249 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20893.3631 | HCLBARA000-IN001012 | QBBI.A21R7 | HCLBBRA000-IN003014 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20909.0231 | HCLBBRC000-IN001024 | QBBI.B21R7 | HCLBARA000-IN001012 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20915.4931 | HCLQATM001-CR000040 | QBQI.21R7 | HCLBBRC000-IN001024 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20931.1531 | HCLBARA000-IN003007 | QQBI.21R7 | HCLQATM001-CR000040 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20946.8131 | HCLBBRA000-IN001023 | QBBI.A22R7 | HCLBARA000-IN003007 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20962.4731 | HCLBARB000-IN002020 | QBBI.B22R7 | HCLBBRA000-IN001023 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20968.9431 | HCLQOAG001-CR000002 | QBQI.22R7 | HCLBARB000-IN002020 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 20984.6031 | HCLBBRA000-IN003042 | QQBI.22R7 | HCLQOAG001-CR000002 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21000.2631 | HCLBARA000-IN001014 | QBBI.A23R7 | HCLBBRA000-IN003042 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21015.9231 | HCLBBRC000-IN001039 | QBBI.B23R7 | HCLBARA000-IN001014 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21022.3931 | 0 | QBQI.23R7 | HCLBBRC000-IN001039 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21038.0531 | HCLBARA000-IN003027 | QQBI.23R7 | 0 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21053.7131 | HCLBBRA000-IN001020 | QBBI.A24R7 | HCLBARA000-IN003027 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21069.3731 | HCLBARB000-IN003008 | QBBI.B24R7 | HCLBBRA000-IN001020 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21075.8431 | HCLQOAG001-CR000016 | QBQI.24R7 | HCLBARB000-IN003008 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21091.5031 | HCLBBRA000-IN002012 | QQBI.24R7 | HCLQOAG001-CR000016 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21107.1631 | HCLBARA000-IN001051 | QBBI.A25R7 | HCLBBRA000-IN002012 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
D | 21122.8231 | HCLBBRC000-IN001006 | QBBI.B25R7 | HCLBARA000-IN001051 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21129.2931 | HCLQOAR001-CR000003 | QBQI.25R7 | HCLBBRC000-IN001006 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21144.9531 | HCLBARA000-IN001053 | QQBI.25R7 | HCLQOAR001-CR000003 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21160.6131 | HCLBBRA000-IN001038 | QBBI.A26R7 | HCLBARA000-IN001053 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21176.2731 | HCLBARB000-IN001055 | QBBI.B26R7 | HCLBBRA000-IN001038 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21182.7431 | HCLQOAG001-CR000017 | QBQI.26R7 | HCLBARB000-IN001055 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21198.4031 | HCLBBRA000-IN003039 | QQBI.26R7 | HCLQOAG001-CR000017 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21214.0631 | HCLBARA000-IN003024 | QBBI.A27R7 | HCLBBRA000-IN003039 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21229.7231 | HCLBBRC000-IN001049 | QBBI.B27R7 | HCLBARA000-IN003024 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21236.1931 | HCLQASE001-CR000078 | QBQI.27R7 | HCLBBRC000-IN001049 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21251.8531 | HCLBARA000-IN002034 | QQBI.27R7 | HCLQASE001-CR000078 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21267.5131 | HCLBBRA000-IN002048 | QBBI.A28R7 | HCLBARA000-IN002034 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21283.1731 | HCLBARB000-IN002011 | QBBI.B28R7 | HCLBBRA000-IN002048 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21289.6431 | HCLQOAG001-CR000023 | QBQI.28R7 | HCLBARB000-IN002011 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21305.3031 | HCLBBRA000-IN001042 | QQBI.28R7 | HCLQOAG001-CR000023 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21320.9631 | HCLBARA000-IN001013 | QBBI.A29R7 | HCLBBRA000-IN001042 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21336.6231 | HCLBBRC000-IN003017 | QBBI.B29R7 | HCLBARA000-IN001013 | 0% | 0% | 0% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21343.0931 | HCLQOBF001-CR000014 | QBQI.29R7 | HCLBBRC000-IN003017 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21358.7531 | HCLBARA000-IN002019 | QQBI.29R7 | HCLQOBF001-CR000014 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21374.4131 | HCLBBRA000-IN001007 | QBBI.A30R7 | HCLBARA000-IN002019 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21390.0731 | HCLBARB000-IN002027 | QBBI.B30R7 | HCLBBRA000-IN001007 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21396.5431 | HCLQOAM001-CR000008 | QBQI.30R7 | HCLBARB000-IN002027 | 8.571% | 0% | 4.286% | 0% | 11.43% | 0% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21412.2031 | HCLBBRA000-IN001041 | QQBI.30R7 | HCLQOAM001-CR000008 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21427.8631 | HCLBARA000-IN002026 | QBBI.A31R7 | HCLBBRA000-IN001041 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21443.5231 | HCLBBRC000-IN001028 | QBBI.B31R7 | HCLBARA000-IN002026 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21449.9931 | HCLQOAV001-CR000076 | QBQI.31R7 | HCLBBRC000-IN001028 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21465.6531 | HCLBARA000-IN003052 | QQBI.31R7 | HCLQOAV001-CR000076 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21481.3131 | HCLBBRA000-IN002052 | QBBI.A32R7 | HCLBARA000-IN003052 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21496.9731 | HCLBARB000-IN002005 | QBBI.B32R7 | HCLBBRA000-IN002052 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21503.4431 | HCLQOAG001-CR000001 | QBQI.32R7 | HCLBARB000-IN002005 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21519.1031 | HCLBBRA000-IN001016 | QQBI.32R7 | HCLQOAG001-CR000001 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21534.7631 | HCLBARA000-IN003023 | QBBI.A33R7 | HCLBBRA000-IN001016 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
E | 21550.4231 | HCLBBRC000-IN002041 | QBBI.B33R7 | HCLBARA000-IN003023 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21556.8931 | HCLQOBJ001-CR000009 | QBQI.33R7 | HCLBBRC000-IN002041 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21572.5531 | HCLBARA000-IN002016 | QQBI.33R7 | HCLQOBJ001-CR000009 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21588.2131 | HCLBBRA000-IN001003 | QBBI.A34R7 | HCLBARA000-IN002016 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21603.8731 | HCLBARB000-IN003025 | QBBI.B34R7 | HCLBBRA000-IN001003 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21610.3431 | HCLQOAM001-CR000012 | QBQI.34R7 | HCLBARB000-IN003025 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21626.0031 | HCLBBRA000-IN001025 | QQBI.34L8 | HCLQOAM001-CR000012 | 8.571% | 0% | 4.286% | 0% | 11.43% | 0% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21641.6631 | HCLBARA000-IN002017 | QBBI.B34L8 | HCLBBRA000-IN001025 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21657.3231 | HCLBBRC000-IN003005 | QBBI.A34L8 | HCLBARA000-IN002017 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21663.7931 | HCLQOBF001-CR000026 | QBQI.34L8 | HCLBBRC000-IN003005 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21679.4531 | HCLBARA000-IN003021 | QQBI.33L8 | HCLQOBF001-CR000026 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21695.1131 | HCLBARB000-IN002523 | QBBI.A33L8 | HCLBBRA000-IN002050 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21710.7731 | HCLQOAM001-CR000021 | QBQI.33L8 | HCLBARB000-IN002523 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21717.2431 | HCLBBRA000-IN001027 | QQBI.32L8 | HCLQOAM001-CR000021 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21732.9031 | HCLBARA000-IN001139 | QBBI.B32L8 | HCLBBRA000-IN001027 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
F | 21748.5631 | HCLBBRC000-IN001033 | QBBI.A32L8 | HCLBARA000-IN001139 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21764.2231 | HCLQOAV001-CR000077 | QBQI.32L8 | HCLBBRC000-IN001033 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21770.6931 | HCLBARA000-IN003064 | QQBI.31L8 | HCLQOAV001-CR000077 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21786.3531 | HCLBBRA000-IN002044 | QBBI.B31L8 | HCLBARA000-IN003064 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21802.0131 | HCLBARB000-IN001140 | QBBI.A31L8 | HCLBBRA000-IN002044 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21817.6731 | HCLQOAG001-CR000015 | QBQI.31L8 | HCLBARB000-IN001140 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21824.1431 | HCLBBRA000-IN003018 | QQBI.30L8 | HCLQOAG001-CR000015 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21839.8031 | HCLBARA000-IN001066 | QBBI.B30L8 | HCLBBRA000-IN003018 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21855.4631 | HCLBBRC000-IN003011 | QBBI.A30L8 | HCLBARA000-IN001066 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21871.1231 | HCLQOBF001-CR000007 | QBQI.30L8 | HCLBBRC000-IN003011 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21877.5931 | HCLBARA000-IN002033 | QQBI.29L8 | HCLQOBF001-CR000007 | 8.571% | 0% | 4.286% | 0% | 11.43% | 0% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21893.2531 | HCLBBRA000-IN001009 | QBBI.B29L8 | HCLBARA000-IN002033 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21908.9131 | HCLBARB000-IN001136 | QBBI.A29L8 | HCLBBRA000-IN001009 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21924.5731 | HCLQOAM001-CR000013 | QBQI.29L8 | HCLBARB000-IN001136 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21931.0431 | HCLBBRA000-IN003015 | QQBI.28L8 | HCLQOAM001-CR000013 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21946.7031 | HCLBARA000-IN002038 | QBBI.B28L8 | HCLBBRA000-IN003015 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21962.3631 | HCLBBRC000-IN003013 | QBBI.A28L8 | HCLBARA000-IN002038 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21978.0231 | HCLQASE001-CR000082 | QBQI.28L8 | HCLBBRC000-IN003013 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 21984.4931 | HCLBARA000-IN003057 | QQBI.27L8 | HCLQASE001-CR000082 | 0% | 0% | 0% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22000.1531 | HCLBBRA000-IN001018 | QBBI.B27L8 | HCLBARA000-IN003057 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22015.8131 | HCLBARB000-IN002030 | QBBI.A27L8 | HCLBBRA000-IN001018 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22031.4731 | HCLQOAG001-CR000020 | QBQI.27L8 | HCLBARB000-IN002030 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | #REF! | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22037.9431 | HCLBBRA000-IN001040 | QQBI.26L8 | HCLQOAG001-CR000020 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22053.6031 | HCLBARA000-IN003044 | QBBI.B26L8 | HCLBBRA000-IN001040 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22069.2631 | HCLBBRC000-IN003259 | QBBI.A26L8 | HCLBARA000-IN003044 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22084.9231 | HCLQOBN001-CR000029 | QBQI.26L8 | HCLBBRC000-IN003259 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22091.3931 | HCLBARA000-IN001135 | QQBI.25L8 | HCLQOBN001-CR000029 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22107.0531 | HCLBBRA000-IN002010 | QBBI.B25L8 | HCLBARA000-IN001135 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22122.7131 | HCLBARB000-IN002037 | QBBI.A25L8 | HCLBBRA000-IN002010 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22138.3731 | HCLQOAG001-CR000018 | QBQI.25L8 | HCLBARB000-IN002037 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22144.8431 | HCLBBRA000-IN003037 | QQBI.24L8 | HCLQOAG001-CR000018 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22160.5031 | HCLBARA000-IN001141 | QBBI.B24L8 | HCLBBRA000-IN003037 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
G | 22176.1631 | HCLBBRD000-IN002021 | QBBI.A24L8 | HCLBARA000-IN001141 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22191.8231 | HCLQASF001-CR000083 | QBQI.24L8 | HCLBBRD000-IN002021 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22198.2931 | HCLBARA000-IN001137 | QQBI.23L8 | HCLQASF001-CR000083 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0% | 0% | 0% | 2.857% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22213.9531 | HCLBBRA000-IN002022 | QBBI.B23L8 | HCLBARA000-IN001137 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22229.6131 | HCLBARB000-IN001138 | QBBI.A23L8 | HCLBBRA000-IN002022 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22245.2731 | HCLQOAG001-CR000004 | QBQI.23L8 | HCLBARB000-IN001138 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22251.7431 | HCLBBRA000-IN002065 | QQBI.22L8 | HCLQOAG001-CR000004 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22267.4031 | HCLBARA000-IN003046 | QBBI.B22L8 | HCLBBRA000-IN002065 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22283.0631 | HCLBBRD000-IN003263 | QBBI.A22L8 | HCLBARA000-IN003046 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22298.7231 | HCLQATK001-CR000048 | QBQI.22L8 | HCLBBRD000-IN003263 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22305.1931 | HCLBARA000-IN001142 | QQBI.21L8 | HCLQATK001-CR000048 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0% | 0% | 0% | 2.857% | 2.857% | 0% | 0% | 0% | 0% | 5.714% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22320.8531 | HCLBBRA000-IN002007 | QBBI.B21L8 | HCLBARA000-IN001142 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22336.5131 | HCLBARB000-IN002036 | QBBI.A21L8 | HCLBBRA000-IN002007 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22352.1731 | HCLQATH001-CR000011 | QBQI.21L8 | HCLBARB000-IN002036 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22358.6431 | HCLBBRA000-IN001015 | QQBI.20L8 | HCLQATH001-CR000011 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 5.714% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22374.3031 | HCLBARA000-IN002028 | QBBI.B20L8 | HCLBBRA000-IN001015 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22389.9631 | HCLBBRD000-IN001029 | QBBI.A20L8 | HCLBARA000-IN002028 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22405.6231 | HCLQATO001-CR000084 | QBQI.20L8 | HCLBBRD000-IN001029 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22412.0931 | HCLBARA000-IN003048 | QQBI.19L8 | HCLQATO001-CR000084 | 0% | 0% | 0% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0% | 0% | 0% | 2.857% | 2.857% | 3.571% | 0% | 0% | 0% | 5.714% | 0% | 14.29% | 0% | 0% | 0% | 0% | 0%
| 22427.7531 | HCLBBRA000-IN003270 | QBBI.B19L8 | HCLBARA000-IN003048 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22443.4131 | HCLBARB000-IN003061 | QBBI.A19L8 | HCLBBRA000-IN003270 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22459.0731 | HCLQATH001-CR000044 | QBQI.19L8 | HCLBARB000-IN003061 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22465.5431 | HCLBBRA000-IN001036 | QQBI.18L8 | HCLQATH001-CR000044 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 5.714% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22481.2031 | HCLBARA000-IN003049 | QBBI.B18L8 | HCLBBRA000-IN001036 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22496.8631 | HCLBBRD000-IN003012 | QBBI.A18L8 | HCLBARA000-IN003049 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22512.5231 | HCLQATK001-CR000042 | QBQI.18L8 | HCLBBRD000-IN003012 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22518.9931 | HCLBARA000-IN002042 | QQBI.17L8 | HCLQATK001-CR000042 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0% | 0% | 0% | 2.857% | 2.857% | 3.571% | 0% | 0% | 0% | 5.714% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22534.6531 | HCLBBRA000-IN002006 | QBBI.B17L8 | HCLBARA000-IN002042 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22550.3131 | HCLBARB000-IN002056 | QBBI.A17L8 | HCLBBRA000-IN002006 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22565.9731 | HCLQATH001-CR000046 | QBQI.17L8 | HCLBARB000-IN002056 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22572.4431 | HCLBBRA000-IN003003 | QQBI.16L8 | HCLQATH001-CR000046 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 5.714% | 0% | 14.29% | 0% | 0% | 0% | 0% | 0%
| 22588.1031 | HCLBARA000-IN003063 | QBBI.B16L8 | HCLBBRA000-IN003003 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
H | 22603.7631 | HCLBBRD000-IN003504 | QBBI.A16L8 | HCLBARA000-IN003063 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22619.4231 | HCLQATO001-CR000049 | QBQI.16L8 | HCLBBRD000-IN003504 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22625.8931 | HCLBARA000-IN003009 | QQBI.15L8 | HCLQATO001-CR000049 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0% | 0% | 0% | 2.857% | 2.857% | 3.571% | 0% | 0% | 0% | 5.714% | 0% | 14.29% | 0% | 0% | 0% | 0% | 0%
| 22641.5531 | HCLBBRA000-IN002014 | QBBI.B15L8 | HCLBARA000-IN003009 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22657.2131 | HCLBARB000-IN003058 | QBBI.A15L8 | HCLBBRA000-IN002014 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22672.8731 | HCLQATH001-CR000045 | QBQI.15L8 | HCLBARB000-IN003058 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22679.3431 | HCLBBRA000-IN001519 | QQBI.14L8 | HCLQATH001-CR000045 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 5.714% | 0% | 14.29% | 0% | 0% | 0% | 0% | 0%
| 22695.0031 | HCLBARA000-IN002031 | QBBI.B14L8 | HCLBBRA000-IN001519 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22710.6631 | HCLBBRD000-IN003038 | QBBI.A14L8 | HCLBARA000-IN002031 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22726.3231 | HCLQATK001-CR000349 | QBQI.14L8 | HCLBBRD000-IN003038 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22732.7931 | HCLBARA000-IN003065 | QQBI.13L8 | HCLQATK001-CR000349 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0% | 0% | 0% | 2.857% | 2.857% | 3.571% | 0% | 0% | 0% | 5.714% | 0% | 14.29% | 0% | 0% | 0% | 0% | 0%
| 22748.4531 | HCLBBRA000-IN003002 | QBBI.B13L8 | HCLBARA000-IN003065 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22764.1131 | HCLBARB000-IN003029 | QBBI.A13L8 | HCLBBRA000-IN003002 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22779.7731 | HCLQATH001-CR000043 | QBQI.13L8 | HCLBARB000-IN003029 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0%
| 22786.2431 | HCLBBRA000-IN001017 | QQBI.12L8 | HCLQATH001-CR000043 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 5.714% | 0% | 14.29% | 0% | 0% | 0% | 0% | 0%
| 22801.9031 | HCLBARA000-IN001133 | QBBI.B12L8 | HCLBBRA000-IN001017 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22817.5631 | HCLBBRD000-IN003034 | QBBI.A12L8 | HCLBARA000-IN001133 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22833.2231 | 0 | QBQI.12L8 | HCLBBRD000-IN003034 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22839.6931 | HCLEBR_000-CR000001 | QQEI.11L8 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22855.3531 | HCLBARA000-IN003066 | QEBI.11L8 | HCLEBR_000-CR000001 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22871.0131 | HCLBBRP000-IN003264 | QBBI.11L8 | HCLBARA000-IN003066 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22886.6731 | HCLQNCE001-CR000602 | QBQI.11L8 | HCLBBRP000-IN003264 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22894.4181 | HCLBARE000-IN003053 | QQBI.10L8 | HCLQNCE001-CR000602 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22907.1928 | HCLBBRG000-IN001030 | QBBI.10L8 | HCLBARE000-IN003053 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22922.8528 | HCLQNJF001-CR000613 | QBQI.10L8 | HCLBBRG000-IN001030 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22938.5128 | HCLBARE000-IN003062 | QQBI.9L8 | HCLQNJF001-CR000613 | 8.571% | 0% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22946.2578 | HCLBBRF000-IN003036 | QBBI.9L8 | HCLBARE000-IN003062 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22961.9178 | HCLQNCE001-CR000601 | QBQI.9L8 | HCLBBRF000-IN003036 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22977.5778 | HCLBARE000-IN003051 | QQBI.8L8 | HCLQNCE001-CR000601 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 22986.7228 | HCLBBRQ000-IN003016 | QBBI.8L8 | HCLBARE000-IN003051 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 23002.3828 | HCLQNFI001-CR000604 | QBQI.8L8 | HCLBBRQ000-IN003016 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
I | 23018.0428 | 0 | QQDI.7L8 | HCLQNFI001-CR000604 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 0% | 0% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 23025.7878 | HCLBRCC001-BL000002 | QQBM.4L8 | HCLQYEB001-CR000607 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 23041.4478 | 0 | QBDI.3L8 | HCLBX__001-BL000002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL

## work status sub sec vac
| 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 5.714% | 0% | 14.29% | 0% | 2.857% | 5.714% | 5.714% | 0%
vacuum sector | Weld V1 V2 | VAC test V1 V2 | Weld E | VAC test E | Solder Main BB | Insulate Main BB | US weld Spools | Insulate spools | PAQ | solder Y | weld X | VAC test X | weld C' | weld M3 | weld K1,K2 | VAC test circuit K1K2C' | weld M1,M2 | insert N | cable N | AIV 1 | US weld N (cables) | AIV 2 | Weld N (sleeve) | insulate N Weld M2N | Close W | VAC final test
VACSEC.A7R4 | 2.449% | 0% | 1.837% | 0% | 4.082% | 1.02% | 1.633% | 0.8163% | 0% | 0.1531% | 0% | 0% | 0.4082% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VACSEC.A11R4 | 6.964% | 0% | 3.482% | 0% | 7.143% | 1.786% | 3.571% | 1.786% | 0% | 0.625% | 2.143% | 0% | 1.607% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VACSEC.A15R4 | 6.964% | 0% | 4.018% | 0% | 8.571% | 2.143% | 4.286% | 2.143% | 0% | 0.7143% | 2.679% | 0% | 0.1786% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VACSEC.A19R4 | 8.036% | 0% | 4.018% | 0% | 8.571% | 2.143% | 4.286% | 2.143% | 0% | 0.7143% | 2.411% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VACSEC.A23R4 | 8.036% | 0% | 4.018% | 0% | 9.286% | 2.321% | 4.643% | 2.143% | 0% | 0.7143% | 0.8036% | 0% | 0.1786% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VACSEC.A27R4 | 8.036% | 0% | 4.018% | 0% | 10.71% | 2.5% | 5% | 2.143% | 0% | 0.7143% | 4.286% | 0% | 2.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VACSEC.A31R4 | 7.857% | 0% | 3.929% | 0% | 8.571% | 1.905% | 4.286% | 2.143% | 0% | 0.7143% | 4.286% | 0% | 2.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VACSEC.A31L5 | 7.857% | 0% | 3.929% | 0% | 8.571% | 2.143% | 4.286% | 1.905% | 0% | 0.7143% | 4.286% | 0% | 2.619% | 0.4762% | 0.5952% | 0% | 1.19% | 1.429% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VACSEC.A27L5 | 8.036% | 0% | 4.018% | 0% | 11.43% | 2.679% | 5.714% | 2.143% | 0% | 0.7143% | 4.286% | 0% | 2.321% | 2.679% | 2.679% | 0% | 5.357% | 6.429% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VACSEC.A23L5 | 8.571% | 0% | 4.286% | 0% | 10.71% | 2.679% | 5.357% | 2.143% | 0% | 0.6696% | 4.018% | 0% | 2.5% | 2.679% | 2.679% | 0% | #REF! | 6.429% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
VACSEC.A19L5 | 8.036% | 0% | 4.018% | 0% | 11.43% | 2.857% | 5.714% | 2.143% | 0% | 0.625% | 3.75% | 0% | 2.5% | 2.679% | 2.902% | 0% | 5.357% | 6.429% | 1.071% | 0% | 0.8929% | 0% | 0.5357% | 0% | 0% | 0%
VACSEC.A15L5 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.679% | 0% | 0.625% | 3.75% | 0% | 2.5% | 2.857% | 3.125% | 0% | 5.357% | 6.429% | 1.429% | 0% | 1.786% | 0% | 1.429% | 0% | 0% | 0%
VACSEC.A11L5 | 8.036% | 0% | 4.018% | 0% | 10.71% | 2.679% | 5.357% | 2.679% | 0% | 0.625% | 3.75% | 0% | 2.321% | 2.321% | 2.455% | 0% | 4.464% | 5.357% | 1.071% | 0% | 2.679% | 0% | 1.25% | 0% | 0% | 0%
VACSEC.A7L5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Sub Sector | Weld package I (V1, V2, E line) | Vacuum test I (V1, V2, E line) | Bus bar brazing | Bus bar insulation | PAQ | Weld package II ( cryo-lines+ M1, M2, M3) | Vacuum test cryo lines | N line and final M welds | AIV 1 | AIV 2 | Close W
VACSEC.A7R4 | 4.286% | 0% | 5.714% | 1.02% | 0% | 0.5612% | 0% | 0% | 0% | 0% | 0%
VACSEC.A11R4 | 10.45% | 0% | 10.71% | 1.786% | 0% | 4.375% | 0% | 0% | 0% | 0% | 0%
VACSEC.A15R4 | 10.98% | 0% | 12.86% | 2.143% | 0% | 3.571% | 0% | 0% | 0% | 0% | 0%
VACSEC.A19R4 | 12.05% | 0% | 12.86% | 2.143% | 0% | 3.125% | 0% | 0% | 0% | 0% | 0%
VACSEC.A23R4 | 12.05% | 0% | 13.93% | 2.321% | 0% | 1.696% | 0% | 0% | 0% | 0% | 0%
VACSEC.A27R4 | 12.05% | 0% | 15.71% | 2.5% | 0% | 7.5% | 0% | 0% | 0% | 0% | 0%
VACSEC.A31R4 | 11.79% | 0% | 12.86% | 1.905% | 0% | 7.143% | 0% | 0% | 0% | 0% | 0%
VACSEC.A31L5 | 11.79% | 0% | 12.86% | 2.143% | 0% | 9.881% | 0% | 1.429% | 0% | 0% | 0%
VACSEC.A27L5 | 12.05% | 0% | 17.14% | 2.679% | 0% | 18.04% | 0% | 6.429% | 0% | 0% | 0%
VACSEC.A23L5 | 12.86% | 0% | 16.07% | 2.679% | 0% | #REF! | 0% | 6.429% | 0% | 0% | 0%
VACSEC.A19L5 | 12.05% | 0% | 17.14% | 2.857% | 0% | 17.81% | 0% | 8.929% | 0% | 0% | 0%
VACSEC.A15L5 | 12.86% | 0% | 17.14% | 2.857% | 0% | 18.21% | 0% | 11.07% | 0% | 0% | 0%
VACSEC.A11L5 | 12.05% | 0% | 16.07% | 2.679% | 0% | 15.94% | 0% | 10.36% | 0% | 0% | 0%
VACSEC.A7L5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## work status sub_sec
| 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 5.714% | 0% | 14.29% | 0% | 2.857% | 5.714% | 5.714% | 0%
SUB SECTOR | Weld V1 V2 | VAC test V1 V2 | Weld E | VAC test E | Solder Main BB | Insulate Main BB | US weld Spools | Insulate spools | PAQ | solder Y | weld X | VAC test X | weld C' | weld M3 | weld K1,K2 | VAC test circuit K1K2C' | weld M1,M2 | insert N | cable N | AIV 1 | US weld N (cables) | AIV 2 | Weld N (sleeve) | insulate N Weld M2N | Close W | VAC final test
A | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
B | 5.806% | 0% | 3.18% | 0% | 6.636% | 1.659% | 3.134% | 1.567% | 0% | 0.4839% | 1.521% | 0% | 1.106% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | 7.532% | 0% | 4.026% | 0% | 8.658% | 2.165% | 4.329% | 2.165% | 0% | 0.7143% | 2.078% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
D | 8.036% | 0% | 4.018% | 0% | 10% | 2.411% | 4.821% | 2.143% | 0% | 0.7143% | 3.08% | 0% | 1.518% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
E | 8% | 0% | 4% | 0% | 8.381% | 1.905% | 4.19% | 1.905% | 0% | 0.7143% | 4.286% | 0% | 2.476% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
F | 8.036% | 0% | 4.018% | 0% | 10.71% | 2.589% | 5.357% | 2.143% | 0% | 0.7143% | 4.286% | 0% | 2.411% | 2.411% | 2.455% | 0% | #REF! | 5.893% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
G | 8.304% | 0% | 4.152% | 0% | 11.43% | 2.857% | 5.714% | 2.321% | 0% | 0.625% | 3.75% | 0% | 2.5% | 2.768% | 2.902% | 0% | 5.357% | 6.429% | 1.071% | 0% | 0.8929% | 0% | 0.625% | 0% | 0% | 0%
H | 8.295% | 0% | 4.147% | 0% | 10.32% | 2.581% | 4.977% | 2.396% | 0% | 0.6221% | 3.733% | 0% | 2.396% | 1.659% | 1.843% | 0% | 3.226% | 3.871% | 0.7373% | 0% | 1.843% | 0% | 1.014% | 0% | 0% | 0%
I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Sub Sector | Weld V1 V2 | VAC test V1 V2 | Weld E | VAC test E | Solder Main BB | Insulate Main BB | US weld Spools | Insulate spools | PAQ | solder Y | weld X | VAC test X | weld C' | weld M3 | weld K1,K2 | VAC test circuit K1K2C' | weld M1,M2 | insert N | cable N | AIV 1 | US weld N (cables) | AIV 2 | Weld N (sleeve) | insulate N Weld M2N | Close W
| A | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| B | 5.806% | 0% | 3.18% | 0% | 6.636% | 1.659% | 3.134% | 1.567% | 0% | 0.4839% | 1.521% | 0% | 1.106% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | 7.532% | 0% | 4.026% | 0% | 8.658% | 2.165% | 4.329% | 2.165% | 0% | 0.7143% | 2.078% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | 8.036% | 0% | 4.018% | 0% | 10% | 2.411% | 4.821% | 2.143% | 0% | 0.7143% | 3.08% | 0% | 1.518% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | 8% | 0% | 4% | 0% | 8.381% | 1.905% | 4.19% | 1.905% | 0% | 0.7143% | 4.286% | 0% | 2.476% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| F | 8.036% | 0% | 4.018% | 0% | 10.71% | 2.589% | 5.357% | 2.143% | 0% | 0.7143% | 4.286% | 0% | 2.411% | 2.411% | 2.455% | 0% | #REF! | 5.893% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | 8.304% | 0% | 4.152% | 0% | 11.43% | 2.857% | 5.714% | 2.321% | 0% | 0.625% | 3.75% | 0% | 2.5% | 2.768% | 2.902% | 0% | 5.357% | 6.429% | 1.071% | 0% | 0.8929% | 0% | 0.625% | 0% | 0%
| H | 8.295% | 0% | 4.147% | 0% | 10.32% | 2.581% | 4.977% | 2.396% | 0% | 0.6221% | 3.733% | 0% | 2.396% | 1.659% | 1.843% | 0% | 3.226% | 3.871% | 0.7373% | 0% | 1.843% | 0% | 1.014% | 0% | 0%
| I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Sub Sector | Weld package I (V1, V2, E line) | Vacuum test I (V1, V2, E line) | Bus bar brazing | Bus bar insulation | PAQ | Weld package II ( cryo-lines+ M1, M2, M3) | Vacuum test cryo lines | N line and final M welds | AIV 1 | AIV 2 | Close W
| A | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| B | 8.986% | 0% | 9.77% | 1.659% | 0% | 3.111% | 0% | 0% | 0% | 0% | 0%
| C | 11.56% | 0% | 12.99% | 2.165% | 0% | 2.792% | 0% | 0% | 0% | 0% | 0%
| D | 12.05% | 0% | 14.82% | 2.411% | 0% | 5.312% | 0% | 0% | 0% | 0% | 0%
| E | 12% | 0% | 12.57% | 1.905% | 0% | 7.476% | 0% | 0% | 0% | 0% | 0%
| F | 12.05% | 0% | 16.07% | 2.589% | 0% | #REF! | 0% | 5.893% | 0% | 0% | 0%
| G | 12.46% | 0% | 17.14% | 2.857% | 0% | 17.9% | 0% | 9.018% | 0% | 0% | 0%
| H | 12.44% | 0% | 15.3% | 2.581% | 0% | 13.48% | 0% | 7.465% | 0% | 0% | 0%
| I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## availability
Magnets MEB (indicative) | QRL available | Magnets in place | Magnets aligned | Inter. for pre-inspection | Inter. Released | Weld package I | Vacuum test I (V1, V2, E line) | Bus bar electrical connection started (brazing) | Bus bar electrical connection completed (insulated) | PAQ | Weld package II | Vacuum test cryo lines | AIV 1 | AIV 2 | N line+ M welds | W closed
0 | 0 | 0 | 0 | 0 | 202 | 175 | 89 | 171 | 151 | 95 | 0 | 21 | 24 | 15 | 0 | 0

## time-analysis int gen
102 | -79 | -23 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | [31 empty] | 212 | 8.571% | 0% | 4.286% | 0% | 11.43% | 2.857% | 5.714% | 2.857% | 0% | 0.7143% | 4.286% | 0% | 2.857% | 2.857% | 3.571% | 0% | 7.143% | 8.571% | 5.714% | 0% | 14.29% | 0% | 2.857% | 5.714% | 5.714% | 0%
week | week start date (Monday) | week end date (Sunday) | Weld V1 V2 | VAC test V1 V2 | RF test | Weld E | VAC test E | Solder Main BB | Insulate Main BB | US weld Spools | Insulate spools | PAQ | solder Y | weld X | VAC test X | weld C' | weld M3 | weld K1,K2 | VAC test circuit K1K2C' | weld M1,M2 | insert N | Tack Weld N (not qbq) | cable N | Test HVQN | AIV 1 | US weld N (cables) | AIV 2 | Weld N (sleeve) | week | week start date (Monday) | week end date (Sunday) | cumulative Weld V1 V2 | cumulative VAC test V1 V2 | cumulative RF test | cumulative Weld E | cumulative VAC test E | cumulative Solder Main BB | cumulative Insulate Main BB | cumulative US weld Spools | cumulative Insulate spools | cumulative PAQ | cumulative solder Y | cumulative weld X | cumulative VAC test X | cumulative weld C' | cumulative weld M3 | cumulative weld K1,K2 | cumulative VAC test circuit K1K2C' | cumulative weld M1,M2 | cumulative insert N | cumulative Tack Weld N (not qbq) | cumulative cable N | cumulative Test HVQN | cumulative AIV 1 | cumulative US weld N (cables) | cumulative AIV 2 | cumulative Weld N (sleeve) | week | week start date (Monday) | week end date (Sunday) | cumulative Weld V1 V2 | cumulative VAC test V1 V2 | cumulative RF test | cumulative Weld E | cumulative VAC test E | cumulative Solder Main BB | cumulative Insulate Main BB | cumulative US weld Spools | cumulative Insulate spools | cumulative PAQ | cumulative solder Y | cumulative weld X | cumulative VAC test X | cumulative weld C' | cumulative weld M3 | cumulative weld K1,K2 | cumulative VAC test circuit K1K2C' | cumulative weld M1,M2 | cumulative insert N | cumulative Tack Weld N (not qbq) | cumulative cable N | cumulative Test HVQN | cumulative AIV 1 | cumulative US weld N (cables) | cumulative AIV 2 | cumulative Weld N (sleeve) | week end date (Sunday) | Weld package I (V1, V2, E line) | Vacuum test I (V1, V2, E line) | Bus bar brazing (main+spools) | Bus bar insulation (main+spools) | PAQ | Weld package II ( cryo-lines+ M1, M2, M3) | Vacuum test cryo lines | N line and final M welds | AIV 1 | AIV 2 | Close W
48 | 2005-11-28 | 2005-12-04 | 1 | 0 | 5 | 0 | 3 | 0 | 3 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 2005-11-28 | 2005-12-04 | 1 | 0 | 5 | 0 | 3 | 0 | 3 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 2005-11-28 | 2005-12-04 | 0.04043% | 0% | 0.1011% | 0% | 0.1617% | 0% | 0.08086% | 0% | 0% | 0.02022% | 0.04043% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2005-12-04 | 0.1415% | 0% | 0.2426% | 0.08086% | 0% | 0.06065% | 0% | 0% | 0% | 0% | 0%
49 | 2005-12-05 | 2005-12-11 | 3 | 0 | 4 | 0 | 3 | 8 | 5 | 1 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2005-12-05 | 2005-12-11 | 4 | 0 | 9 | 0 | 6 | 8 | 8 | 1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2005-12-05 | 2005-12-11 | 0.1617% | 0% | 0.1819% | 0% | 0.3235% | 0.1078% | 0.2156% | 0.01348% | 0% | 0.02695% | 0.1617% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2005-12-11 | 0.3437% | 0% | 0.6469% | 0.3369% | 0% | 0.1887% | 0% | 0% | 0% | 0% | 0%
50 | 2005-12-12 | 2005-12-18 | 5 | 0 | 1 | 0 | 3 | 1 | 3 | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2005-12-12 | 2005-12-18 | 9 | 0 | 10 | 0 | 9 | 9 | 11 | 7 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2005-12-12 | 2005-12-18 | 0.3639% | 0% | 0.2022% | 0% | 0.4852% | 0.1213% | 0.2965% | 0.09434% | 0% | 0.03369% | 0.1617% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2005-12-18 | 0.566% | 0% | 0.903% | 0.5121% | 0% | 0.1954% | 0% | 0% | 0% | 0% | 0%
51 | 2005-12-19 | 2005-12-25 | 4 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 2005-12-19 | 2005-12-25 | 13 | 0 | 10 | 0 | 11 | 11 | 13 | 7 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 2005-12-19 | 2005-12-25 | 0.5256% | 0% | 0.2022% | 0% | 0.593% | 0.1482% | 0.3504% | 0.09434% | 0% | 0.03369% | 0.1617% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2005-12-25 | 0.7278% | 0% | 1.092% | 0.593% | 0% | 0.1954% | 0% | 0% | 0% | 0% | 0%
52 | 2005-12-26 | 2006-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 2005-12-26 | 2006-01-01 | 13 | 0 | 10 | 0 | 11 | 11 | 13 | 7 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 2005-12-26 | 2006-01-01 | 0.5256% | 0% | 0.2022% | 0% | 0.593% | 0.1482% | 0.3504% | 0.09434% | 0% | 0.03369% | 0.1617% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-01-01 | 0.7278% | 0% | 1.092% | 0.593% | 0% | 0.1954% | 0% | 0% | 0% | 0% | 0%
1 | 2006-01-02 | 2006-01-08 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2006-01-02 | 2006-01-08 | 13 | 0 | 10 | 0 | 12 | 13 | 15 | 7 | 0 | 11 | 8 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2006-01-02 | 2006-01-08 | 0.5256% | 0% | 0.2022% | 0% | 0.6469% | 0.1752% | 0.4043% | 0.09434% | 0% | 0.03706% | 0.1617% | 0% | 0.04043% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-01-08 | 0.7278% | 0% | 1.226% | 0.6739% | 0% | 0.2392% | 0% | 0% | 0% | 0% | 0%
2 | 2006-01-09 | 2006-01-15 | 6 | 0 | 2 | 0 | 7 | 4 | 4 | 4 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2006-01-09 | 2006-01-15 | 19 | 0 | 12 | 0 | 19 | 17 | 19 | 11 | 0 | 18 | 8 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2006-01-09 | 2006-01-15 | 0.7682% | 0% | 0.2426% | 0% | 1.024% | 0.2291% | 0.5121% | 0.1482% | 0% | 0.06065% | 0.1617% | 0% | 0.06739% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-01-15 | 1.011% | 0% | 1.765% | 0.8895% | 0% | 0.2898% | 0% | 0% | 0% | 0% | 0%
3 | 2006-01-16 | 2006-01-22 | 1 | 0 | 10 | 0 | 3 | 4 | 5 | 2 | 0 | 8 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2006-01-16 | 2006-01-22 | 20 | 0 | 22 | 0 | 22 | 21 | 24 | 13 | 0 | 26 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2006-01-16 | 2006-01-22 | 0.8086% | 0% | 0.4447% | 0% | 1.186% | 0.283% | 0.6469% | 0.1752% | 0% | 0.0876% | 0.1617% | 0% | 0.09434% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-01-22 | 1.253% | 0% | 2.116% | 1.105% | 0% | 0.3437% | 0% | 0% | 0% | 0% | 0%
4 | 2006-01-23 | 2006-01-29 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2006-01-23 | 2006-01-29 | 20 | 0 | 25 | 0 | 22 | 21 | 25 | 13 | 0 | 27 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2006-01-23 | 2006-01-29 | 0.8086% | 0% | 0.5054% | 0% | 1.186% | 0.283% | 0.6739% | 0.1752% | 0% | 0.09097% | 0.1617% | 0% | 0.09434% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-01-29 | 1.314% | 0% | 2.143% | 1.132% | 0% | 0.347% | 0% | 0% | 0% | 0% | 0%
5 | 2006-01-30 | 2006-02-05 | 6 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2006-01-30 | 2006-02-05 | 26 | 0 | 26 | 0 | 24 | 21 | 25 | 13 | 0 | 27 | 13 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2006-01-30 | 2006-02-05 | 1.051% | 0% | 0.5256% | 0% | 1.294% | 0.283% | 0.6739% | 0.1752% | 0% | 0.09097% | 0.2628% | 0% | 0.09434% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-02-05 | 1.577% | 0% | 2.251% | 1.132% | 0% | 0.4481% | 0% | 0% | 0% | 0% | 0%
6 | 2006-02-06 | 2006-02-12 | 1 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 0 | 14 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2006-02-06 | 2006-02-12 | 27 | 0 | 26 | 0 | 28 | 21 | 28 | 13 | 0 | 27 | 27 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2006-02-06 | 2006-02-12 | 1.092% | 0% | 0.5256% | 0% | 1.509% | 0.283% | 0.7547% | 0.1752% | 0% | 0.09097% | 0.5458% | 0% | 0.1887% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-02-12 | 1.617% | 0% | 2.547% | 1.213% | 0% | 0.8255% | 0% | 0% | 0% | 0% | 0%
7 | 2006-02-13 | 2006-02-19 | 5 | 25 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2006-02-13 | 2006-02-19 | 32 | 25 | 26 | 0 | 33 | 21 | 32 | 13 | 0 | 27 | 27 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2006-02-13 | 2006-02-19 | 1.294% | 0% | 0.5256% | 0% | 1.779% | 0.283% | 0.8625% | 0.1752% | 0% | 0.09097% | 0.5458% | 0% | 0.2561% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-02-19 | 1.819% | 0% | 2.925% | 1.321% | 0% | 0.8929% | 0% | 0% | 0% | 0% | 0%
8 | 2006-02-20 | 2006-02-26 | 4 | 0 | 7 | 0 | 5 | 0 | 7 | 0 | 0 | 9 | 2 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2006-02-20 | 2006-02-26 | 36 | 25 | 33 | 0 | 38 | 21 | 39 | 13 | 0 | 36 | 29 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2006-02-20 | 2006-02-26 | 1.456% | 0% | 0.6671% | 0% | 2.049% | 0.283% | 1.051% | 0.1752% | 0% | 0.1213% | 0.5863% | 0% | 0.3235% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-02-26 | 2.123% | 0% | 3.383% | 1.509% | 0% | 1.031% | 0% | 0% | 0% | 0% | 0%
9 | 2006-02-27 | 2006-03-05 | 7 | 0 | 6 | 0 | 7 | 0 | 6 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2006-02-27 | 2006-03-05 | 43 | 25 | 39 | 0 | 45 | 21 | 45 | 13 | 0 | 41 | 29 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2006-02-27 | 2006-03-05 | 1.739% | 0% | 0.7884% | 0% | 2.426% | 0.283% | 1.213% | 0.1752% | 0% | 0.1381% | 0.5863% | 0% | 0.3235% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-03-05 | 2.527% | 0% | 3.922% | 1.671% | 0% | 1.048% | 0% | 0% | 0% | 0% | 0%
10 | 2006-03-06 | 2006-03-12 | 8 | 8 | 4 | 0 | 5 | 0 | 7 | 0 | 0 | 23 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2006-03-06 | 2006-03-12 | 51 | 33 | 43 | 0 | 50 | 21 | 52 | 13 | 0 | 64 | 29 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2006-03-06 | 2006-03-12 | 2.062% | 0% | 0.8693% | 0% | 2.695% | 0.283% | 1.402% | 0.1752% | 0% | 0.2156% | 0.5863% | 0% | 0.3369% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-03-12 | 2.931% | 0% | 4.38% | 1.86% | 0% | 1.139% | 0% | 0% | 0% | 0% | 0%
11 | 2006-03-13 | 2006-03-19 | 2 | 4 | 21 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 7 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 2006-03-13 | 2006-03-19 | 53 | 37 | 64 | 0 | 51 | 21 | 54 | 13 | 0 | 64 | 36 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 2006-03-13 | 2006-03-19 | 2.143% | 0% | 1.294% | 0% | 2.749% | 0.283% | 1.456% | 0.1752% | 0% | 0.2156% | 0.7278% | 0% | 0.4447% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-03-19 | 3.437% | 0% | 4.488% | 1.914% | 0% | 1.388% | 0% | 0% | 0% | 0% | 0%
12 | 2006-03-20 | 2006-03-26 | 0 | 2 | 0 | 0 | 0 | 10 | 0 | 2 | 0 | 0 | 24 | 28 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2006-03-20 | 2006-03-26 | 53 | 39 | 64 | 0 | 51 | 31 | 54 | 15 | 0 | 64 | 60 | 28 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2006-03-20 | 2006-03-26 | 2.143% | 0% | 1.294% | 0% | 2.749% | 0.4178% | 1.456% | 0.2022% | 0% | 0.2156% | 1.213% | 0% | 0.5795% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-03-26 | 3.437% | 0% | 4.623% | 2.075% | 0% | 2.008% | 0% | 0% | 0% | 0% | 0%
13 | 2006-03-27 | 2006-04-02 | 5 | 0 | 4 | 20 | 2 | 2 | 1 | 0 | 19 | 6 | 0 | 7 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 2006-03-27 | 2006-04-02 | 58 | 39 | 68 | 20 | 53 | 33 | 55 | 15 | 19 | 70 | 60 | 35 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 2006-03-27 | 2006-04-02 | 2.345% | 0% | 1.375% | 0% | 2.857% | 0.4447% | 1.482% | 0.2022% | 0% | 0.2358% | 1.213% | 0% | 0.7412% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-04-02 | 3.72% | 0% | 4.784% | 2.129% | 0% | 2.19% | 0% | 0% | 0% | 0% | 0%
14 | 2006-04-03 | 2006-04-09 | 6 | 0 | 6 | 0 | 8 | 2 | 6 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 2006-04-03 | 2006-04-09 | 64 | 39 | 74 | 20 | 61 | 35 | 61 | 16 | 19 | 70 | 60 | 35 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 2006-04-03 | 2006-04-09 | 2.588% | 0% | 1.496% | 0% | 3.288% | 0.4717% | 1.644% | 0.2156% | 0% | 0.2358% | 1.213% | 0% | 0.7682% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-04-09 | 4.084% | 0% | 5.404% | 2.332% | 0% | 2.217% | 0% | 0% | 0% | 0% | 0%
15 | 2006-04-10 | 2006-04-16 | 3 | 0 | 1 | 0 | 5 | 26 | 4 | 9 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2006-04-10 | 2006-04-16 | 67 | 39 | 75 | 20 | 66 | 61 | 65 | 25 | 19 | 70 | 60 | 35 | 57 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2006-04-10 | 2006-04-16 | 2.709% | 0% | 1.516% | 0% | 3.558% | 0.8221% | 1.752% | 0.3369% | 0% | 0.2358% | 1.213% | 0% | 0.7682% | 0.02695% | 0% | 0% | 0.03369% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-04-16 | 4.225% | 0% | 6.132% | 2.911% | 0% | 2.244% | 0% | 0% | 0% | 0% | 0%
16 | 2006-04-17 | 2006-04-23 | 5 | 6 | 4 | 8 | 5 | 9 | 6 | 13 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2006-04-17 | 2006-04-23 | 72 | 45 | 79 | 28 | 71 | 70 | 71 | 38 | 19 | 70 | 60 | 35 | 57 | 8 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2006-04-17 | 2006-04-23 | 2.911% | 0% | 1.597% | 0% | 3.827% | 0.9434% | 1.914% | 0.5121% | 0% | 0.2358% | 1.213% | 0% | 0.7682% | 0.1078% | 0% | 0% | 0.2358% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-04-23 | 4.508% | 0% | 6.685% | 3.369% | 0% | 2.325% | 0% | 0% | 0% | 0% | 0%
17 | 2006-04-24 | 2006-04-30 | 9 | 0 | 9 | 0 | 3 | 3 | 4 | 25 | 3 | 14 | 9 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 2006-04-24 | 2006-04-30 | 81 | 45 | 88 | 28 | 74 | 73 | 75 | 63 | 22 | 84 | 69 | 35 | 60 | 10 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 2006-04-24 | 2006-04-30 | 3.275% | 0% | 1.779% | 0% | 3.989% | 0.9838% | 2.022% | 0.8491% | 0% | 0.283% | 1.395% | 0% | 0.8086% | 0.1348% | 0% | 0% | 0.2695% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-04-30 | 5.054% | 0% | 6.995% | 3.854% | 0% | 2.621% | 0% | 0% | 0% | 0% | 0%
18 | 2006-05-01 | 2006-05-07 | 7 | 16 | 5 | 0 | 8 | 8 | 6 | 2 | 0 | 0 | 1 | 0 | 10 | 0 | 2 | 0 | 0 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 2006-05-01 | 2006-05-07 | 88 | 61 | 93 | 28 | 82 | 81 | 81 | 65 | 22 | 84 | 70 | 35 | 70 | 10 | 2 | 0 | 8 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 2006-05-01 | 2006-05-07 | 3.558% | 0% | 1.88% | 0% | 4.42% | 1.092% | 2.183% | 0.876% | 0% | 0.283% | 1.415% | 0% | 0.9434% | 0.1348% | 0.03369% | 0% | 0.2695% | 0.3639% | 0.05391% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2006-05-07 | 5.438% | 0% | 7.695% | 4.151% | 0% | 2.776% | 0% | 0.4178% | 0% | 0% | 0%
19 | 2006-05-08 | 2006-05-14 | 8 | 0 | 12 | 0 | 8 | 8 | 6 | 2 | 0 | 13 | 0 | 0 | 0 | 3 | 4 | 0 | 3 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 19 | 2006-05-08 | 2006-05-14 | 96 | 61 | 105 | 28 | 90 | 89 | 87 | 67 | 22 | 97 | 70 | 35 | 70 | 13 | 6 | 0 | 11 | 9 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 19 | 2006-05-08 | 2006-05-14 | 3.881% | 0% | 2.123% | 0% | 4.852% | 1.199% | 2.345% | 0.903% | 0% | 0.3268% | 1.415% | 0% | 0.9434% | 0.1752% | 0.1011% | 0% | 0.3706% | 0.3639% | 0.05391% | 0% | 0.06739% | 0% | 0% | 0% | 0% | 0% | 2006-05-14 | 6.004% | 0% | 8.396% | 4.447% | 0% | 2.861% | 0% | 0.4852% | 0% | 0% | 0%
20 | 2006-05-15 | 2006-05-21 | 9 | 6 | 10 | 18 | 9 | 4 | 7 | 3 | 0 | 5 | 0 | 7 | 0 | 5 | 3 | 0 | 5 | 12 | 1 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 20 | 2006-05-15 | 2006-05-21 | 105 | 67 | 115 | 46 | 99 | 93 | 94 | 70 | 22 | 102 | 70 | 42 | 70 | 18 | 9 | 0 | 16 | 21 | 3 | 6 | 1 | 3 | 0 | 0 | 0 | 0 | 20 | 2006-05-15 | 2006-05-21 | 4.245% | 0% | 2.325% | 0% | 5.337% | 1.253% | 2.534% | 0.9434% | 0% | 0.3437% | 1.415% | 0% | 0.9434% | 0.2426% | 0.1516% | 0% | 0.5391% | 0.8491% | 0.08086% | 0% | 0.06739% | 0% | 0% | 0% | 0% | 0% | 2006-05-21 | 6.57% | 0% | 9.124% | 4.73% | 0% | 2.945% | 0% | 0.9973% | 0% | 0% | 0%
21 | 2006-05-22 | 2006-05-28 | 15 | 0 | 15 | 15 | 12 | 4 | 8 | 2 | 18 | 16 | 3 | 0 | 0 | 2 | 7 | 0 | 2 | 12 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 21 | 2006-05-22 | 2006-05-28 | 120 | 67 | 130 | 61 | 111 | 97 | 102 | 72 | 40 | 118 | 73 | 42 | 70 | 20 | 16 | 0 | 18 | 33 | 3 | 6 | 1 | 3 | 3 | 0 | 0 | 0 | 21 | 2006-05-22 | 2006-05-28 | 4.852% | 0% | 2.628% | 0% | 5.984% | 1.307% | 2.749% | 0.9704% | 0% | 0.3976% | 1.476% | 0% | 0.9434% | 0.2695% | 0.2695% | 0% | 0.6065% | 1.334% | 0.08086% | 0% | 0.06739% | 0% | 0.04043% | 0% | 0% | 0% | 2006-05-28 | 7.48% | 0% | 10.04% | 5.027% | 0% | 3.086% | 0% | 1.482% | 0% | 0% | 0%
22 | 2006-05-29 | 2006-06-04 | 17 | 0 | 14 | 1 | 16 | 17 | 15 | 2 | 0 | 24 | 2 | 0 | 0 | 10 | 6 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 2006-05-29 | 2006-06-04 | 137 | 67 | 144 | 62 | 127 | 114 | 117 | 74 | 40 | 142 | 75 | 42 | 70 | 30 | 22 | 0 | 22 | 33 | 3 | 6 | 1 | 3 | 3 | 0 | 0 | 0 | 22 | 2006-05-29 | 2006-06-04 | 5.539% | 0% | 2.911% | 0% | 6.846% | 1.536% | 3.154% | 0.9973% | 0% | 0.4784% | 1.516% | 0% | 0.9434% | 0.4043% | 0.3706% | 0% | 0.7412% | 1.334% | 0.08086% | 0% | 0.06739% | 0% | 0.04043% | 0% | 0% | 0% | 2006-06-04 | 8.45% | 0% | 11.54% | 5.687% | 0% | 3.342% | 0% | 1.482% | 0% | 0% | 0%
23 | 2006-06-05 | 2006-06-11 | 20 | 0 | 20 | 0 | 17 | 22 | 14 | 16 | 12 | 5 | 0 | 0 | 0 | 9 | 11 | 0 | 11 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 2006-06-05 | 2006-06-11 | 157 | 67 | 164 | 62 | 144 | 136 | 131 | 90 | 52 | 147 | 75 | 42 | 70 | 39 | 33 | 0 | 33 | 39 | 10 | 6 | 1 | 3 | 3 | 0 | 0 | 0 | 23 | 2006-06-05 | 2006-06-11 | 6.348% | 0% | 3.315% | 0% | 7.763% | 1.833% | 3.531% | 1.213% | 0% | 0.4953% | 1.516% | 0% | 0.9434% | 0.5256% | 0.5559% | 0% | 1.112% | 1.577% | 0.2695% | 0% | 0.06739% | 0% | 0.04043% | 0% | 0% | 0% | 2006-06-11 | 9.663% | 0% | 13.13% | 6.577% | 0% | 3.48% | 0% | 1.914% | 0% | 0% | 0%
24 | 2006-06-12 | 2006-06-18 | 7 | 16 | 14 | 1 | 11 | 17 | 19 | 14 | 0 | 22 | 30 | 0 | 0 | 9 | 9 | 0 | 10 | 0 | 0 | 9 | 1 | 0 | 4 | 0 | 0 | 0 | 24 | 2006-06-12 | 2006-06-18 | 164 | 83 | 178 | 63 | 155 | 153 | 150 | 104 | 52 | 169 | 105 | 42 | 70 | 48 | 42 | 0 | 43 | 39 | 10 | 15 | 2 | 3 | 7 | 0 | 0 | 0 | 24 | 2006-06-12 | 2006-06-18 | 6.631% | 0% | 3.598% | 0% | 8.356% | 2.062% | 4.043% | 1.402% | 0% | 0.5694% | 2.123% | 0% | 0.9434% | 0.6469% | 0.7075% | 0% | 1.449% | 1.577% | 0.2695% | 0% | 0.1348% | 0% | 0.09434% | 0% | 0% | 0% | 2006-06-18 | 10.23% | 0% | 14.46% | 7.507% | 0% | 4.282% | 0% | 1.981% | 0% | 0% | 0%
25 | 2006-06-19 | 2006-06-25 | 1 | 3 | 5 | 16 | 0 | 0 | 6 | 25 | 9 | 13 | 21 | 0 | 9 | 1 | 2 | 12 | 0 | 0 | 0 | 0 | 3 | 0 | 8 | 0 | 0 | 0 | 25 | 2006-06-19 | 2006-06-25 | 165 | 86 | 183 | 79 | 155 | 153 | 156 | 129 | 61 | 182 | 126 | 42 | 79 | 49 | 44 | 12 | 43 | 39 | 10 | 15 | 5 | 3 | 15 | 0 | 0 | 0 | 25 | 2006-06-19 | 2006-06-25 | 6.671% | 0% | 3.699% | 0% | 8.356% | 2.062% | 4.205% | 1.739% | 0% | 0.6132% | 2.547% | 0% | 1.065% | 0.6604% | 0.7412% | 0% | 1.449% | 1.577% | 0.2695% | 0% | 0.3369% | 0% | 0.2022% | 0% | 0% | 0% | 2006-06-25 | 10.37% | 0% | 14.62% | 8.005% | 0% | 4.885% | 0% | 2.183% | 0% | 0% | 0%
26 | 2006-06-26 | 2006-07-02 | 3 | 3 | 6 | 0 | 8 | 11 | 8 | 21 | 12 | 5 | 19 | 0 | 22 | 8 | 8 | 0 | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 2006-06-26 | 2006-07-02 | 168 | 89 | 189 | 79 | 163 | 164 | 164 | 150 | 73 | 187 | 145 | 42 | 101 | 57 | 52 | 12 | 51 | 57 | 10 | 15 | 5 | 3 | 15 | 0 | 0 | 0 | 26 | 2006-06-26 | 2006-07-02 | 6.792% | 0% | 3.821% | 0% | 8.787% | 2.21% | 4.42% | 2.022% | 0% | 0.6301% | 2.931% | 0% | 1.361% | 0.7682% | 0.876% | 0% | 1.718% | 2.305% | 0.2695% | 0% | 0.3369% | 0% | 0.2022% | 0% | 0% | 0% | 2006-07-02 | 10.61% | 0% | 15.42% | 8.652% | 0% | 5.691% | 0% | 2.911% | 0% | 0% | 0%
27 | 2006-07-03 | 2006-07-09 | 0 | 0 | 0 | 0 | 4 | 3 | 2 | 1 | 9 | 1 | 7 | 0 | 19 | 19 | 12 | 9 | 9 | 3 | 0 | 0 | 1 | 9 | 3 | 0 | 0 | 0 | 27 | 2006-07-03 | 2006-07-09 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 82 | 188 | 152 | 42 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 15 | 6 | 12 | 18 | 0 | 0 | 0 | 27 | 2006-07-03 | 2006-07-09 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-07-09 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
28 | 2006-07-10 | 2006-07-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 3 | 0 | 0 | 0 | 0 | 28 | 2006-07-10 | 2006-07-16 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 28 | 2006-07-10 | 2006-07-16 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-07-16 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
29 | 2006-07-17 | 2006-07-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 2006-07-17 | 2006-07-23 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 29 | 2006-07-17 | 2006-07-23 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-07-23 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
30 | 2006-07-24 | 2006-07-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2006-07-24 | 2006-07-30 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 30 | 2006-07-24 | 2006-07-30 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-07-30 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
31 | 2006-07-31 | 2006-08-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 2006-07-31 | 2006-08-06 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 31 | 2006-07-31 | 2006-08-06 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-08-06 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
32 | 2006-08-07 | 2006-08-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 2006-08-07 | 2006-08-13 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 32 | 2006-08-07 | 2006-08-13 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-08-13 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
33 | 2006-08-14 | 2006-08-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 2006-08-14 | 2006-08-20 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 33 | 2006-08-14 | 2006-08-20 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-08-20 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
34 | 2006-08-21 | 2006-08-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 2006-08-21 | 2006-08-27 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 34 | 2006-08-21 | 2006-08-27 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-08-27 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
35 | 2006-08-28 | 2006-09-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 2006-08-28 | 2006-09-03 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 35 | 2006-08-28 | 2006-09-03 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-09-03 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
36 | 2006-09-04 | 2006-09-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 2006-09-04 | 2006-09-10 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 36 | 2006-09-04 | 2006-09-10 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-09-10 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
37 | 2006-09-11 | 2006-09-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 2006-09-11 | 2006-09-17 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 37 | 2006-09-11 | 2006-09-17 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-09-17 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
38 | 2006-09-18 | 2006-09-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 2006-09-18 | 2006-09-24 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 38 | 2006-09-18 | 2006-09-24 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-09-24 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
39 | 2006-09-25 | 2006-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 2006-09-25 | 2006-10-01 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 39 | 2006-09-25 | 2006-10-01 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-10-01 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
40 | 2006-10-02 | 2006-10-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2006-10-02 | 2006-10-08 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 40 | 2006-10-02 | 2006-10-08 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-10-08 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
41 | 2006-10-09 | 2006-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 2006-10-09 | 2006-10-15 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 41 | 2006-10-09 | 2006-10-15 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-10-15 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
42 | 2006-10-16 | 2006-10-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 2006-10-16 | 2006-10-22 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 42 | 2006-10-16 | 2006-10-22 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-10-22 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
43 | 2006-10-23 | 2006-10-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 2006-10-23 | 2006-10-29 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 43 | 2006-10-23 | 2006-10-29 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-10-29 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
44 | 2006-10-30 | 2006-11-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 2006-10-30 | 2006-11-05 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 44 | 2006-10-30 | 2006-11-05 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-11-05 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
45 | 2006-11-06 | 2006-11-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 2006-11-06 | 2006-11-12 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 45 | 2006-11-06 | 2006-11-12 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-11-12 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
46 | 2006-11-13 | 2006-11-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 2006-11-13 | 2006-11-19 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 46 | 2006-11-13 | 2006-11-19 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-11-19 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
47 | 2006-11-20 | 2006-11-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 2006-11-20 | 2006-11-26 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 47 | 2006-11-20 | 2006-11-26 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-11-26 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
48 | 2006-11-27 | 2006-12-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 2006-11-27 | 2006-12-03 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 48 | 2006-11-27 | 2006-12-03 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-12-03 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
49 | 2006-12-04 | 2006-12-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2006-12-04 | 2006-12-10 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 49 | 2006-12-04 | 2006-12-10 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-12-10 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
50 | 2006-12-11 | 2006-12-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2006-12-11 | 2006-12-17 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 50 | 2006-12-11 | 2006-12-17 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-12-17 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
51 | 2006-12-18 | 2006-12-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 2006-12-18 | 2006-12-24 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 51 | 2006-12-18 | 2006-12-24 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-12-24 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%
52 | 2006-12-25 | 2006-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 2006-12-25 | 2006-12-31 | 168 | 89 | 189 | 79 | 167 | 167 | 166 | 151 | 95 | 188 | 152 | 48 | 120 | 76 | 64 | 21 | 60 | 60 | 10 | 24 | 6 | 15 | 18 | 0 | 0 | 0 | 52 | 2006-12-25 | 2006-12-31 | 6.792% | 0% | 3.821% | 0% | 9.003% | 2.251% | 4.474% | 2.035% | 0% | 0.6334% | 3.073% | 0% | 1.617% | 1.024% | 1.078% | 0% | 2.022% | 2.426% | 0.2695% | 0% | 0.4043% | 0% | 0.2426% | 0% | 0% | 0% | 2006-12-31 | 10.61% | 0% | 15.73% | 8.76% | 0% | 6.348% | 0% | 3.1% | 0% | 0% | 0%