## CC2058
|  |  | ELECTRICAL TESTS OF DIPOLES | [8 empty] | RAW_Data [Logger] | [5 empty] | RAW_Data [Gain Phase Analyser]
AFTER COLLARING
|  |  | (WITH BEAM TUBES) | [6 empty] | [DataQHs_Cl] |  | [DataPoles_Cl]
[10 empty] | QHs |  | Poles | Poles | Poles | f | Q | L |  | Q | L
[10 empty] | [W] |  | [V] | [mW] | R20[mW] | [Hz] |  | [mH] |  |  | [mH]
MAIN CONTRACTOR : |  |  | ANSALDO SUPERCONDUTTORI s.p.a. |  | CONTRACT NUMBER : F462 |  |  |  | YT111 | 22.4707 | Magnet | 6.1848 | 6184.805 | 6172.4601 | 10 | 0.876 | 21.7 |  | 0.876 | 21.9
SUB CONTRACTOR : | [8 empty] | YT112 | 22.4817 | Aperture1 | 3.0923 | 3092.34 | 3086.1677 | 100 | 4.68 | 21.5 |  | 4.63 | 21.5
[9 empty] | YT121 | 22.5529 | Aperture2 | 3.0925 | 3092.465 | 3086.2924 | 1000 | 1.62 | 15.1 |  | 1.62 | 15
COMPONENT NAME : |  |  | Collared Coils | [5 empty] | YT122 | 22.488 | Apt1 Pup | 1.5461 | 1546.074 | 1542.988
CERN PART NUMBER : |  |  | HCMBB_A001 |  | Serial Number : |  | 2058 |  | YT211 | 23.4473 | Apt1 Plw | 1.5463 | 1546.261 | 1543.1747 | 10 | 0.875 | 21.7 |  | 0.882 | 21.9
[9 empty] | YT212 | 23.3864 | Apt2 Pup | 1.546 | 1546.025 | 1542.9391 | 100 | 4.69 | 21.4 |  | 4.59 | 21.5
CERN INSPECTION & TEST PLAN NUMBER : 9a To 9i |  |  |  |  | TEST NUMBER : |  | 9a to 9i |  | YT221 | 24.7343 | Apt2 Plw | 1.5464 | 1546.439 | 1543.3523 | 1000 | 1.63 | 14.8 |  | 1.63 | 14.8
NON CONFORMITY: |  |  | No |  | NON CONFORMITY: |  | Number |  | YT222 | 24.5622
[15 empty] | 10 | 0.881 | 43.5 |  | 0.879 | 43.6
NAME OF TEST OPERATOR: |  |  | M.Levrero | [11 empty] | 100 | 4.68 | 42.9 |  | 4.62 | 42.9
NAME OF RESPONSIBLE: |  |  | B.Caserza | [11 empty] | 1000 | 1.63 | 29.9 |  | 1.62 | 29.8
DATE OF TEST : |  |  | 2003-10-11 |  | TIME : |  | 08:30:00 AM
[15 empty] | 10 | 0.88 | 87.4
[15 empty] | 100 | 4.69 | 85.8
[15 empty] | 1000 | 1.62 | 59.7
R[dc] of the Poles |  |  | ITP step 9a
I = | 1 | A | Apt 1 | [ext] |  | Apt 2 | [int]
Temp.* : | 20.5 | °C | Upper | Lower |  | Upper | Lower
Humidite: | 63 | % | [mW] | [mW] |  | [mW] | [mW]
Poles |  |  | 1546.074 | 1546.261 |  | 1546.025 | 1546.439
Poles [20°C] |  | * | 1542.988 | 1543.1747 |  | 1542.9391 | 1543.3523
D1 & D2 |  | * | 3086.1677 | mW |  | 3086.2924 | mW
Magnet |  |  | * | 6172.4601 | mW
|  | Poles Nr. | 02P00230 | 02P00231 |  | 02P00232 | 02P00233
R[dc] of the Quench Heaters |  |  | ITP step 9b
|  |  | Apt 1 | [ext] |  | Apt 2 | [int]
|  |  | Left | Right |  | Left | Right
|  |  | [W] | [W] |  | [W] | [W]
D1 & D2 |  | * | 22.4707 | 22.5529 |  | 23.4473 | 24.7343
|  | * | 22.4817 | 22.488 |  | 23.3864 | 24.5622
Capacitance |  |  | ITPstep 9d/e
[ Megger 100V ; > 1'] |  |  | Apt 1 | [ext] |  | Apt 2 | [int]
QHs | --> Dipoles |  | 220 | nF |  | 220 | nF
D1 & D2 | --> Masse |  | 200 | nF |  | 210 | nF
Magnet | --> Masse |  | * | 410 | nF
ELECTRICAL TESTS OF DIPOLES
AFTER COLLARING
(WITH BEAM TUBE)
INDUCTANCE L/Q[10Hz] |  |  | ITP step 9c
|  |  | Apt 1 | [ext] |  | Apt 2 | [int]
|  |  | Upper | Lower |  | Upper | Lower
|  |  | [mH] | [mH] |  | [mH] | [mH]
POLES |  | (L) | 21.7 | 21.7 |  | 21.9 | 21.9
|  | (Q) | 0.876 | 0.875 |  | 0.876 | 0.882
D1 & D2 |  | (L) | 43.5 | mH |  | 43.6 | mH
|  | (Q) | 0.881 |  |  | 0.879
Magnet |  |  | (L) | 87.4 | mH
|  |  | (Q) | 0.88
INDUCTANCE L/Q[100Hz] |  |  | ITP step 9c
|  |  | Apt 1 | [ext] |  | Apt 2 | [int]
|  |  | Upper | Lower |  | Upper | Lower
|  |  | [mH] | [mH] |  | [mH] | [mH]
POLES | * | (L) | 21.5 | 21.4 |  | 21.5 | 21.5
|  | (Q) | 4.68 | 4.69 |  | S16 | 4.59
D1 & D2 | * | (L) | 42.9 | mH |  | 42.9 | mH
|  | (Q) | 4.68 |  |  | 4.62
Magnet | * |  | (L) | 85.8 | mH
|  |  | (Q) | 4.69
INDUCTANCE L/Q[1.0KHz] |  |  | ITP step 9c
|  |  | Apt 1 | [ext] |  | Apt 2 | [int]
|  |  | Upper | Lower |  | Upper | Lower
|  |  | [mH] | [mH] |  | [mH] | [mH]
POLES | * | (L) | 15.1 | 14.8 |  | 15 | 14.8
|  | (Q) | 1.62 | 1.63 |  | 1.62 | 1.63
D1 & D2 | * | (L) | 29.9 | mH |  | 29.8 | mH
|  | (Q) | 1.63 |  |  | 1.62
Magnet | * |  | (L) | 59.7 | mH
|  |  | (Q) | 1.62
ELECTRICAL TESTS OF DIPOLES
AFTER COLLARING
(WITH BEAM TUBE)
INSULATION RESISTANCE
Dipole D1 + QHs D1 ----> Masse * |  |  |  | 13.1 | GW |  | >1000MW
[V=1.0.KV, 60'']
Dipole D2 + QHs D2 ----> Masse * |  |  |  | 13.8 | GW |  | >1000MW
[V=1.0.KV, 60'']
| QHs D1(8x) D1 |  | * | 6.6 | GW |  | >1000MW
[V=1.0.KV, 60'']
| QHs D2(8x) D2 |  | * | 7.65 | GW |  | >1000MW
[V=1.0.KV, 60'']
DIPOLE 1
| POLE UP -----> POLE LW |  | * | 21.8 | GW |  | >1000MW
[V=1.0.KV, 60'']
DIPOLE 2
| POLE UP -----> POLE LW |  | * | 23.6 | GW |  | >1000MW
DIELECTRIC TESTS |  |  | ITP step 9f/h
Dipole D1 + QHs D1 ----> Masse * |  |  |  | 0.256 | µA |  | < 20 µA
[V=5.0KV 5' ]
Dipole D2 + QHs D2 ----> Masse * |  |  |  | 0.356 | µA |  | < 20 µA
[V=5.0KV 5' ]
| QHs D1(8x) D1 |  | * | 0.156 | µA |  | < 20 µA
[V=3.0.KV 5' ]
| QHs D2(8x) D2 |  | * | 0.141 | µA |  | < 20 µA
[V=3.0.KV 5' ]
DIPOLE 1
| POLE UP -----> POLE LW |  | * | 0.05 | µA |  | < 20 µA
[V=3.0.KV 5' ]
DIPOLE 2
| POLE UP -----> POLE LW |  | * | 0.048 | µA |  | < 20 µA
[V=3.0.KV 5' ]
DISCHARGE TEST |  |  | ITP step 9i
V = 100V/turn |  |  | Apt 1 | [ext] |  | Apt 2 | [int]
[C= 2µF] |  |  | Upper | Lower |  | Upper | Lower
|  |  | mS | mS |  | mS | mS
| Poles [4.0KV] | * | 0.9398 | 0.964 |  | 0.975 | 0.956
| Dipoles D1 & D2 [4KV] * |  | 1.7 | mS | * | 1.69 | mS
| Magnet [4KV] |  | * | 2.518 | mS
| Quench Heaters |  | YT111 & 112 | YT121 & 122 |  | YT211 & 212 | YT221 & 222
| [V=800V] |  | 205 / 197 | 197 / 197 | µS | 197 / 195 | 197 / 197 | µS
| [C= 2µF] | Current | 29.5 / 30.5 | 30.5 / 30.0 | A | 29.0 / 29.0 | 28.0 /28.0 | A
Apt1
Apt2
Up
Lw
Dip
Magnet
LHC/MMS TRACEABILITY INFORMATION