## WP-structure
WP | Title |  |  | Project Engineer
1 | Project management
2 | Optics and beam performance
3 | Layout and integration
4 | Low-beta quadrupoles and correctors
| 4.1 | Design and construction of model quadrupole magnet
|  | 4.1.1 | Design and qualification of the coil
|  | 4.1.2 | Design of the support structure
|  | 4.1.3 | Preparation of the tooling
|  | 4.1.4 | Assembly
| 4.2 | Design and construction of prototype quadrupole
|  | 4.2.1 | Design of the cold mass
|  | 4.2.2 | Preparation of the tooling
|  | 4.2.3 | Assembly
| 4.3 | Design and production of correctors
| 4.4 | Production of quadrupole cold masses
| 4.5 | Cryostating
| 4.6 | Interconnections
5 | D1 separation dipoles
| 5.1 | Design and construction of D1 dipoles
6 | Magnet testing
7 | Quench protection
8 | Cold powering
9 | Power convertors
10 | TAS, absorbers, shielding
11 | Vacuum equipment
12 | Beam instrumentation
13 | Support and alignment equipment
14 | QRL modifications
15 | LSS magnet modifications
16 | String test

## budget summary
| 2008 | 2009 | 2010 | 2011 | 2012 | total
Job BE | 197013 | 680172.72 | 160682.3595 | 101873.8994 | 24480 | 1164221.9789
FSU | 92800 | 167080 | 290687.76 | 3846348.396 | 1943777.5513 | 6340693.7073
Specific tooling | 139000 | 1252500 | 200000 | 0 | 0 | 1591500
Components | 247420 | #REF! | #REF! | 1672650 | 0 | #REF!
travels different tasks | 40000 | 40000 | 40000 | 20000 | 20000 | 160000
travels central team, comp follow up | 40000 | 60000 | 60000 | 40000 | 20000 | 220000
raw material | 2008 | 2009 | 2010 | 2011 | 2012 | total | possible real purchase need
Nippon steel | 0 | 1595157.732 | 0 | 0 | 0 | 1595157.732 | 0
low carbon steel | 0 | 259994.28 | 0 | 0 | 0 | 259994.28 | 0
| 2008 | 2009 | 2010 | 2011 | 2012
FTE BE year with 230 working day /year | 2.0995 | 7.1935 | 2.712 | 1.038 | 0.26087
FTE FSU | 0.88 | 1.62 | 2.54 | 32.95 | 16.325
FTE CERN | 3.21 | 4.44 | 8.2 | 7.6 | 3.55
Central team FTE (part of above FTE CERN) | 2.15 | 2.8 | 3 | 2.5 | 1.6
FTE CERN without central team | 1.06 | 1.64 | 5.2 | 5.1 | 1.95
total components only
#REF!
total specifica tooling only
1591500
total work package
#REF!

## task and budget overview
[12 empty] | 1 hour BE |  | 1 man year FSU | [8 empty] | 1 hour BE |  | 1 man year FSU | [8 empty] | 1 hour BE |  | 1 man year FSU | [8 empty] | 1 hour BE |  | 1 man year FSU | [8 empty] | 1 hour BE |  | 1 man year FSU
[12 empty] | 51 |  | 110000 | [8 empty] | 52.02 |  | 112200 | [8 empty] | 53.0604 |  | 114444 | [8 empty] | 54.1216 |  | 116732.88 | [8 empty] | 55.204 |  | 119067.5376
project phase | type of activity | task | task leader |  | sub-tasks | preceeding task | end of preceeding task | start time | end time | budget 2008 | [10 empty] | budget 2009 | [10 empty] | budget 2010 | [10 empty] | budget 2011 | [10 empty] | budget 2012
|  |  |  | section inc harge | [5 empty] | material | jobs [d] | job cost | FSU | cost | CERN personnel name | CERN personnel FTE year | Cost | Temporary CERN personnel | Temporary CERN percentage | cost | material | jobs [d] | job cost | FSU | cost | CERN personnel name | CERN personnel FTE year | Cost | Temporary CERN personnel | Temporary CERN percentage | cost | material | jobs [d] | job cost | FSU | cost | CERN personnel name | CERN personnel FTE year | Cost | Temporary CERN personnel | Temporary CERN percentage | cost | material | jobs [d] | job cost | FSU | cost | CERN personnel name | CERN personnel FTE year | Cost | Temporary CERN personnel | Temporary CERN percentage | cost | material | jobs [d] | job cost | FSU | cost | CERN personnel name | CERN personnel FTE year | Cost | Temporary CERN personnel | Temporary CERN percentage | cost
model | design activities | Cable insulation: test and definition | D. Tommasini | MCS-NCM | cable insulation tests | none | none | 2008-02-01 | 2008-06-01 | 4000 |  | 0 |  |  | D. Richter | 0.2
[5 empty] | small mandrel winding test | [6 empty] | 0 | [5 empty] | PHD student | 0.3
[5 empty] | electrical tests | [6 empty] | 0
[5 empty] | curing small mandrel winding | [6 empty] | 0
[5 empty] | electrical tests cured winding | [6 empty] | 0
[5 empty] | heat transfer tests | [6 empty] | 0
|  | EM 2D design | E. Todesco | MCS-MDE |  | none | none | 2008-02-01 | 2008-04-01 |  |  | 0 |  |  | E. Todesco | 0.1 |  | F. Borgnolutti | 0.3
|  | 2D coil components design | Central Team |  | drawings copper wedges | EM 2D design |  | 2008-04-01 | 2008-05-01 |  | 12 | 4896
[5 empty] | design and drawing straigh part and fishbones | [5 empty] | 12 | 4896
|  | Protection | Central Team |  |  | EM 2D design |  | 2008-05-01 | 2008-07-01 |  |  | 0
[5 empty] | drawing Q.H. | [5 empty] | 11 | 4488
0
|  | EM 3D design | Central Team |  |  | EM 2D design |  | 2008-04-01 | 2008-06-01 |  |  | 0
|  | 3D coil components design | Central Team |  | design and drawings end spacers and 3d Coil | EM 3D design |  | 2008-06-01 | 2008-07-01 |  | 40 | 16320
[5 empty] | design and drawings layer jump comp | [5 empty] | 13 | 5304
|  | Mechanical 2D design | Central Team |  |  | EM 2D design |  | 2008-06-01 | 2008-09-01 |  |  | 0
|  | Design straight part mech components | Central Team |  | design and drawings collars | Mechanical 2D design |  | 2008-09-01 | 2008-10-01 |  | 15 | 6120
[5 empty] | design and drawings yokes shell and cross section | [5 empty] | 15 | 6120
[5 empty] | design and drawings shim retainer | [5 empty] | 10 | 4080
[5 empty] | design and drawings ground insulation | [5 empty] | 10 | 4080
|  | Mechanical 3D design | Central Team |  |  | Mechanical 2D design |  | 2008-09-01 | 2008-12-01 |  |  | 0
|  | End 3D components design | Central Team |  | design drawing collar packs | Mechanical 3D design |  | 2008-11-01 | 2009-02-01 |  | 4 | 1632
[5 empty] | design drawing yoke packs | [5 empty] | 8 | 3264
[5 empty] | design drawing collared coil end plate | [5 empty] | 8 | 3264
[5 empty] | design drawing cold mass end plate | [5 empty] | 4 | 1632
[5 empty] | design drawing tie rods | [5 empty] | 6.5 | 2652
[5 empty] | design drawing ends supports | [5 empty] | 13 | 5304
|  | Design office contingency for model | Central Team |  |  |  |  | 2008-05-01 | 2008-12-31 |  | 42.5 | 17340
0
0
| procurement activities | Cable Insulation | Central Team |  | insulation for 6 short poles material | Cable insulation: test and definition |  | 2008-06-01 | 2008-09-01 | 3000 |  | 0 |  |  | procurement follow up
|  |  | R, Maccaferri | MCS-LAB | insulation work |  |  |  |  | 1500 |  | 0
|  | 2D Coil components dummy+ model | Central Team |  | copper wedges 6 poles | 2D coil components design |  | 2008-05-01 | 2008-09-01 | 4800 |  | 0
[5 empty] | Fishbones 6 poles |  |  |  |  | 7500 |  | 0
|  | 3D Coil components dummy | Central Team |  | end spacers 2 poles | 3D coil components design |  | 2008-07-01 | 2008-09-01 | 31480 |  | 0
[5 empty] | layer jump components 2 poles |  |  |  |  | 1000 |  | 0
|  | 3D Coil components model | Central Team |  | end spacers 6 poles | dummy coil winding and curing |  | 2008-10-01 | 2009-02-01 | 27440 |  | 0
[5 empty] | layer jump components 6 poles |  |  |  |  | 3000 |  | 0
|  | Q.H. | Central Team |  | cables | protection study |  | 2008-07-01 | 2008-12-01 | 500 |  | 0
[5 empty] | Q.H. and ancillaries for 8 poles |  |  |  |  | 9600 |  | 0
|  | Straight part mechanical components | Central Team |  | collars for 1.25 models | Design straight part mech components |  | 2008-10-01 | 2009-02-01 | 29750 |  | 0
[5 empty] | yokes for 1.25 models |  |  |  |  | 63750 |  | 0
[5 empty] | shim retainer for 2 model |  |  |  |  | 2000 |  | 0
[5 empty] | G.I for 2 model |  |  |  |  | 2000 |  | 0
[5 empty] | shells |  |  |  |  | 56100 |  | 0
|  | End 3D components | Central Team |  | collared coil end plate 1 model | End 3D components design |  | 2009-01-01 | 2009-04-01 |  |  | 0 | [8 empty] | 7800 |  |  |  |  | procurement follow up | 0.2 | [15 empty] | 0 |  |  |  |  | procurement follow up | 0.2 |  |  |  |  | 0 |  |  |  |  | procurement follow up | 0.2
[5 empty] | cold mass end plate 1 model | [6 empty] | 0 | [8 empty] | 19500 | [21 empty] | 0 | [10 empty] | 0
[5 empty] | collaring keys | [6 empty] | 0 | [8 empty] | 20000 | [21 empty] | 0 | [10 empty] | 0
[5 empty] | tie rods 1 model | [6 empty] | 0 | [8 empty] | 750 | [21 empty] | 0 | [10 empty] | 0
[5 empty] | insulating pieces extremity | [6 empty] | 0 | [8 empty] | 2250 | [21 empty] | 0 | [10 empty] | 0
[5 empty] | consumables | [6 empty] | 0 | [8 empty] | 15000 | [21 empty] | 0 | [10 empty] | 0
[5 empty] | ends supports 1 model | [6 empty] | 0 | [8 empty] | 20000 | [21 empty] | 0 | [10 empty] | 0
0
| Tooling: design, assembly, commissioning | Short model tooling | R, Maccaferri | MCS-LAB | installation ACCEL winding machine | none |  | 2008-02-01 | 2008-09-01 | 0 |  | 0 | 0.4 | 40000
|  |  | F. Savary | MCS-MF | modification cable insulating machine | insulation studies |  | 2008-06-01 | 2008-09-01 | 0 |  | 0
|  |  | R, Maccaferri | MCS-LAB | installation modification ACCEL curing press | none |  | 2008-02-01 | 2008-09-01 | 0 |  | 0
|  |  | R, Maccaferri | MCS-LAB | new curing mould | approx aperture |  | 2008-04-01 | 2008-09-01 | 0 |  | 0
|  |  | R, Maccaferri | MCS-LAB | new shells for curing | EM 2D design |  | 2008-04-01 | 2008-09-01 | 10000 |  | 0
|  |  | R, Maccaferri | MCS-LAB | new winding mandrel | aperture definition |  | 2008-04-01 | 2008-09-01 | 20000 |  | 0
|  |  | R, Maccaferri | MCS-LAB | new winding post | EM 2D design |  | 2008-04-01 | 2008-09-01 | 5000 |  | 0
|  |  | R, Maccaferri | MCS-LAB | new E-modulus machine | none/ EM 2D design |  | 2008-04-01 | 2008-09-01 | 0 |  | 0
|  |  | R, Maccaferri | MCS-LAB | head impregantion tooling | 3D coil components design |  | 2008-04-01 | 2008-09-01 | 25000 |  | 0
|  |  | R, Maccaferri | MCS-LAB | collaring press | 2D mech design |  | 2008-10-01 | 2009-01-01 | 20000 |  | 0
|  |  | R, Maccaferri | MCS-LAB | collaring tooling |  |  | 2008-10-01 | 2009-01-01 | 2000 |  | 0
|  |  | R, Maccaferri | MCS-LAB | press for yoke packs |  |  | 2008-10-01 | 2009-01-01 | 2500 |  | 0
|  |  | R, Maccaferri | MCS-LAB | G.I. forming tool |  |  | 2008-10-01 | 2009-01-01 | 2000 |  | 0
|  |  | R, Maccaferri | MCS-LAB | instrumentation model |  |  | 2009-01-01 | 2009-06-01 |  |  | 0 | [8 empty] | 10000 |  |  | 0.1 | 10000
|  |  | R, Maccaferri | MCS-LAB | mandrel for aperture assembly |  |  | 2008-10-01 | 2009-01-01 | 5000 |  | 0
|  |  | S. Savary | MCS-MF | welding press cradles |  |  | 2008-10-01 | 2009-01-01 | 15000 |  | 0
[5 empty] | re-commissioning W press 181 |  |  | 2008-10-01 | 2009-01-01 |  |  | 0 | 0.16 | 17600
[6 empty] | aperture definition | [5 empty] | 0 |  | 0
| Magnet: assembly phases | dummy coil winding | R, Maccaferri | MCS-LAB | dummy coil winding and curing |  |  | 2008-09-01 | 2008-11-01 |  |  | 0 | 0.16 | 17600 | Cat 4 | 0.16
[5 empty] | head impregnation | [6 empty] | 0
[5 empty] | electrical tests | [6 empty] | 0
[5 empty] | E mod measurements | [6 empty] | 0
[5 empty] | destructuve tests | [6 empty] | 0
[5 empty] | splices tests | [6 empty] | 0
|  | 4 poles winding |  |  | winding curing and surfacing 4 poles |  |  | 2008-11-01 | 2009-01-01 |  |  | 0 | 0.16 | 17600 | cat 3 | 0.16
[5 empty] | E- mod measurements | [6 empty] | 0
[5 empty] | electrical tests | [6 empty] | 0
[5 empty] | splices | [6 empty] | 0
|  | collared coil |  |  | assembly 4 poles with G. I | [6 empty] | 0
[5 empty] | aperture preparation |  |  | 2009-01-01 | 2009-02-01 |  |  | 0 | [11 empty] | 0.4 | 44880 | cat 3 | 0.32
[5 empty] | consumable |  |  | 2009-01-01 | 2009-05-01 | [11 empty] | 15000
[5 empty] | collaring short test and colllaring |  |  | 2009-02-01 | 2009-03-01 |  |  | 0
|  | cold mass assembly | F. Savary | MCS-MF | dummy cold mass welding |  |  | 2009-02-01 | 2009-03-01 |  |  | 0 | [11 empty] | 0.04 |  | cat 3 | 0.04
[5 empty] | cold mass assembly |  |  | 2009-03-01 | 2009-05-01 |  |  | 0 |  | 0 | [9 empty] | 0.08 |  | cat 3 | 0.04
[5 empty] | instrumentation assembly |  |  | 2009-01-01 | 2009-05-01 |  |  | 0 |  | 0 | [6 empty] | 40000
[5 empty] | procedures establishement |  |  | 2008-10-01 | 2009-05-01 |  |  | 0 |  | 0 | [11 empty] | cat 4 | 0.08
[5 empty] | Warm magnetic measurements |  |  | 2009-05-01 | 2009-06-01 |  |  | 0 |  | 0 | [11 empty] | cat 3 | 0.04
[12 empty] | 0 |  | 0
Prototype | design phases | integration studies | H. Prin | Central team |  | none |  | 2008-02-01 | 2010-10-01 |  | 60 | 24480 |  | 0 | [7 empty] | 80 | 32640 | [9 empty] | 90 | 36720 | [9 empty] | 60 | 24480 | [9 empty] | 60 | 24480
0
|  | cryostat and support studies | V. Parma | MCS-CI | cryostat design | layout definition |  | 2008-09-01 | 2009-10-01 |  | 74.375 | 30345 | [6 empty] | 0.5 | 30000 | 48000 | 701.25 | 286110 |  |  | cat 4 | 1 | [5 empty] | 170 | 9020.268 |  |  | cat 4 | 0.5
[5 empty] | feed through design | instrumentation definition
[5 empty] | cold feet design | none
[5 empty] | screens design | none
[5 empty] | extremity cryostat design | aperture
0
|  | Magnet design | Central team |  | end covers design | layout and corrector design |  | 2009-03-01 | 2009-07-01 |  |  | 0 | [9 empty] | 30 | 12240
|  | Magnet design electrical connection | F. Savary | MCS-MF | bus bar design | powering input |  | 2009-03-01 | 2009-10-01 |  | 42.5 | 17340 | [9 empty] | 63.75 | 26010 | [9 empty] | 85 | 36081.072 | [9 empty] | 63.75 | 27602.0201
[5 empty] | electrical connection design | bus bar design |  | 2009-03-01 | 2009-10-01 |  |  | 0 | [9 empty] | 30 | 12240
|  | Design office contingency for proto | Central Team |  |  |  |  | 2009-01-01 | 2009-12-31 |  |  | 0 | [9 empty] | 60 | 24480
0
0
|  | Interconnection design | J. P. Tock | MCS-CI | electrical joint design | poweing scheme and bus bar |  | 2009-01-01 | 2011-12-01 | [12 empty] | 86.25 | 35893.8 |  |  | Cat 2 | 0.5 | [5 empty] | 86.25 | 36611.676 |  |  | cat 2 | 0.8 | [5 empty] | 57.5 | 24895.9397 |  |  | cat 2 | 0.8
[5 empty] | bellows design | layout and end covers design |  | 2009-01-01 | 2011-12-01 | [12 empty] | 86.25 | 35893.8 | [9 empty] | 86.25 | 36611.676 | [9 empty] | 57.5 | 24895.9397
[5 empty] | assembly procedure and tooling definition | [6 empty] | 0
|  | Correctors | M. Karppinen | MCS-Lab |  |  |  | 2008-10-01 | 2009-10-01 |  | 60 | 24480 |  |  | M. Karppinen | 0.2 |  |  |  |  | 140000 | 230 | 95716.8 | 1 | 112200 | M. Karppinen | 0.6 |  | fellow | 0.6 |  | 600000 |  |  | 1 | 114444
|  | Geometrical ITP definition | [9 empty] | 0
0
| procurement activities | Cable Insulation | Central team | Central team | insulation for 20 magnets | model testing |  | 2009-04-01 | 2010-05-01 |  |  | 0 | [8 empty] | 810000
|  | Coil components |  |  | copper wedges 20 magnets | [6 empty] | 0 | [8 empty] | 123640
[5 empty] | Fishbones 20 magnets | [6 empty] | 0 | [8 empty] | 576000
[5 empty] | end spacers 20 magnets | [6 empty] | 0 | [8 empty] | 492400
[5 empty] | layer jump components 20 magnets poles | [6 empty] | 0 | [8 empty] | 54000
|  | Q.H. | [9 empty] | 0
[5 empty] | Q.H. and ancillaris for 2 magnets | [6 empty] | 0 | [8 empty] | #REF!
|  | Straight part mechanical components |  |  | collars for 20 magnets | [6 empty] | 0 | [8 empty] | 1370000
[5 empty] | yokes for 20 magents | [6 empty] | 0 | [8 empty] | 1772000
[5 empty] | shim retainer for 20 magnets | [6 empty] | 0 | [8 empty] | 417857.1429
[5 empty] | G.I for 20 magnets | [6 empty] | 0 | [8 empty] | 162000
[5 empty] | shells for 20 magnets | [6 empty] | 0 | [8 empty] | 7020000
|  | End 3D components |  |  | collared coil end plates | [6 empty] | 0 | [8 empty] | 270000
[5 empty] | cold mass end plate 20 magnets | [6 empty] | 0 | [8 empty] | 450000
[5 empty] | tie rods 20 magnets | [6 empty] | 0 | [8 empty] | 390000
[5 empty] | ends supports 20 magnets | [6 empty] | 0 | [8 empty] | #REF!
[5 empty] | collaring keys | [15 empty] | 520000
[5 empty] | end covers | [15 empty] | 2200000
[5 empty] | cold bore tubes | [15 empty] | 624000
[5 empty] | heat exhanger tube | [15 empty] | 198000
[5 empty] | support cold mass | [15 empty] | 945000
[5 empty] | flanges | [15 empty] | 189000
[5 empty] | filling pieces | [15 empty] | #REF!
[5 empty] | shuttle piece | [15 empty] | #REF!
[5 empty] | insulating pieces extremity | [15 empty] | 270000
[5 empty] | bus bars | [6 empty] | 0 | [8 empty] | 1490000
|  | Interconnection | J. P. Tock | MCS-CI | tooling desing procurement |  |  | 2009-10-01 | 2010-08-01 |  |  | 0 | [8 empty] | 50000 |  |  |  |  | Cat III | 0.5 |  |  |  |  | #REF!
[5 empty] | interconnections for 3 magnets | cryostat design | [5 empty] | 0 | [8 empty] | 20000
|  | cryostat | V. Parma | MCS-CI | cryostat for 1 magnet | [6 empty] | 0 | [19 empty] | #REF!
[5 empty] | feed through for 1 magnet | [6 empty] | 0
[5 empty] | cold feet 2 magnets | [6 empty] | 0
[5 empty] | screens for 1 magnet | [6 empty] | 0
[5 empty] | estremity ryostat for 1 magnet | [6 empty] | 0
[5 empty] | MLI | [6 empty] | 0
|  | correctors prototype package | M. Karppinen | MCS-Lab |  |  |  | 01/062009 | 2010-06-01 |  |  | 0 | [8 empty] | #REF!
0
| Tooling: design, assembly, commissioning | long tooling | F. Savary | MCS-MF | modification cable insulation machine | insulation studies |  | 2008-02-01 | 2010-01-01 | 20000 |  | 0 |  |  | cat 3 | 0.16
[5 empty] | installation and modfication dipole wind. Machine | def of lenghts |  | 2008-02-01 |  | 12500 | 22 | 8976 |  |  | cat 3 | 0.08 |  |  |  |  | 12500 | 22 | 9155.52 |  |  | cat 3 | 0.08
[5 empty] | winding mandrel 1 I.+1 O. | EM 2D design |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 100000 | 20 | 8323.2 |  |  | cat 3 | 0.08
[5 empty] | winding posts | EM 2D design |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 20000 | 20 | 8323.2 |  |  | cat 3 | 0.08
[5 empty] | curing mould and curing beam | aperture |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 550000 | 20 | 8323.2 |  |  | cat 3 | 0.04
[5 empty] | curing shells | EM 2D design |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 50000 | 20 | 8323.2 |  |  | cat 3 | 0.04
[5 empty] | installation head surfacing tool from 927 | model completion |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 10000 |  |  |  |  | cat 2 | 0.04
[5 empty] | installation E modulus machine from 927 | model completion |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 20000 | 10 | 4161.6 |  |  | cat 3 | 0.08
[5 empty] | G.I. forming tooling | 2D coil components design |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 20000 | 10 | 4161.6 |  |  | cat 2 | 0.08
[5 empty] | mandrel for aperture assembly | EM 2D design |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 65000 | 25 | 10404 |  |  | cat 3 | 0.08
[5 empty] | installation collaring press from 927 | model completion |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 200000 | 60 | 24969.6 |  |  | cat 3 | 0.24
[5 empty] | collaring tooling | layout |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 30000 |  |  |  |  | cat 2 | 0.04
[5 empty] | installation yoking press from 927 | model completion |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 10000 |  |  |  |  | cat 2 | 0.04
[5 empty] | cradles | layout |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 60000 |  |  |  |  | cat 2 | 0.08
[5 empty] | rotating cutting device | mechanical 2D design |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 5000
[5 empty] | orbital welding machine for end covers | mechanical 2D design |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 5000
[5 empty] | orbital welding machine for extremities ? | interconnection desing |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 5000
[5 empty] | laser tracker and moulds | 3D extremity design, |  | 2008-02-01 |  |  |  | 0 | [8 empty] | 50000 | 20 | 8323.2 |  |  | cat 4 | 0.08
[5 empty] | pressure leak test tank | [6 empty] | 0 | [8 empty] | 10000 |  |  |  |  | cat 3 | 0.04
0
|  | Cryostating | V.Parma | MCS-CI | cryostating bench |  |  |  | 2010-06-01 |  |  | 0 | [8 empty] | 15000 | [10 empty] | 100000 |  |  | 0.25 | 28611 | cat 4 | 0.5
[5 empty] | other cryostating tooling | [6 empty] | 0 | [8 empty] | 15000 | [10 empty] | 100000 |  |  | 0.25 | 28611
0
|  | correctors tooling | [9 empty] | 0
0
| Magnet: assembly phases | dummy coils winding | F. Savary | MCS-MF | winding |  |  | 2010-01-01 | 2010-02-01 |  |  | 0 | [22 empty] | 0.16 | 18311.04 | cat 3 | 0.16
[5 empty] | curing |  |  | 2010-01-01 | 2010-02-01 |  |  | 0
[5 empty] | head surfacing |  |  | 2010-01-01 | 2010-02-01 |  |  | 0
0
|  | dummy collared coils | F. Savary | MCS-MF | [7 empty] | 0 | [22 empty] | 0.16 | 18311.04 | cat 3 | 0.16
0
|  | collared coils | F. Savary | MCS-MF | winding 4 poles |  |  | 2010-02-01 | 2010-04-01 |  |  | 0 | [22 empty] | 0.16 | 18311.04 | cat 3 | 0.16
[5 empty] | aperture assembly |  |  | 2010-04-01 | 2010-04-15 |  |  | 0 | [22 empty] | 0.08 | 9155.52 | cat 3 | 0.08
[5 empty] | collared coil |  |  | 2010-04-15 | 2010-06-01 |  |  | 0 | [22 empty] | 0.16 | 18311.04 | cat 3 | 0.16
|  | cold mass assembly |  |  | yoking |  |  | 2010-06-01 | 2010-07-01 |  |  | 0 | [22 empty] | 0.08 | 9155.52 | cat 3 | 0.04
[5 empty] | welding |  |  | 2010-07-01 | 2010-08-01 |  |  | 0 | [22 empty] | 0.08 | 9155.52 | cat 3 | 0.08
|  | cold mass finishing |  |  | extremity assembly |  |  | 2010-08-01 | 2010-09-01 |  |  | 0 | [22 empty] | 0.16 | 18311.04 | cat 3 | 0.16
consumable
[5 empty] | geometrical measurements |  |  | 2010-08-01 | 2010-09-01 |  |  | 0 | [24 empty] | cat 3 | 0.08
|  | cryostating | V. Parma | MCS-CI | cryostating |  |  | 2010-10-01 | 2010-12-01 |  |  | 0 | [24 empty] | cat 3 | 0.32
0
|  | correctors dummy coil | M. Karppinen | MCS-LAB | [7 empty] | 0
|  | correctors assembly tests | [9 empty] | 0
|  | correctors prototype assembly | [9 empty] | 0
0
|  | Design office contingency for series | Central Team |  |  |  |  | 2010-01-01 | 2010-12-31 |  |  | 0 | [9 empty] | 60 | 24480 | [9 empty] | 106.25 | 5637.6675
long | procurement activities | [10 empty] | 0
|  | Q.H. | Central team |  | Q.H. and ancillaris for 22 magnets |  |  | 01/03 2010 | 2010-12-31 |  |  | 0 | [19 empty] | 936000
|  | consumable |  |  | consumable | [6 empty] | 0 | [19 empty] | 270000
|  | phase separator | [9 empty] | 0 | [19 empty] | #REF!
0
|  | cryostat 19 units | V. Parma | MCS-CI |  |  |  | 2010-03-01 | 2010-12-31 |  |  | 0 | [19 empty] | #REF! |  |  |  |  | cat 4 | 1
|  | cryostat ancillaries | [9 empty] | 0 | [19 empty] | #REF! |  |  |  |  | cat 3 | 1
0
|  | interconnections for 6 triplet | J.P. Tock | MCS-CI |  |  |  | 2011-06-01 | 2012-06-01 |  |  | 0 | [30 empty] | 1672650
0
| manget assembly phases | series production | F Savary | MCS-MF |  |  |  | 2011-01-01 | 2012-06-01 |  |  | 0
[5 empty] | winding and curing | [6 empty] | 0 | [33 empty] | 5.6 | 653704.128 | cat 3 | 0.1 | [7 empty] | 2.8 | 333389.1053 | cat 3 | 0.05
[5 empty] | pole preparation | [6 empty] | 0 | [33 empty] | 3.2 | 373545.216 | cat 2 | 0.2 | [7 empty] | 1.6 | 190508.0602 | cat 2 | 0.1
[5 empty] | collared col assembly | [6 empty] | 0 | [33 empty] | 2.4 | 280158.912 | cat 2 | 0.4 | [7 empty] | 1.2 | 142881.0451 | cat 2 | 0.2
[5 empty] | yoking and CM welding | [6 empty] | 0 | [33 empty] | 4.2 | 490278.096 | cat 3 | 0.4 | [7 empty] | 2.1 | 250041.829 | cat 3 | 0.2
[5 empty] | extremity finishing | [6 empty] | 0 | [33 empty] | 2.45 | 285995.556 | cat 2 | 0.8 | [7 empty] | 1.225 | 145857.7336 | cat 2 | 0.4
[5 empty] | other production taksks | [6 empty] | 0 | [33 empty] | 9.2 | 1073942.496 | cat 3 | 1.1 | [7 empty] | 4.6 | 547710.673 | cat 3 | 0.55
0
|  | corrrectors production | M. Karppinen | MCS-Lab |  |  |  | 01706/2010 | 2012-02-01 |  |  | 0 | [19 empty] | #REF!
| exceptional | continency | Central Team |  |  |  |  | 2011-01-01 | 2012-06-01 |  |  | 0 | [30 empty] | 0 | [10 empty] | 0
| cryostating | cryostating 19 units | V. Parma | MCS-CI |  |  |  | 2011-01-01 | 2012-06-01 |  |  | 0 | [33 empty] | 5.6 | 653704.128 | Cat3 + cat 4 | 0.5 | [7 empty] | 2.8 | 333389.1053 | Cat3 + cat 4 | 0.25
| string | string assembly | J. P. Tock | MCs-Ci |  |  |  | 2011-08-01 | 2011-12-01 |  |  | 0 | [33 empty] | 0.3 | 35019.864 | Cat 4 | 0.6
central team |  | P. Fessia | [13 empty] | 0.8 | [9 empty] | 0.8 | [11 empty] | 0.8 | [10 empty] | 0.8 | [10 empty] | 0.6
|  | H. Prin | [13 empty] | 0.5 | [9 empty] | 0.6 | [11 empty] | 0.7 | [10 empty] | 0.7 | [10 empty] | 0.6
|  | O. Crettiez | [13 empty] | 0.6 | [9 empty] | 0.8 | [11 empty] | 0.8 | [10 empty] | 0.5 | [10 empty] | 0.2
|  | Purchasing help (Ph. Canard) | [13 empty] | 0.25 | [9 empty] | 0.6 | [11 empty] | 0.7 | [10 empty] | 0.5 | [10 empty] | 0.2
[10 empty] | budget 2008 | [10 empty] | budget 2009 | [10 empty] | budget 2010 | [10 empty] | budget 2011 | [10 empty] | budget 2012
[10 empty] | material | jobs [d] | job cost | FSU | cost | CERN personnel name | CERN personnel FTE year | Cost | Temporary CERN personnel | Temporary CERN percentage | cost | material | jobs [d] | job cost | FSU | cost | CERN personnel name | CERN personnel FTE year | Cost | Temporary CERN personnel | Temporary CERN percentage | cost | material | jobs [d] | job cost | FSU | cost | CERN personnel name | CERN personnel FTE year | Cost | Temporary CERN personnel | Temporary CERN percentage | cost | material | jobs [d] | job cost | FSU | cost | CERN personnel name | CERN personnel FTE year | Cost | Temporary CERN personnel | Temporary CERN percentage | cost | material | jobs [d] | job cost | FSU | cost | CERN personnel name | CERN personnel FTE year | Cost | Temporary CERN personnel | Temporary CERN percentage | cost
[10 empty] | 386420 | 482.875 | 197013 | 0.88 | 92800 | 0 | 3.21 | 0 | 0 | 1.1 | 30000 | #REF! | 1654.5 | 680172.72 | 1.62 | 167080 | 2.8 | 4.44 | 0 | 0 | 0.6 | 0 | #REF! | 623.75 | 160682.3595 | 2.54 | 290687.76 | 0 | 8.2 | 0 | 0 | 0 | 0 | 1672650 | 238.75 | 101873.8994 | 32.95 | 3846348.396 | 0 | 7.6 | 0 | 0 | 0 | 0 | 0 | 60 | 24480 | 16.325 | 1943777.5513 | 0 | 3.55 | 0 | 0 | 0 | 0
4.1
[9 empty] | tooling | 139000 | [9 empty] | tooling | 1252500 | [9 empty] | tooling | 200000 | [9 empty] | tooling | 0 | [5 empty] | 2.5 |  |  |  | tooling | 0
[9 empty] | components | 247420 | [9 empty] | components | #REF! | [9 empty] | components | #REF! | [9 empty] | components | 1672650 | [9 empty] | components | 0

## assembly personnel jens
personnel
production of long magnets
working days
phase | sub-phase, task | N FSU | CERN technician | CERN engineer
winding and curing 2.5 coils /week | insulation of copper wedge | 0.5
| insulation of cable | 4
| preparation end spacers and cutting copper wedges | 0.5
| preparation mandrel | 3
| winding | 7.5 |  | 0.5
| preparation for curing | 5
| curing follow up | 2.5
| extraction of coil | 2
| electrical measurements | 1
| visual inspection | 2
| total wordays/week | 28 | 0 | 0.5
| total FTE | 5.6 | 0 | 0.1
pole preparation | coil E modulus measurements | 4
| inter layer spacer assembly | 1
| electrical measurements after E-modulus | 1
| splice soldering | 2 |  | 1
| electrical measurements pole | 0.5
| length adjustement | 0.5
| aperture preparation with G.I. and coil prtection sheet | 7
| total wordays/week | 16 | 0 | 1
| total FTE | 3.2 | 0 | 0.2
collared coil assembly | pack preparation | 2
| collared coil pre-collaring operations | 4
| collaring operations | 5 |  | 2
| electrical tests | 1
| total wordays/week | 12 | 0 | 2
| total FTE | 2.4 | 0 | 0.4
yoking and CM welding including CP | preparation of packs | 3
| preparation of half yoke | 2
| insertion of collared coil in the yoke | 3 |  | 2
| preparation under the press | 4.5
| welding | 3.5
| electrical connection | 3.5
| electrical tests | 1.5
| total wordays/week | 21 | 0 | 2
| total FTE | 4.2 | 0 | 0.4
extremity finishing | cylinder cut | 1.5
| end cover welding | 5
| gometrical measurements | 2.5 |  | 4
| electrical measurements | 1
| pressure leak test | 1.25
| mgnetic meaurements | 1
| total wordays/week | 12.25 | 0 | 4
| total FTE | 2.45 | 0 | 0.8
other tasks | incoming inspections | 5
| store management | 4
| manipulation | 6 |  | 2
| machining | 5
| other quality tests and report filling | 7
| quality control, procedures, NCRs | 5
| orders consumables | 1
| repairs and NCR solution | 7
| maintenance tooling | 6
| total wordays/week | 46 |  | 5.5
| total FTE | 9.2 | 0 | 1.1
[5 empty] | hours eq | pirce /hour |  | yers of production | total techcnicians
| total | 27.05 | 0 | 3 | 56264 | 87 | 4894968 | 4 | 19.5799
cryostat
working days
phase | sub-phase, task | N FSU | CERN technician | CERN engineer
| coordination pressure leak test | 7
| mechanician | 7
| welder | 7
| electromechanician | 7
|  |  |  | 2.5 | hours eq | pirce /hour |  | yers of production | total techcnicians
| total FTE | 5.6 | 0 | 0.5 | 11648 | 87 | 1013376 | 4 | 4.0535
|  |  |  | total eng | hours eq | pirce /hour |  | yers of production | total eng |  | total personnel over 4 years
|  |  |  | 3.5 | 7280 | 100 | 728000 | 4 | 2.912 |  | 26.5454
[9 empty] | halle rent/month | total time | total cost
[9 empty] | 50000 | 48 | 2.4
[9 empty] | tooling MCHF | 5
tooling+personnel+hall
33.9454
development and procurement
[8 empty] | 3 FTE eng for 3 years | 1872000 |  | 208000
[8 empty] | 3 FTE tech for 3 years | 1404000 |  | 468000
[8 empty] | total development and procurement | 3276000 |  |  | 0.68889
[10 empty] | short model | tooling | 3 MCHF
[11 empty] | personnel | 1 MCHF
[11 empty] | material | 0.5 MCHF

## component cost estimation jens
model length 1.5m
final length10m
component | phase of order | phase covered | N cold mass | quantity/cold mass | spare in cold mass | price unit | estimated cost/unit | total cost | available | spare reason | method of estimation
cable insulation | model | dummy and model | 1 | 4 | 0.5 | poles | 500 | 3000 | yes | dummy+ model+ 1 pole spare | price of the offer multiplied by two repsect yen price. Lenth 2 m
copper wedges | model | dummy and model | 1 | 4 | 0.5 | poles | 800 | 4800 | no | dummy+ model+ 1 pole spare | guess
inter-layer spacers | model | dummy and model | 1 | 4 | 0.5 | poles | 1250 | 7500 | no | dummy+ model+ 1 pole spare | dipole: 5500 CHF/cold mass: scaling on length and number of poles + cost for small series facro 2
end spacers | model | dummy | 0.5 | 4 | 0 | poles | 2240 | 31480 | no | dummy + 1 pole | 3 pieces NCS, 4 pieces CS, 4 layer->28 pieces. Dipole 170CHF/piece for 30 sets. Unit cost*2 for small series+10000 tooling+15000 program+2000 material
end spacers | model | model | 1 | 4 | 0.5 | poles | 2240 | 27440 | no | iteration, cold mass + 1 spare+ extra | 3 pieces NCS, 4 pieces CS, 4 layer->28 pieces. Dipole 170CHF/piece for 30 sets. Unit cost*2 for small series+5000 tooling+5000 program+4000 material
layer jump components | model | dummy | 0.25 | 4 | 0.25 | poles | 500 | 1000 | no | dummy + 1 pole | dipole series: 300chf/pole. Small series cofficient 2.
layer jump components | model | model | 1 | 4 | 0.5 | poles | 500 | 3000 | no | iteration, cold mass + 1 spare+ extra | dipole series: 300chf/pole. Small series cofficient 2. d
Quench heater | model | model | 1 | 4 | 1 | poles | 1200 | 9600 | no recover dipoles ? | 1 model+ 1 re-collaring | dipole series: 12500chf/magnet. Scale on length= Small series cofficient 4.
Ground insulation | model | model | 1 | 1 | 1 | model | 500 | 2000 | yes | 1 model+ 1 re-collaring | material + 1000 of cutting and forming
collars | model | model | 1 | 1 | 0.25 | model | 23800 | 29750 | no | 1 model + collaring model | estimation for NED dipole: 750 pieces 33.000 euro-> here 500*2 pieces cost reduced of 30% because of shorter perimeter eur to chf 1.7
yoke | model | model | 1 | 1 | 0.25 | model | 51000 | 63750 | no | 1 model + welding model | estimation for NED dipole: 900 pieces 50.000 euro-> here 600 pieces euro to chf 1.7
shim retainer | model | model | 1 | 1 | 1 | model | 1000 | 2000 | no | 1 model +1 re-collaring | dipole 5000 CHF/magnet. Quad double of pieces scale on length. Small series coef 2
shells | model | model | 1 | 1 | 0.5 | model | 37400 | 56100 | no | 1 model+ 1 welding model | ned estimation using 304 for 1.6 m 24000 euro
collared coil end plate | model | model | 1 | 2 | 0 | units | 3900 | 7800 | no | 1 model | dipole:3000 chf/magnet. Coeff for reduced series: 2. increase price of steel 30%
cold masse end plates | model | model | 1 | 2 | 1 | units | 4875 | 19500 | no | 1 model | dipole:5000 chf/magnet. Coeff for reduced series: 1.5 increase price of steel 40%
tie rods | model | model | 1 | 1 | 0 | units | 750 | 750 | no | 1 model | dipole 5000, scale length, small series factor 1.5
end supports | model | model | 1 | 2 | 0 | units | 10000 | 20000 | no | 1 model | guess
consumables | model | dummy and model | 1 | 1 | 0 | package | 15000 | 15000 | no | package | guess
collaring keys | model | model | 1 | 8 | 1 | model | 1333.3333 | 21333.3333 | no | 1 model+ 1 re-collaring | dipole: 10000. quad scale length, multiply by 2 for quantity and for 2 for small series
insulating pieces for extremity | model | model | 1 | 1 | 0 | model | 2250 | 2250 | no | 1 model | dipole: 1500 chf coff 1.6
cable insulation | prototype | series | 90 | 1 | 0 | magnets | 9000 | 810000 | partally | 86 CM + 4 spare | price of the offer multiplied by two respect yen price. Length 10 m. 144 Kg P1 and 139 Kg A1 available: we lack of 173 kg and 40 kg | in case of 3 layer multiply by factor 2
copper wedges | prototype | series | 90 | 2 | 0 | poles | 598 | 123640 | no | 86 CM + 4 spare | 2 copper wedge each coil, 8000 CHF extrusion tooling per shape. Small series factor 2 | constant
inter-layer spacers | prototype | series | 90 | 2 | 0 | poles | 3200 | 576000 | no | 86 CM + 4 spare | dipole: 3000 CHF/cold mass: scaling on length and number of poles + cost for small series facto 1.5 | in case of 3 layer multiply by factor 2
end spacers | prototype | series | 90 | 2 | 0 | poles | 2180 | 492400 | no | 86 CM + 4 spare | 8 pieces NCS, 11 pieces CS. Dipole 130CHF/piece for 30 sets +500 chf materal/set. Estiamtion here 130*19+700=3200 chf/pole+100.000 CHF tooling and CNC pgoramming | average
layer jump components | prototype | series | 90 | 2 | 0 | poles | 300 | 54000 | no | 86 CM + 4 spare | dipole series: 250chf/pole. Small series cofficient 1.2 | in case of 3 layer multiply by 2 |  | length | collar thickness | types of collars | total number collars 1 magnet | cost for a shot
collar material maximum |  | series | 90 | 1 | 0 | cold mass | 10000 | 900000 |  | 86 CM + 4 spare | price per kg steel 8 chf/kg larget aperture
collar material minimum |  | series | 90 | 1 | 0 | cold mass | 6500 | 585000 |  | 86 CM + 4 spare | price per kg steel 8 chf/kg small aperture
collars | prototype | series | 90 | 1 | 0 | cold mass | 13000 | 1370000 | no yes steel | 86 CM + 4 spare | length 10m 20 magnets 2 collars each 3 mm, 8666 pieces/magnet, tooling 200000, price for shot 1.5CHF. | indipendent layers |  | 13000 | 3 | 2 | 8666.6667 | 1.5 | 13000
yoke | prototype | series | 90 | 1 | 1 | cold mass | 17000 | 1772000 | no partially iron | 86 CM + 4 spare | length 13m 90 magnets 2 yokes each 5.8 mm, tooling 225000, price for shot 3.8CHF. | indipendent layers
iron for yoke min | series | series | 90 | 1 | 0 | cold mass | 4600 | 414000 |  | 86 CM + 4 spare | price per kg steel 2.5 chf/kg small aperture |  |  | 2.5 | 1.25 | 0.03 | 8 | 0.09375 | 812.5 | 8 | 6500
iron yoke max | series | series | 90 | 1 | 0 | cold mass | 10000 | 900000 |  | 86 CM + 4 spare | price per kg steel 2.5 chf/kg larget aperture
shim retainer | prototype | series | 90 | 1 | 0 | cold mass | 4642.8571 | 417857.1429 | no | 86 CM + 4 spare | dipole 5000 CHF/magnet. | average |  | 3.1 | 1.55 | 0.03 | 8 | 0.14415 | 1249.3 | 8 | 9994.4
ground insulation | prototype | series | 90 | 1 | 0 | cold mass | 1800 | 162000 | no | 86 CM + 4 spare |  | average
shells | prototype | series | 90 | 1 | 0 | model |  | 7020000 |  | 86 CM + 4 spare | information Herve (arket survey) | indipendent layers |  | length | yoke thickness | types of yoke | total number yoke lamination 1 magnet | cost for a shot
collared coil end plate | prototype | series | 90 | 2 | 0 | units | 1500 | 270000 | no | 86 CM + 4 spare | dipole:3100 chf/magnet. | indipendent layers |  | 13000 | 5.8 | 2 | 4482.7586 | 3.8 | 17034.4828
cold mass end plates | prototype | series | 90 | 2 | 0 | units | 2500 | 450000 | no | 86 CM + 4 spare | dipole:5200 chf/magnet.
tie rods | prototype | series | 90 | 1 | 0 | units | 4333.3333 | 390000 | no | 86 CM + 4 spare | dipole 5000, scale length |  |  | 3.7 | 1.9 | 0.058 | 8 | 0.40774 | 1827.8 | 2.5 | 4569.5
consumables | prototype | series | 90 | 1 | 0 | package | 3000 | 270000 | no | 20 CM | guess |  |  | 5.5 | 2.8 | 0.058 | 8 | 0.8932 | 4004 | 2.5 | 10010
collaring rods | prototype | series | 90 | 2 | 0 | cold mass | 2888.8889 | 520000 | no | 86 CM + 4 spare | dipole: 11000. scaled length
insulating pieces for extremity | prototype | series | 90 | 2 | 0 | cold mass | 1500 | 270000 | no | 86 CM + 4 spare | dipole: 1500 chf
end covers | prototype | series | 90 | 2 | 0 | cold mass | 6000 | 2200000 | no | 86 CM + 4 spare | unit estimation on the base of the cold mass production. In addition 40000 chf tooling 1 piece 6000 chf
Quench heater | prototype | series | 90 | 4 | 0 | poles | 2600 | 936000 | no | 86 CM + 4 spare | dipole series: 12500chf/magnet.
bus bar | prototype | series | 90 | 1 | 0 | cold mass | 16000 | 1490000 | no | 86 CM + 4 spare | estiamtion on the present dipole bus bar design with extra 50000 CHF for tooling refurbishement
cold bore tubes | prototype | series | 90 | 1 | 0 | cold mass | 6933.3333 | 624000 | no | 86 CM + 4 spare | estimation with F. Savary on the base of LHC experience
heat exhanger tube | prototype | series | 90 | 1 | 0 | cold mass | 2200 | 198000 | no | 86 CM + 4 spare | estimation with F.savary H. Prin based on present trpliet repair. 1 HX diam 100 mm
support cold mass | prototype | series | 90 | 3 | 0 | pieces | 3500 | 945000 | no | 86 CM + 4 spare | dipole contract
flanges | prototype | series | 90 | 1 | 0 | cold mass set | 2100 | 189000 | no | 86 CM + 4 spare | guess
Interconnections | series | series | 90 | 1 | 0 | kit | 18585 | 1672650 | no | 90 interconnect | from Interconnect experience
[8 empty] | 26021547.1429 | 26.0215
insulation
[14 empty] | total standard 1 magnet P1 | total adhesive 1 magnet A1 | n of units | total amount stadard | total amount adhesive | price standard (double special price) 100kg
| cable width | cable thickness | perimeter | tape length 1 meter | tape thickness | volume l/m |  | density | weight/meter [kg/m] | n of turns | length |  |  | 15.0736 | 8.4086 | 1 | 15.0736 | 8.4086 | 19800
1st insulation 1st layer | 15.1 | 1.9 | 34 | 34000 | 0.05 | 0.0017 |  | 1.4 | 0.00238 | 1 | 1340 |  | n poles | [6 empty] | price adhesive (double special price) | price foreseen quantity in CHF P1 1 pole | price foreseen quantity in CHF A1 1 pole
2nd insulation 1st layer | 15.2 | 2 | 34.4 | 34400 | 0.05 | 0.00172 |  | 1.4 | 0.002408 | 1 | 1340 | 6.3784 | 1 | [6 empty] | 66925.4736 | 2984.5791 | 5627.4956 | 8612.0748
3rd layer | 15.3 | 2.1 | 34.8 | 28472.7273 | 0.067 | 0.0019077 |  | 1.4 | 0.0026707 | 1 | 1340 | 6.4534 | 1 |  |  |  | total amount P1 20 magnets | total amount A1 20 magnets
[12 empty] | 7.1576 | 1 |  |  |  | 1205.8906 | 672.688
1st insulation 1st layer | 15.1 | 1.48 | 33.16 | 33160 | 0.05 | 0.001658 |  | 1.4 | 0.0023212 | 24 | 10 |  |  |  |  | available CERN | 144 | 139
2nd insulation 1st layer | 15.2 | 1.58 | 33.56 | 33560 | 0.05 | 0.001678 |  | 1.4 | 0.0023492 | 24 | 10 | 1.1142 | 1
3rd layer | 15.3 | 1.68 | 33.96 | 27785.4545 | 0.067 | 0.0018616 |  | 1.4 | 0.0026063 | 24 | 10 | 1.1276 | 1
[12 empty] | 1.251 | 1
60.2945
33.6344
ground insulation
dipole: weight of needed GI Kg | length | weight for aperture and 1 m | external diameter dipole | external diameter quadrupole triplet | ratio | GI per meter estimation quad | weight 1 quad 10m | need for 20 CM | price per kg | total 20 CM
15 | 15 | 0.5 | 117.6 | 196.6 | 1.6718 | 0.83588 | 8.3588 | 167.1769 | 214.1551 | 35801.7722
[8 empty] | 8.3588 | 1790.0886
bus bar | time | cost 15m | cost 10 m | update 2007 |  | cost of a set
manufacturing time | 170 | 10163.0435 | 10163.0435 | 10163.0435 |  | 15959.7101
copper |  | 900 | 600 | 1200
spool |  | 800 | 533.3333 | 693.3333
brazing material |  | 150 | 100 | 130
copper for lyra |  | 20 | 20 | 40
polyimide |  | 100 | 66.6667 | 133.3333
pre-preg |  | 2200 | 1466.6667 | 2200
other |  | 700 | 700 | 1400
heat exchanger
material/unit
copper | 1386
forming | 10416.6667
steel - copper welding | 10000

## steel-iron
yoke
radius | surface lamination | min surface sheet | thickness | volume | density | weight
270 | 114510.9555 | 147424 | 5.8 | 0.85506 | 7.9 | 6.755
length | necessary weight | for 20 magnets
10000 | 23292.992 | 372.6879
collars
radius | surface lamination | min surface sheet | thickness | volume | density | weight
137.3 | 29611.5121 | 38530.38 | 3 | 0.11559 | 7.5 | 0.86693
length | necessary weight | for 20 magnets |  | price/ton | total cost
11500 | 6646.4906 | 132.9298 |  | 12000 | 1595157.732
N magneti | L magneti | thickness | density | total pieces needed | weight of plate around | total weight material needed in ton | available material in ton
20 | 10000 | 3 | 7.5 | 133333.3333 | 0.86693 | 115.5911 | 134
N magneti | L magneti | thickness | density | total pieces needed
6 | 7000 | 5.8 | 7.8 | 14482.7586
for LHC in 4105mm had 15 laminations
needs in plates
965.5172
weight 1 plate |  | total needs ton |  | avaialble |  | price/ton | total cost
107.7119 |  | 103.9977 |  | 262 |  | 2500 | 259994.28
N magneti | L magneti | thickness | density | total pieces needed |  | 445 | 262 | 183 | 457500
16 | 8000 | 5.8 | 7.8 | 44137.931 |  | 510 | 262 | 248 | 620000
[6 empty] | 570 | 262 | 308 | 770000
for LHC in 4105mm had 15 laminations
needs in plates
2942.5287
weight 1 plate |  | total needs ton |  | avaialble
107.7119 |  | 316.9454 |  | 262

## tooling needs
model magnet |  | in common with long magnet | availability date | option 1 | option 2 | option 3
coil
| winding mandrels | no | 2008-09-01 | to be built
| winding post | no | 2008-09-01 | to be built
| winding machine | no | 2008-09-01 | installation of ACCEL machine
| cable insulation machine | no | 2008-09-01 | modification of present system at 927
| end surfacing mould | yes | 2008-09-01 | new moulds: possible re- use of external structure from BNN
| E modulus measuring machine | yes if possible | 2008-09-01 | Jeumont machine: needs adaptation in legnth diamter and system | machine recovered from ACCEL or TESLA | new machine
| curing press | no | 2008-09-01 | ACCEL curing press | piece of Noell red press
| curing mould | no | 2008-09-01 | to be built
| heating center | no
pole
| splice soldering equipment | yes | 2008-09-01 | BNN equipment | new one
| bench for length adjustement | low importance | 2008-11-01
aperture
| tooling for ground insulation folding | no | 2008-11-01 | to be defined
| mandrel for aperture assembly | no | 2008-11-01 | to be built
collared coil | collaring press | to be studied | 2008-11-01 | new horizontal press with travelling active module to be installed at long workshop | re-use of vertical lift from TESLA on which we need to isntall new active module
| collaring tool | to be studied | 2008-11-01
| collaring mandrel | to be studied | 2008-11-01
| magnetic measurement system | partially | 2008-11-01 | possibly use old equipment with new mould
yoking and shell welding | yoke pack press | yes | 2009-01-01 | something available?
| cradles | no | 2009-01-01
| welding press | possibly yes | 2009-01-01 | press at 181 | dipole welding press | press at 927
| magnetic measurement system | partially | 2009-01-01 | see above
long magnet |  | in common with model magnet | availability date | option 1 | option 2 | option 3
coil
| winding mandrel | no | 2010-01-01 | to be built
| winding post | no | 2010-01-01 | to be built
| winding machine | no | 2010-01-01 | modification of dipole winding machine
| cable insulation machine | no | 2010-01-01 | modification of Jeumont insulating machine
| end surfacing mould | yes | X
| E modulus measuring machine | yes if possible | X
| curing press | no | 2010-01-01 | use of dipole press with modifications
| curing mould | no | 2010-01-01 | to be built
| heating center | no | 2010-01-01 | recovered?
pole
| splice soldering equipment | yes | X
| bench for length adjustement | low importance | X
aperture
| tooling for ground insulation folding | no | 2010-02-01
| mandrel for aperture assembly | no | 2010-02-01
collared coil | collaring press | to be studied | X or March 2010 | see above
| collaring tool | to be studied | X or March 2010 | see above
| collaring mandrel | to be studied | X or March 2010 | see above
| magnetic measurement system | partially | 2010-03-01 | see above
yoking and shell welding | yoke pack press | yes | X | see above
| cradles | no | 2010-04-01
| welding press | possibly yes | X or April 2010 | press at 181 | dipole press
| magnetic measurement system | partially | 2010-04-01 | see above
proposed action
model magnet | tooling | start
| winding mandrels | need definition of aperture: target end of march
| winding post | need definition of aperture: target end of march
| winding machine | ok
| cable insulation machine | ok
| end surfacing mould | need definition of aperture: target end of march
| E modulus measuring machine | pre-study and policy to be fixed asap
| curing press | ok
| curing mould | curing mould for coil from O.D. 116 to O.D. of 210
| heating center | ok
| splice soldering equipment | to checked asap
| bench for length adjustement | later
| tooling for ground insulation folding | later
| mandrel for aperture assembly | later
| collaring press | studied to be started
| collaring tool | later
| collaring mandrel | later
| magnetic measurement system | later
| yoke pack press | later
| cradles | later
| welding press | later
| magnetic measurement system | later

## labour and material indexes
Epistemes
increase salary from 1999 to 2005
diff %
UK | 27.8
Norway | 25.6
Netherland | 21.3
Finland | 21.1
France | 17.5
Spain | 17.2
Portugal | 16.6
Denmark | 16
Belgium | 15.9
italy | 13.7
Germany | 11
Sweden | 7.7
average | 17.6167
Switzerland I
|  | Indice 1993=100 | [7 empty] | T1.93_I |  |  | Indice 1993=100
|  | 1994 | 1995 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | Branches économiques |  |  | 2002 | 2003 | 2004 | 2005 | 2006
15-37 | Industries manufacturières | 101.8053 | 102.7006 | 103.9285 | 104.1747 | 104.9857 | 105.2257 | 106.5794 | 109.452 | D | 15-37 | Industries manufacturières | 111.4116 | 112.7834 | 113.5423 | 115.0296 | 116.3394
15-16 | Industries alimentaires, industries des boissons et du tabac | 101.3415 | 101.7845 | 102.2939 | 103.7462 | 103.8206 | 104.484 | 106.2597 | 108.3594 |  | 15-16 | Industries alimentaires, industries des boissons et du tabac | 110.2088 | 111.6744 | 112.489 | 114.0178 | 115.1959
17-18 | Industrie textile, habillement et fourrures | 101.8397 | 103.2138 | 105.3331 | 104.9989 | 105.1946 | 104.2602 | 105.2686 | 106.39 |  | 17-18 | Industrie textile, habillement et fourrures | 108.3394 | 109.409 | 110.5007 | 112.3592 | 114.7696
20 | Travail du bois et fabrication d'articles en bois (sans les meubles) | 101.0167 | 102.7959 | 104.6849 | 104.7396 | 105.2971 | 105.3814 | 106.9441 | 108.8181 |  | 20 | Travail du bois et fabrication d'articles en bois (sans les meubles) | 110.1753 | 110.7634 | 111.5619 | 113.3857 | 114.3044
21-22 | Industrie du papier et du carton; édition et impression | 101.3042 | 101.9616 | 103.2676 | 103.1443 | 103.2617 | 103.6892 | 104.6462 | 107.278 |  | 21-22 | Industrie du papier et du carton; édition et impression | 108.3544 | 109.2734 | 109.7015 | 110.4949 | 110.8013
19, 23-25 | Industrie du cuir, de la chaussure, cokéfaction, chimie, fabrication d'articles en caoutchouc et en matières plastiques | 103.7656 | 104.6019 | 106.6065 | 106.3189 | 108.786 | 108.4068 | 109.9002 | 113.2003 |  | 19, 23-25 | Industrie du cuir, de la chaussure, cokéfaction, chimie, fabrication d'articles en caoutchouc et en matières plastiques | 116.1571 | 118.0996 | 119.5184 | 123.1885 | 125.2733
26 | Fabrication d'autres produits minéraux non métalliques | 100.2886 | 103.9022 | 104.3736 | 105.1758 | 104.0327 | 105.0921 | 107.2809 | 109.4279 |  | 26 | Fabrication d'autres produits minéraux non métalliques | 111.7326 | 112.5614 | 112.5893 | 113.3034 | 114.818
27-28 | Métallurgie et travail des métaux | 101.0839 | 102.2998 | 104.0183 | 104.4417 | 103.9048 | 104.4748 | 106.23 | 109.1574 |  | 27-28 | Métallurgie et travail des métaux | 111.0596 | 112.2912 | 113.1986 | 113.7547 | 115.2111
29, 34-35 | Fabrication de machines, d'équipements et de moyens de transport | 101.456 | 102.5474 | 102.4947 | 103.0595 | 103.8799 | 104.064 | 104.6471 | 107.477 |  | 29, 34-35 | Fabrication de machines, d'équipements et de moyens de transport | 109.8878 | 111.4593 | 112.042 | 112.4675 | 113.7709
30-33 | Fabrication d'équip. électriques et électroniques, mécanique de précision, optique | 102.2002 | 102.0949 | 103.722 | 103.6625 | 105.2985 | 105.5627 | 107.2503 | 111.0734 |  | 30-33 | Fabrication d'équip. électriques et électroniques, mécanique de précision, optique | 112.4738 | 113.9412 | 114.4904 | 116.2997 | 117.3509
36-37 | Fabrication de meubles, de bijoux, industries diverses | 101.1009 | 102.6627 | 104.7908 | 104.957 | 105.3276 | 106.2056 | 107.5754 | 109.5363 |  | 36-37 | Fabrication de meubles, de bijoux, industries diverses | 111.061 | 111.8099 | 112.6259 | 113.5182 | 115.2575
45 | Construction | 101.425 | 103.209 | 104.4866 | 104.6917 | 105.0792 | 104.5546 | 106.4994 | 109.4586 | F | 45 | Construction | 111.2035 | 112.3026 | 112.7493 | 113.9803 | 115.2148
France
100 fin 1998 |  | juin | sept. | déc. | mars | juin | Variations en juin 2005 sur:
|  | 2004 | 2004 | 2004 | 2005 | 2005 | 3 mois | 6 mois | 12 mois
ENS | Ensemble des secteurs non agricoles | 114 | 115.2 | 115.6 | 116.6 | 117.3 | 0.6 | 1.4 | 2.9
Ventilation par secteur d'activité
EB | Industries agricoles et alimentaires (B0) | 112.6 | 113.6 | 113.9 | 114.7 | 115.6 | 0.7 | 1.4 | 2.6
EC | Industries des biens de commation (C1 à C4) | 112.6 | 113.9 | 114.1 | 115 | 115.5 | 0.4 | 1.2 | 2.6
C1 | Habillement, cuir | 112.5 | 114.3 | 114.6 | 115.3 | 115.6 | 0.2 | 0.9 | 2.7
C2 | Édition, imprimerie reproduction | 110.3 | 111.3 | 111.4 | 112.2 | 112.8 | 0.5 | 1.2 | 2.3
C3 | Pharmacie, parfumerie et entretien | 113.2 | 113.8 | 114 | 115.5 | 116 | 0.4 | 1.8 | 2.5
C4 | Industrie des équipements du foyer | 113.9 | 115.3 | 115.7 | 116.5 | 117 | 0.5 | 1.1 | 2.7
D0 | Industries automobile (B0) | 116.8 | 117.4 | 117.8 | 119.7 | 120.5 | 0.6 | 2.3 | 3.2
EE | Industries des biens d'équipement (E1 à E3) | 114.3 | 115.2 | 115.5 | 116.7 | 117.4 | 0.6 | 1.6 | 2.7
E1 | Construction navale, aéronautique et ferroviaiare | 116.2 | 116.7 | 117.3 | 118 | 119 | 0.8 | 1.5 | 2.4
E2 | Industries des équipements mécaniques | 114.2 | 115.3 | 115.6 | 116.8 | 117.5 | 0.6 | 1.7 | 2.9
E3 | Industries des équipements électriques et électroniques | 113.4 | 114.2 | 114.5 | 115.6 | 116.3 | 0.6 | 1.6 | 2.5
EF | Industries des biens intermédiaies (F1 à F6) | 113.4 | 114.5 | 114.9 | 115.9 | 116.7 | 0.7 | 1.6 | 2.9
F1 | Industries des produits minéraux | 112.3 | 113.3 | 113.5 | 114.7 | 115.5 | 0.6 | 1.7 | 2.8
F2 | Industrie textile | 111.9 | 113.8 | 114.2 | 114.9 | 115.8 | 0.7 | 1.4 | 3.5
F3 | Industrie du bois et du papier | 114 | 115.3 | 115.6 | 116.4 | 117.1 | 0.6 | 1.3 | 2.7
F4 | Chimie, caoutchouc, plastiques | 112.9 | 114 | 114.3 | 115.3 | 116.1 | 0.8 | 1.6 | 2.9
F5 | Métallurgie et transformation des métaux | 114 | 115 | 115.5 | 116.7 | 117.4 | 0.7 | 1.6 | 3
F6 | Industries des composants électriques et électroniques | 113.8 | 114.8 | 115 | 115.9 | 116.9 | 0.9 | 1.7 | 2.7
ISTAT Italie
2000=100
2007= 114
EUROSTAT
ndic_lc | lci_tot Labour Cost Index - Total labour costs
| nace | Indice 1993=100 1994: d Manufacturing
| p_adj | Indice 1993=100 1994: nominal Nominal value
| unit | Indice 1993=100 1994: i1999 Index, 1999=100
| time | Indice 1993=100 1994: 1999a00; Indice 1993=100 1996: 2000a00; Indice 1993=100 1998: 2001a00; Indice 1993=100 2000: 2002a00 | 2003a00 |  | 2004a00 |  | 2005a00 |  | 2006a00
geo
eu27 European Union (27 countries) |  | Indice 1993=100 1994: 1; Indice 1993=100 1996: 104.0583; Indice 1993=100 1998: 108.845; Indice 1993=100 2000: 113.1113 | 117.0656 |  | 121.1238 |  | 124.4537 |  | 128.9282
estimation pour budget | france | Indice 1993=100 1994: suisse; Indice 1993=100 1995: episternes; Indice 1993=100 1996: eurostat
1998 | 100 | Indice 1993=100 1994: 1; Indice 1993=100 1995: 100
1999 |  | Indice 1993=100 1994: 100.4302; Indice 1993=100 1996: 100
2000 |  | Indice 1993=100 1994: 102.0554; Indice 1993=100 1996: 104.0583
2001 |  | Indice 1993=100 1994: 105.3059; Indice 1993=100 1996: 108.845
2002 |  | Indice 1993=100 1994: 106.8834; Indice 1993=100 1996: 113.1113
2003 |  | Indice 1993=100 1994: 108.1262; Indice 1993=100 1996: 117.0656
2004 | 115.6 | Indice 1993=100 1994: 108.8432; Indice 1993=100 1996: 121.1238
2005 | 118.5 | Indice 1993=100 1994: 110.0048; Indice 1993=100 1995: 118; Indice 1993=100 1996: 124.4537
2006 |  | Indice 1993=100 1994: 111.2428; Indice 1993=100 1996: 128.9282
2007 |  | Indice 1993=100 1994: 112.5
2008 |  | Indice 1993=100 1994: 114
1999a00
copper | USD/lb
1997-01-01 | 0.7
2003-01-01 | 0.8
2004-01-01 | 1
2005-01-01 | 1.4
2006-01-01 | 2
2007-01-01 | 3
2008-01-01 | 3.2
steel
2000-01-01 | 100
2007-01-01 | 190
aluminium | CHF/Kg
2001-01-01 | 4.3
2002-01-01 | 4.2
2003-01-01 | 3.75
2004-01-01 | 3.6
2005-01-01 | 4
2006-01-01 | 4.5
2007-01-01 | 5.5

## information components
Assumptions
increase labor cost | 1999 to 2007 | 25%
increase labor cost | 1998 to 2007 | 27%
Austenitic steel laminations
firm | pieces | price per piece | price for tooling | year | revision formula P=P0*(0.2+0.8L/L0)
ATIKA inserts | 7000 | 0.51 | no | 1999 | 0.612
FSG | 35000 | 1.24 | no | 1999 | 1.488
ATIKA | 35000 | 5.64 | 544143 | 1999 | 6.768
FSG inserts | 70000 | 0.21 | no | 1999 | 0.252
FSG | 324000 | 1.14 | no | 1999 | 1.368
Garconnet | 324000 | 2.2541 | 141240 | 1999 | 2.7049
ATIKA | 324000 | 3.7205 | 544143 | 1999 | 4.4647
ATIKA inserts | 624000 | 0.51 | no | 1999 | 0.612
FSG inserts | 642000 | 0.19 | no | 1999 | 0.228
Garconnet inserts | 642000 | 0.24 | no | 1999 | 0.288
Collars |  |  |  |  | 66666.6667
firm | pieces | price per piece | price for tooling | year | revision formula P=P0*(0.2+0.8L/L0) | comments
ELAY | 2940000 | 1.8867 | 656385 | 1999 | 2.2641 | steel in coils
Garconnets | 2940000 | 1.9954 | 190000 | 1999 | 2.3944 | steel in coils
AKITA | 2940000 | 1.5955 | 1042157 | 1999 | 1.9146 | steel in coils
Malvestiti | 2940000 | 1.1 | 125000 | 1999 | 1.32 | steel in coils
FSG | 2205000 | 0.64966 | 111000 | 1999 | 0.77959
ELAY | 88000 | 2 |  | 2000 | 2.352
ELAY | 4500 | 4.68 | 170000 | 2000 | 5.5037
ELAY
iron laminations |  |  |  |  | 34482.7586
firm | pieces | price per piece | price for tooling | year | revision formula P=P0*(0.2+0.8L/L0)
Malvestiti | 2900000 | 2.5586 | 120000 | 1999 | 3.0703
ELAY | 2900000 | 2.0169 | 560000 | 1999 | 2.4203
Garconnet | 2900000 | 2.1248 | 131000 | 1999 | 2.5498
Algat | 2900000 | 3.0128 | 630000 | 1999 | 3.6153
FSG | 2900000 | 1.1552 | 130000 | 1999 | 1.3862
Malvestiti | 15000 | 3.7 |  | 1998 | 4.4992
Malvestiti | 21000 | 3 |  | 1998 | 3.648
copper wedges
firm | pieces | price per piece | price for tooling | year | revision formula P=P0*(0.2+0.5L/L0+0.3*cu/cu0)
outokumpu profile 3 | 41500 | 15.7072 | 8000 | 1999 | 34.4998
shell
firm | pieces | price per piece | price for tooling | year | revision formula P=P0*(0.2+0.3L/L0+0.5*M/M0)
SCAI 2 *16 m 10 mm thick 316LN | 2 | 29500 | 59000 | 1996 | 46757.5
support cold mass
end covers
firm | pieces | price per piece | price for tooling | year | revision formula P=P0*(0.2+0.3L/L0+0.5*M/M0)
Metso | 1241 | 5150 | 33700 |  | 7853.75
ALC | 1241 | 5316 |  |  | 8106.9
ASCO | 1241 | 5395 |  |  | 8227.375
HTM | 1241 | 5525 |  |  | 8425.625
Goodwin | 1241 | 5682 |  |  | 8665.05