## Coils
Activity ID | FNAL Coils
|  | Start | Finish
| Coil QXFA-108 Fab | 20-Nov-17 A | 25-May-18 A
| Coil QXFA-109 Fab | 31-Jan-18 A | 13-Jul-18 A
| Coil QXFA-110 Fab | 23-Apr-18 A | 31-Aug-18 A
| Coil QXFP06 Fab | 18-Jun-18 A | 19-Oct-18 A
| Coil QXFA-111 Fab | 02-Jul-18 A | 31-Oct-18 A
| Coil QXFA-112 Fab | 20-Aug-18 A | 19-Dec-18 A
A21717 | Coil QXFA-113 Fab | 10-Oct-18 A | 27-Feb-19 A
A21722 | Coil QXFA-114 Fab | 03-Dec-18 A | 29-Mar-19 A
A21727 | Coil QXFA-115 Fab | 06-Feb-19 A | 2019-05-10
A21732 | Coil QXFA-116 Fab | 27-Mar-19 A | 2019-07-23
A21737 | Coil QXFA-117 Fab | 2019-06-05 | 2019-10-03
A21742 | Coil QXFA-118 Fab | 2019-08-15 | 2019-12-16
A21747 | Coil QXFA-119 Fab | 2019-10-25 | 2020-03-02
A21752 | Coil QXFA-120 Fab | 2020-01-13 | 2020-05-11
A21757 | Coil QXFA-121 Fab | 2020-03-03 | 2020-06-30 | 1st coil for #8
A21762 | Coil QXFA-122 Fab | 2020-03-31 | 2020-07-29
A21767 | Coil QXFA-123 Fab | 2020-04-28 | 2020-08-26
A21772 | Coil QXFA-124 Fab | 2020-05-27 | 2020-09-24
A21777 | Coil QXFA-125 Fab | 2020-06-24 | 2020-10-22
A21782 | Coil QXFA-126 Fab | 2020-07-23 | 2020-11-19
A21787 | Coil QXFA-127 Fab | 2020-08-20 | 2020-12-21
A21792 | Coil QXFA-128 Fab | 2020-09-18 | 2021-01-25
A21797 | Coil QXFA-129 Fab | 2020-10-16 | 2021-02-22
A21802 | Coil QXFA-130 Fab | 2020-11-11 | 2021-03-18
A21807 | Coil QXFA-131 Fab | 2020-12-09 | 2021-04-13
A21812 | Coil QXFA-132 Fab | 2021-01-08 | 2021-05-07
A21817 | Coil QXFA-133 Fab | 2021-02-04 | 2021-06-03
A21822 | Coil QXFA-134 Fab | 2021-03-02 | 2021-06-29
A21827 | Coil QXFA-135 Fab | 2021-03-26 | 2021-07-26
A21832 | Coil QXFA-136 Fab | 2021-04-21 | 2021-08-19
A21837 | Coil QXFA-137 Fab | 2021-05-17 | 2021-09-15
A21842 | Coil QXFA-138 Fab | 2021-06-11 | 2021-10-11
A21847 | Coil QXFA-139 Fab | 2021-07-08 | 2021-11-04
A21852 | Coil QXFA-140 Fab | 2021-08-03 | 2021-12-02
A21857 | Coil QXFA-141 Fab | 2021-08-27 | 2021-12-30
A21862 | Coil QXFA-142 Fab | 2021-09-23 | 2022-01-28
A21867 | Coil QXFA-143 Fab | 2021-10-19 | 2022-02-23
A21872 | Coil QXFA-144 Fab | 2021-11-12 | 2022-03-21
A21877 | Coil QXFA-145 Fab | 2021-12-10 | 2022-04-14
A21882 | Coil QXFA-146 Fab | 2022-01-11 | 2022-05-10
A21887 | Coil QXFA-147 Fab | 2022-02-07 | 2022-06-06
A21892 | Coil QXFA-148 Fab | 2022-03-03 | 2022-06-30
A21897 | Coil QXFA-149 Fab | 2022-03-29 | 2022-07-27
A21902 | Coil QXFA-150 Fab | 2022-04-22 | 2022-08-22
A21907 | Coil QXFA-151 Fab | 2022-05-18 | 2022-09-16
A21912 | Coil QXFA-152 Fab | 2022-06-14 | 2022-10-12
A21917 | Coil QXFA-153 Fab | 2022-07-11 | 2022-11-07
A21922 | Coil QXFA-154 Fab | 2022-08-04 | 2022-12-05
A21927 | Coil QXFA-155 Fab | 2022-08-30 | 2023-01-04
A205790 | Coil QXFA-156 Fab | 2022-09-26 | 2023-01-31
BNL Coils
|  | Start | Finish
| Coil QXFA-202 Fab | 04-Sep-18 A | 27-Feb-19 A
A20870 | Coil QXFA-203 Fab | 15-Oct-18 A | 2019-04-19
A21931 | Coil QXFA-204 Fab | 03-Jan-19 A | 2019-05-14
A21936 | Coil QXFA-205 Fab | 05-Mar-19 A | 25-Mar-19 A
A21941 | Coil QXFA-206 Fab | 2019-04-15 | 2019-08-12
A21946 | Coil QXFA-207 Fab | 2019-06-24 | 2019-10-22
A21951 | Coil QXFA-208 Fab | 2019-09-04 | 2020-01-08
A21956 | Coil QXFA-209 Fab | 2019-11-13 | 2020-03-19
A21961 | Coil QXFA-210 Fab | 2020-01-09 | 2020-05-07
A21966 | Coil QXFA-211 Fab | 2020-02-07 | 2020-06-05 | 1st coil for #8
A21971 | Coil QXFA-212 Fab | 2020-03-06 | 2020-07-06
A21976 | Coil QXFA-213 Fab | 2020-04-03 | 2020-08-03
A21981 | Coil QXFA-214 Fab | 2020-05-01 | 2020-08-31
A21986 | Coil QXFA-215 Fab | 2020-06-01 | 2020-09-29
A21991 | Coil QXFA-216 Fab | 2020-06-29 | 2020-10-27
A21996 | Coil QXFA-217 Fab | 2020-07-28 | 2020-11-24
A22001 | Coil QXFA-218 Fab | 2020-08-25 | 2020-12-28
A22006 | Coil QXFA-219 Fab | 2020-09-21 | 2021-01-26
A22011 | Coil QXFA-220 Fab | 2020-10-15 | 2021-02-19
A22016 | Coil QXFA-221 Fab | 2020-11-10 | 2021-03-17
A22021 | Coil QXFA-222 Fab | 2020-12-08 | 2021-04-12
A22026 | Coil QXFA-223 Fab | 2021-01-07 | 2021-05-06
A22031 | Coil QXFA-224 Fab | 2021-02-03 | 2021-06-02
A22036 | Coil QXFA-225 Fab | 2021-03-01 | 2021-06-28
A22041 | Coil QXFA-226 Fab | 2021-03-25 | 2021-07-23
A22046 | Coil QXFA-227 Fab | 2021-04-20 | 2021-08-18
A22051 | Coil QXFA-228 Fab | 2021-05-14 | 2021-09-14
A22056 | Coil QXFA-229 Fab | 2021-06-10 | 2021-10-08
A22061 | Coil QXFA-230 Fab | 2021-07-07 | 2021-11-03
A22066 | Coil QXFA-231 Fab | 2021-08-02 | 2021-12-01
A22071 | Coil QXFA-232 Fab | 2021-08-26 | 2021-12-29
A22076 | Coil QXFA-233 Fab | 2021-09-22 | 2022-01-27
A22081 | Coil QXFA-234 Fab | 2021-10-18 | 2022-02-22
A22086 | Coil QXFA-235 Fab | 2021-11-11 | 2022-03-18
A22091 | Coil QXFA-236 Fab | 2021-12-09 | 2022-04-13
A22096 | Coil QXFA-237 Fab | 2022-01-10 | 2022-05-09
A22101 | Coil QXFA-238 Fab | 2022-02-04 | 2022-06-03
A22106 | Coil QXFA-239 Fab | 2022-03-02 | 2022-06-29
A22111 | Coil QXFA-240 Fab | 2022-03-28 | 2022-07-26
A22116 | Coil QXFA-241 Fab | 2022-04-21 | 2022-08-19
A22121 | Coil QXFA-242 Fab | 2022-05-17 | 2022-09-15
A22126 | Coil QXFA-243 Fab | 2022-06-13 | 2022-10-11
A22131 | Coil QXFA-244 Fab | 2022-07-08 | 2022-11-04
A22136 | Coil QXFA-245 Fab | 2022-08-03 | 2022-12-02
A22141 | Coil QXFA-246 Fab | 2022-08-29 | 2023-01-03
A22146 | Coil QXFA-247 Fab | 2022-09-23 | 2023-01-30
A22151 | Coil QXFA-248 Fab | 2022-10-19 | 2023-02-23

## Magnets
Start Activity ID | Finish Activity ID |  | Start | Finish
|  | Magnet Ass'y MQXFA-1b | 26-Oct-18 A | 22-Mar-19 A
A20911 | A20914 | Magnet Ass'y MQXFA-03 | 25-Mar-19 A | 2019-08-23
A20918 | A20921 | Magnet Ass'y MQXFA-04 | 2019-06-27 | 2019-12-10
A20927 | A20930 | Magnet Ass'y MQXFA-05 | 2019-11-06 | 2020-02-12
A20936 | A20940 | Magnet Ass'y MQXFA-06 | 2020-01-16 | 2020-04-17
A20946 | A20949 | Magnet Ass'y MQXFA-07 | 2020-05-28 | 2020-08-20
A20955 | A20958 | Magnet Ass'y MQXFA-08 | 2020-08-14 | 2020-10-28
A20964 | A20967 | Magnet Ass'y MQXFA-09 | 2020-11-09 | 2021-02-10
A20973 | A20976 | Magnet Ass'y MQXFA-10 | 2021-01-14 | 2021-03-26
A20982 | A20985 | Magnet Ass'y MQXFA-11 | 2021-03-10 | 2021-05-21
A20991 | A20994 | Magnet Ass'y MQXFA-12 | 2021-04-29 | 2021-07-14
A21000 | A21004 | Magnet Ass'y MQXFA-13 | 2021-07-16 | 2021-09-29
A21010 | A21014 | Magnet Ass'y MQXFA-14 | 2021-09-07 | 2021-11-18
A21020 | A21024 | Magnet Ass'y MQXFA-15 | 2021-10-27 | 2022-01-18
A21030 | A21033 | Magnet Ass'y MQXFA-16 | 2022-01-20 | 2022-04-04
A21039 | A21042 | Magnet Ass'y MQXFA-17 | 2022-03-11 | 2022-05-24
A21048 | A21051 | Magnet Ass'y MQXFA-18 | 2022-05-02 | 2022-07-15
A21057 | A21060 | Magnet Ass'y MQXFA-19 | 2022-06-22 | 2022-09-06
A21066 | A21069 | Magnet Ass'y MQXFA-20 | 2022-09-08 | 2022-11-21
A21075 | A21078 | Magnet Ass'y MQXFA-21 | 2022-10-28 | 2023-01-19
A21084 | A21087 | Magnet Ass'y MQXFA-22 | 2022-12-21 | 2023-03-10
A21093 | A21096 | Magnet Ass'y MQXFA-23 | 2023-03-10 | 2023-05-23
A21099 | A21102 | Magnet Ass'y MQXFA-R1 | 2023-04-21 | 2023-06-26
A21105 | A21108 | Magnet Ass'y MQXFA-R2 | 2023-06-05 | 2023-08-08
A21110 | A21114 | Magnet Ass'y MQXFA-R3 | 2023-07-18 | 2023-09-20
A230760 | A230840 | Magnet Ass'y MQXFA-R4 | 2023-08-29 | 2023-11-01

## Vertical Test
Start Activity ID | Finish Activity ID |  | Start | Finish
|  | Magnet Vert Test MQXFA-02 | 01-Aug-18 A | 06-Feb-19 A
A208692 | A208697 | Magnet Vert Test MQXFA-1b | 2019-04-08 | 2019-07-03
A21141 | A21145 | Magnet Vert Test MQXFA-03 | 2019-09-10 | 2019-11-19
A21155 | A21159 | Magnet Vert Test MQXFA-04 | 2019-12-27 | 2020-03-11
A21162 | A21166 | Magnet Vert Test MQXFA-05 | 2020-02-27 | 2020-05-07
A21169 | A21173 | Magnet Vert Test MQXFA-06 | 2020-05-04 | 2020-07-15
A21176 | A21180 | Magnet Vert Test MQXFA-07 | 2020-09-04 | 2020-11-16
A21183 | A21187 | Magnet Vert Test MQXFA-08 | 2020-11-12 | 2021-02-01
A21190 | A21194 | Magnet Vert Test MQXFA-09 | 2021-02-25 | 2021-05-06
A21197 | A21201 | Magnet Vert Test MQXFA-10 | 2021-04-23 | 2021-07-06
A21205 | A21209 | Magnet Vert Test MQXFA-11 | 2021-06-22 | 2021-09-01
A21212 | A21216 | Magnet Vert Test MQXFA-12 | 2021-08-19 | 2021-10-29
A21219 | A21223 | Magnet Vert Test MQXFA-13 | 2021-10-18 | 2022-01-04
A21226 | A21230 | Magnet Vert Test MQXFA-14 | 2021-12-16 | 2022-03-03
A21233 | A21237 | Magnet Vert Test MQXFA-15 | 2022-02-18 | 2022-04-29
A21240 | A21244 | Magnet Vert Test MQXFA-16 | 2022-04-19 | 2022-06-29
A21247 | A21251 | Magnet Vert Test MQXFA-17 | 2022-06-16 | 2022-08-26
A21254 | A21258 | Magnet Vert Test MQXFA-18 | 2022-08-15 | 2022-10-25
A21261 | A21265 | Magnet Vert Test MQXFA-19 | 2022-10-12 | 2022-12-27
A21268 | A21272 | Magnet Vert Test MQXFA-20 | 2022-12-12 | 2023-02-27
A21275 | A21279 | Magnet Vert Test MQXFA-21 | 2023-02-14 | 2023-04-25
A231160 | A231180 | Magnet Vert Test MQXFA-22 | 2023-03-27 | 2023-06-06

## Cold Mass
Activity ID |  | Start | Finish
A20898 | Ass'y LMQXFA-P (L) | 2019-10-16 | 2020-02-06
A22162 | Ass'y LMQXFA-01 (L) | 2020-09-23 | 2020-12-10
A22166 | Ass'y LMQXFA-02 (L) | 2021-02-19 | 2021-05-06
A22170 | Ass'y LMQXFA-03 (L) | 2021-07-21 | 2021-09-15
A22174 | Ass'y LMQXFA-04 (L) | 2021-11-15 | 2022-01-18
A22178 | Ass'y LMQXFA-05 (L) | 2022-03-18 | 2022-05-12
A22181 | Ass'y LMQXFA-R1 Re-Work (L) | 2022-05-13 | 2022-07-11
A22185 | Ass'y LMQXFA-06 (L) | 2022-09-13 | 2022-11-07
A22189 | Ass'y LMQXFA-07 (L) | 2023-01-13 | 2023-03-10
A22193 | Ass'y LMQXFA-08 (L) | 2023-05-10 | 2023-07-06
A22197 | Ass'y LMQXFA-09 (L) | 2023-08-23 | 2023-10-18
A22199 | Ass'y LMQXFA-10 (L) | 2023-11-16 | 2024-01-19

## Cryo Assemblies
Activity ID |  | Start | Finish
A20607 | Prototype Cryostating LMQXFA-P (L) | 2020-02-07 | 2020-05-07
A20609 | CryoStating LMQXFA-01 (L) | 2020-12-11 | 2021-02-18
A21585 | CryoStating LMQXFA-02 (L) | 2021-05-07 | 2021-07-12
A21589 | CryoStating LMQXFA-03 (L) | 2021-09-16 | 2021-11-17
A21593 | CryoStating LMQXFA-04 (L) | 2022-01-19 | 2022-03-22
A21597 | CryoStating LMQXFA-05 (L) | 2022-05-13 | 2022-07-18
A21598 | CryoStating LMQXFA-R1 Re-Work (L) | 2022-07-19 | 2022-10-18
A21602 | CryoStating LMQXFA-06 (L) | 2022-11-08 | 2023-01-18
A21606 | CryoStating LMQXFA-07 (L) | 2023-03-13 | 2023-05-12
A21610 | CryoStating LMQXFA-08 (L) | 2023-07-07 | 2023-09-08
A21614 | CryoStating LMQXFA-09 (L) | 2023-10-19 | 2023-12-26
A21618 | CryoStating LMQXFA-10 (L) | 2024-01-22 | 2024-03-22

## Horizontal Test
Activity ID |  | Start | Finish
A21317 | Horizontal Test Cryo-Ass'y LQXFP | 2020-05-08 | 2020-08-24
A21321 | Horizontal Test Cryo-Ass'y LQXFA/B-01 | 2021-02-19 | 2021-06-04
A21325 | Horizontal Test Cryo-Ass'y LQXFA/B-02 | 2021-07-13 | 2021-10-26
A21317 | Horizontal Test Cryo-Ass'y LQXFA/B-03 | 2021-11-18 | 2022-02-09
A21329 | Horizontal Test Cryo-Ass'y LQXFA/B-04 | 2022-03-23 | 2022-05-26
A21333 | Horizontal Test Cryo-Ass'y LQXFA/B-05 | 2022-07-19 | 2022-09-22
A21337 | Horizontal Test Cryo-Ass'y LQXFA/B-R1 | 2022-10-19 | 2022-12-28
A21341 | Horizontal Test Cryo-Ass'y LQXFA/B-06 | 2023-01-19 | 2023-03-24
A21345 | Horizontal Test Cryo-Ass'y LQXFA/B-07 | 2023-05-15 | 2023-07-20
A21349 | Horizontal Test Cryo-Ass'y LQXFA/B-08 | 2023-09-11 | 2023-11-14
A21353 | Horizontal Test Cryo-Ass'y LQXFA/B-09 | 2023-12-27 | 2024-04-22
A21357 | Horizontal Test Cryo-Ass'y LQXFA/B-10 | 2024-04-23 | 2024-08-15

## CERN External Milestones
Activity ID |  | Finish
A203506 | EX:AVAIL Receipt of CERN Cold Mass Ass'y Parts LMQXFA-01 to 05 | 21-Oct-2019*
A203416 | EX:AVAIL Receipt of CERN Cold Mass Ass'y Parts LMQXFA-06 to 10 | 01-Feb-2022*
A230725 | EX:AVAIL Receipt of CERN Cold Mass Ass'y Remaining Parts LMQXFA-P | 01-Oct-2019*
A203626 | EX:AVAIL Receipt of CERN Cold Mass Shell Plates LMQXFA-P | 15-Jul-2019*
A203606 | EX:AVAIL Receipt of 5 CERN Cryostat Kits LMQXFA-01 to 05 | 01-Jun-2020*
A203516 | EX:AVAIL Receipt of 5 CERN Cryostat Kits LMQXFA-06 to 10 | 01-Jun-2022*
A203616 | EX:AVAIL Receipt of CERN Cryostat Kit LMQXFA-P | 30-Aug-2019*
A235610 | EX:AVAIL Receipt of CERN Cryostat Tooling | 30-Aug-2019*