## Planning overview
Waiting for shuffling module readiness | D |  | Delivery to CERN | [6 empty] | CMA | [5 empty] | Cryostating |  |  |  |  | Co |  | Commissioning | [7 empty] | Beamscreen+BPM installation | [9 empty] | Magnet preparation in SMS18 | [13 empty] | Helium needed (CD/tests/TC)
[9 empty] | -1 | Cold mass dismantling |  |  |  |  | -1 | Decryostating |  |  |  |  | SM18 |  | Assembly in SM18 | [17 empty] | Magnet at warm or warming up in SM18
[21 empty] | SMI2 |  | Assembly in SMI2
Delivery of shuffling module parts for assembly
|  |  |  | Xmas | SM18 | maintenance | 2021 | [14 empty] | Xmas | SM18 maintenance | 2022 | [20 empty] | Xmas | SM18 miantenance |  |  | 2023 | [22 empty] | Xmas | SM18 maintenance
|  |  | 12 |  | 1 |  | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 |  | 11 |  | 12 |  | 1 | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 | 8 |  |  |  | 9 | 10 |  | 11 |  | 12 |  | 1 |  |  | 2 |  | 3 |  | 4 |  |  | 5 |  | 6 |  | 7 |  | 8 | 9 |  | 10 |  |  | 11 |  | 12 |  |  | 1 | 2
WP3 cryoassemblies (excluding LQXFB)
LQXFA01 (Q1) | [25 empty] | D | [16 empty] | A2 | [33 empty] | 1st on A2 (=> adding +50% contingency on SM18 bench)
LQXFA02 (Q3) | [31 empty] | D
LQXFA03 (Q1) | [62 empty] | D | [12 empty] | ..
LQXFA04 (Q3) | [67 empty] | D | [7 empty] | ..
LCXFP (CP P) | [25 empty] | D |  | D | [22 empty] | A2
LCXF01 (CP S1) | [34 empty] | D | [22 empty] | A2
LCXF02 (CP S2) | [43 empty] | D | [23 empty] | A2 | [7 empty] | ..
LCXF03 (CP S3) | [48 empty] | D | [25 empty] | A2 | ..
LCXF04 (CP S4) | [52 empty] | D | [22 empty] | ..
LCXF05 (CP Spare 1) | [75 empty] | ..
LBXFP (D1 P) | [25 empty] | D | [10 empty] | A1
LBXF01 (D1 S1) | [34 empty] | D | [14 empty] | B2 | [26 empty] | 1st on B2 (=> adding +50% contingency on SM18 bench)
LBXF02 (D1 S2) | [48 empty] | D | [9 empty] | B2
LBXF03 (D1 S3) | [61 empty] | D | [8 empty] | B2 |  |  |  |  | ..
LBXF04 (D1 S4) | [73 empty] | D |  | ..
LBRDP (D2 P) | [15 empty] | D | Temp. conf. | [11 empty] | C2 | [47 empty] | Duration between D2 P and D2 S1 is because we wait for results on D2 P to start producing the coils
LBRD01 (D2 S1) | [45 empty] | D | [17 empty] | C2 | [11 empty] | .. | 1st on C2 (=> adding +50% contingency on SM18 bench)
LBRD02 (D2 S2) | [52 empty] | D | [15 empty] | C2 | [6 empty] | ..
LBRD03 (D2 S3) | [61 empty] | D | [13 empty] | ..
LBRD04 (D2 S4) | [67 empty] | D | [7 empty] | ..
LQXFB (WP3) and Cold Powering System (WP6a)
LQXFBP2 (Q2 P2) (Q2b) | [6 empty] | A1 | [10 empty] | -1 | -1 | [16 empty] | F1
LQXFBP3 (Q2 P3) (former LQXFB01) (Q2a) | [13 empty] | -1 |  | Temp. conf. | [7 empty] | A1 |  |  | -1 | -1 | [12 empty] | F1
LQXFB02 (Q2 S2) (Q2b) | [19 empty] | Temp. conf. | [9 empty] | A1 |  |  | -1 | -1 | [14 empty] | F1
LQXFB03 (Q2 S3) (Q2a) | [53 empty] | F1
LQXFB04 (Q2 S4) (Q2b) | [60 empty] | F1
LQXFB05 (Q2 S5) (Q2a) | [67 empty] | F1 | [7 empty] | ..
LQXFB06 (Q2 S6) (Q2b) | [75 empty] | ..
Cold powering system (on F2 bench) | [24 empty] | F2 | [14 empty] | Details TBD
SM18 benches activity
A1 | [6 empty] | Q2 P2* | [16 empty] | Q2 P3 | [5 empty] | Q2 S2 | [5 empty] | D1 P
A2 | [33 empty] | SMI2 | SM18 |  |  |  |  | Co |  |  | Q1 |  |  |  |  | CP P | [8 empty] | CP S1 | [9 empty] | CP S2 | [6 empty] | CP S3
B1 (LHC MB/MQ)
B2 | [39 empty] | SMI2 |  | SM18 |  |  |  |  | Co |  |  | D1 S1 | [7 empty] | D1 S2 | [11 empty] | D1 S3
C1 (11T) | [37 empty] | 11T hybrid | [38 empty] | Date TBD (likely 2nd semester 2022)
C2 | [28 empty] | D2 P* | [34 empty] | D2 S1 |  |  |  |  | D2 S2 | [7 empty] | Bench readiness TBD but should be ready anyway for D2 series
E1 (LHC MB/MQ) | [76 empty] | On B1, E1 or E2. Dates TBD (~3 per month)
E2 (LHC MB/MQ)
F1 | [27 empty] | SMI2 |  | SM18 |  |  |  | Co |  | D2 P2 |  |  |  |  | Q2 P3 | [7 empty] | Q2 S2 |  |  |  |  | Q2 S3 | [6 empty] | Q2 S4 | [6 empty] | Q2 S5
F2 (WP6A) | [24 empty] | Proto | [14 empty] | Details TBD
SMS activity
Preparation bench (i.e. before tests) | [65 empty] | !
Stripping bench (i.e. after tests) | [75 empty] | ..
|  | Important remarks | [49 empty] | Questions:
- We restrict to 2 magnets in parallel on benches
- The preparation for the tunnel (cryostating + BPM/BS installation) must be studied => might shift
- One needs 8 months between reception of last magnet and start of string commissioning
- Here we considering 4 weeks per month
- "Temp. conf." stands for the cryomagnets in "temporary configuration" for tests in "direct connection bench"
Bench readiness TBD

## Duration at Point 18
| Q1 or Q3 | Q2 | Q2 temp. conf. | CP | D1 | D2 | D2 temp. conf.
Magnet preparation in SMS18 (before test), including transport | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5
Magnet at warm or warming up in SM18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Helium needed (CD/tests/TC) | 14.5 | 28 | 18 | 10 | 12 | 20 | 40
Magnet at warm or warming up in SM18 | 5 | 5 | 5 | 4 | 4 | 4 | 4
Magnet preparation in SMS18 (after test), including transport | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Total working days | 30.5 | 44 | 34 | 25 | 27 | 35 | 55
Notes: Add 50% more time for the 1st test following shuffling module installation
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Approximation, based on discussion with Franco 23.07.2021