## Comments
1. The schedule tables are based on the AUP working schedule of February 2023 assuming no failures in assembly testing (i.e., this is not the AUP baseline schedule we report to DOE, which includes production yields)
2. Covid inefficiency impacts are included through December 2022.

## Coil Fabrication
Dates From February 2023 Working Schedule
Fermilab Coils |  |  | Brookhaven Coils
Activity Name | Start | Finish | Activity Name | Start | Finish
Coil QXFA-133 Fab | 05-Apr-21 A | 2022-08-01 | Coil QXFA-222 Fab | 17-Feb-21 A | 22-Sep-21 A
Coil QXFA-134 Fab | 23-Apr-21 A | 01-Sep-21 A | Coil QXFA-223 Fab | 11-Mar-21 A | 22-Sep-21 A
Coil QXFA-135 Fab | 13-May-21 A | 01-Sep-21 A | Coil QXFA-224 Fab | 13-Apr-21 A | 16-Nov-21 A
Coil QXFA-136 Fab | 25-May-21 A | 29-Oct-21 A | Coil QXFA-225 Fab | 29-Apr-21 A | 16-Nov-21 A
Coil QXFA-137 Fab | 17-Jun-21 A | 04-Jan-22 A | Coil QXFA-226 Fab | 17-May-21 A | 09-Jan-23 A
Coil QXFA-138 Fab | 20-Jul-21 A | 27-Oct-21 A | Coil QXFA-227 Fab | 11-Jun-21 A | 25-Aug-23 A
Coil QXFA-139 Fab | 06-Aug-21 A | 24-Jan-22 A | Coil QXFA-228 Fab | 12-Jul-21 A | 2023-03-31
Coil QXFA-140 Fab | 16-Sep-21 A | 24-Jan-22 A | Coil QXFA-229 Fab | 04-Aug-21 A | 25-Aug-22 A
Coil QXFA-141 Fab | 15-Oct-21 A | 02-Sep-22 A | Coil QXFA-230 Fab | 30-Aug-21 A | 31-Oct-22 A
Coil QXFA-142 Fab | 12-Nov-21 A | 05-Oct-22 A | Coil QXFA-231 Fab | 24-Sep-21 A | 31-Oct-22 A
Coil QXFA-143 Fab | 18-Feb-22 A | 05-Oct-22 A | Coil QXFA-232 Fab | 20-Oct-21 A | 28-Feb-22 A
Coil QXFA-144 Fab | 30-Mar-22 A | 2023-03-02 | Coil QXFA-233 Fab | 09-Feb-22 A | 09-Jan-23 A
Coil QXFA-145 Fab | 02-May-22 A | 2023-03-02 | Coil QXFA-234 Fab | 16-Mar-22 A | 15-Feb-23 A
Coil QXFA-146 Fab | 11-May-22 A | 2023-03-02 | Coil QXFA-235 Fab | 08-Apr-22 A | 15-Feb-23 A
Coil QXFA-147 Fab | 27-May-22 A | 2023-03-02 | Coil QXFA-236 Fab | 29-Apr-22 A | 2023-03-30
Coil QXFA-148 Fab | 20-Jun-22 A | 2023-03-02 | Coil QXFA-237 Fab | 20-May-22 A | 2023-03-30
Coil QXFA-149 Fab | 28-Jul-22 A | 2023-03-02 | Coil QXFA-238 Fab | 15-Jun-22 A | 2023-03-30
Coil QXFA-150 Fab | 19-Aug-22 A | 2023-03-02 | Coil QXFA-239 Fab | 12-Jul-22 A | 2023-03-30
Coil QXFA-151 Fab | 19-Sep-22 A | 2023-03-02 | Coil QXFA-240 Fab | 09-Aug-22 A | 2023-03-30
Coil QXFA-152 Fab | 12-Oct-22 A | 2023-03-02 | Coil QXFA-241 Fab | 09-Sep-22 A | 2023-03-30
Coil QXFA-153 Fab | 08-Nov-22 A | 2023-03-02 | Coil QXFA-242 Fab | 20-Oct-22 A | 2023-03-30
Coil QXFA-154 Fab | 17-Nov-22 A | 2023-03-02 | Coil QXFA-243 Fab | 18-Nov-22 A | 2023-04-10
Coil QXFA-155 Fab | 29-Dec-22 A | 2023-04-12 | Coil QXFA-244 Fab | 13-Dec-22 A | 2023-04-14
Coil QXFA-156 Fab | 07-Feb-23 A | 2023-06-06 | Coil QXFA-245 Fab | 24-Jan-23 A | 2023-04-17
Coil QXFA-157 Fab | 2023-03-07 | 2023-06-07 | Coil QXFA-246 Fab | 22-Feb-23 A | 2023-05-19
Coil QXFA-158 Fab | 2023-04-17 | 2023-08-25 | Coil QXFA-247 Fab | 2023-03-23 | 2023-06-23
Coil QXFA-159 Fab | 2023-05-26 | 2023-10-06 | Coil QXFA-248 Fab | 2023-04-18 | 2023-08-01
|  |  | Coil QXFA-249 Fab | 2023-05-12 | 2023-08-16
|  |  | Coil QXFA-250 Fab | 2023-06-22 | 2023-10-20
|  |  | Coil QXFA-251 Fab | 2023-07-19 | 2023-11-15

## Magnet Fabrication
Dates From February 2023 working schedule
Activity Name | Start | Finish
Magnet Ass'y MQXFA-09 | 15-Jun-21 A | 29-Dec-21 A
Magnet Ass'y MQXFA-10 | 28-Sep-21 A | 08-Apr-22 A
Magnet Ass'y MQXFA-11 | 30-Apr-22 A | 15-Jul-22 A
Magnet Ass'y MQXFA-R2/8b | 02-May-22 A | 24-Sep-22 A
Magnet Ass'y MQXFA-12 | 12-Jul-22 A | 22-Dec-22 A
Magnet Ass'y MQXFA-13 | 15-Sep-22 A | 2023-03-01
Magnet Ass'y MQXFA-14 | 04-Nov-22 A | 2023-04-14
Magnet Ass'y MQXFA-15 | 2023-03-08 | 2023-05-26
Magnet Ass'y MQXFA-R1/7b | 2023-04-25 | 2023-06-27
Magnet Ass'y MQXFA-09b | 2023-06-07 | 2023-08-11
Magnet Ass'y MQXFA-16 | 2023-07-20 | 2023-09-28
Magnet Ass'y MQXFA-12b | 2023-08-31 | 2023-11-06
Magnet Ass'y MQXFA-17 | 2023-10-13 | 2023-12-20
Magnet Ass'y MQXFA-18 | 2023-11-28 | 2024-02-07
Magnet Ass'y MQXFA-19 | 2024-01-16 | 2024-03-20
Magnet Ass'y MQXFA-20 | 2024-02-27 | 2024-05-01
Magnet Ass'y MQXFA-21 | 2024-04-09 | 2024-06-13
Magnet Ass'y MQXFA-22 | 2024-05-21 | 2024-07-26
Magnet Ass'y MQXFA-23 | 2024-07-03 | 2024-09-09
Magnet Ass'y MQXFA-R3 | 2024-08-15 | 2024-10-23
Magnet Ass'y MQXFA-R4 | 2025-02-14 | 2025-04-23

## Vertical Testing
Dates From February 2023 working schedule
Activity Name | Start | Finish
Magnet Vert Test MQXFA-08 | 08-Oct-21 A | 25-Apr-22 A
Vert Endurance Test MQXFA-05 | 01-Mar-22 A | 27-May-22 A
Magnet Vert Test MQXFA-10 | 02-May-22 A | 04-Nov-22 A
Magnet Vert Test MQXFA-11 | 29-Aug-22 A | 30-Nov-22 A
Magnet Vert Test MQXFA-R2/8b | 31-Oct-22 A | 2023-03-31
Magnet Vert Test MQXFA-13 | 2023-03-27 | 2023-06-05
Magnet Vert Test MQXFA-14 | 2023-07-03 | 2023-09-11
Magnet Vert Test MQXFA-15 | 2023-08-25 | 2023-11-02
Magnet Vert Test MQXFA-R1/7b | 2023-10-19 | 2024-01-03
Magnet Vert Test MQXFA-9b | 2023-12-14 | 2024-02-27
Magnet Vert Test MQXFA-16 | 2024-02-13 | 2024-04-19
Magnet Vert Test MQXFA-12b | 2024-04-05 | 2024-06-13
Magnet Vert Test MQXFA-17 | 2024-05-30 | 2024-08-07
Magnet Vert Test MQXFA-18 | 2024-07-24 | 2024-10-01
Magnet Vert Test MQXFA-19 | 2024-09-17 | 2024-11-22
Magnet Vert Test MQXFA-20 | 2024-11-15 | 2025-01-31

## Cold Mass Assembly
Dates From February 2023 success oriented schedule
Activity Name | Start | Finish
Ass'y LMQXFA-01 (L) | 04-Feb-21 A | 29-Jul-22 A
Ass'y LMQXFA-02 (L) | 02-May-22 A | 2023-06-06
Ass'y LMQXFA-03 (L) | 27-Dec-22 A | 2023-07-27
Ass'y LMQXFA-04 (L) | 2023-05-12 | 2023-11-07
Ass'y LMQXFA-05 (L) | 2023-11-14 | 2024-05-22
Ass'y LMQXFA-06 (L) | 2024-05-03 | 2024-11-05
Ass'y LMQXFA-07 (L) | 2024-06-25 | 2025-01-02
Ass'y LMQXFA-08 (L) | 2024-10-15 | 2025-04-23
Ass'y LMQXFA-09 (L) | 2024-11-20 | 2025-06-02
Ass'y LMQXFA-10 (L) | 2025-03-19 | 2025-09-22

## Cryostating
Dates From February 2023 success oriented schedule
Activity Name | Start | Finish
CryoStating LMQXFA-01 (L) | 10-Aug-22 A | 14-Nov-22 A
CryoStating LMQXFA-02 (L) | 2023-06-06 | 2023-08-09
CryoStating LMQXFA-03 (L) | 2023-08-09 | 2023-10-12
CryoStating LMQXFA-04 (L) | 2023-12-04 | 2024-02-12
CryoStating LMQXFA-05 (L) | 2024-05-22 | 2024-07-26
CryoStating LMQXFA-06 (L) | 2024-11-05 | 2025-01-15
CryoStating LMQXFA-07 (L) | 2025-01-15 | 2025-03-20
CryoStating LMQXFA-08 (L) | 2025-04-23 | 2025-06-26
CryoStating LMQXFA-09 (L) | 2025-06-26 | 2025-08-29
CryoStating LMQXFA-10 (L) | 2025-09-22 | 2025-11-24

## Horizontal Testing
Dates From February 2023 success oriented schedule
Activity Name | Start | Finish
Test LQXFA/B-01 Cryo-Ass'y Horz (L) | 19-Dec-22 A | 2023-06-14
Test LQXFA/B-02 Cryo-Ass'y Horz (L) | 2023-08-09 | 2023-12-27
Test LQXFA/B-03 Cryo-Ass'y Horz (L) | 2024-02-28 | 2024-05-10
Test LQXFA/B-04 Cryo-Ass'y Horz (L) | 2024-05-10 | 2024-07-25
Test LQXFA/B-05 Cryo-Ass'y Horz (L) | 2024-07-26 | 2024-10-09
Test LQXFA/B-06 Cryo-Ass'y Horz (L) | 2025-01-15 | 2025-03-31
Test LQXFA/B-07 Cryo-Ass'y Horz (L) | 2025-03-31 | 2025-06-12
Test LQXFA/B-08 Cryo-Ass'y Horz (L) | 2025-06-26 | 2025-09-10
Test LQXFA/B-09 Cryo-Ass'y Horz (L) | 2025-10-09 | 2026-02-12
Test LQXFA/B-10 Cryo-Ass'y Horz (L) | 2026-02-12 | 2026-06-10

## Assembly Delivery To CERN
Dates From February 2023 success oriented schedule
Activity Name | Current Date
T4:Delivered LQXFA/B-02 [01] to CERN | 2023-08-10
T4:Delivered LQXFA/B-01 [02] to CERN | 2024-02-26
T4:Delivered LQXFA/B-04 [03] to CERN | 2024-07-09
T4:Delivered LQXFA/B-05 [04] to CERN | 2024-09-20
T4:Delivered LQXFA/B-06 [05] to CERN | 2024-12-06
T4:Delivered LQXFA/B-07 [06] to CERN | 2024-05-27
T4:Delivered LQXFA/B-03 [07] to CERN | 2025-08-08
T5:Delivered LQXFA/B-08 [08] to CERN | 2025-11-05
T4:Delivered LQXFA/B-09 [09] to CERN | 2026-04-09
T5:Delivered LQXFA/B-10 [10] to CERN | 2026-08-06