## Coils_detail_CERN
Date last Update | 2021-02-15 |  | 60 | [10 empty] | axis
Coil ID | Start Winding&Curing | End Winding&Curing | Start Reaction | End Reaction | Start Impregnation | End Impregnation | End coil | Winding&Curing | Prep. Reaction | Reaction | Prep. Impregnation | Impregnation | Finishing | May 1st: | 43586
110 | 2019-05-13 | 2019-06-07 | 2019-10-18 | 2019-10-31 | 2019-12-02 | 2019-12-06 | 2020-01-10 | 25 | 133 | 13 | 32 | 4 | 35 |  | 43951
111 | 2019-09-23 | 2019-10-04 | 2019-11-15 | 2019-11-29 | 2020-01-06 | 2020-01-10 | 2020-01-23 | 11 | 42 | 14 | 38 | 4 | 13
112 | 2019-10-14 | 2019-10-25 | 2019-12-02 | 2019-12-17 | 2020-01-20 | 2020-01-24 | 2020-02-13 | 11 | 38 | 15 | 34 | 4 | 20
113 | 2019-11-13 | 2019-11-29 | 2020-01-06 | 2020-01-16 | 2020-02-24 | 2020-02-29 | 2020-03-13 | 16 | 38 | 10 | 39 | 5 | 13
114 | 2019-12-04 | 2019-12-19 | 2020-01-22 | 2020-02-03 | 2020-03-12 | 2020-03-18 | 2020-05-15 | 15 | 34 | 12 | 38 | 6 | 58
115 | 2020-01-29 | 2020-02-21 | 2020-03-13 | 2020-03-24 | 2020-06-25 | 2020-07-01 | 2020-07-14 | 23 | 21 | 11 | 93 | 6 | 13
116 | 2020-02-28 | 2020-03-13 | 2020-06-05 | 2020-06-17 | 2020-07-24 | 2020-07-30 | 2020-08-18 | 14 | 84 | 12 | 37 | 6 | 19
117 | 2020-05-25 | 2020-06-24 | 2020-07-03 | 2020-07-15 | 2020-08-10 | 2020-08-14 | 2020-08-28 | 30 | 9 | 12 | 26 | 4 | 14
118 | 2020-06-24 | 2020-07-13 | 2020-07-17 | 2020-07-29 | 2020-08-26 | 2020-09-02 | 2020-09-28 | 19 | 4 | 12 | 28 | 7 | 26
119 | 2020-07-21 | 2020-07-31 | 2020-08-21 | 2020-09-01 | 2020-10-02 | 2020-10-09 | 2020-10-20 | 10 | 21 | 11 | 31 | 7 | 11
120 | 2020-08-31 | 2020-10-02 | 2020-10-09 | 2020-10-23 | 2020-11-26 | 2020-12-03 | 2020-12-16 | 32 | 7 | 14 | 34 | 7 | 13
121 | 2020-10-26 | 2020-11-06 | 2020-11-13 | 2020-11-25 | 2021-01-04 | 2021-01-11 | 2021-01-22 | 11 | 7 | 12 | 40 | 7 | 11
122 | 2020-11-10 | 2020-11-26 | 2020-12-04 | 2020-12-15 | 2021-02-01 | 2021-02-05 |  | 16 | 8 | 11 | 48 | 4 | 20
123 | 2020-12-02 | 2020-12-16 | 2021-01-12 | 2021-01-22 | 2021-02-17 | 2021-02-24 |  | 14 | 27 | 10 | 26 | 7 | 20
124 | 2021-01-06 | 2021-01-21 | 2021-01-29 | 2021-02-09 |  |  |  | 15 | 8 | 11 | 30 | 7 | 20
125 | 2021-01-26 | 2021-02-09 | 2021-02-17 | 2021-02-26 |  |  |  | 14 | 8 | 9 | 30 | 7 | 20
[8 empty] | 14 | 10 | 11 | 30 | 7 | 20
Last update
15/02/2021

## Coils_overview
Date last Update | 2021-02-15 | AUP dates from 01/02/2021
FNAL | [6 empty] | BNL | [7 empty] | CERN
Coil | Lab. | Number | Start fab. | Duration | End. Fab | Coil Status |  |  |  | Start fab. | Duration | End. Fab | Diff to FNAL end | Coil Status |  |  | Start fab. | Duration | End. Fab | Coil Status
Coil QXFA101 | LARP | 1 | 2016-07-18 | 385 | 2017-08-07 | Rejected | Coil #201 | AUP | 1 | 2017-08-07 | 0 | 2017-08-07 | 0 |  | Coil 001 | 1 | 2016-03-21 | 305 | 2017-01-20 | Practice coil
Coil QXFA102 | LARP | 2 | 2016-09-21 | 390 | 2017-10-16 | MQXFAP2 | Coil QXFA202 | AUP | 2 | 2018-09-15 | 153 | 2019-02-15 | 334 | MQXFA03 | Coil 002 | 2 | 2016-08-15 | 39 | 2016-09-23 | Practice coil
Coil QXFA103 | LARP | 3 | 2016-11-01 | 45 | 2016-12-16 | Rejected | Coil QXFA203 | AUP | 3 | 2018-10-15 | 151 | 2019-03-15 | 668 | MQXFA04 | Coil 101 | 3 | 2016-10-03 | 207 | 2017-04-28 | Practice coil
Coil QXFA104 | LARP | 4 | 2017-01-30 | 296 | 2017-11-22 | MQXFAP2 | Coil QXFA204 | AUP | 4 | 2019-01-15 | 90 | 2019-04-15 | 419 | MQXFA03 | Coil 102 | 4 | 2016-11-07 | 289 | 2017-08-23 | Practice coil
Coil QXFA105 | LARP | 5 | 2017-04-04 | 248 | 2017-12-08 | MQXFAP2 | Coil QXFA205 | AUP | 5 | 2019-03-15 | 10 | 2019-03-25 | 462 | Rejected | Coil 103 | 5 | 2017-04-24 | 179 | 2017-10-20 | NC
Coil QXFA106 | LARP | 6 | 2017-05-25 | 196 | 2017-12-07 | MQXFAP2 | Coil QXFA206 | AUP | 6 | 2019-04-15 | 122 | 2019-08-15 | 494 | MQXFA04 | Coil 104 | 6 | 2017-06-19 | 301 | 2018-04-16 | MQXFBP1
Coil QXFA107 | LARP | 7 | 2017-08-07 | 295 | 2018-05-29 | On Hold | Coil QXFA207 | AUP | 7 | 2019-05-15 | 153 | 2019-10-15 | 351 | MQXFA05 | Coil 105 | 7 | 2017-07-24 | 340 | 2018-06-29 | MQXFBP1
Coil QXFA108 | AUP | 8 | 2017-12-06 | 175 | 2018-05-30 | Rejected | Coil QXFA208 | AUP | 8 | 2019-06-15 | 10 | 2019-06-25 | 381 | Rejected | Coil 106 | 8 | 2017-09-18 | 10 | 2017-09-28 | NC
Coil QXFA109 | AUP | 9 | 2018-02-05 | 161 | 2018-07-16 | On Hold | Coil QXFA209 | AUP | 9 | 2019-09-15 | 122 | 2020-01-15 | 426 | MQXFA05 | Coil 107 | 9 | 2017-11-13 | 291 | 2018-08-31 | MQXFBP1
Coil QXFA110 | AUP | 10 | 2018-04-23 | 122 | 2018-08-23 | MQXFA03 | Coil QXFA210 | AUP | 10 | 2019-10-15 | 152 | 2020-03-15 | 418 | On hold | Coil 108 | 10 | 2018-02-05 | 228 | 2018-09-21 | MQXFBP1
Coil QXFA111 | AUP | 11 | 2018-07-05 | 118 | 2018-10-31 | MQXFA03 | Coil QXFA211 | AUP | 11 | 2019-11-15 | 274 | 2020-08-15 | 380 | MQXFA06 | Coil 201 | 11 | 2018-03-19 | 319 | 2019-02-01 | NC
Coil QXFA112 | AUP | 12 | 2018-08-22 | 118 | 2018-12-18 | MQXFA04 | Coil QXFA212 | AUP | 12 | 2019-12-15 | 275 | 2020-09-15 | 362 | MQXFA07 | Coil 109 | 12 | 2018-05-21 | 151 | 2018-10-19 | Not tested
Coil QXFA113 | AUP | 13 | 2018-10-10 | 128 | 2019-02-15 | MQXFA04 | Coil QXFA213 | AUP | 13 | 2020-02-15 | 335 | 2021-01-15 | 365 | Accepted | Coil 202 | 13 | 2018-10-01 | 144 | 2019-02-22 | NC
Coil QXFA114 | AUP | 14 | 2018-12-11 | 113 | 2019-04-03 | MQXFA07 | Coil QXFA214 | AUP | 14 | 2020-03-15 | 272 | 2020-12-12 | 347 | MQXFA07 | Coil 203 | 14 | 2018-11-09 | 140 | 2019-03-29 | NC
Coil QXFA115 | AUP | 15 | 2019-02-11 | 112 | 2019-06-03 | MQXFA05 | Coil QXFA215 | AUP | 15 | 2020-07-15 | 184 | 2021-01-15 | 408 | Accepted | Coil 204 | 15 | 2018-12-10 | 348 | 2019-11-23 | NC
Coil QXFA116 | AUP | 16 | 2019-03-26 | 176 | 2019-09-18 | MQXFA05 | Coil QXFA216 | AUP | 16 | 2020-08-15 | 184 | 2021-02-15 | 332 |  | Coil 205 | 16 | 2019-01-21 | 331 | 2019-12-18 | NC
Coil QXFA117 | AUP | 17 | 2019-05-17 | 161 | 2019-10-25 | Accepted | Coil QXFA217 | AUP | 17 | 2020-09-15 | 153 | 2021-02-15 | 326 |  | Coil 003 | 17 | 2019-07-18 | 127 | 2019-11-22 | Practice coil
Coil QXFA118 | AUP | 18 | 2019-07-24 | 10 | 2019-08-03 | Rejected | Coil QXFA218 | AUP | 18 | 2020-10-15 | 123 | 2021-02-15 | 439 |  | Coil 110 | 18 | 2019-05-13 | 242 | 2020-01-10 | MQXFBP2
Coil QXFA119 | AUP | 19 | 2019-09-17 | 129 | 2020-01-24 | MQXFA06 | [5 empty] | 2021-02-15 |  |  | Coil 111 | 19 | 2019-09-23 | 122 | 2020-01-23 | MQXFBP2
Coil QXFA120 | AUP | 20 | 2019-11-01 | 30 | 2019-12-01 | Rejected | [5 empty] | 2021-02-15 |  |  | Coil 112 | 20 | 2019-10-14 | 122 | 2020-02-13 | MQXFBP2
Coil QXFA121 | AUP | 21 | 2019-12-11 | 188 | 2020-06-16 | On Hold | [5 empty] | 2021-02-15 |  |  | Coil 113 | 21 | 2019-11-13 | 121 | 2020-03-13 | MQXFBP2
Coil QXFA122 | AUP | 22 | 2020-01-21 | 192 | 2020-07-31 | MQXFA06 | [5 empty] | 2021-02-15 |  |  | Coil 114 | 22 | 2019-12-04 | 163 | 2020-05-15 | On hold
Coil QXFA123 | AUP | 23 | 2020-02-20 | 176 | 2020-08-14 | MQXFA06 | [5 empty] | 2021-02-15 |  |  | Coil 115 | 23 | 2020-01-29 | 167 | 2020-07-14 | MQXFB01
Coil QXFA124 | AUP | 24 | 2020-03-19 | 175 | 2020-09-10 | MQXFA07 | [5 empty] | 2021-02-15 |  |  | Coil 116 | 24 | 2020-02-28 | 172 | 2020-08-18 | On hold
Coil QXFA125 | AUP | 25 | 2020-06-29 | 143 | 2020-11-19 | On Hold | [5 empty] | 2021-02-15 |  |  | Coil 117 | 25 | 2020-05-25 | 95 | 2020-08-28 | MQXFB01
Coil QXFA126 | AUP | 26 | 2020-08-07 | 133 | 2020-12-18 | Accepted | [5 empty] | 2021-02-15 |  |  | Coil 118 | 26 | 2020-06-24 | 96 | 2020-09-28 | MQXFB01
Coil QXFA127 | AUP | 27 | 2020-09-17 | 151 | 2021-02-15 | On Hold | [8 empty] | Coil 119 | 27 | 2020-07-14 | 98 | 2020-10-20 | MQXFB01
Coil QXFA128 | AUP | 28 | 2020-10-19 | 119 | 2021-02-15 | [9 empty] | Coil 120 | 28 | 2020-08-31 | 107 | 2020-12-16 | Rejected
Coil QXFA129 | AUP | 29 | 2020-11-17 | 90 | 2021-02-15 | [9 empty] | Coil 121 | 29 | 2020-10-26 | 88 | 2021-01-22 | Accepted
Coil QXFA130 | AUP | 30 | 2021-01-07 | 39 | 2021-02-15 | [9 empty] | Coil 122 | 30 | 2020-11-10 | 97 | 2021-02-15
Coil QXFA131 | AUP | [13 empty] | Coil 123 | 31 | 2020-12-02 | 75 | 2021-02-15
[15 empty] | Coil 124 | 32 | 2021-01-11 | 35 | 2021-02-15
[15 empty] | Coil 125 | 33 | 2021-01-26 | 20 | 2021-02-15
Formulas:
Start fab. = [End. Fab]
End. Fab = [Start fab.]
End. Fab = [Start fab.]+10
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: coil with IL QH, the first one 4.2 m, it was not planned to go in a production magnet so it is cut.
Note on G17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Originally on-hold, fast impregnation
Note on G20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Originally planned for MQXFA06, but then replaced by 123 (better fitting in terms of geometry)
Note on G21: Susana Izquierdo Bermudez: Cable rope during winding L2, 15th Turn
Note on G23: Susana Izquierdo Bermudez: Unexpected high tension on cable during winding. On hold after curing In Aukguat the tried again to use Selva but due to an issue during winding cable collapsed
Note on G24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: lead slightly bent after reaction, coil completed, on hold
Note on G28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Conductor exposed during post-impregnation clean-up DR12166
Note on G30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EMDS 2470711, QH to coil short after impregnation
Note on O8: Susana Izquierdo Bermudez: Cable damaged during winding
Note on O11: Susana Izquierdo Bermudez: Cable damated during curing
Note on O13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cable damaged after reaction, splice (DR AM-156);
Note on O16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Areas of epoxy delamination on midplane when removing the impreg tooling (DR AM-171); coil re-impregnated
Note on R32: Susana Izquierdo Bermudez: Cable damated during curing
Note on U8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: leads damaged during reaction
Note on U11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: error on spool lenght during winding
Note on U14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: weak electrical insulation coil to pole/endparts
Note on U16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: weak electrical insulation coil to endparts
Note on U17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: weak electrical insulation coil to endparts
Note on U18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: leads damaged during heat treatment
Note on U19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: leads damaged during curing
Note on U25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coil to QH short, repaired
Note on U27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: damaged during handling in the outer radius mid-plane turn
Note on U31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cable ropped ruing winding
FNAL
BNL
15/02/2021
AUP
Last update
15/02/2021
FNAL
BNL