## Mapping Table
I. Pong | [5 empty] | A. Nobrega/M.Yu | [7 empty] | J. Schmalzle | [7 empty] | S. Prestemon | [7 empty] | P. Joshi | [5 empty] | S. Feher
Cable | [5 empty] | FNAL Coil | [7 empty] | BNL Coil | [7 empty] | Magnet Assembly | [7 empty] | Magnet Vertical Test | [5 empty] | Cold Mass
|  | Accepted |  | Schedule |  | Cable Used |  |  |  | Accepted |  | Schedule |  | Cable Used |  |  |  | Accepted |  | Schedule |  | Coil Used |  |  |  | Accepted |  | Schedule |  |  |  | Accepted |  | Schedule |  | Magnet Used |  |  |  | Accepted |  | Schedule
P6 Label | Serial # | Actual | P6 Assum. | Start | Finish | P6 Logic | Actual | Location | P6 Label/Serial # | Actual* | P6 Assum. | Start | Finish | P6 Logic | Actual | Location | P6 Label/Serial # | Actual* | P6 Assum. | Start | Finish | P6 Logic | Actual | P6 Label | Serial # | Actual | P6 Assum. | Start | Finish | P6 Label | Serial # | Actual | P6 Assum. | Start | Finish | P6 Logic | Actual | P6 Label | Serial # | Actual | P6 Assum. | Start | Finish
1 | P43OL1095 | Y |  | 11-Jan-18 A |  | LARP Cable | P43OL1086 | used | QXFA-108 | N | N | 20-Nov-17 A | 25-May-18 A | LARP Cable | P43OL1092 | used | QXFA-202 | Y |  | 04-Sep-18 A | 27-Feb-2019 A | LARP Coil |  | MQXFA-1b | MQXFA-P1 |  | 1b-r | 26-Oct-18 A | 22-Mar-2019 A | MQXFA-02 | MQXFA-02 |  |  | 01-Aug-18 A | 06-Feb-2019 A | 1b |  | LMQXFA-P | LMQXFA-P |  | Practice | 2020-03-03 | 2020-08-12
2 | P43OL1096 | Y |  | 19-Jan-18 A | 31-Aug-18 A | LARP Cable | P43OL1090 | used | QXFA-109 | Q |  | 31-Jan-18 A | 13-Jul-18 A | 5 | P43OL1096 | used | QXFA-203 | CY-AF |  | 15-Oct-18 A | 21-May-2019 A | LARP Coil | [13 empty] | 2
3 | P43OL1097 | Y |  | 06-Feb-18 A | 31-Aug-18 A | LARP Cable | P43OL1091 | used | QXFA-110 | Y |  | 23-Apr-18 A | 31-Aug-18 A | 7 | P43OL1099 | used | QXFA-204 | Y |  | 03-Jan-19 A | 21-May-2019 A | LARP Coil | [13 empty] | MQXFA-03 |  | LMQXFA-01 | LMQXFA-1 |  | N | 2020-09-01 | 2020-11-17
4 | P43OL1098 | Y |  | 09-Feb-18 A | 16-Aug-18 A | 1 | P43OL1095 | used | QXFP 06 | Y |  | 18-Jun-18 A | 19-Oct-18 A | 9 | P43OL1101 | used/FNAL | QXFA-205 | N | N | 05-Mar-2019 A | 25-Mar-2019 A | QXFP 06 | [13 empty] | MQXFA-05
5 | P43OL1099 | Y |  | 22-Feb-18 A | 26-Aug-18 A | 2 | P43OL1098 | used | QXFA-111 | Y |  | 02-Jul-18 A | 31-Oct-18 A | 12 | P43OL1103 | used | QXFA-206 | CY-AF |  | 01-Apr-2019 A | 26-Sep-2019 A | 202 | 202 | MQXFA-03 | MQXFA-03 |  |  | 25-Mar-2019 A | 20-Sep-2019 A | MQXFA-1b | MQXFA-P1 |  |  | 01-Apr-2019 A | 08-Jul-2019 A | MQXFA-06 |  | LMQXFA-02 |  |  |  | 2021-02-19 | 2021-05-06
6 | P43OL1100 | Y |  | 27-Mar-18 A | 14-Sep-18 A | 3 | P43OL1100 | used | QXFA-112 | CY-AF |  | 20-Aug-18 A | 19-Dec-18 A | 14 | P43OL1106 | used | QXFA-207 | CY-AF |  | 01-May-2019 A | 08-Nov-2019 A | 204 | 204 | [12 empty] | MQXFA-07
7 | P43OL1101 | Y |  | 06-Apr-18 A | 14-Sep-18 A | 4 | P43OL1094 | used | QXFA-113 | CY-AF |  | 10-Oct-18 A | 27-Feb-2019 A | 16 | P43OL1111 | used/BNL | QXFA-208 | N |  | 04-Jun-2019 A | 04-Sep-2019 A | 110 | 110 | [12 empty] | Rework of 01 |  | LMQXFA-R1 |  |  |  | 2021-08-31 | 2021-10-26
8 | P43OL1102 | Y |  | 17-Apr-18 A | 26-Aug-18 A | 6 | P43OL1097 | used | QXFA-114 | Q |  | 03-Dec-18 A | 43801 | 18 | P43OL1114 | used | QXFA-209 | CY-AF |  | 28-Aug-2019 A | 2020-01-24 | 111 | 111
9 | P43OL1103 | Y |  | 09-May-18 A | 31-Aug-18 A | 8 | P43OL1102 | used | QXFA-115 | CY-AF |  | 06-Feb-2019 A | 03-Sep-2019 A | 20 | P43OL1116 | used | QXFA-210 | Q |  | 08-Oct-2019 A | 2020-02-27 | 203 | 203 | MQXFA-04 |  |  |  | 20-Sep-2019 A | 2020-03-04 | MQXFA-03 | MQXFA-03 |  |  | 01-Oct-2019 A | 2020-01-29 | MQXFA-08 |  | LMQXFA-03 |  |  | N | 2021-10-27 | 2021-12-23
10 | P43OL1105 | Y |  | 18-May-18 A | 14-Sep-18 A | 10 | P43OL1105 | used | QXFA-116 | CY-AF |  | 27-Mar-2019 A | 20-Sep-2019 A | 23 | P43OL1120 | used | QXFA-211 | CY-50% |  | 12-Nov-2019 A | 2020-04-03 | 206 | 206 | [12 empty] | MQXFA-10
11 | P43OL1106 | Y | N | 30-May-18A | 11-Sep-18 A | 13 | P43OL1107 | used | QXFA-117 | CY-AF |  | 08-May-2019 A | 07-Nov-2019 A | 25 | P43OL1124 | used | QXFA-212 | CY-28% |  | 2020-01-06 | 2020-05-04 | 112 | 112 | [12 empty] | MQXFA-11 |  | LMQXFA-04 |  |  |  | 2021-12-28 | 2022-02-24
12 | P43OL1107 | Y |  | 22-Jun-18 A | 14-Sep-18 A | 15 | P43OL1113 | used | QXFA-118 | N |  | 19-Jul-2019 A | 04-Sep-2019 A | 27 | P43OL1123 | used | QXFA-213 |  |  | 2020-02-04 | 2020-06-02 | 115 | 113 | [12 empty] | MQXFA-12
13 | P43OL1111 | Y |  | 27-Aug-18 A | 12-Feb-2019 A | 17 | P43OL1117 | used | QXFA-119 | CY-F99% |  | 12-Sep-2019 A | 2020-01-03 | 29 | P43OL1127 | BNL | QXFA-214 |  |  | 2020-03-03 | 2020-06-30 | 207 |  | MQXFA-05 |  |  |  | 2020-02-04 | 2020-05-20 | MQXFA-04 |  |  | N | 2020-03-19 | 2020-06-17 | MQXFA-13 |  | LMQXFA-05 |  |  |  | 2022-03-17 | 2022-05-11
14 | P43OL1112 | N |  | 05-Sep-18 A | N | 19 | P43OL1115 | used | QXFA-120 | Q |  | 28-Oct-2019 A | 2020-01-02 | 32 | P43OL1122 | BNL | QXFA-215 |  |  | 2020-03-31 | 2020-07-29 | 113 | [13 empty] | MQXFA-14
15 | P43OL1113 | Y |  | 20-Sep-18 A | 11-Apr-2019 A | 22 | P43OL1125 | used | QXFA-121 | Q-75% |  | 29-Nov-2019 A | 2020-04-03 | 34 | P43OL1128 | BNL | QXFA-216 |  | N | 2020-04-28 | 2020-08-26 | 116 | [13 empty] | MQXFA-16 |  | LMQXFA-06 |  |  |  | 2022-09-14 | 2022-11-08
16 | P43OL1114 | Y |  | 01-Oct-18 A | 11-Apr-2019 A | 24 | P43OL1126 | used | QXFA-122 | CY-F33% |  | 2020-02-03 | 2020-06-02 | 36 | P43OL1129 | BNL | QXFA-217 |  |  | 2020-05-27 | 2020-09-24 | 117 | [13 empty] | MQXFA-17
17 | P43OL1115 | Y |  | 01-Oct-18 A | 31-Jul-2019 A | 26 | P43OL1130 | used | QXFA-123 | CY-F15% |  | 2020-03-02 | 2020-06-30 | 38 | P43OL1133 | BNL | QXFA-218 |  |  | 2020-06-24 | 2020-10-22 | 209 |  | MQXFA-06 |  |  |  | 2020-04-07 | 2020-07-29 | MQXFA-05 |  |  |  | 2020-06-05 | 2020-08-17 | MQXFA-18 |  | LMQXFA-07 |  |  |  | 2023-01-17 | 2023-03-13
18 | P43OL1116 | Y |  | 06-Nov-18 A | 11-Apr-2019 A | 28 | P43OL1121 | FNAL | QXFA-124 |  | N | 2020-03-30 | 2020-07-29 | 40 | P43OL1134 | BNL | QXFA-219 |  |  | 2020-07-21 | 2020-11-17 | 210 | [13 empty] | MQXFA-19
19 | P43OL1117 | Y |  | 15-Nov-18 A | 11-Apr-2019 A | 30 | P43OL1131 | FNAL | QXFA-125 |  |  | 2020-04-27 | 2020-08-26 | 43 | P43OL1135 | BNL | QXFA-220 |  |  | 2020-08-14 | 2020-12-15 | 211 | [13 empty] | Rework of 03 |  | LMQXFA-R2 |  |  |  | 2023-03-14 | 2023-05-08
20 | P43OL1120 | Y |  | 11-Jan-19 A | 09-May-2019 A | 33 | P43OL1132 | FNAL | QXFA-126 |  |  | 2020-05-26 | 2020-09-24 | 45 |  |  | QXFA-221 |  |  | 2020-09-10 | 2021-01-14 | 119
21 | P43OL1121 |  | N | 17-Jan-19 A | 2020-01-30 | 35 | P43OL1136 | FNAL | QXFA-127 |  |  | 2020-06-23 | 2020-10-22 | 47 |  |  | QXFA-222 |  |  | 2020-11-13 | 2021-03-22 | 212 |  | MQXFA-07 |  |  |  | 2020-06-05 | 2020-09-09 | MQXFA-06 |  |  |  | 2020-08-13 | 2020-10-14 | MQXFA-20 |  | LMQXFA-08 |  |  |  | 2023-05-11 | 2023-07-07
22 | P43OL1122 | Y |  | 04-Feb-2019 A | 2020-01-30 | 37 | P43OL1137 | FNAL | QXFA-128 |  |  | 2020-07-22 | 2020-11-19 | 49 |  |  | QXFA-223 |  |  | 2020-12-11 | 2021-04-15 | 213 | [13 empty] | MQXFA-21
23 | P43OL1123 | Y |  | 27-Feb-2019 A | 25-Sep-2019 A | 39 | P43OL1138 | FNAL | QXFA-129 |  |  | 2020-08-19 | 2020-12-21 | 52 |  |  | QXFA-224 |  | N | 2021-01-12 | 2021-05-11 | 120 | [13 empty] | MQXFA-23 |  | LMQXFA-09 |  |  |  | 2023-08-02 | 2023-09-27
24 | P43OL1124 | Y |  | 01-Mar-2019 A | 25-Sep-2019 A | 42 |  |  | QXFA-130 |  |  | 2020-09-15 | 2021-01-21 | 54 |  |  | QXFA-225 |  |  | 2021-02-08 | 2021-06-07 | 121 | [13 empty] | MQXFA-R2
25 | P43OL1125 | Y |  | 01-Mar-2019 A | 25-Sep-2019 A | 44 |  |  | QXFA-131 |  |  | 2020-10-09 | 2021-02-16 | 56 |  |  | QXFA-226 |  |  | 2021-03-04 | 2021-07-01 | 214 |  | MQXFA-08 |  |  |  | 2020-08-17 | 2020-10-27 | MQXFA-07 |  |  |  | 2020-10-12 | 2021-01-07 | MQXFA-R3 |  | LMQXFA-10 |  |  |  | 2023-10-26 | 2023-12-26
26 | P43OL1126 | Y |  | 15-Mar-2019 A | 2020-01-30 | 46 |  |  | QXFA-132 |  | N | 2020-11-04 | 2021-03-12 | 58 |  |  | QXFA-227 |  |  | 2021-03-30 | 2021-07-28 | 215 | [13 empty] | MQXFA-R4
27 | P43OL1127 | Y |  | 19-Mar-2019 A | 2020-01-30 | 48 |  |  | QXFA-133 |  |  | 2020-12-02 | 2021-04-07 | 60 |  |  | QXFA-228 |  |  | 2021-04-23 | 2021-08-23 | 122
28 | P43OL1128 | Y |  | 10-Apr-2019 A | 2020-01-30 | 50 |  |  | QXFA-134 |  |  | 2020-12-30 | 2021-05-03 | 63 |  |  | QXFA-229 |  |  | 2021-05-19 | 2021-09-17 | 123
29 | P43OL1129 | Y |  | 16-Apr-2019 A | 2020-01-30 | 53 |  |  | QXFA-135 |  |  | 2021-01-28 | 2021-05-27 | 65 |  |  | QXFA-230 |  |  | 2021-06-15 | 2021-10-13 | 217 |  | MQXFA-09 |  |  |  | 2020-09-29 | 2021-02-05 | MQXFA-08 |  |  |  | 2020-12-10 | 2021-03-08
30 | P43OL1130 | Y |  | 18-Apr-2019 A | 2020-01-30 | 55 |  |  | QXFA-136 |  |  | 2021-02-23 | 2021-06-23 | 67 |  |  | QXFA-231 |  |  | 2021-07-12 | 2021-11-08 | 218
31 | P43OL1131 | Y | N | 13-May-2019 A | 2020-01-30 | 57 |  |  | QXFA-137 |  |  | 2021-03-19 | 2021-07-20 | 69 |  |  | QXFA-232 |  | N | 2021-08-05 | 2021-12-06 | 125
32 | P43OL1132 | Y |  | 22-May-2019 A | 2020-01-30 | 59 |  |  | QXFA-138 |  |  | 2021-04-14 | 2021-08-13 | 71 |  |  | QXFA-233 |  |  | 2021-08-31 | 2022-01-05 | 126
33 | P43OL1133 | Y |  | 31-May-2019 A | 2020-01-30 | 62 |  |  | QXFA-139 |  |  | 2021-05-10 | 2021-09-09 | 74 |  |  | QXFA-234 |  |  | 2021-09-27 | 2022-02-01 | 219 |  | MQXFA-10 |  |  |  | 2020-11-30 | 2021-03-25 | MQXFA-09 |  |  | N | 2021-02-22 | 2021-05-04
34 | P43OL1134 |  |  | 17-Jun-2019 A | 2020-02-17 | 64 |  |  | QXFA-140 |  | N | 2021-06-04 | 2021-10-05 | 76 |  |  | QXFA-235 |  |  | 2021-10-21 | 2022-02-25 | 127
35 | P43OL1135 |  |  | 01-Jul-2019 A | 2020-02-17 | 66 |  |  | QXFA-141 |  |  | 2021-06-30 | 2021-10-29 | 78 |  |  | QXFA-236 |  |  | 2021-11-16 | 2022-03-23 | 128
36 | P43OL1136 |  |  | 19-Aug-2019 A | 2020-02-17 | 68 |  |  | QXFA-142 |  |  | 2021-07-27 | 2021-11-24 | 80 |  |  | QXFA-237 |  |  | 2021-12-14 | 2022-04-18 | 129
37 | P43OL1137 |  |  | 23-Aug-2019 A | 2020-03-16 | 70 |  |  | QXFA-143 |  |  | 2021-08-20 | 2021-12-22 | 83 |  |  | QXFA-238 |  |  | 2022-01-13 | 2022-05-12 | 220 |  | MQXFA-11 |  |  |  | 2021-01-15 | 2021-05-14 | MQXFA-10 |  |  |  | 2021-04-20 | 2021-07-01
38 | P43OL1138 |  |  | 30-Aug-2019 A | 2020-03-16 | 73 |  |  | QXFA-144 |  |  | 2021-09-16 | 2022-01-24 | 85 |  |  | QXFA-239 |  |  | 2022-02-09 | 2022-06-08 | 221
39 | P43OL1139 |  |  | 18-Nov-2019 A | 2020-05-18 | 75 |  |  | QXFA-145 |  |  | 2021-10-12 | 2022-02-17 | 87 |  |  | QXFA-240 |  | N | 2022-03-07 | 2022-07-05 | 130
40 | P43OL1140 |  |  | 25-Nov-2019 A | 2020-03-16 | 77 |  |  | QXFA-146 |  |  | 2021-11-05 | 2022-03-15 | 89 |  |  | QXFA-241 |  |  | 2022-03-31 | 2022-07-29 | 131
41 | P43OL1141 |  | N | 09-Dec-2019 A | 2020-03-16 | 79 |  |  | QXFA-147 |  |  | 2021-12-03 | 2022-04-08 | 91 |  |  | QXFA-242 |  |  | 2022-04-26 | 2022-08-24 | 222 |  | MQXFA-12 |  |  |  | 2021-03-03 | 2021-08-02 | MQXFA-11 |  |  |  | 2021-06-17 | 2021-08-30
42 | P43OL1142 |  |  | 16-Dec-2019 A | 2020-03-19 | 81 |  |  | QXFA-148 |  | N | 2022-01-04 | 2022-05-04 | 94 |  |  | QXFA-243 |  |  | 2022-05-20 | 2022-09-20 | 223
43 | P43OL1143 |  |  | 2020-01-16 | 2020-04-22 | 84 |  |  | QXFA-149 |  |  | 2022-01-31 | 2022-05-31 | 96 |  |  | QXFA-244 |  |  | 2022-06-16 | 2022-10-14 | 133
44 | P43OL1144 |  |  | 2020-01-28 | 2020-04-22 | 86 |  |  | QXFA-150 |  |  | 2022-02-24 | 2022-06-24 | 98 |  |  | QXFA-245 |  |  | 2022-07-13 | 2022-11-09 | 134
45 | P43OL1145 |  |  | 2020-02-06 | 2020-04-27 | 88 |  |  | QXFA-151 |  |  | 2022-03-22 | 2022-07-21 | 100 |  |  | QXFA-246 |  |  | 2022-08-08 | 2022-12-07 | 225 |  | MQXFA-13 |  |  |  | 2021-05-18 | 2021-09-30 | MQXFA-12 |  |  |  | 2021-08-17 | 2021-10-27
46 | P43OL1146 |  |  | 2020-03-06 | 2020-06-02 | 90 |  |  | QXFA-152 |  |  | 2022-04-15 | 2022-08-16 | 101 |  |  | QXFA-247 |  | N | 2022-09-01 | 2023-01-06 | 226
47 | P43OL1147 |  |  | 2020-03-17 | 2020-06-05 | 93 |  |  | QXFA-153 |  |  | 2022-05-11 | 2022-09-12 | 102 |  |  | QXFA-248 |  |  | 2022-09-28 | 2023-02-02 | 135
48 | P43OL1148 |  |  | 2020-03-26 | 2020-07-01 | 95 |  |  | QXFA-154 |  |  | 2022-06-07 | 2022-10-06 | [8 empty] | 136
49 | P43OL1149 |  |  | 2020-04-06 | 2020-07-01 | 97 |  |  | QXFA-155 |  | N | 2022-07-01 | 2022-11-01 | [8 empty] | 227 |  | MQXFA-14 |  |  |  | 2021-07-19 | 2021-11-19 | MQXFA-13 |  |  |  | 2021-10-15 | 2021-12-30
50 | P43OL1150 |  |  | 2020-04-15 | 2020-07-07 | 99 |  |  | QXFA-156 |  |  | 2022-07-28 | 2022-11-29 | [8 empty] | 228
51 | P43OL1151 |  | N | 2020-04-24 | 2020-07-31 | [16 empty] | 137
52 | P43OL1152 |  |  | 2020-05-05 | 2020-07-31 | [16 empty] | 138
53 | P43OL1153 |  |  | 2020-05-14 | 2020-08-05 |  |  |  | : Pre-Series coil w/o b6 correction | [12 empty] | 229 |  | MQXFA-15 |  |  |  | 2021-09-08 | 2022-02-04 | MQXFA-14 |  |  |  | 2021-12-15 | 2022-03-02
54 | P43OL1154 |  |  | 2020-05-26 | 2020-08-31 |  |  |  | : Prototype/Pre-Series | [12 empty] | 230
55 | P43OL1155 |  |  | 2020-06-04 | 2020-08-31 |  |  |  | : CD-3b Scope (ESAAB Feb 2019) | [12 empty] | 139
56 | P43OL1156 |  |  | 2020-06-15 | 2020-09-03 |  |  |  | : CD-3c Scope (ESAAB Aug 2020) | [12 empty] | 141
57 | P43OL1157 |  |  | 2020-06-24 | 2020-09-30 |  |  |  | : CD-3 Scope (ESAAB Dec 2021) | [12 empty] | 231 |  | MQXFA-16 |  |  |  | 2021-11-15 | 2022-04-05 | MQXFA-15 |  |  | N | 2022-02-21 | 2022-04-28
58 | P43OL1158 |  |  | 2020-07-06 | 2020-09-30 | [16 empty] | 233
59 | P43OL1159 |  |  | 2020-07-15 | 2020-10-05 | [16 empty] | 142
60 | P43OL1160 |  |  | 2020-07-24 | 2020-10-29 |  |  | *Legend for Accepted¦Actual Coils Status | [13 empty] | 143
61 | P43OL1161 |  | N | 2020-08-04 | 2020-10-29 |  |  | CY-F% | :Indicates the coil is conditionally accepted during fabrication, the % indicates the coil fabrication % complete | [12 empty] | 234 |  | MQXFA-17 |  |  |  | 2022-01-21 | 2022-05-25 | MQXFA-16 |  |  |  | 2022-04-20 | 2022-06-30
62 | P43OL1162 |  |  | 2020-08-13 | 2020-11-03 |  |  | CY-AF | :Indicates the coil is conditionally accepted after fabrication is 100% complete | [12 empty] | 235
63 | P43OL1163 |  |  | 2020-08-24 | 2020-12-01 |  |  | CY-AM | :Indicates the coil is conditionally accepted after Magnet Fabrication | [12 empty] | 144
64 | P43OL1164 |  |  | 2020-09-02 | 2020-12-01 |  |  | Y | :Indicates the coil is fully accepted after Vertical Test (or Horizontal Test if Vertical Test is skipped) | [12 empty] | 145
65 | P43OL1165 |  |  | 2020-09-14 | 2020-12-04 |  |  | Q | : Indicates the coil is quarantined | [12 empty] | 236 |  | MQXFA-18 |  |  |  | 2022-03-14 | 2022-07-18 | MQXFA-17 |  |  |  | 2022-06-17 | 2022-08-29
66 | P43OL1166 |  |  | 2020-09-23 | 2021-01-05 |  |  | N | : Indicates the coil is rejected | [12 empty] | 237
67 | P43OL1167 |  |  | 2020-10-02 | 2021-01-05 | [16 empty] | 146
68 | P43OL1168 |  |  | 2020-10-13 | 2021-01-08 | [16 empty] | 147
69 | P43OL1169 |  |  | 2020-10-22 | 2021-02-04 | [16 empty] | 238 |  | MQXFA-19 |  |  |  | 2022-05-03 | 2022-09-23 | MQXFA-18 |  |  |  | 2022-08-16 | 2022-10-26
70 | P43OL1170 |  |  | 2020-11-02 | 2021-02-04 | [16 empty] | 239
71 | P43OL1171 |  |  | 2020-11-11 | 2021-02-09 | [16 empty] | 149
72 | P43OL1172 |  | N | 2020-11-20 | 2021-03-05 | [16 empty] | 150
73 | P43OL1173 |  |  | 2020-12-03 | 2021-03-05 | [16 empty] | 241 |  | MQXFA-20 |  |  |  | 2022-07-12 | 2022-11-22 | MQXFA-19 |  |  |  | 2022-10-13 | 2022-12-28
74 | P43OL1174 |  |  | 2020-12-14 | 2021-03-10 | [16 empty] | 242
75 | P43OL1175 |  |  | 2020-12-23 | 2021-04-05 | [16 empty] | 151
76 | P43OL1176 |  |  | 2021-01-07 | 2021-04-05 | [16 empty] | 152
77 | P43OL1177 |  |  | 2021-01-19 | 2021-04-08 | [16 empty] | 243 |  | MQXFA-21 |  |  |  | 2022-09-09 | 2023-01-20 | MQXFA-20 |  |  |  | 2022-12-13 | 2023-02-28
78 | P43OL1178 |  |  | 2021-01-28 | 2021-05-04 | [16 empty] | 244
79 | P43OL1179 |  |  | 2021-02-08 | 2021-05-04 | [16 empty] | 153
80 | P43OL1180 |  |  | 2021-02-17 | 2021-05-07 | [16 empty] | 154
81 | P43OL1181 |  |  | 2021-02-26 | 2021-06-03 | [16 empty] | 245 |  | MQXFA-22 |  |  |  | 2022-10-31 | 2023-05-02 | MQXFA-21 |  |  |  | 2023-02-15 | 2023-04-26
82 | P43OL1182 |  | N | 2021-03-09 | 2021-06-03 | [16 empty] | 246
83 | P43OL1183 |  |  | 2021-03-18 | 2021-06-08 | [16 empty] | 248
84 | P43OL1184 |  |  | 2021-03-29 | 2021-07-02 | [16 empty] | 156
85 | P43OL1185 |  |  | 2021-04-07 | 2021-07-09 | [16 empty] | 109 |  | MQXFA-23 |  |  |  | 2023-02-17 | 2023-05-18 | MQXFA-22 |  |  | N | 2023-05-17 | 2023-07-28
86 | P43OL1186 |  |  | 2021-04-26 | 2021-07-16 | [16 empty] | 114
87 | P43OL1187 |  |  | 2021-05-05 | 2021-08-11
88 | P43OL1188 |  |  | 2021-05-14 | 2021-08-11
89 | P43OL1189 |  |  | 2021-05-25 | 2021-08-16 | [16 empty] | Rework |  | MQXFA-R1 |  |  | N | 2023-03-31 | 2023-06-05
90 | P43OL1190 |  |  | 2021-06-22 | 2021-09-28
91 | P43OL1191 |  |  | 2021-07-01 | 2021-09-28
92 | P43OL1192 |  | N | 2021-07-13 | 2021-10-01
93 | P43OL1193 |  |  | 2021-07-22 | 2021-11-10 | [16 empty] | Rework |  | MQXFA-R2 |  |  |  | 2023-05-12 | 2023-07-18
94 | P43OL1194 |  |  | 2021-08-25 | 2021-11-19
95 | P43OL1195 |  |  | 2021-09-03 | 2021-11-24
96 | P43OL1196 |  |  | 2021-09-15 | 2022-01-11
97 | P43OL1197 |  |  | 2021-09-24 | 2022-01-19 | [16 empty] | Rework |  | MQXFA-R3 |  |  |  | 2023-06-26 | 2023-08-29
98 | P43OL1198 |  |  | 2021-10-28 | 2022-01-26
99 | P43OL1199 |  |  | 2021-11-08 | 2022-02-21
100 | P43OL1200 |  |  | 2021-11-17 | 2022-02-21
101 | P43OL1201 |  |  | 2021-11-30 | 2022-02-24 | [16 empty] | Rework |  | MQXFA-R4 |  |  |  | 2023-08-08 | 2023-10-11
102 | P43OL1202 |  |  | 2021-12-09 | 2022-03-11
Formulas:
Schedule = VLOOKUP([P6 Label],'Schedule Data'!$R5:T101,2,FALSE)
Schedule = VLOOKUP([P6 Label/Serial #],'Schedule Data'!$F5:H101,2,FALSE)
Finish = VLOOKUP([P6 Label],'Schedule Data'!$R5:T101,3,FALSE)
Finish = VLOOKUP([P6 Label/Serial #],'Schedule Data'!$F5:H101,3,FALSE)

## Sheet1
|  |  | 3 | QXFA-202 | 04-Sep-18 A | 27-Feb-2019 A | 2018-04-01 | 2019-05-01
|  |  |  | QXFA-204 | 03-Jan-19 A | 21-May-2019 A
|  |  |  | QXFA-110 | 23-Apr-18 A | 31-Aug-18 A
|  |  |  | QXFA-111 | 02-Jul-18 A | 31-Oct-18 A
|  |  | 4 | QXFA-203 | 15-Oct-18 A | 21-May-2019 A | 2018-10-01 | 2019-09-01
|  |  |  | QXFA-206 | 01-Apr-2019 A | 26-Sep-2019 A
|  |  |  | QXFA-112 | 20-Aug-18 A | 19-Dec-18 A
|  |  |  | QXFA-113 | 10-Oct-18 A | 27-Feb-2019 A
|  |  | 5 | QXFA-207 | 01-May-2019 A | 08-Nov-2019 A | 2019-03-01
|  |  |  | QXFA-116 | 27-Mar-2019 A | 20-Sep-2019 A
|  |  |  | QXFA-117 | 08-May-2019 A | 07-Nov-2019 A
Past |  |  | 6 |  |  |  | 2018-12-01 | 2020-01-01
QXFA-115 | 06-Feb-2019 A | 03-Sep-2019 A |  | QXFA-114 | 03-Dec-18 A | 2019-12-02
QXFA-118 | 19-Jul-2019 A | 04-Sep-2019 A |  | QXFA-120 | 28-Oct-2019 A | 2020-01-02
QXFA-208 | 04-Jun-2019 A | 04-Sep-2019 A |  | QXFA-119 | 12-Sep-2019 A | 2020-01-03
QXFA-109 | 31-Jan-18 A | 13-Jul-18 A | 7 | QXFA-209 | 28-Aug-2019 A | 2020-01-24 | 2019-08-01 | 2020-04-01
QXFP 06 | 18-Jun-18 A | 19-Oct-18 A |  | QXFA-210 | 08-Oct-2019 A | 2020-02-27
QXFA-205 | 05-Mar-2019 A | 25-Mar-2019 A |  | QXFA-121 | 29-Nov-2019 A | 2020-04-03
QXFA-108 | 20-Nov-17 A | 25-May-18 A |  | QXFA-211 | 12-Nov-2019 A | 2020-04-03
|  |  | 8 | QXFA-212 | 2020-01-06 | 2020-05-04 | 2020-01-01 | 2020-06-01
|  |  |  | QXFA-122 | 2020-02-03 | 2020-06-02
|  |  |  | QXFA-213 | 2020-02-04 | 2020-06-02
|  |  |  | QXFA-123 | 2020-03-02 | 2020-06-30
|  |  |  | QXFA-214 | 2020-03-03 | 2020-06-30
|  |  | 9 | QXFA-124 | 2020-03-30 | 2020-07-29 | 2020-03-01 | 2020-08-01
|  |  |  | QXFA-215 | 2020-03-31 | 2020-07-29
|  |  |  | QXFA-125 | 2020-04-27 | 2020-08-26
|  |  |  | QXFA-216 | 2020-04-28 | 2020-08-26
|  |  | 10 | QXFA-126 | 2020-05-26 | 2020-09-24 | 2020-05-01 | 2020-11-01
|  |  |  | QXFA-217 | 2020-05-27 | 2020-09-24
|  |  |  | QXFA-127 | 2020-06-23 | 2020-10-22
|  |  |  | QXFA-218 | 2020-06-24 | 2020-10-22
|  |  |  | QXFA-219 | 2020-07-21 | 2020-11-17
|  |  | 11 | QXFA-128 | 2020-07-22 | 2020-11-19 | 2020-07-01 | 2021-01-01
|  |  |  | QXFA-220 | 2020-08-14 | 2020-12-15
|  |  |  | QXFA-129 | 2020-08-19 | 2020-12-21
|  |  |  | QXFA-221 | 2020-09-10 | 2021-01-14
|  |  | 12 | QXFA-130 | 2020-09-15 | 2021-01-21 | 2020-09-01 | 2021-04-01
|  |  |  | QXFA-131 | 2020-10-09 | 2021-02-16
|  |  |  | QXFA-132 | 2020-11-04 | 2021-03-12
|  |  |  | QXFA-222 | 2020-11-13 | 2021-03-22
|  |  |  | QXFA-133 | 2020-12-02 | 2021-04-07
|  |  | 13 | QXFA-223 | 2020-12-11 | 2021-04-15 | 2020-12-01 | 2021-05-01
|  |  |  | QXFA-134 | 2020-12-30 | 2021-05-03
|  |  |  | QXFA-224 | 2021-01-12 | 2021-05-11
|  |  |  | QXFA-135 | 2021-01-28 | 2021-05-27
|  |  | 14 | QXFA-225 | 2021-02-08 | 2021-06-07 | 2021-02-01 | 2021-07-01
|  |  |  | QXFA-136 | 2021-02-23 | 2021-06-23
|  |  |  | QXFA-226 | 2021-03-04 | 2021-07-01
|  |  |  | QXFA-137 | 2021-03-19 | 2021-07-20
|  |  |  | QXFA-227 | 2021-03-30 | 2021-07-28
|  |  | 15 | QXFA-138 | 2021-04-14 | 2021-08-13 | 2021-04-01 | 2021-09-01
|  |  |  | QXFA-228 | 2021-04-23 | 2021-08-23
|  |  |  | QXFA-139 | 2021-05-10 | 2021-09-09
|  |  |  | QXFA-229 | 2021-05-19 | 2021-09-17
|  |  | 16 | QXFA-140 | 2021-06-04 | 2021-10-05 | 2021-06-01 | 2021-11-01
|  |  |  | QXFA-230 | 2021-06-15 | 2021-10-13
|  |  |  | QXFA-141 | 2021-06-30 | 2021-10-29
|  |  |  | QXFA-231 | 2021-07-12 | 2021-11-08
|  |  |  | QXFA-142 | 2021-07-27 | 2021-11-24
|  |  | 17 | QXFA-232 | 2021-08-05 | 2021-12-06 | 2021-08-01 | 2022-01-01
|  |  |  | QXFA-143 | 2021-08-20 | 2021-12-22
|  |  |  | QXFA-233 | 2021-08-31 | 2022-01-05
|  |  |  | QXFA-144 | 2021-09-16 | 2022-01-24
|  |  | 18 | QXFA-234 | 2021-09-27 | 2022-02-01 | 2021-09-01 | 2022-03-01
|  |  |  | QXFA-145 | 2021-10-12 | 2022-02-17
|  |  |  | QXFA-235 | 2021-10-21 | 2022-02-25
|  |  |  | QXFA-146 | 2021-11-05 | 2022-03-15
|  |  |  | QXFA-236 | 2021-11-16 | 2022-03-23
|  |  | 19 | QXFA-147 | 2021-12-03 | 2022-04-08 | 2021-12-01 | 2022-05-01
|  |  |  | QXFA-237 | 2021-12-14 | 2022-04-18
|  |  |  | QXFA-148 | 2022-01-04 | 2022-05-04
|  |  |  | QXFA-238 | 2022-01-13 | 2022-05-12
|  |  | 20 | QXFA-149 | 2022-01-31 | 2022-05-31 | 2022-01-01 | 2022-07-01
|  |  |  | QXFA-239 | 2022-02-09 | 2022-06-08
|  |  |  | QXFA-150 | 2022-02-24 | 2022-06-24
|  |  |  | QXFA-240 | 2022-03-07 | 2022-07-05
|  |  |  | QXFA-151 | 2022-03-22 | 2022-07-21
|  |  | 21 | QXFA-241 | 2022-03-31 | 2022-07-29 | 2022-03-01 | 2022-09-01
|  |  |  | QXFA-152 | 2022-04-15 | 2022-08-16
|  |  |  | QXFA-242 | 2022-04-26 | 2022-08-24
|  |  |  | QXFA-153 | 2022-05-11 | 2022-09-12
|  |  | 22 | QXFA-243 | 2022-05-20 | 2022-09-20 | 2022-05-01 | 2022-11-01
|  |  |  | QXFA-154 | 2022-06-07 | 2022-10-06
|  |  |  | QXFA-244 | 2022-06-16 | 2022-10-14
|  |  |  | QXFA-155 | 2022-07-01 | 2022-11-01
|  |  |  | QXFA-245 | 2022-07-13 | 2022-11-09
|  |  | 23 | QXFA-156 | 2022-07-28 | 2022-11-29 | 2022-07-01 | 2023-02-01
|  |  |  | QXFA-246 | 2022-08-08 | 2022-12-07
|  |  |  | QXFA-247 | 2022-09-01 | 2023-01-06
|  |  |  | QXFA-248 | 2022-09-28 | 2023-02-02

## Trace-Coil
Pre-series QH Trace |  |  |  |  | Series QH Trace
ID | CERN QC | FNAL QC | Coil | Note | ID | CERN QC | FNAL QC | Coil | Note
Cern3-011 |  | x | QXFA 109 |  | 221-49-01-1 | x | x | QXFA 215 | Polyimide defect at 2.93 m. Defect was repaired by Trackwise
Cern_112 |  | x | QXFA 110 |  | 221-49-01-2 | x | x | QXFA 123 | Cut in polyimide foil at 2.14 m à fixed with Kapton tape
CERN3-001 |  | x | QXFA 111 |  | 221-49-01-3 | x | x | QXFA 216 | Small copper deposit on the polyimide at 0.270 m
|  | x | QXFA 202 |  | 221-49-02-1 | x | x
221-60-01-01 |  | x | QXFA 203 |  | 221-49-02-2 | x | x |  | QH212 fixed at CERN by adding Kapton
221-60-01-02 |  | x | QXFA 112 |  | 221-49-02-3 | x | x
221-60-02-01 |  | x | QXFA 204 |  | 221-49-03-1 | x | x |  | Small hole in polyimide film at 1.43 m. Was repaired with self-adhesive polyimide tape, and HV test passed after repair. QH211 fixed at CERN by adding Kapton
221-60-02-02 |  | x | QXFA 113 |  | 221-49-03-2 | x | x
221-60-03-01 |  | x | x | fail Hipot at BNL, cannot be used in coil | 221-49-03-3 | x | x
221-60-03-02 |  | x | QXFA 114 |  | 221-49-04-3 | x | x |  | Traces on the copper coating all along the circuit edges. Small region with reduced copper coating thickness at 1.0 m on the mid left circuit (see Figure 12-14)  But still enough copper coating thickness
221-60-04-01 |  | x | QXFA 116 |  | 221-49-06-1 | x | x |  | Copper coating thickness on the left circuit is slightly less than on the other circuits.HV test: default at 1.65m on the middle right trace (see Figure 12 & 13) 1. repaired by applying self-adhesive Kapton tape on the bottom of the polyimide foil 2. HV test: Conform after reparation. QH213 fixed at CERN by adding Kapton
221-60-05-01 |  | x | QXFA 206 |  | 221-49-07-1 | x | x
221-60-05-02 |  | x | QXFA 115 |  | 221-49-07-2 | x | x |  | HV test: default at 0.40m on the middle right trace (see Figure 14, 15 & 16) 1. repaired by applying self-adhesive Kapton tape on the bottom of the polyimide foil (QH214 fixed at CERN by adding Kapton) 2. HV test: Conform after reparation
221-60-06-01 |  | x | QXFA 209 |  | 221-49-07-3 | x | x
221-60-06-02 |  | x | QXFA 117 |  | 221-49-08-1 | x | x
221-60-07-01 |  | x | QXFA 207 |  | 221-49-08-2 | x | x
221-60-07-02 |  | x | QXFA 119 |  | 221-49-08-3 | x | x |  | The copper coating thickness is less than 5 µm on the right trace of the QH, But still higher than 4.0 µm Conform
221-60-08-01 |  | x | QXFA 210 |  | 221-49-09-3 | x | x | x | HV test: default at 2.80m on the middle right trace (see Figure 18 & 19) 1. repaired by applying self-adhesive Kapton tape on the bottom of the polyimide foil (QH212 fixed at CERN by adding Kapton) 2. HV test: Conform after reparation 3. Trace destructive test, cannot be used in coil
221-60-08-02 |  | x | QXFA 211 |  | 221-49-10-1 | x | x
221-60-09-01 |  | x | QXFA 212 |  | 221-49-10-2 | x | x
221-60-09-02 |  | x | QXFA 121 |  | 221-49-10-3 | x | x
221-60-09-03 |  | x | QXFA 122 |  | 221-49-11-1 | x | x |  | About 4.0 µm Cu at 0.30m on the mid-right circuit (see Figure11)
221-60-10-01 |  | x | QXFA 213 |  | 221-49-11-2 | x | x
221-60-10-02 |  | x | QXFA 214 |  | 221-49-11-3 | x | x
[5 empty] | 221-49-12-1 | x | x
[5 empty] | 221-49-12-2 | x | x
[5 empty] | 221-49-12-3 | x | x |  | excessive splatters on heaters top side
[5 empty] | 221-49-13-1 |  | x
[5 empty] | 221-49-13-2 |  | x
[5 empty] | 221-49-13-3 |  | x |  | At approximately 2500mm there is a dented area on stainless surface.
[5 empty] | 221-49-14-1 |  | x
[5 empty] | 221-49-14-2 |  | x
[5 empty] | 221-49-14-3 |  | x
[5 empty] | 221-49-15-1 |  | x
[5 empty] | 221-49-15-2 |  | x
[5 empty] | 221-49-15-3 |  | x
221-49-16-1
221-49-16-2
221-49-16-3
[5 empty] | 221-49-17-1 |  | x |  | There are three small dents in the stainless steel material at approximately 292.0mm, 1230.0mm and 4000.0mm from one end
[5 empty] | 221-49-17-2 |  | x |  | Small dents found in copper/Stainless Steel at the following approximate locations: 241.0mm, 3352.0mm and 4152.0mm
[5 empty] | 221-49-17-3 |  | x
221-49-18-1
221-49-18-2
221-49-18-3
221-49-19-1
221-49-19-2
221-49-19-3
221-49-20-1
221-49-20-2
221-49-20-3
221-49-21-1
221-49-21-2
221-49-21-3
221-49-22-1
221-49-22-2
221-49-22-3

## Schedule Data
Updated: | Nov '19 WS
|  | T6:Begin UL Cable Fab | HO:RQD Finish UL Cable Fab |  | T5:Begin Coil | T5:Finish Coil |  | T5:Begin Magnet Ass'y | T5:Finish Magnet Ass'y |  | AVAIL:Begin Magnet Vert Test | T6:Finish Magnet Vert Test |  | Ass'y LMQXFA |  |  | CryoStating LMQXFA |  |  | T6:Begin LQXFA | T6:Finish LQXFA
Cable |  | P6 Schedule |  | Coils (FNAL/BNL) | P6 Schedule |  | Magnet Assembly | P6 Schedule |  | Magnet Vertical Test | P6 Schedule |  | Cold Mass | P6 Schedule |  | Cryo-Assembly | P6 Schedule |  | Horizontal Test | P6 Schedule
P6 Label | Serial # | Start | Finish | P6 Label/Serial # | Start | Finish | P6 Label | Start | Finish | P6 Label | Start | Finish | P6 Label | Start | Finish | P6 Label | Start | Finish | P6 Label | Start | Finish
1 | P43OL1095 | 11-Jan-18 A | 14-Sep-18 A | QXFA-108 | 20-Nov-17 A | 25-May-18 A | MQXFA-1b | 26-Oct-18 A | 22-Mar-2019 A | MQXFA-02 | 01-Aug-18 A | 06-Feb-2019 A | LMQXFA-P | 2020-03-03 | 2020-08-12 | CryoStating LMQXFA-01 (L) | 2020-11-18 | 2021-02-18 | Horizontal Test Cryo-Ass'y LQXFA/B-01 | 2021-02-19 | 2021-06-04
2 | P43OL1096 | 19-Jan-18 A | 31-Aug-18 A | QXFA-109 | 31-Jan-18 A | 13-Jul-18 A | MQXFA-03 | 25-Mar-2019 A | 20-Sep-2019 A | MQXFA-1b | 01-Apr-2019 A | 08-Jul-2019 A | LMQXFA-01 | 2020-09-01 | 2020-11-17 | CryoStating LMQXFA-02 (L) | 2021-05-07 | 2021-07-12 | Horizontal Test Cryo-Ass'y LQXFA/B-02 | 2022-04-12 | 2022-07-27
3 | P43OL1097 | 06-Feb-18 A | 31-Aug-18 A | QXFA-110 | 23-Apr-18 A | 31-Aug-18 A | MQXFA-04 | 20-Sep-2019 A | 2020-03-04 | MQXFA-03 | 01-Oct-2019 A | 2020-01-29 | LMQXFA-02 | 2021-02-19 | 2021-05-06 | CryoStating LMQXFA-03 (L) | 2022-02-04 | 2022-04-07 | Horizontal Test Cryo-Ass'y LQXFA/B-03 | 2022-09-27 | 2022-12-12
4 | P43OL1098 | 09-Feb-18 A | 16-Aug-18 A | QXFP 06 | 18-Jun-18 A | 19-Oct-18 A | MQXFA-05 | 2020-02-04 | 2020-05-20 | MQXFA-04 | 2020-03-19 | 2020-06-17 | LMQXFA-03 | 2021-10-27 | 2021-12-23 | CryoStating LMQXFA-04 (L) | 2022-04-08 | 2022-06-10 | Horizontal Test Cryo-Ass'y LQXFA/B-04 | 2022-12-13 | 2023-02-22
5 | P43OL1099 | 22-Feb-18 A | 26-Aug-18 A | QXFA-111 | 02-Jul-18 A | 31-Oct-18 A | MQXFA-06 | 2020-04-07 | 2020-07-29 | MQXFA-05 | 2020-06-05 | 2020-08-17 | LMQXFA-04 | 2021-12-28 | 2022-02-24 | CryoStating LMQXFA-05 (L) | 2022-07-25 | 2022-09-26 | Horizontal Test Cryo-Ass'y LQXFA/B-05 | 2023-02-23 | 2023-04-28
6 | P43OL1100 | 27-Mar-18 A | 14-Sep-18 A | QXFA-112 | 20-Aug-18 A | 19-Dec-18 A | MQXFA-07 | 2020-06-05 | 2020-09-09 | MQXFA-06 | 2020-08-13 | 2020-10-14 | LMQXFA-05 | 2022-03-17 | 2022-05-11 | CryoStating LMQXFA-R1 Re-Work (L) | 2021-10-27 | 2022-02-03 | Horizontal Test Cryo-Ass'y LQXFA/B-R1 | 2022-02-04 | 2022-04-11
7 | P43OL1101 | 06-Apr-18 A | 14-Sep-18 A | QXFA-113 | 10-Oct-18 A | 27-Feb-2019 A | MQXFA-08 | 2020-08-17 | 2020-10-27 | MQXFA-07 | 2020-10-12 | 2021-01-07 | LMQXFA-R1 | 2021-08-31 | 2021-10-26 | CryoStating LMQXFA-R2 Re-Work (L) | 2023-05-16 | 2023-08-16 | Horizontal Test Cryo-Ass'y LQXFA/B-R2 | 2023-10-12 | 2023-12-19
8 | P43OL1102 | 17-Apr-18 A | 26-Aug-18 A | QXFA-114 | 03-Dec-18 A | 2019-12-02 | MQXFA-09 | 2020-09-29 | 2021-02-05 | MQXFA-08 | 2020-12-10 | 2021-03-08 | LMQXFA-R2 | 2023-03-14 | 2023-05-08 | CryoStating LMQXFA-06 (L) | 2022-11-09 | 2023-01-19 | Horizontal Test Cryo-Ass'y LQXFA/B-06 | 2023-05-31 | 2023-08-04
9 | P43OL1103 | 09-May-18 A | 31-Aug-18 A | QXFA-115 | 06-Feb-2019 A | 03-Sep-2019 A | MQXFA-10 | 2020-11-30 | 2021-03-25 | MQXFA-09 | 2021-02-22 | 2021-05-04 | LMQXFA-06 | 2022-09-14 | 2022-11-08 | CryoStating LMQXFA-07 (L) | 2023-03-14 | 2023-05-15 | Horizontal Test Cryo-Ass'y LQXFA/B-07 | 2023-08-07 | 2023-10-11
10 | P43OL1105 | 18-May-18 A | 14-Sep-18 A | QXFA-116 | 27-Mar-2019 A | 20-Sep-2019 A | MQXFA-11 | 2021-01-15 | 2021-05-14 | MQXFA-10 | 2021-04-20 | 2021-07-01 | LMQXFA-07 | 2023-01-17 | 2023-03-13 | CryoStating LMQXFA-08 (L) | 2023-08-17 | 2023-10-19 | Horizontal Test Cryo-Ass'y LQXFA/B-08 | 2023-12-20 | 2024-02-29
11 | P43OL1106 | 30-May-18A | 11-Sep-18 A | QXFA-117 | 08-May-2019 A | 07-Nov-2019 A | MQXFA-12 | 2021-03-03 | 2021-08-02 | MQXFA-11 | 2021-06-17 | 2021-08-30 | LMQXFA-08 | 2023-05-11 | 2023-07-07 | CryoStating LMQXFA-09 (L) | 2023-10-20 | 2023-12-27 | Horizontal Test Cryo-Ass'y LQXFA/B-09 | 2024-04-01 | 2024-07-24
12 | P43OL1107 | 22-Jun-18 A | 14-Sep-18 A | QXFA-118 | 19-Jul-2019 A | 04-Sep-2019 A | MQXFA-13 | 2021-05-18 | 2021-09-30 | MQXFA-12 | 2021-08-17 | 2021-10-27 | LMQXFA-09 | 2023-08-02 | 2023-09-27 | CryoStating LMQXFA-10 (L) | 2023-12-28 | 2024-03-04 | Horizontal Test Cryo-Ass'y LQXFA/B-10 | 2024-07-25 | 2024-11-15
13 | P43OL1111 | 27-Aug-18 A | 12-Feb-2019 A | QXFA-119 | 12-Sep-2019 A | 2020-01-03 | MQXFA-14 | 2021-07-19 | 2021-11-19 | MQXFA-13 | 2021-10-15 | 2021-12-30 | LMQXFA-10 | 2023-10-26 | 2023-12-26
14 | P43OL1112 | 05-Sep-18 A | N | QXFA-120 | 28-Oct-2019 A | 2020-01-02 | MQXFA-15 | 2021-09-08 | 2022-02-04 | MQXFA-14 | 2021-12-15 | 2022-03-02
15 | P43OL1113 | 20-Sep-18 A | 11-Apr-2019 A | QXFA-121 | 29-Nov-2019 A | 2020-04-03 | MQXFA-16 | 2021-11-15 | 2022-04-05 | MQXFA-15 | 2022-02-21 | 2022-04-28
16 | P43OL1114 | 01-Oct-18 A | 11-Apr-2019 A | QXFA-122 | 2020-02-03 | 2020-06-02 | MQXFA-17 | 2022-01-21 | 2022-05-25 | MQXFA-16 | 2022-04-20 | 2022-06-30
17 | P43OL1115 | 01-Oct-18 A | 31-Jul-2019 A | QXFA-123 | 2020-03-02 | 2020-06-30 | MQXFA-18 | 2022-03-14 | 2022-07-18 | MQXFA-17 | 2022-06-17 | 2022-08-29
18 | P43OL1116 | 06-Nov-18 A | 11-Apr-2019 A | QXFA-124 | 2020-03-30 | 2020-07-29 | MQXFA-19 | 2022-05-03 | 2022-09-23 | MQXFA-18 | 2022-08-16 | 2022-10-26
19 | P43OL1117 | 15-Nov-18 A | 11-Apr-2019 A | QXFA-125 | 2020-04-27 | 2020-08-26 | MQXFA-20 | 2022-07-12 | 2022-11-22 | MQXFA-19 | 2022-10-13 | 2022-12-28
20 | P43OL1120 | 11-Jan-19 A | 09-May-2019 A | QXFA-126 | 2020-05-26 | 2020-09-24 | MQXFA-21 | 2022-09-09 | 2023-01-20 | MQXFA-20 | 2022-12-13 | 2023-02-28
21 | P43OL1121 | 17-Jan-19 A | 2020-01-30 | QXFA-127 | 2020-06-23 | 2020-10-22 | MQXFA-22 | 2022-10-31 | 2023-05-02 | MQXFA-21 | 2023-02-15 | 2023-04-26
22 | P43OL1122 | 04-Feb-2019 A | 2020-01-30 | QXFA-128 | 2020-07-22 | 2020-11-19 | MQXFA-23 | 2023-02-17 | 2023-05-18 | MQXFA-22 | 2023-05-17 | 2023-07-28
23 | P43OL1123 | 27-Feb-2019 A | 25-Sep-2019 A | QXFA-129 | 2020-08-19 | 2020-12-21 | MQXFA-R1 | 2023-03-31 | 2023-06-05
24 | P43OL1124 | 01-Mar-2019 A | 25-Sep-2019 A | QXFA-130 | 2020-09-15 | 2021-01-21 | MQXFA-R2 | 2023-05-12 | 2023-07-18
25 | P43OL1125 | 01-Mar-2019 A | 25-Sep-2019 A | QXFA-131 | 2020-10-09 | 2021-02-16 | MQXFA-R3 | 2023-06-26 | 2023-08-29
26 | P43OL1126 | 15-Mar-2019 A | 2020-01-30 | QXFA-132 | 2020-11-04 | 2021-03-12 | MQXFA-R4 | 2023-08-08 | 2023-10-11
27 | P43OL1127 | 19-Mar-2019 A | 2020-01-30 | QXFA-133 | 2020-12-02 | 2021-04-07
28 | P43OL1128 | 10-Apr-2019 A | 2020-01-30 | QXFA-134 | 2020-12-30 | 2021-05-03
29 | P43OL1129 | 16-Apr-2019 A | 2020-01-30 | QXFA-135 | 2021-01-28 | 2021-05-27
30 | P43OL1130 | 18-Apr-2019 A | 2020-01-30 | QXFA-136 | 2021-02-23 | 2021-06-23
31 | P43OL1131 | 13-May-2019 A | 2020-01-30 | QXFA-137 | 2021-03-19 | 2021-07-20
32 | P43OL1132 | 22-May-2019 A | 2020-01-30 | QXFA-138 | 2021-04-14 | 2021-08-13
33 | P43OL1133 | 31-May-2019 A | 2020-01-30 | QXFA-139 | 2021-05-10 | 2021-09-09
34 | P43OL1134 | 17-Jun-2019 A | 2020-02-17 | QXFA-140 | 2021-06-04 | 2021-10-05
35 | P43OL1135 | 01-Jul-2019 A | 2020-02-17 | QXFA-141 | 2021-06-30 | 2021-10-29
36 | P43OL1136 | 19-Aug-2019 A | 2020-02-17 | QXFA-142 | 2021-07-27 | 2021-11-24
37 | P43OL1137 | 23-Aug-2019 A | 2020-03-16 | QXFA-143 | 2021-08-20 | 2021-12-22
38 | P43OL1138 | 30-Aug-2019 A | 2020-03-16 | QXFA-144 | 2021-09-16 | 2022-01-24
39 | P43OL1139 | 18-Nov-2019 A | 2020-05-18 | QXFA-145 | 2021-10-12 | 2022-02-17
40 | P43OL1140 | 25-Nov-2019 A | 2020-03-16 | QXFA-146 | 2021-11-05 | 2022-03-15
41 | P43OL1141 | 09-Dec-2019 A | 2020-03-16 | QXFA-147 | 2021-12-03 | 2022-04-08
42 | P43OL1142 | 16-Dec-2019 A | 2020-03-19 | QXFA-148 | 2022-01-04 | 2022-05-04
43 | P43OL1143 | 2020-01-16 | 2020-04-22 | QXFA-149 | 2022-01-31 | 2022-05-31
44 | P43OL1144 | 2020-01-28 | 2020-04-22 | QXFA-150 | 2022-02-24 | 2022-06-24
45 | P43OL1145 | 2020-02-06 | 2020-04-27 | QXFA-151 | 2022-03-22 | 2022-07-21
46 | P43OL1146 | 2020-03-06 | 2020-06-02 | QXFA-152 | 2022-04-15 | 2022-08-16
47 | P43OL1147 | 2020-03-17 | 2020-06-05 | QXFA-153 | 2022-05-11 | 2022-09-12
48 | P43OL1148 | 2020-03-26 | 2020-07-01 | QXFA-154 | 2022-06-07 | 2022-10-06
49 | P43OL1149 | 2020-04-06 | 2020-07-01 | QXFA-155 | 2022-07-01 | 2022-11-01
50 | P43OL1150 | 2020-04-15 | 2020-07-07 | QXFA-156 | 2022-07-28 | 2022-11-29
51 | P43OL1151 | 2020-04-24 | 2020-07-31 | QXFA-202 | 04-Sep-18 A | 27-Feb-2019 A
52 | P43OL1152 | 2020-05-05 | 2020-07-31 | QXFA-203 | 15-Oct-18 A | 21-May-2019 A
53 | P43OL1153 | 2020-05-14 | 2020-08-05 | QXFA-204 | 03-Jan-19 A | 21-May-2019 A
54 | P43OL1154 | 2020-05-26 | 2020-08-31 | QXFA-205 | 05-Mar-2019 A | 25-Mar-2019 A
55 | P43OL1155 | 2020-06-04 | 2020-08-31 | QXFA-206 | 01-Apr-2019 A | 26-Sep-2019 A
56 | P43OL1156 | 2020-06-15 | 2020-09-03 | QXFA-207 | 01-May-2019 A | 08-Nov-2019 A
57 | P43OL1157 | 2020-06-24 | 2020-09-30 | QXFA-208 | 04-Jun-2019 A | 04-Sep-2019 A
58 | P43OL1158 | 2020-07-06 | 2020-09-30 | QXFA-209 | 28-Aug-2019 A | 2020-01-24
59 | P43OL1159 | 2020-07-15 | 2020-10-05 | QXFA-210 | 08-Oct-2019 A | 2020-02-27
60 | P43OL1160 | 2020-07-24 | 2020-10-29 | QXFA-211 | 12-Nov-2019 A | 2020-04-03
61 | P43OL1161 | 2020-08-04 | 2020-10-29 | QXFA-212 | 2020-01-06 | 2020-05-04
62 | P43OL1162 | 2020-08-13 | 2020-11-03 | QXFA-213 | 2020-02-04 | 2020-06-02
63 | P43OL1163 | 2020-08-24 | 2020-12-01 | QXFA-214 | 2020-03-03 | 2020-06-30
64 | P43OL1164 | 2020-09-02 | 2020-12-01 | QXFA-215 | 2020-03-31 | 2020-07-29
65 | P43OL1165 | 2020-09-14 | 2020-12-04 | QXFA-216 | 2020-04-28 | 2020-08-26
66 | P43OL1166 | 2020-09-23 | 2021-01-05 | QXFA-217 | 2020-05-27 | 2020-09-24
67 | P43OL1167 | 2020-10-02 | 2021-01-05 | QXFA-218 | 2020-06-24 | 2020-10-22
68 | P43OL1168 | 2020-10-13 | 2021-01-08 | QXFA-219 | 2020-07-21 | 2020-11-17
69 | P43OL1169 | 2020-10-22 | 2021-02-04 | QXFA-220 | 2020-08-14 | 2020-12-15
70 | P43OL1170 | 2020-11-02 | 2021-02-04 | QXFA-221 | 2020-09-10 | 2021-01-14
71 | P43OL1171 | 2020-11-11 | 2021-02-09 | QXFA-222 | 2020-11-13 | 2021-03-22
72 | P43OL1172 | 2020-11-20 | 2021-03-05 | QXFA-223 | 2020-12-11 | 2021-04-15
73 | P43OL1173 | 2020-12-03 | 2021-03-05 | QXFA-224 | 2021-01-12 | 2021-05-11
74 | P43OL1174 | 2020-12-14 | 2021-03-10 | QXFA-225 | 2021-02-08 | 2021-06-07
75 | P43OL1175 | 2020-12-23 | 2021-04-05 | QXFA-226 | 2021-03-04 | 2021-07-01
76 | P43OL1176 | 2021-01-07 | 2021-04-05 | QXFA-227 | 2021-03-30 | 2021-07-28
77 | P43OL1177 | 2021-01-19 | 2021-04-08 | QXFA-228 | 2021-04-23 | 2021-08-23
78 | P43OL1178 | 2021-01-28 | 2021-05-04 | QXFA-229 | 2021-05-19 | 2021-09-17
79 | P43OL1179 | 2021-02-08 | 2021-05-04 | QXFA-230 | 2021-06-15 | 2021-10-13
80 | P43OL1180 | 2021-02-17 | 2021-05-07 | QXFA-231 | 2021-07-12 | 2021-11-08
81 | P43OL1181 | 2021-02-26 | 2021-06-03 | QXFA-232 | 2021-08-05 | 2021-12-06
82 | P43OL1182 | 2021-03-09 | 2021-06-03 | QXFA-233 | 2021-08-31 | 2022-01-05
83 | P43OL1183 | 2021-03-18 | 2021-06-08 | QXFA-234 | 2021-09-27 | 2022-02-01
84 | P43OL1184 | 2021-03-29 | 2021-07-02 | QXFA-235 | 2021-10-21 | 2022-02-25
85 | P43OL1185 | 2021-04-07 | 2021-07-09 | QXFA-236 | 2021-11-16 | 2022-03-23
86 | P43OL1186 | 2021-04-26 | 2021-07-16 | QXFA-237 | 2021-12-14 | 2022-04-18
87 | P43OL1187 | 2021-05-05 | 2021-08-11 | QXFA-238 | 2022-01-13 | 2022-05-12
88 | P43OL1188 | 2021-05-14 | 2021-08-11 | QXFA-239 | 2022-02-09 | 2022-06-08
89 | P43OL1189 | 2021-05-25 | 2021-08-16 | QXFA-240 | 2022-03-07 | 2022-07-05
90 | P43OL1190 | 2021-06-22 | 2021-09-28 | QXFA-241 | 2022-03-31 | 2022-07-29
91 | P43OL1191 | 2021-07-01 | 2021-09-28 | QXFA-242 | 2022-04-26 | 2022-08-24
92 | P43OL1192 | 2021-07-13 | 2021-10-01 | QXFA-243 | 2022-05-20 | 2022-09-20
93 | P43OL1193 | 2021-07-22 | 2021-11-10 | QXFA-244 | 2022-06-16 | 2022-10-14
94 | P43OL1194 | 2021-08-25 | 2021-11-19 | QXFA-245 | 2022-07-13 | 2022-11-09
95 | P43OL1195 | 2021-09-03 | 2021-11-24 | QXFA-246 | 2022-08-08 | 2022-12-07
96 | P43OL1196 | 2021-09-15 | 2022-01-11 | QXFA-247 | 2022-09-01 | 2023-01-06
97 | P43OL1197 | 2021-09-24 | 2022-01-19 | QXFA-248 | 2022-09-28 | 2023-02-02
98 | P43OL1198 | 2021-10-28 | 2022-01-26
99 | P43OL1199 | 2021-11-08 | 2022-02-21
100 | P43OL1200 | 2021-11-17 | 2022-02-21
101 | P43OL1201 | 2021-11-30 | 2022-02-24
102 | P43OL1202 | 2021-12-09 | 2022-03-11

## Total EAC Per CA
CA |  | ΔEAC ($K) | ΔBAC ($K) | Net Cost I ($K)
302.2.02 | Strand | 940 |  | 940
302.2.03 | Cable | 208.8889 | 0 | 208.8889
302.2.04 | Coil Parts | 0 |  | 0
302.2.05 | FNAL Coils | 675.4286 | -394 | 281.4286
302.2.06 | BNL Coils | 324.5714 | -506.3314 | -181.76
| TOTAL | 2148.8889 | -900.3314 | 1248.5575
With LOE Adjustment
CA |  | ΔEAC ($K)
302.2.02 | Strand | 940
302.2.03 | Cable | 208.8889
302.2.04 | Coil Parts | 0
302.2.05 | FNAL Coils | 1185.4286 |  |  | September 2019 Adjustments
302.2.06 | BNL Coils | 494.5714
| TOTAL | 2828.8889

## LOE Adjustment
LOE Adjustment
CABLES
no LOE adjustment due to 3 month float on these activities
COILS
#rejected coils above yield assumption @FNAL | #rejected coils above yield assumption @BNL | Coils/month production rate | Added LOE duration | LOE Monthly Burn Rate K$ | Total LOE Adjustment K$ | %FNAL | %BNL | Total FNAL LOE Adjust K$ | Total BNL LOE Adjust K$
3 | 1 | 2 | 2 | 340 | 680 | 75% | 25% | 510 | 170
MAGNETS

## Cable EAC
From Mapping Table |  |  | Cable CAM Input |  | Cable ΔEAC, ΔBAC |  |  | Cable Cumulative ΔEAC, ΔBAC
| Accepted |  | Assigned | % Finished | ΔEAC | ΔEAC | ΔBAC | EAC | EAC | EAC | ΔBAC | Net Cost I | Assumed Failure Legend
P6 Label/Serial # | Actual | P6 Assum. | Assumed Failure? | when rejected | Strand | Cable | Cable | Strand | Cable | Project | Project | (ΔEAC+ΔBAC) | P | Planned failure that does not fail
1 | Y | 0 | - | 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | Unplanned failure that does not reassign a planned future failure as a usable coil
2 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Unplanned failure that reassigns a planned future failure as a usable coil
3 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | actual = planned
4 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Y | N | P | 100% | -235 | -52.2222 | 0 | -235 | -52.2222 | -287.2222 | 0 | -287.2222
12 | Y | 0 | - | 100% | 0 | 0 | 0 | -235 | -52.2222 | -287.2222 | 0 | -287.2222
13 | Y | 0 | - | 100% | 0 | 0 | 0 | -235 | -52.2222 | -287.2222 | 0 | -287.2222
14 | N | 0 | N | 100% | 235 | 52.2222 | 0 | 0 | 0 | 0 | 0 | 0
15 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 0 | N | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Y | N | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Y | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 0 | N | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 0 | N | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 0 | N | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 0 | N | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 0 | N | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 0 | N | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 0 | 0 | - | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0

## FNAL Coil EAC
From Mapping Table |  |  | FNAL Coil CAM Input |  |  | FNAL Coil ΔEAC, ΔBAC |  |  |  |  | FNAL Coil Cumulative ΔEAC, ΔBAC
| Accepted |  | Assigned | % Finished | % Recovered | ΔEAC | ΔEAC | ΔEAC | ΔEAC | ΔBAC | ΔEAC | ΔEAC | ΔEAC | ΔEAC | ΔEAC | ΔBAC | Net Cost I | Assumed Failure Legend
P6 Label/Serial # | Actual | P6 Assum. | Assumed Failure? | when rejected | Coil Parts | Strand | Cable | Parts | Coil Fab | Coil Fab | Strand | Cable | Parts | Coil | Project | Project | (ΔEAC+ΔBAC) | P | Planned failure that does not fail
QXFA-108 | N | N | Y | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | Unplanned failure that does not reassign a planned future failure as a usable coil
QXFA-109 | Q | 0 | N | 100% | 0% | 235 | 52.2222 | 48 | 225.1429 | 0 | 235 | 52.2222 | 48 | 225.1429 | 560.3651 | 0 | 560.3651 | Y | Unplanned failure that reassigns a planned future failure as a usable coil
QXFA-110 | Y | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | 48 | 225.1429 | 560.3651 | 0 | 560.3651 | - | actual = planned
QXFP 06 | Y | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | 48 | 225.1429 | 560.3651 | 0 | 560.3651
QXFA-111 | Y | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | 48 | 225.1429 | 560.3651 | 0 | 560.3651
QXFA-112 | CY-AF | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | 48 | 225.1429 | 560.3651 | 0 | 560.3651
QXFA-113 | CY-AF | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | 48 | 225.1429 | 560.3651 | 0 | 560.3651
QXFA-114 | Q | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | 48 | 225.1429 | 560.3651 | 0 | 560.3651
QXFA-115 | CY-AF | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | 48 | 225.1429 | 560.3651 | 0 | 560.3651
QXFA-116 | CY-AF | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | 48 | 225.1429 | 560.3651 | 0 | 560.3651
QXFA-117 | CY-AF | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | 48 | 225.1429 | 560.3651 | 0 | 560.3651
QXFA-118 | N | 0 | N | 20% | 100% | 235 | 52.2222 | 0 | 225.1429 | -180.1143 | 470 | 104.4444 | 48 | 450.2857 | 1072.7302 | -180.1143 | 892.6159
QXFA-119 | CY-F99% | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 470 | 104.4444 | 48 | 450.2857 | 1072.7302 | -180.1143 | 892.6159
QXFA-120 | Q | 0 | N | 5% | 100% | 235 | 52.2222 | 0 | 225.1429 | -213.8857 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-121 | Q-75% | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-122 | CY-F33% | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-123 | CY-F15% | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-124 | 0 | N | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-125 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-126 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-127 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-128 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-129 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-130 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-131 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-132 | 0 | N | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-133 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-134 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-135 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-136 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-137 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-138 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-139 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-140 | 0 | N | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-141 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-142 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-143 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-144 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-145 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-146 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-147 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-148 | 0 | N | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-149 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-150 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-151 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-152 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-153 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-154 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-155 | 0 | N | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
QXFA-156 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 705 | 156.6667 | 48 | 675.4286 | 1585.0952 | -394 | 1191.0952
0

## BNL Coil EAC
From Mapping Table |  |  | BNL Coil CAM Input |  |  | BNL Coil ΔEAC, ΔBAC |  |  |  |  | BNL Coil Cumulative ΔEAC, ΔBAC
| Accepted |  | Assigned | % Finished | % Recovered | ΔEAC | ΔEAC | ΔEAC | ΔEAC | ΔBAC | ΔEAC | ΔEAC | ΔEAC | ΔEAC | ΔEAC | ΔBAC | Net Cost I | Assumed Failure Legend
P6 Label/Serial # | Actual | P6 Assum. | Assumed Failure? | when rejected | Coil Parts | Strand | Cable | Parts | Coil Fab | Coil Fab | Strand | Cable | Parts | Coil | Project | Project | (ΔEAC+ΔBAC) | P | Planned failure that does not fail
QXFA-202 | Y | 0 | - | 50% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | Unplanned failure that does not reassign a planned future failure as a usable coil
QXFA-203 | CY-AF | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | Unplanned failure that reassigns a planned future failure as a usable coil
QXFA-204 | Y | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | actual = planned
QXFA-205 | N | N | Y | 25% | 100% | 0 | 0 | -48 | 0 | -243.4286 | 0 | 0 | -48 | 0 | -48 | -243.4286 | -291.4286
QXFA-206 | CY-AF | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48 | 0 | -48 | -243.4286 | -291.4286
QXFA-207 | CY-AF | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48 | 0 | -48 | -243.4286 | -291.4286
QXFA-208 | N | 0 | N | 19% | 100% | 235 | 52.2222 | 0 | 324.5714 | -262.9029 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-209 | CY-AF | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-210 | Q | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-211 | CY-50% | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-212 | CY-28% | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-213 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-214 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-215 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-216 | 0 | N | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-217 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-218 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-219 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-220 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-221 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-222 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-223 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-224 | 0 | N | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-225 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-226 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-227 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-228 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-229 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-230 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-231 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-232 | 0 | N | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-233 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-234 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-235 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-236 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-237 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-238 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-239 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-240 | 0 | N | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-241 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-242 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-243 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-244 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-245 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-246 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-247 | 0 | N | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622
QXFA-248 | 0 | 0 | - | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 235 | 52.2222 | -48 | 324.5714 | 563.7937 | -506.3314 | 57.4622

## Cost Per Part
| Cost ($K)* | Yield Assumption | Cost/Yield
Strand Unit Length | 235 | 1 | 235
Cable Fabrication Unit Length | 47 | 0.9 | 52.2222
1 set of Coil Parts | 48 | 1 | 48
1 FNAL Coil Fabrication | 197 | 0.875 | 225.1429
1 BNL Coil Fabrication | 284 | 0.875 | 324.5714
1 MQXFA Magnet Structure Parts | 973 | 1 | 973
1 MQXFA Magnet Fabrication | 243 | 0.85 | 285.8824
1 Magnet Structure Disassembly | 34 | 1 | 34
1 Vertical Test | 603 | 1 | 603
1 Cold Mass Assembly Fabrication | 253 | 1 | 253
1 Cold Mass Rework | 177 | 1 | 177
1 Cryostating | 219 | 0.9 | 243.3333
1 Disassembly of Failed Cryoassembly | 102 | 1 | 102
1 Horizontal Test Trained at BNL | 188 | 1 | 188
1 Horizontal Test Trained at FNAL | 303 | 1 | 303
*Cost is fully loaded and escalated to end of production
updated with August 2019 Baseline