## schedule March 2023
WP3 schedule December 2022 |  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
MQXF SHORT |  | MQXFS1 (RRP LARP) | 2015 4: S; 2015 5: M; 2016 3: F; 2016 9: F; 2017 5: F
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5; 2018 0; 2019 7 to 2019 0; 2021 5 to 2021 6; 2021 0 to 2021 2; 2023 1 to 2023 5
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0; 2019 5 to 2019 8; 2019 0; 2020 2 to 2020 3; 2020 7 to 2020 0
MQXFSM2 (Mirror AUP) | bar: 2019 5 to 2019 2
MQXFS7 (2 RRP 2 PIT CERN) | bar: 2019 1 to 2020 2; 2020 7 to 2020 8; 2020 1 to 2020 2; 2021 2; 2021 6; 2021 8 to 2021 1; 2022 1; 2022 5 to 2022 2
MQXFS8 (mini-swap) | bar: 2021 1 to 2022 3; 2022 6 to 2022 7
Q1/3 |  | Q1/3 4.0 m proto 1 MQXFAP1 | bar: 2015 5 to 2017 2; 2019 1 to 2019 7
Q1/3 4.2 m proto 2 MQXFAP2 - LXQFP | bar: 2016 7 to 2018 1
Q1/3 4.2 m proto 3 MQXFA03 | bar: 2018 3 to 2020 1
|  | Q1/3-series MQXFA04 - LQXFA01 (Q1) | 2020 8: B; 2022 2: F; 2023 4: D; 2023 6: C
Q1/3-series MQXFA05 | bar: 2019 2 to 2020 3; 2020 7; 2021 4 to 2021 5; 2022 4 to 2022 6
|  | Q1/3-series MQXFA06 - LQXFA02 (Q3) | 2021 6: B; 2023 6: F; 2023 0: D
Q1/3-series MQXFA07 | bar: 2019 2 to 2020 3; 2020 7 to 2021 1; 2021 8 to 2021 9; 2023 1 to 2023 2; 2023 7 to 2023 8
Q1/3-series MQXFA08 | bar: 2020 7 to 2020 2; 2021 4 to 2021 6; 2021 0 to 2022 1; 2022 4 to 2022 5; 2022 1 to 2022 2
|  | Q1/3-series MQXFA09 - LQXFA09 | 2025 0: F; 2026 2: D; 2026 5: V
|  | Q1/3-series MQXFA10 - LQXFA03 | 2022 6: B; 2023 1: F; 2024 2: D; 2024 5: V
Q1/3-series MQXFA11 | bar: 2021 1 to 2021 6; 2022 4 to 2022 6; 2022 9 to 2022 0
|  | Q1/3-series MQXFA12 - LQXFA04 | 2023 1: B; 2024 2: F; 2024 5: D; 2024 7: C; 2024 1: V
Q1/3-series MQXFA13 | bar: 2021 5 to 2021 9; 2022 8 to 2022 9; 2023 3 to 2023 4
|  | Q1/3-series MQXFA14 - LQXFA05 | 2023 5: B; 2024 4: F; 2024 8: D; 2025 6: V
Q1/3-series MQXFA15 | bar: 2021 9 to 2022 3; 2022 1 to 2022 2; 2023 7 to 2023 8
|  | Q1/3-series MQXFA16 - LQXFA06 | 2023 2: B; 2024 9: F; 2024 2: D; 2025 0: V
Q1/3-series MQXFA17 | bar: 2022 3 to 2022 7; 2023 4 to 2023 5; 2024 2 to 2024 3
|  | Q1/3-series MQXFA18 - LQXFA07 | 2024 3: B; 2024 1: F; 2025 2: D; 2025 2: V
Q1/3-series MQXFA19 | bar: 2022 8 to 2022 2; 2023 6 to 2023 7; 2024 5 to 2024 6
|  | Q1/3-series MQXFA20 - LQXFA08 | 2024 7: B; 2025 2: F; 2025 5: D; 2026 3: V
Q1/3-series MQXFA21 | bar: 2023 1 to 2023 5; 2023 1 to 2023 2
|  | Q1/3-series MQXFA22 - LQXFA10 | 2025 6: F; 2025 0: D; 2026 7: V
Q1/3-series MQXFA23 | bar: 2023 6 to 2023 0
Q2 cold mass | Q2 | MQXFBMT4 | bar: 2022 0 to 2023 6
MQXFBMT5 | bar: 2023 1 to 2023 4; 2023 6 to 2023 8
Q2-proto 1 MQXFBP1 | bar: 2016 4 to 2020 2; 2020 7 to 2020 8
Q2-proto 2 MQXFBP2 (Q2b) | bar: 2019 4 to 2020 3; 2020 7 to 2021 5; 2021 0 to 2021 2; 2022 7 to 2023 1; 2023 5 to 2023 1
Q2-proto 3 MQXFBP3 (Q2a) | bar: 2020 3; 2020 7 to 2021 4; 2021 1 to 2021 2; 2022 4 to 2023 5; 2023 8 to 2023 2
Q2-series 2 MQXFB02 | bar: 2020 8 to 2021 4; 2022 6 to 2023 8; 2023 0 to 2023 1; 2024 2 to 2025 3
Q2-series 3 MQXFB03 | bar: 2022 6 to 2024 6; 2024 8 to 2024 9; 2025 3 to 2025 6
Q2-series 4 MQXFB04 | bar: 2023 4 to 2024 7; 2025 7 to 2025 0
Q2-series 5 MQXFB05 | bar: 2023 9 to 2024 2; 2025 1 to 2026 2
Q2-series 6 MQXFB06 | bar: 2024 2 to 2025 5; 2026 2 to 2026 4
Q2-series 7 MQXFB07 | bar: 2024 7 to 2025 0; 2026 4 to 2026 6
Q2-series 8 MQXFB08 | bar: 2024 2 to 2026 3; 2026 7 to 2026 9
Q2-spare 1 MQXFB09 | bar: 2025 5 to 2026 1
Q2-spare 2 MQXFB10 | bar: 2025 0 to 2027 2
| MCBXFB | MCBXFBP1 - proto 1 (CIEMAT/CERN) | 2017 4: S; 2018 2: C; 2019 2: D; 2019 3: C; 2019 6: C; 2019 9: C
MCBXFBP2 - proto 2 (CIEMAT/CERN) | bar: 2019 3 to 2020 2; 2020 7 to 2020 9; 2022 1 to 2022 5
MCBXFB01 - series 1 (CIEMAT/CERN) | bar: 2020 3; 2020 7 to 2021 6
|  | MCBXFB02 - series 2 | 2021 3: T; 2022 8: D; 2022 9: C
MCBXFB03 - series 3 | bar: 2022 5 to 2022 1; 2023 2 to 2023 3
MCBXFB04 - series 4 | bar: 2022 1 to 2023 5
MCBXFB05 - series 5 | bar: 2023 2 to 2023 8
MCBXFB06 - series 6 | bar: 2023 5 to 2023 1
MCBXFB07 - series 7 | bar: 2023 8 to 2024 2
MCBXFB08 - series 8 | bar: 2023 1 to 2024 5
MCBXFB09 - spare 1 | bar: 2024 2 to 2024 8
|  | MCBXFB10 - spare 2 | 2024 0: D; 2024 1: C; 2024 2: Z
|  | MCBXFB11 - spare 3 | 2025 1: D; 2025 2: C; 2025 3: Z
|  | MCBXFB12 - spare 4 | 2025 4: D; 2025 5: C; 2025 6: Z
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
Corrector package | MCBXFA | MCBXFAP1 - string | bar: 2021 1 to 2023 2
|  | MCBXFA1 - series 1 | 2021 3: T; 2023 4: D; 2023 5: C; 2024 4: C; 2024 6: V
|  | MCBXFA2 - series 2 | 2023 8: D; 2023 9: C; 2024 2: C; 2025 2: V
|  | MCBXFA3 - series 3 | 2023 2: D; 2024 2: C; 2025 7: C; 2025 9: V
|  | MCBXFA4 - series 4 | 2024 4: D; 2024 5: C; 2026 2: C; 2026 4: V
|  | MCBXFA5 - spare 1 | 2024 8: D; 2024 9: C; 2026 1: C; 2026 2: Z
|  | MCBXFA6 - spare 2 | 2024 2: D; 2025 2: C; 2025 3: Z
| HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 8 to 2019 6; 2020 2; 2020 6 to 2020 7
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 0
MgB2 corrector - proto | bar: 2017 8 to 2018 1; 2019 4 to 2019 8
|  | Batch 1a (9 magnets) | 2019 1: T; 2020 9: L; 2020 1: L; 2020 2: L; 2021 1: D
Batch 1b (9 magnets) | bar: 2020 9 to 2021 5
Batch 2 (18 magnets) | bar: 2021 1 to 2022 3
|  | Batch 3 (18 magnets) | 2022 3: L; 2022 5: L; 2022 7: L; 2022 8: L; 2022 9: D; 2022 0: Z
D1 |  | MBXFS1 - short model 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
MBXFS2 - short model 2 | bar: 2017 1 to 2018 7; 2018 9
MBXFS3 - short model 3 | bar: 2018 6 to 2019 6; 2019 8 to 2019 9
|  | MBXFP1 - prototype | 2019 4: T; 2021 6: K; 2021 9: K; 2023 3: D; 2023 7: C
|  | MBXF1 - series 1 | 2023 3: K; 2024 2: D; 2024 7: C; 2025 7: V
|  | MBXF2 - series 2 | 2023 6: K; 2024 6: D; 2024 0: C; 2025 1: V
|  | MBXF3 - series 3 | 2024 3: K; 2025 2: D; 2025 6: C; 2026 5: V
|  | MBXF4 - series 4 | 2024 7: K; 2025 8: D; 2025 2: C; 2026 3: Z
|  | MBXF5 - spare 1 | 2023 0: K; 2024 0: D; 2025 2: C; 2026 2: V
|  | MBXF6 - spare 2 | 2025 3: K; 2026 2: D; 2026 6: C; 2026 8: Z
DCM |  | DCM - prototype | bar: 2022 1 to 2023 9
DCM - series 1 | bar: 2023 2 to 2024 4
DCM - series 2 | bar: 2024 6 to 2024 0
DCM - series 3 | bar: 2024 0 to 2025 2
DCM - series 4 | bar: 2025 2 to 2025 6
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
D2 cold mass | D2 | MBRDS1 - short model | bar: 2016 9; 2017 2 to 2019 2; 2019 5 to 2020 2; 2020 8
|  | MBRDP1 - prototype | 2018 0: T; 2021 0: D; 2022 9: C
|  | MBRD1 - series 1 | 2021 2: T*; 2023 8: D; 2024 5: C; 2024 8: V
|  | MBRD2 - series 2 | 2023 2: D; 2024 8: C; 2025 2: V
|  | MBRD3 - series 3 | 2024 5: D; 2025 2: C; 2025 7: V
|  | MBRD4 - series 4 | 2024 0: D; 2025 6: C; 2026 5: V
|  | MBRD5 - spare 1 | 2025 3: D; 2025 1: C; 2026 9: Z
|  | MBRD6 - spare 2 | 2025 7: D; 2026 3: C; 2026 2: Z
| D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDS2 - short model double aperture | bar: 2017 9 to 2018 5
MCBRDP1 - prototype | bar: 2018 6 to 2018 1; 2019 7 to 2019 9
|  | MCBRDP2 - prototype IHEP | 2020 6: I; 2020 9: D; 2020 0: C
MCBRDP3 - third prototype | bar: 2020 0 to 2021 3; 2021 5
MCBRDP4 - fourth prototype | bar: 2022 1 to 2022 6
|  | MCBRD01 - series 1 | 2020 8: T; 2021 8: I; 2021 2: D; 2022 3: U
|  | MCBRD02 - series 2 | 2022 3: I; 2022 5: D; 2022 6: C
MCBRD03 - series 3 | bar: 2022 8 to 2022 2; 2023 3
|  | MCBRD04 - series 4 | 2023 2: I; 2023 3: D; 2023 4: C
MCBRD05 - series 5 | bar: 2023 2 to 2023 4; 2023 9
MCBRD06 - series 6 | bar: 2023 4 to 2023 6; 2023 9
|  | MCBRD07 - series 7 | 2023 8: I; 2023 9: D; 2023 0: C
MCBRD08 - series 8 | bar: 2023 8 to 2023 0; 2024 5
MCBRD09 - spare 1 | bar: 2023 0 to 2023 2; 2024 5
MCBRD10 - spare 2 | bar: 2023 2 to 2024 2; 2024 5
MCBRD11 - spare 3 | bar: 2023 3 to 2023 7
MCBRD12 - spare 4 | bar: 2022 2 to 2023 4
MQYY |  | Q4 - short model | bar: 2016 9 to 2019 0; 2020 1 to 2020 2
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 2; 2020 7 to 2020 9; 2020 2 to 2021 1
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 2; 2020 7 to 2020 9; 2020 2 to 2021 1
|  |  | Magnet construction | [30 empty] | M |  | Mirror or single coil test | [24 empty] | C | Test at CERN
|  |  | Vertical test | [30 empty] | S |  | Slice (mechanical model) | [24 empty] | B | Test at BNL
|  |  | Cold mass assembly | [30 empty] | T |  | Contract signed | [24 empty] | F | Test at FNAL
|  |  | Cryostating | [30 empty] | D |  | Delivery at CERN | [24 empty] | S | Test at Saclay
|  |  | Horizontal test | [30 empty] | V |  | Delivery to vacuum | [24 empty] | L | Test at LASA
|  |  | Available for STRING | [30 empty] | Z |  | Delivery to storage | [24 empty] | K | Test at KEK
[61 empty] | U | Test at FREIA
[61 empty] | I | Test at IMP
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
| Q4 stdalone | 1 | bar: 2026 5 to 2026 0
2 | bar: 2026 1 to 2027 3
3 | bar: 2027 4 to 2027 7
4 | bar: 2027 8 to 2027 1
| MS Q10 | 1 | bar: 2026 5 to 2026 0
2 | bar: 2026 8 to 2027 1
3 | bar: 2026 1 to 2027 5
4 | bar: 2027 3 to 2027 8
21
59
40
Note on B136: Délio Ramos: Convert to stand-alone
Note on B140: Délio Ramos: Convert to stand-alone