## MQXF COILS
True date
MQXFA | [7 empty] | MQXFBP1
|  | Beginning | End | ok | coil n. | Rejected | Quarantine |  |  | Beginning | End | ok | coil n. | R | Q | P
|  | 2015-05-05 |  | 1 | p01 |  |  | Practice coil | Coil 001 | 2016-03-21 | Fri 20/01/17 | 1 | 1 |  |  | 1
|  | 2015-10-01 |  | 2 | p02 |  |  | Practice coil | Coil 002 | 2016-08-15 | Fri 23/09/16 (W&C) | 2 | 2 |  |  | 2
|  | 2016-01-06 |  | 3 | po3 |  |  | Practice coil | Coil 101 | 2016-10-03 | Fri 28/04/17 | 3 | 101 |  |  | 3
|  | 2016-03-07 |  | 4 | po4 |  |  | Practice coil | Coil 102 | 2016-11-07 | Wed 23/08/17 | 4 | 102 |  |  | 4
|  | 2016-05-05 |  | 5 | po5 |  |  | NC | Coil 103 | 2017-04-24 | Fri 20/10/17 | 5 | 103 | 5 |  | 5
|  | 2016-06-13 |  | 6 | po6 |  |  | MQXFBP1 | Coil 104 | 2017-06-19 | Mon 16/04/18 | 6 | 104
Quarantine | Coil QXFA101 | 2016-07-05 | Mon 07/08/17 |  | 101 |  | 7 | MQXFBP1 | Coil 105 | 2017-07-24 | Fri 29/06/18 | 7 | 105
MQXFAP2 | Coil QXFA102 | 2016-09-13 | Mon 16/10/17 | 8 | 102 |  |  | NC | Coil 106 | 2017-09-18 | Fri 22/09/17 (W) |  | 106 | 8
Rejected | Coil QXFA103 | 2016-10-31 | Fri 16/12/16 |  | 103 | 9 |  | MQXFBP1 | Coil 107 | 2017-11-13 | Fri 31/08/18 | 9 | 107
MQXFAP2 | Coil QXFA104 | 2017-01-27 | Wed 22/11/17 | 10 | 104 |  |  | MQXFBP1 | Coil 108 | 2018-02-05 | Fri 21/09/18 | 10 | 108
MQXFAP2 | Coil QXFA105 | 2017-03-23 | Fri 08/12/17 | 11 | 105 |  |  | NC | Coil 201 | 2018-03-19 | Fri 01/02/19 |  | 201 | 11
MQXFAP2 | Coil QXFA106 | 2017-05-25 | Thu 07/12/17 | 12 | 106 |  |  | Not tested | Coil 109 | 2018-05-21 | Fri 19/10/18 | 12 | 109
Not tested | Coil QXFA107 | 2017-08-07 | Tue 29/05/18 | 13 | 107 |  |  | Not tested | Coil 202 | 2018-10-01 | Fri 22/02/19 | 13 | 202
Not tested | Coil QXFA108 | 2017-12-06 | Wed 30/05/18 | 14 | 108 |  |  | Not tested | Coil 203 | 2018-11-09 | Fri 29/03/19 | 14 | 203
Quarantine | Coil QXFA109 | 2018-02-05 | Mon 16/07/18 |  | 109 |  | 15 | NC | Coil 204 | 2018-12-10 | Not finished |  | 204 | 15
MQXFAP3 | Coil QXFA110 | 2018-04-23 | Thu 23/08/18 | 16 | 110 |  |  | NC | Coil 205 | 2019-01-21 | Not finished |  | 205 | 16
MQXFAP3 | Coil QXFA111 | 2018-07-05 | Wed 31/10/18 | 17 | 111 |  |  | Not tested | 0.03 | 2019-07-18 | Not finished | 18 | 3 |  |  | 17
Not tested | Coil QXFA112 | 2018-08-22 | Tue 18/12/18 | 18 | 112 |  |  | Not tested | 110 | 2019-05-13 | Not finished | 17 | 110
Not tested | Coil QXFA113 | 2018-10-10 | Fri 15/02/19 | 19 | 113 |  |  | Not tested | 111 | Not started | Not finished
Quarantine | Coil QXFA114 | 2018-12-11 | Wed 03/04/19 |  | 114 |  | 20 | Not tested | 112 | Not started | Not finished
Quarantine | Coil QXFA115 | 2019-02-11 | Mon 03/06/19 |  | 115 |  | 21 | Not tested | 113 | Not started | Not finished
Not tested | Coil QXFA116 | 2019-03-26 | Not finished | 22 | 116 |  |  | Not tested | 114 | Not started | Not finished
Not tested | Coil QXFA117 | 2019-05-17 | Not finished | 23 | 117
Not tested | Coil QXFA118 | 2019-07-24 | Not finished | 24 | 118
MQXFAP3 | Coil QXFA202 | 2018-09-17 | Fri 15/02/19 | 1 | 202
Not tested | Coil QXFA203 | 2018-10-15 | Fri 15/03/19 | 2 | 203
MQXFAP3 | Coil QXFA204 | 2019-01-15 | Mon 15/04/19 | 3 | 204
Rejected | Coil QXFA205 | 2019-03-15 | Mon 15/04/19 |  | 205 | 4
Not tested | Coil QXFA206 | 2019-04-15 | Not finished | 5 | 206
Not tested | Coil QXFA207 | 2019-05-15 | Not finished | 6 | 207
Rejected | Coil QXFA208 | 2019-06-17 | Mon 15/07/19 |  | 208 | 7

## CIEMAT
|  | 2018 | 2019 | 2020 | 2021 | 2022
M1 | First MCBXFB prototype
M2 | Second MCBXFB prototype
M3 | Contract Award
M4 | Completion of first MCBXFB
M5 | Completion of second MCBXFB
M6 | Completion of first MCBXFA
M7 | Completion of 5 MCBXFB
M8 | Completion of 6 MCBXFA
M9 | Completion of 5 MCBXFB

## US coils January 2018
FNAL | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | True date
101 | [23 empty] | 2
102 | [23 empty] | 2
103
104 | [23 empty] | 2
105 | [23 empty] | 2 | [81 empty] | nc
106 | [98 empty] | 2015-05-05 | 1 | p01 |  | 1 | 2016-03-21 | 1
107 | [98 empty] | 2015-10-01 | 2 | p02 |  | 2 | 2016-08-15 | 2
108 | [37 empty] | 3 | [60 empty] | 2016-01-06 | 3 | po3 |  | 101 | 2016-10-03 | 3
109 | [37 empty] | 3 | [60 empty] | 2016-03-07 | 4 | po4 |  | 102 | 2016-11-07 | 4
110 | [37 empty] | 3 | [60 empty] | 2016-05-05 | 5 | po5 |  | 103 | 2017-04-24 | 5 | 5
111 | [37 empty] | 3 | [60 empty] | 2016-06-13 | 6 | po6 |  | 104 | 2017-06-19 | 6
112 | [40 empty] | 4 | [57 empty] | 2016-07-18 | 7 | 101 |  | 105 | 2017-07-24 | 7
113 | [40 empty] | 4 | [57 empty] | 2016-09-21 | 8 | 102 |  | 106 | 2017-09-18 | 8 | 8
114 | [45 empty] | 5 | [52 empty] | 2016-11-09 | 9 | 103 |  | 107 | 2017-11-13 | 9
115 | [45 empty] | 5 | [52 empty] | 2017-01-30 | 10 | 104 |  | 108 | 2018-02-05 | 10
116 | [98 empty] | 2017-04-05 | 11 | 105 |  | 201 | 2018-03-19 | 11 | 11
117 | [49 empty] | 6 | [48 empty] | 2017-05-25 | 12 | 106 |  | 109 | 2018-06-01 | 12
118 | [49 empty] | 6 | [48 empty] | 2017-08-07 | 13 | 107 |  | 202 | 2018-09-27 | 13
119 | [53 empty] | 7 | [44 empty] | 2017-12-06 | 14 | 108 |  | 203 | 2018-11-09 | 14
120 | [53 empty] | 7 | [44 empty] | 2018-02-07 | 15 | 109 |  | 204 | 2018-12-10 | 15
121 | [56 empty] | 8 | [41 empty] | 2018-04-24 | 16 | 110 |  | 205 | 2019-01-21 | 16
122 | [56 empty] | 8 | [41 empty] | 2018-07-05 | 17 | 111
123 | [58 empty] | 9 | [39 empty] | 2018-08-22 | 18 | 112
124 | [98 empty] | 2018-10-10 | 19 | 113
125 | [58 empty] | 9 | [38 empty] | 87 | 2018-12-11 | 20 | 114
126 | [60 empty] | 10 | [36 empty] | 76 | 2018-09-15 |  | 202 | 1
127 | [60 empty] | 10 | [36 empty] | 76 | 2018-10-15 |  | 203 | 2
128 | [62 empty] | 11
129 | [62 empty] | 11
130 | [64 empty] | 12
131 | [64 empty] | 12
132
133 | [66 empty] | 13
134 | [66 empty] | 13
135 | [68 empty] | 14
136 | [68 empty] | 14
137 | [70 empty] | 15
138 | [70 empty] | 15
139 | [72 empty] | 16
140
141 | [72 empty] | 16
142 | [74 empty] | 17
143 | [74 empty] | 17
144 | [76 empty] | 18
145 | [76 empty] | 18
146 | [78 empty] | 19
147 | [78 empty] | 19
148
149 | [80 empty] | 20
150 | [80 empty] | 20
151 | [82 empty] | 21
152 | [82 empty] | 21
153 | [84 empty] | 22
154 | [84 empty] | 22
155 | [86 empty] | 23
BNL | [24 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
[25 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
202 | [24 empty] | 2019 5: 4
203 | [24 empty] | 2019 5: 4
204 | [24 empty] | 2019 0: 5
205 | [24 empty] | 2019 0: 5
206 | [24 empty] | 2020 2: 6
207 | [24 empty] | 2020 2: 6
208
209 | [24 empty] | 2020 6: 7
210 | [24 empty] | 2020 6: 7
211 | [24 empty] | 2020 9: 8
212 | [24 empty] | 2020 9: 8
213 | [24 empty] | 2020 1: 9
214 | [24 empty] | 2020 1: 9
215 | [24 empty] | 2021 1: 10
216
217 | [24 empty] | 2021 1: 10
218 | [24 empty] | 2021 3: 11
219 | [24 empty] | 2021 3: 11
220 | [24 empty] | 2021 5: 12
221 | [24 empty] | 2021 5: 12
222 | [24 empty] | 2021 7: 13
223 | [24 empty] | 2021 7: 13
224
225 | [24 empty] | 2021 9: 14
226 | [24 empty] | 2021 9: 14
227 | [24 empty] | 2021 1: 15
228 | [24 empty] | 2021 1: 15
229 | [24 empty] | 2022 1: 16
230 | [24 empty] | 2022 1: 16
231 | [24 empty] | 2022 3: 17
232
233 | [24 empty] | 2022 3: 17
234 | [24 empty] | 2022 5: 18
235 | [24 empty] | 2022 5: 18
236 | [24 empty] | 2022 7: 19
237 | [24 empty] | 2022 7: 19
238 | [24 empty] | 2022 9: 20
239 | [24 empty] | 2022 9: 20
240
241 | [24 empty] | 2022 1: 21
242 | [24 empty] | 2022 1: 21
243 | [24 empty] | 2023 1: 22
244 | [24 empty] | 2023 1: 22
245 | [24 empty] | 2023 3: 23
246 | [24 empty] | 2023 3: 23
247
248 | [24 empty] | 2023 3: 23

## Advencement test
Type | Object | Date 11.21 | Progr 11.21 | Date 3.22 | Progr 3.22
1 | MQXFS1 | 2016-03-01 03:50 | 3 | 2016-03-01 03:50
2 | MQXFS3 | 2016-09-01 03:50 | 4 | 2016-09-01 03:50
3 | MQXFS5 | 2017-06-09 03:50 | 7 | 2017-06-09 03:50
4 | MQXFS4 | 2018-06-09 03:50 | 10 | 2018-06-09 03:50
5 | MQXFS6 | 2019-10-09 03:50 | 18 | 2019-10-09 03:50
6 | MQXFS7 | 2020-09-09 03:50 | 26 | 2020-09-09 03:50
7 | MQXFAP1 | 2017-06-09 03:50 | 6 | 2017-06-09 03:50
8 | MQXFAP2 | 2018-09-09 03:50 | 13 | 2018-09-09 03:50
9 | MQXFA03 | 2019-11-09 03:50 | 19 | 2019-11-09 03:50
10 | MQXFA04 | 2020-09-09 03:50 | 25 | 2020-09-09 03:50
11 | MQXFA05 | 2021-04-09 03:50 | 47 | 2021-04-09 03:50
12 | MQXFA06 | 2021-06-09 03:50 | 53 | 2021-06-09 03:50
13 | MQXFA07 | 2021-08-09 03:50 | 55 | 2021-08-09 03:50
14 | MQXFA08 | 2021-11-09 03:50 | 64 | 2021-11-09 03:50
15 | MQXFA09 | 2022-01-01 | 71
16 | MQXFA10 | 2022-03-01 | 78
17 | MQXFA11 | 2022-05-01 | 87
18 | MQXFA12 | 2022-07-01 | 101
19 | MQXFA13 | 2022-09-01 | 109
20 | MQXFA14 | 2022-11-01 | 113
21 | MQXFA15 | 2023-01-01 | 118
22 | MQXFA16 | 2023-03-01 | 122
23 | MQXFA17 | 2023-05-01 | 126
24 | MQXFA18 | 2023-07-01 | 131
25 | MQXFA19 | 2023-09-01 | 137
26 | MQXFA20 | 2023-11-01 | 139
27 | MQXFA21 | 2024-01-01 | 141
28 | MQXFA22 | 2024-03-01 | 144
29 | MQXFA23 | 2024-05-01 | 146
30 | MQXFBP1 | 2020-08-01 | 22 | 2020-08-01
31 | MQXFBP2 | 2021-03-01 | 38 | 2021-03-01
32 | MQXFB01 | 2022-03-01 | 79 | 2022-06-01
33 | MQXFB02 | 2022-07-01 | 102 | 2022-10-01
34 | MQXFB03 | 2023-05-01 | 127 | 2024-03-01
35 | MQXFB04 | 2023-08-01 | 133 | 2024-06-01
36 | MQXFB05 | 2024-01-01 | 142 | 2024-11-01
37 | MQXFB06 | 2024-07-01 | 148 | 2025-04-01
38 | MQXFB07 | 2024-11-01 | 150 | 2025-09-01
39 | MQXFB08 | 2025-05-01 | 152 | 2026-02-01
40 | MQXFB09 | 2025-09-01 | 153 | 2026-07-01
41 | MQXFB10 | 2026-03-01 | 154 | 2026-12-01
42 | MBXFS1 | 2016-03-01 | 2 | 2016-03-01
43 | MBXFS2 | 2018-07-01 | 11 | 2018-07-01
44 | MBXFS3 | 2019-08-01 | 17 | 2019-08-01
45 | MBXFP1 | 2021-06-01 | 49 | 2021-06-01
46 | MBXF1 | 2022-07-01 | 95
47 | MBXF2 | 2022-09-01 | 104
48 | MBXF3 | 2023-01-01 | 115
49 | MBXF4 | 2023-05-01 | 124
50 | MBXF5 | 2023-11-01 | 138
51 | MBXF6 | 2024-05-01 | 145
52 | MBRDS1 | 2019-01-01 | 16 | 2019-01-01
53 | MBRDP1 | 2022-07-01 | 94 | 2022-06-01
54 | MBRD1 | 2023-09-01 | 134 | 2023-10-01
55 | MBRD2 | 2023-12-01 | 140 | 2024-02-01
56 | MBRD3 | 2024-03-01 | 143 | 2024-06-01
57 | MBRD4 | 2024-06-01 | 147 | 2024-10-01
58 | MBRD5 | 2024-09-01 | 149 | 2025-02-01
59 | MBRD6 | 2024-12-01 | 151 | 2025-06-01
60 | MCBXFBP1 | 2018-12-01 | 15 | 2018-12-01
61 | MCBXFBP2 | 2020-09-01 | 23 | 2020-09-01
62 | MCBXFB01 | 2021-07-01 | 54 | 2021-07-01
63 | MCBXFB02 | 2022-01-01 | 66 | 2022-11-01
64 | MCBXFB03 | 2022-03-01 | 73 | 2023-02-01
65 | MCBXFB04 | 2022-05-01 | 86 | 2023-05-01
66 | MCBXFB05 | 2022-07-01 | 97 | 2023-08-01
67 | MCBXFB06 | 2022-09-01 | 105 | 2023-11-01
68 | MCBXFB07 | 2022-11-01 | 112 | 2024-02-01
69 | MCBXFB08 | 2023-01-01 | 117 | 2024-05-01
70 | MCBXFB09 | 2023-03-01 | 121 | 2024-08-01
71 | MCBXFB10 | 2023-05-01 | 125 | 2024-11-01
72 | MCBXFB11 | 2023-07-01 | 130 | 2025-02-01
73 | MCBXFB12 | 2023-09-01 | 136 | 2025-05-01
74 | MCBXFAP1 | 2022-04-01 | 81
75 | MCBXFA01 | 2022-07-01 | 96
76 | MCBXFA02 | 2022-11-01 | 111
77 | MCBXFA03 | 2023-01-01 | 116
78 | MCBXFA04 | 2023-03-01 | 120
79 | MCBXFA05 | 2023-06-01 | 129
80 | MCBXFA06 | 2023-09-01 | 135
81 | MCBRDP1 | 2018-11-01 | 14 | 2018-11-01
82 | MCBRDP2 | 2020-06-01 | 20 | 2020-06-01
83 | MCBRDP3 | 2021-05-01 | 48 | 2021-05-01
84 | MCBRDP4 | 2022-06-01 | 89 | 2022-06-01
85 | MCBRD01 | 2021-09-01 | 56 | 2021-09-01
86 | MCBRD02 | 2021-12-01 | 65
87 | MCBRD03 | 2022-02-01 | 72
88 | MCBRD04 | 2022-04-01 | 80
89 | MCBRD05 | 2022-06-01 | 88
90 | MCBRD06 | 2022-08-01 | 103
91 | MCBRD07 | 2022-10-01 | 110
92 | MCBRD08 | 2022-12-01 | 114
93 | MCBRD09 | 2023-02-01 | 119
94 | MCBRD10 | 2023-04-01 | 123
95 | MCBRD11 | 2023-06-01 | 128
96 | MCBRD12 | 2023-08-01 | 132
97 | MQSXFP1 | 2018-02-01 | 9 | 2018-02-01
98 | MQSXF1 | 2021-04-01 | 46 | 2021-04-01
99 | MQSXF2 | 2021-03-01 | 37 | 2021-03-01
100 | MQSXF3 | 2021-06-01 | 52 | 2021-06-01
101 | MQSXF4 | 2021-11-01 | 63 | 2022-03-01
102 | MQSXF5 | 2022-04-01 | 85 | 2022-06-01
103 | MQSXF6 | 2022-07-01 | 100 | 2022-10-01
104 | MCSXFP1 | 2016-02-01 | 1 | 2016-02-01
105 | MCSXF01 | 2020-11-01 | 28 | 2020-11-01
106 | MCSXF02 | 2021-03-01 | 36 | 2021-03-01
107 | MCSXF03 | 2021-01-01 | 32 | 2021-01-01
108 | MCSXF04 | 2021-04-01 | 42 | 2021-04-01
109 | MCSXF05 | 2021-04-01 | 43 | 2021-04-01
110 | MCSXF06 | 2021-06-01 | 51 | 2021-06-01
111 | MCSXF07 | 2021-09-01 | 59 | 2021-09-01
112 | MCSXF08 | 2022-01-01 | 69 | 2021-11-01
113 | MCSXF09 | 2022-04-01 | 84 | 2022-01-01
114 | MCSXF10 | 2022-07-01 | 99 | 2022-10-01
115 | MCSXF11 | 2022-09-01 | 106 | 2022-12-01
116 | MCSXF12 | 2022-09-01 | 107 | 2022-12-01
117 | MCOXFP1 | 2017-03-01 | 5 | 2017-03-01
118 | MCOXF01 | 2020-09-01 | 24 | 2020-09-01
119 | MCOXF02 | 2021-03-01 | 34 | 2021-03-01
120 | MCOXF03 | 2021-01-01 | 31 | 2021-01-01
121 | MCOXF04 | 2021-03-01 | 35 | 2021-03-01
122 | MCOXF05 | 2021-11-01 | 61 | 2021-11-01
123 | MCOXF06 | 2021-11-01 | 62 | 2022-01-01
124 | MCOXF07 | 2021-06-01 | 50 | 2021-06-01
125 | MCOXF08 | 2022-01-01 | 68 | 2022-01-01
126 | MCOXF09 | 2022-03-01 | 75 | 2022-03-01
127 | MCOXF10 | 2022-04-01 | 83 | 2022-06-01
128 | MCOXF11 | 2022-06-01 | 90 | 2022-08-01
129 | MCOXF12 | 2022-07-01 | 98 | 2022-12-01
130 | MCDXFP1 | 2017-09-01 | 8 | 2017-09-01
131 | MCDXF01 | 2020-06-01 | 21 | 2020-06-01
132 | MCDXF02 | 2020-11-01 | 27 | 2020-11-01
133 | MCDXF03 | 2021-01-01 | 30 | 2021-01-01
134 | MCDXF04 | 2021-04-01 | 39 | 2021-04-01
135 | MCDXF05 | 2021-04-01 | 40 | 2021-04-01
136 | MCDXF06 | 2021-04-01 | 41 | 2021-04-01
137 | MCDXF07 | 2021-09-01 | 57 | 2021-09-01
138 | MCDXF08 | 2021-09-01 | 58 | 2021-09-01
139 | MCDXF09 |  | 155
140 | MCDXF10 | 2022-01-01 | 67 | 2022-03-01
141 | MCDXF11 | 2022-03-01 | 74 | 2022-03-01
142 | MCDXF12 | 2022-04-01 | 82 | 2022-08-01
143 | MCTXFP1 | 2018-08-01 | 12 | 2018-08-01
144 | MCTXF1 | 2020-11-01 | 29 | 2020-11-01
145 | MCTXF2 | 2021-01-01 | 33 | 2021-01-01
146 | MCTXF3 | 2021-09-01 | 60 | 2021-09-01
147 | MCTXF4 | 2022-01-01 | 70 | 2021-11-01
148 | MCTXF5 | 2022-03-01 | 77 | 2022-06-01
149 | MCTXF6 | 2022-06-01 | 93 | 2022-08-01
150 | MCTSXF1 | 2021-04-01 | 44 | 2021-04-01
151 | MCTSXF2 | 2021-04-01 | 45 | 2021-04-01
152 | MCTSXF3 | 2022-03-01 | 76 | 2022-06-01
153 | MCTSXF4 | 2022-06-01 | 91 | 2022-10-01
154 | MCTSXF5 | 2022-06-01 | 92 | 2022-10-01
155 | MCTSXF6 | 2022-09-01 | 108 | 2022-12-01

## string
Status on 15 April 2021
| Coils | Magnet | Test V or H standalone | Cold mass
Q1a | DONE | DONE | OK | Ongoing
Q1b | DONE | DONE | OK
Q2a | DONE | DONE | 6.8 TeV limited
MCBXFB | DONE | DONE | OK**
MCBXFB | DONE | DONE | OK**
Q2b | DONE | DONE* | Jun.21*
Q3a | DONE | DONE | Apr.21 | July.21 (start)
Q3b | DONE | DONE | Jun.21
MCBXFA | May-Aug.21 | Sept.21 | Oct.21 | Nov.21 (start)
MQSXF | DONE | DONE | OK
MCSXF | DONE | DONE | OK
MCSSXF | DONE | DONE | OK
MCOXF | DONE | DONE | OK
MCOSXF | DONE | DONE | Apr.21
MCDXF | DONE | DONE | OK
MCDSXF | DONE | DONE | OK
MCTXF | DONE | DONE | OK
MCTSXF | DONE | DONE | Ongoing
D1 | DONE | May.21 | 2021-06-01 | July.21 (start)
Status on 29 July 2021
| Coils | Magnet | Test V or H standalone | Cold mass
Q1a | DONE | DONE | OK | Ongoing
Q1b | DONE | DONE | OK
Q2a | DONE | DONE | 7.0-6.8 TeV limited
MCBXFB | DONE | DONE | OK**
MCBXFB | DONE | DONE | OK**
Q2b | DONE | TBD | TBD
Q3a | DONE | DONE | OK | Nov.21 (start)
Q3b | DONE | DONE | OK
MCBXFA | Sept.21-Jan.22 | Jan.22 | Feb.22 | Mar.22
MQSXF | DONE | DONE | OK
MCSXF | DONE | DONE | OK
MCSSXF | DONE | DONE | OK
MCOXF | DONE | DONE | OK
MCOSXF | DONE | DONE | OK
MCDXF | DONE | DONE | OK
MCDSXF | DONE | DONE | OK
MCTXF | DONE | DONE | OK
MCTSXF | DONE | DONE | OK
D1 | DONE | DONE | OK, th. cycle in Sept.21 | September.21 (start)

## schedule September 2023
WP3 schedule September 2023 |  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
MQXF SHORT |  | MQXFS1 (RRP LARP) | 2015 4: S; 2015 5: M; 2016 3: F; 2016 9: F; 2017 5: F
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5; 2018 0; 2019 7 to 2019 0; 2021 5 to 2021 6; 2021 0 to 2021 2; 2023 1 to 2023 5
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0; 2019 5 to 2019 8; 2019 0; 2020 2 to 2020 3; 2020 7 to 2020 0
MQXFSM2 (Mirror AUP) | bar: 2019 5 to 2019 2
MQXFS7 (2 RRP 2 PIT CERN) | bar: 2019 1 to 2020 2; 2020 7 to 2020 8; 2020 1 to 2020 2; 2021 2; 2021 6; 2021 8 to 2021 1; 2022 1; 2022 5 to 2022 2; 2023 2; 2023 4; 2023 7
MQXFS8 (mini-swap) | bar: 2021 1 to 2022 3; 2022 6 to 2022 7
Q1/3 |  | Q1/3 4.0 m proto 1 MQXFAP1 | bar: 2015 5 to 2017 2; 2019 1 to 2019 7
Q1/3 4.2 m proto 2 MQXFAP2 - LXQFP | bar: 2016 7 to 2018 1
Q1/3 4.2 m proto 3 MQXFA03 | bar: 2018 3 to 2020 1
|  | Q1/3-series MQXFA04 - LQXFA01 (Q3) | 2020 8: B; 2021 3: 3; 2021 4: +; 2021 5: 4; 2023 3: F; 2023 2: D; 2024 3: C
Q1/3-series MQXFA05 | bar: 2019 2 to 2020 3; 2020 7; 2021 4 to 2021 5; 2022 4 to 2022 5
|  | Q1/3-series MQXFA06 - LQXFA02 (Q1) | 2021 6: B; 2022 5: 5; 2022 6: +; 2022 7: 6; 2024 1: F; 2024 6: D
Q1/3-series MQXFA07 | bar: 2019 2 to 2020 3; 2020 7 to 2021 1; 2021 8 to 2021 9; 2023 4 to 2023 5; 2023 2 to 2024 1
|  | Q1/3-series MQXFA08 - LQXFA04 | 2021 1: B; 2023 1: B; 2023 6: 8; 2023 7: +; 2023 8: 14; 2024 9: F; 2025 1: D; 2025 4: V
|  | Q1/3-series MQXFA09 - LQXFA07 | 2024 7: 7; 2024 8: +; 2024 9: 9; 2025 8: F; 2025 0: D; 2026 1: V
Q1/3-series MQXFA10 | bar: 2020 1 to 2021 4; 2021 0 to 2022 3; 2022 5 to 2022 7
|  | Q1/3-series MQXFA11 - LQXFA03 | 2022 9: B; 2023 1: 10; 2023 2: +; 2023 3: 11; 2024 6: F; 2024 0: D; 2025 5: V
Q1/3-series MQXFA12 | bar: 2021 3 to 2021 8; 2022 7 to 2022 2; 2023 9 to 2023 0; 2024 4 to 2024 5
Q1/3-series MQXFA13 | bar: 2021 5 to 2021 9; 2022 0 to 2023 2; 2023 4 to 2023 6; 2024 2 to 2024 3
|  | Q1/3-series MQXFA14 - LQXFA05 | 2023 7: B; 2023 2: 12; 2024 1: +; 2024 2: 13; 2025 1: F; 2025 5: D; 2025 8: V
Q1/3-series MQXFA15 | bar: 2021 9 to 2022 3; 2023 3 to 2023 4; 2023 1 to 2023 2
|  | Q1/3-series MQXFA16 - LQXFA06 | 2024 5: 15; 2024 6: +; 2024 7: 16; 2025 5: F; 2025 8: D; 2025 2: V
Q1/3-series MQXFA17 | bar: 2022 3 to 2022 7; 2023 1 to 2023 2
|  | Q1/3-series MQXFA18 - LQXFA08 | 2024 5: B; 2024 1: 17; 2024 2: +; 2025 1: 18; 2025 0: F; 2026 1: D; 2026 4: V
Q1/3-series MQXFA19 | bar: 2022 8 to 2022 2; 2024 2 to 2024 3; 2024 7 to 2024 8
|  | Q1/3-series MQXFA20 - LQXFA09 | 2024 9: B; 2025 2: 19; 2025 3: +; 2025 4: 20; 2025 2: F; 2026 4: D; 2026 7: V
Q1/3-series MQXFA21 | bar: 2023 1 to 2023 5; 2024 5 to 2024 6; 2024 1 to 2024 2
|  | Q1/3-series MQXFA22 - LQXFA10 | 2025 1: B; 2025 4: 21; 2025 5: +; 2025 6: 22; 2026 4: F; 2026 8: D; 2026 1: V
Q1/3-series MQXFA23 | bar: 2023 6 to 2023 0; 2024 8 to 2024 9
Q2 cold mass | Q2 | MQXFBMT4 | bar: 2022 0 to 2022 2; 2023 2 to 2023 7
Q2-proto 1 MQXFBP1 | bar: 2016 4 to 2020 2; 2020 7 to 2020 8
Q2-proto 2 MQXFBP2 (Q2b) | bar: 2019 4 to 2020 3; 2020 7 to 2021 5; 2021 0 to 2021 2; 2022 6 to 2023 2; 2023 9 to 2024 4
Q2-proto 3 MQXFBP3 (Q2a) | bar: 2020 3; 2020 7 to 2021 4; 2021 1 to 2021 2; 2022 4 to 2023 7; 2024 2 to 2024 5
Q2-series 2 MQXFB02 | bar: 2020 0 to 2021 4; 2022 6 to 2023 3; 2023 5 to 2023 9; 2024 2 to 2025 3
Q2-series 3 MQXFB03 | bar: 2022 6 to 2023 1; 2024 1 to 2024 6; 2024 8 to 2024 9; 2025 3 to 2025 6
Q2-series 4 MQXFB04 | bar: 2023 4 to 2024 7; 2025 7 to 2025 0
Q2-series 5 MQXFB05 | bar: 2023 9 to 2024 2; 2025 1 to 2026 2
Q2-series 6 MQXFB06 | bar: 2024 2 to 2025 5; 2026 2 to 2026 4
Q2-series 7 MQXFB07 | bar: 2024 7 to 2025 0; 2026 4 to 2026 6
Q2-series 8 MQXFB08 | bar: 2024 2 to 2026 3; 2026 7 to 2026 9
Q2-spare 1 MQXFB09 | bar: 2025 5 to 2026 1
Q2-spare 2 MQXFB10 | bar: 2025 0 to 2027 2
| MCBXFB | MCBXFBP1 - proto 1 (CIEMAT/CERN) | 2017 4: S; 2018 2: C; 2019 2: D; 2019 3: C; 2019 6: C; 2019 9: C
MCBXFBP2 - proto 2 (CIEMAT/CERN) | bar: 2019 3 to 2020 2; 2020 7 to 2020 9; 2022 1 to 2022 5
MCBXFB01 - series 1 (CIEMAT/CERN) | bar: 2020 3; 2020 7 to 2021 6
|  | MCBXFB02 - series 2 | 2021 3: T; 2022 8: D; 2022 9: C; 2023 2: C
MCBXFB03 - series 3 | bar: 2022 5 to 2022 1; 2023 3 to 2023 5
MCBXFB04 - series 4 | bar: 2022 1 to 2023 0
MCBXFB05 - series 5 | bar: 2023 3 to 2024 1
MCBXFB06 - series 6 | bar: 2023 0 to 2024 4
MCBXFB07 - series 7 | bar: 2023 2 to 2024 6
MCBXFB08 - series 8 | bar: 2024 3 to 2024 9
MCBXFB09 - spare 1 | bar: 2024 6 to 2024 2
|  | MCBXFB10 - spare 2 | 2025 2: D; 2025 3: C; 2025 4: Z
|  | MCBXFB11 - spare 3 | 2025 5: D; 2025 6: C; 2025 7: Z
|  | MCBXFB12 - spare 4 | 2025 8: D; 2025 9: C; 2025 0: Z
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
Corrector package | MCBXFA | MCBXFAP1 - LCXF1 | bar: 2021 1 to 2023 2; 2024 6 to 2024 8
|  | MCBXFA1 - LCXF2 | 2021 3: T; 2023 1: D; 2023 2: C; 2024 9: C; 2024 1: V
|  | MCBXFA2 - LCXF3 | 2024 2: D; 2024 3: C; 2025 4: C; 2025 6: V
|  | MCBXFA3 - LCXF4 | 2024 6: D; 2024 8: C; 2025 0: C; 2025 2: V
|  | MCBXFA4 - LCXF5 | 2024 0: D; 2024 1: C; 2026 4: C; 2026 6: V
MCBXFA5 | bar: 2024 8 to 2025 3
| HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 8 to 2019 6; 2020 2; 2020 6 to 2020 7
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 0
MgB2 corrector - proto | bar: 2017 8 to 2018 1; 2019 4 to 2019 8
|  | Batch 1a (9 magnets) | 2019 1: T; 2020 9: L; 2020 1: L; 2020 2: L; 2021 1: D
Batch 1b (9 magnets) | bar: 2020 9 to 2021 5
Batch 2 (18 magnets) | bar: 2021 1 to 2022 5
|  | Batch 3 (18 magnets) | 2022 6: L; 2022 8: L; 2022 0: L; 2022 1: L; 2022 2: D; 2023 1: Z
D1 |  | MBXFS1 - short model 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
MBXFS2 - short model 2 | bar: 2017 1 to 2018 7; 2018 9
MBXFS3 - short model 3 | bar: 2018 6 to 2019 6; 2019 8 to 2019 9
|  | MBXFP1 - prototype | 2019 4: T; 2021 6: K; 2021 9: K; 2023 4: D; 2023 0: C
|  | MBXF1 - series 1 | 2023 4: K; 2024 5: D; 2024 9: C; 2025 7: V
|  | MBXF2 - series 2 | 2024 2: K; 2025 1: D; 2025 5: C; 2026 1: V
|  | MBXF3 - series 3 | 2024 6: K; 2025 7: D; 2025 1: C; 2026 5: V
|  | MBXF4 - series 4 | 2024 1: K; 2025 0: D; 2026 2: C; 2026 8: V
|  | MBXF5 - spare 1 | 2023 0: K; 2026 1: D; 2026 5: C; 2026 8: Z
|  | MBXF6 - spare 2 | 2025 2: K; 2026 3: D; 2026 7: C; 2026 9: Z
DCM |  | DCM - prototype | bar: 2022 1 to 2024 2
DCM - series 1 | bar: 2024 4 to 2024 8
DCM - series 2 | bar: 2024 0 to 2025 2
DCM - series 3 | bar: 2025 2 to 2025 6
DCM - series 4 | bar: 2025 6 to 2025 0
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
D2 cold mass | D2 | MBRDS1 - short model | bar: 2016 9; 2017 2 to 2019 2; 2019 5 to 2020 2; 2020 8
|  | MBRDP1 - prototype | 2018 0: T; 2021 0: D; 2022 0: C
|  | MBRD1 - series 1 | 2021 2: T*; 2023 9: D; 2024 6: C; 2024 9: V
|  | MBRD2 - series 2 | 2024 1: D; 2024 9: C; 2025 3: V
|  | MBRD3 - series 3 | 2024 6: D; 2025 3: C; 2025 8: V
|  | MBRD4 - series 4 | 2024 1: D; 2025 7: C; 2026 5: V
|  | MBRD5 - spare 1 | 2025 4: D; 2025 2: C; 2026 9: Z
|  | MBRD6 - spare 2 | 2025 8: D; 2026 4: C; 2026 2: Z
| D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDS2 - short model double aperture | bar: 2017 9 to 2018 5
MCBRDP1 - prototype | bar: 2018 6 to 2018 1; 2019 7 to 2019 9
|  | MCBRDP2 - prototype IHEP | 2020 6: I; 2020 9: D; 2020 0: C
MCBRDP3 - third prototype | bar: 2020 0 to 2021 3; 2021 5
MCBRDP4 - fourth prototype | bar: 2022 1 to 2022 6
|  | MCBRD01 - series 1 | 2020 8: T; 2021 8: I; 2021 2: D; 2022 3: U
|  | MCBRD02 - series 2 | 2022 3: I; 2022 5: D; 2022 6: C
MCBRD03 - series 3 | bar: 2022 8 to 2022 2; 2023 3; 2023 5
MCBRD04 - series 4 | bar: 2023 3 to 2023 7; 2023 9; 2023 1
MCBRD05 - series 5 | bar: 2023 9 to 2023 2; 2024 5
MCBRD06 - series 6 | bar: 2023 2 to 2024 3; 2024 5
MCBRD07 - series 7 | bar: 2024 3 to 2024 6; 2024 1
MCBRD08 - series 8 | bar: 2024 6 to 2024 9; 2024 1
MCBRD09 - spare 1 | bar: 2024 9 to 2024 2; 2025 5
MCBRD10 - spare 2 | bar: 2024 2 to 2025 3; 2025 5
MCBRD11 - spare 3 | bar: 2023 4 to 2024 3
MCBRD12 - spare 4 | bar: 2023 1 to 2023 2
MQYY |  | Q4 - short model | bar: 2016 9 to 2019 0; 2020 1 to 2020 2
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 2; 2020 7 to 2020 9
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 2; 2020 7 to 2020 9
|  |  | Magnet construction | [30 empty] | M |  | Mirror or single coil test | [24 empty] | C | Test at CERN
|  |  | Vertical test | [30 empty] | S |  | Slice (mechanical model) | [24 empty] | B | Test at BNL
|  |  | Cold mass assembly | [30 empty] | T |  | Contract signed | [24 empty] | F | Test at FNAL
|  |  | Cryostating | [30 empty] | D |  | Delivery at CERN | [24 empty] | S | Test at Saclay
|  |  | Horizontal test | [30 empty] | V |  | Delivery to vacuum | [24 empty] | L | Test at LASA
|  |  | Available for STRING | [30 empty] | Z |  | Delivery to storage | [24 empty] | K | Test at KEK
[61 empty] | U | Test at FREIA
[61 empty] | I | Test at IMP
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
| Q4 stdalone | 1 | bar: 2026 5 to 2026 0
2 | bar: 2026 1 to 2027 3
3 | bar: 2027 4 to 2027 7
4 | bar: 2027 8 to 2027 1
| MS Q10 | 1 | bar: 2025 7 to 2025 9; 2026 8 to 2026 0
2 | bar: 2025 0 to 2025 2; 2026 1 to 2027 1
3 | bar: 2026 2 to 2026 4; 2027 3 to 2027 5
4 | bar: 2026 5 to 2026 7; 2027 6 to 2027 8
21
59
40
Note on B134: Délio Ramos: Convert to stand-alone
Note on B138: Délio Ramos: Convert to stand-alone

## schedule March 2023
WP3 schedule March 2023 |  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
MQXF SHORT |  | MQXFS1 (RRP LARP) | 2015 4: S; 2015 5: M; 2016 3: F; 2016 9: F; 2017 5: F
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5; 2018 0; 2019 7 to 2019 0; 2021 5 to 2021 6; 2021 0 to 2021 2; 2023 1 to 2023 5
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0; 2019 5 to 2019 8; 2019 0; 2020 2 to 2020 3; 2020 7 to 2020 0
MQXFSM2 (Mirror AUP) | bar: 2019 5 to 2019 2
MQXFS7 (2 RRP 2 PIT CERN) | bar: 2019 1 to 2020 2; 2020 7 to 2020 8; 2020 1 to 2020 2; 2021 2; 2021 6; 2021 8 to 2021 1; 2022 1; 2022 5 to 2022 2
MQXFS8 (mini-swap) | bar: 2021 1 to 2022 3; 2022 6 to 2022 7
Q1/3 |  | Q1/3 4.0 m proto 1 MQXFAP1 | bar: 2015 5 to 2017 2; 2019 1 to 2019 7
Q1/3 4.2 m proto 2 MQXFAP2 - LXQFP | bar: 2016 7 to 2018 1
Q1/3 4.2 m proto 3 MQXFA03 | bar: 2018 3 to 2020 1
|  | Q1/3-series MQXFA04 - LQXFA01 (Q1) | 2020 8: B; 2021 3: 3; 2021 4: +; 2021 5: 4; 2023 3: F; 2023 8: D; 2023 2: C
Q1/3-series MQXFA05 | bar: 2019 2 to 2020 3; 2020 7; 2021 4 to 2021 5; 2022 4 to 2022 5
|  | Q1/3-series MQXFA06 - LQXFA02 (Q3) | 2021 6: B; 2023 1: 5; 2023 2: +; 2023 3: 6; 2023 9: F; 2024 2: D
Q1/3-series MQXFA07 | bar: 2019 2 to 2020 3; 2020 7 to 2021 1; 2021 8 to 2021 9; 2023 4 to 2023 5; 2023 1 to 2023 2
|  | Q1/3-series MQXFA08 | 2021 1: B; 2023 1: B; 2023 6: 8; 2023 7: +; 2023 8: 13; 2024 6: F; 2024 9: D; 2025 3: V
|  | Q1/3-series MQXFA09 - LQXFA09 | 2024 1: B; 2024 7: 7; 2024 8: +; 2024 9: 9; 2025 4: F; 2025 8: D; 2025 2: V
Q1/3-series MQXFA10 - LQXFA03 | bar: 2020 1 to 2021 4; 2021 0 to 2022 3; 2022 5 to 2022 7
|  | Q1/3-series MQXFA11 | 2022 9: B; 2023 1: 10; 2023 2: +; 2023 3: 11; 2024 3: F; 2024 7: D; 2025 5: V
Q1/3-series MQXFA12 - LQXFA04 | bar: 2021 3 to 2021 8; 2022 7 to 2023 2; 2023 9 to 2023 0; 2024 4 to 2024 5
Q1/3-series MQXFA13 | bar: 2021 5 to 2021 9; 2022 0 to 2023 5
|  | Q1/3-series MQXFA14 - LQXFA05 | 2023 7: B; 2023 2: 12; 2024 1: +; 2024 2: 14; 2024 9: F; 2024 2: D; 2025 7: V
Q1/3-series MQXFA15 | bar: 2021 9 to 2022 3; 2023 3 to 2023 4; 2023 9 to 2023 0
|  | Q1/3-series MQXFA16 - LQXFA06 | 2024 3: B; 2024 5: 15; 2024 6: +; 2024 7: 16; 2025 2: F; 2025 5: D; 2025 0: V
Q1/3-series MQXFA17 | bar: 2022 3 to 2022 7; 2023 1 to 2023 2; 2024 6 to 2024 7
|  | Q1/3-series MQXFA18 - LQXFA07 | 2024 8: B; 2024 1: 17; 2024 2: +; 2025 1: 18; 2025 7: F; 2025 1: D; 2026 4: V
Q1/3-series MQXFA19 | bar: 2022 8 to 2022 2; 2024 2 to 2024 3; 2024 0 to 2024 1
|  | Q1/3-series MQXFA20 - LQXFA08 | 2024 2: B; 2025 2: 19; 2025 3: +; 2025 4: 20; 2025 2: F; 2026 4: D; 2026 7: V
Q1/3-series MQXFA21 | bar: 2023 1 to 2023 5; 2024 5 to 2024 6
|  | Q1/3-series MQXFA22 - LQXFA10 | 2025 4: 21; 2025 5: +; 2025 6: 22; 2026 3: F; 2026 8: D; 2026 1: V
Q1/3-series MQXFA23 | bar: 2023 6 to 2023 0; 2024 8 to 2024 9
Q2 cold mass | Q2 | MQXFBMT4 | bar: 2022 0 to 2022 2; 2023 2 to 2023 7
Q2-proto 1 MQXFBP1 | bar: 2016 4 to 2020 2; 2020 7 to 2020 8
Q2-proto 2 MQXFBP2 (Q2b) | bar: 2019 4 to 2020 3; 2020 7 to 2021 5; 2021 0 to 2021 2; 2022 7 to 2023 3; 2023 6 to 2024 1
Q2-proto 3 MQXFBP3 (Q2a) | bar: 2020 3; 2020 7 to 2021 4; 2021 1 to 2021 2; 2022 4 to 2023 3; 2023 6 to 2024 1
Q2-series 2 MQXFB02 | bar: 2020 8 to 2021 4; 2022 6 to 2023 7; 2023 0 to 2023 1; 2024 2 to 2024 3; 2024 2 to 2025 3
Q2-series 3 MQXFB03 | bar: 2022 6 to 2024 6; 2024 8 to 2024 9; 2025 3 to 2025 6
Q2-series 4 MQXFB04 | bar: 2023 4 to 2024 7; 2025 7 to 2025 0
Q2-series 5 MQXFB05 | bar: 2023 9 to 2024 2; 2025 1 to 2026 2
Q2-series 6 MQXFB06 | bar: 2024 2 to 2025 5; 2026 2 to 2026 4
Q2-series 7 MQXFB07 | bar: 2024 7 to 2025 0; 2026 4 to 2026 6
Q2-series 8 MQXFB08 | bar: 2024 2 to 2026 3; 2026 7 to 2026 9
Q2-spare 1 MQXFB09 | bar: 2025 5 to 2026 1
Q2-spare 2 MQXFB10 | bar: 2025 0 to 2027 2
| MCBXFB | MCBXFBP1 - proto 1 (CIEMAT/CERN) | 2017 4: S; 2018 2: C; 2019 2: D; 2019 3: C; 2019 6: C; 2019 9: C
MCBXFBP2 - proto 2 (CIEMAT/CERN) | bar: 2019 3 to 2020 2; 2020 7 to 2020 9; 2022 1 to 2022 5
MCBXFB01 - series 1 (CIEMAT/CERN) | bar: 2020 3; 2020 7 to 2021 6
|  | MCBXFB02 - series 2 | 2021 3: T; 2022 8: D; 2022 9: C; 2023 2: C
MCBXFB03 - series 3 | bar: 2022 5 to 2022 1; 2023 3 to 2023 5
MCBXFB04 - series 4 | bar: 2022 1 to 2023 6
MCBXFB05 - series 5 | bar: 2023 3 to 2023 9
MCBXFB06 - series 6 | bar: 2023 6 to 2023 2
MCBXFB07 - series 7 | bar: 2023 8 to 2024 2
MCBXFB08 - series 8 | bar: 2023 1 to 2024 5
MCBXFB09 - spare 1 | bar: 2024 2 to 2024 8
|  | MCBXFB10 - spare 2 | 2024 0: D; 2024 1: C; 2024 2: Z
|  | MCBXFB11 - spare 3 | 2025 1: D; 2025 2: C; 2025 3: Z
|  | MCBXFB12 - spare 4 | 2025 4: D; 2025 5: C; 2025 6: Z
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
Corrector package | MCBXFA | MCBXFAP1 - string | bar: 2021 1 to 2023 1; 2024 2 to 2024 4
|  | MCBXFA1 - series 1 | 2021 3: T; 2023 6: D; 2023 7: C; 2024 4: C; 2024 6: V
|  | MCBXFA2 - series 2 | 2023 9: D; 2023 0: C; 2024 2: C; 2025 2: V
|  | MCBXFA3 - series 3 | 2024 1: D; 2024 3: C; 2025 7: C; 2025 9: V
|  | MCBXFA4 - series 4 | 2024 5: D; 2024 6: C; 2026 2: C; 2026 4: V
|  | MCBXFA5 - spare 1 | 2024 9: D; 2024 0: C; 2026 1: C; 2026 2: Z
|  | MCBXFA6 - spare 2 | 2025 1: D; 2025 3: C; 2025 4: Z
| HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 8 to 2019 6; 2020 2; 2020 6 to 2020 7
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 0
MgB2 corrector - proto | bar: 2017 8 to 2018 1; 2019 4 to 2019 8
|  | Batch 1a (9 magnets) | 2019 1: T; 2020 9: L; 2020 1: L; 2020 2: L; 2021 1: D
Batch 1b (9 magnets) | bar: 2020 9 to 2021 5
Batch 2 (18 magnets) | bar: 2021 1 to 2022 5
|  | Batch 3 (18 magnets) | 2022 6: L; 2022 8: L; 2022 0: L; 2022 1: L; 2022 2: D; 2023 1: Z
D1 |  | MBXFS1 - short model 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
MBXFS2 - short model 2 | bar: 2017 1 to 2018 7; 2018 9
MBXFS3 - short model 3 | bar: 2018 6 to 2019 6; 2019 8 to 2019 9
|  | MBXFP1 - prototype | 2019 4: T; 2021 6: K; 2021 9: K; 2023 4: D; 2023 9: C
|  | MBXF1 - series 1 | 2023 4: K; 2024 5: D; 2024 9: C; 2025 7: V
|  | MBXF2 - series 2 | 2023 2: K; 2024 2: D; 2025 4: C; 2026 1: V
|  | MBXF3 - series 3 | 2024 4: K; 2025 5: D; 2025 9: C; 2026 5: V
|  | MBXF4 - series 4 | 2024 8: K; 2025 8: D; 2025 2: C; 2026 3: Z
|  | MBXF5 - spare 1 | 2023 0: K; 2025 2: D; 2025 6: C; 2026 2: V
|  | MBXF6 - spare 2 | 2025 1: K; 2026 2: D; 2026 6: C; 2026 8: Z
DCM |  | DCM - prototype | bar: 2022 1 to 2023 0
DCM - series 1 | bar: 2023 2 to 2024 4
DCM - series 2 | bar: 2024 6 to 2024 0
DCM - series 3 | bar: 2024 0 to 2025 2
DCM - series 4 | bar: 2025 2 to 2025 6
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
D2 cold mass | D2 | MBRDS1 - short model | bar: 2016 9; 2017 2 to 2019 2; 2019 5 to 2020 2; 2020 8
|  | MBRDP1 - prototype | 2018 0: T; 2021 0: D; 2022 0: C
|  | MBRD1 - series 1 | 2021 2: T*; 2023 8: D; 2024 5: C; 2024 8: V
|  | MBRD2 - series 2 | 2023 2: D; 2024 8: C; 2025 2: V
|  | MBRD3 - series 3 | 2024 5: D; 2025 2: C; 2025 7: V
|  | MBRD4 - series 4 | 2024 0: D; 2025 6: C; 2026 5: V
|  | MBRD5 - spare 1 | 2025 3: D; 2025 1: C; 2026 9: Z
|  | MBRD6 - spare 2 | 2025 7: D; 2026 3: C; 2026 2: Z
| D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDS2 - short model double aperture | bar: 2017 9 to 2018 5
MCBRDP1 - prototype | bar: 2018 6 to 2018 1; 2019 7 to 2019 9
|  | MCBRDP2 - prototype IHEP | 2020 6: I; 2020 9: D; 2020 0: C
MCBRDP3 - third prototype | bar: 2020 0 to 2021 3; 2021 5
MCBRDP4 - fourth prototype | bar: 2022 1 to 2022 6
|  | MCBRD01 - series 1 | 2020 8: T; 2021 8: I; 2021 2: D; 2022 3: U
|  | MCBRD02 - series 2 | 2022 3: I; 2022 5: D; 2022 6: C
MCBRD03 - series 3 | bar: 2022 8 to 2022 2; 2023 3; 2023 5
|  | MCBRD04 - series 4 | 2023 5: I; 2023 6: D; 2023 7: C
MCBRD05 - series 5 | bar: 2023 5 to 2023 7; 2023 2
MCBRD06 - series 6 | bar: 2023 7 to 2023 9; 2023 2
|  | MCBRD07 - series 7 | 2023 1: I; 2023 2: D; 2024 1: C
MCBRD08 - series 8 | bar: 2023 1 to 2024 1; 2024 8
MCBRD09 - spare 1 | bar: 2024 1 to 2024 3; 2024 8
MCBRD10 - spare 2 | bar: 2024 3 to 2024 5; 2024 8
MCBRD11 - spare 3 | bar: 2023 4 to 2023 0
MCBRD12 - spare 4 | bar: 2023 1 to 2023 9
MQYY |  | Q4 - short model | bar: 2016 9 to 2019 0; 2020 1 to 2020 2
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 2; 2020 7 to 2020 9
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 2; 2020 7 to 2020 9
|  |  | Magnet construction | [30 empty] | M |  | Mirror or single coil test | [24 empty] | C | Test at CERN
|  |  | Vertical test | [30 empty] | S |  | Slice (mechanical model) | [24 empty] | B | Test at BNL
|  |  | Cold mass assembly | [30 empty] | T |  | Contract signed | [24 empty] | F | Test at FNAL
|  |  | Cryostating | [30 empty] | D |  | Delivery at CERN | [24 empty] | S | Test at Saclay
|  |  | Horizontal test | [30 empty] | V |  | Delivery to vacuum | [24 empty] | L | Test at LASA
|  |  | Available for STRING | [30 empty] | Z |  | Delivery to storage | [24 empty] | K | Test at KEK
[61 empty] | U | Test at FREIA
[61 empty] | I | Test at IMP
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
| Q4 stdalone | 1 | bar: 2026 5 to 2026 0
2 | bar: 2026 1 to 2027 3
3 | bar: 2027 4 to 2027 7
4 | bar: 2027 8 to 2027 1
| MS Q10 | 1 | bar: 2025 7 to 2025 9; 2026 8 to 2026 0
2 | bar: 2025 0 to 2025 2; 2026 1 to 2027 1
3 | bar: 2026 2 to 2026 4; 2027 3 to 2027 5
4 | bar: 2026 5 to 2026 7; 2027 6 to 2027 8
21
59
40
Note on B135: Délio Ramos: Convert to stand-alone
Note on B139: Délio Ramos: Convert to stand-alone

## schedule October 2022
WP3 schedule October 2022 |  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
MQXF SHORT |  | MQXFS1 (RRP LARP) | 2015 4: S; 2015 5: M; 2016 3: F; 2016 9: F; 2017 5: F
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5; 2018 0; 2019 7 to 2019 0; 2021 5 to 2021 6; 2021 0 to 2021 2; 2023 1 to 2023 5
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0; 2019 5 to 2019 8; 2019 0; 2020 2 to 2020 3; 2020 7 to 2020 0
MQXFSM2 (Mirror AUP) | bar: 2019 5 to 2019 2
MQXFS7 (2 RRP 2 PIT CERN) | bar: 2019 1 to 2020 2; 2020 7 to 2020 8; 2020 1 to 2020 2; 2021 2; 2021 6; 2021 8 to 2021 1; 2022 1; 2022 5 to 2022 2
MQXFS8 (mini-swap) | bar: 2021 1 to 2022 3; 2022 6 to 2022 7
Q1/3 |  | Q1/3 4.0 m proto 1 MQXFAP1 | bar: 2015 5 to 2017 2; 2019 1 to 2019 7
Q1/3 4.2 m proto 2 MQXFAP2 - LXQFP | bar: 2016 7 to 2018 1
Q1/3 4.2 m proto 3 MQXFA03 | bar: 2018 3 to 2020 1
|  | Q1/3-series MQXFA04 - LQXFA01 (Q1) | 2020 8: B; 2022 2: F; 2023 4: D; 2023 6: C
Q1/3-series MQXFA05 | bar: 2019 2 to 2020 3; 2020 7; 2021 4 to 2021 5; 2022 4 to 2022 6
|  | Q1/3-series MQXFA06 - LQXFA02 (Q3) | 2021 6: B; 2023 6: F; 2023 0: D
Q1/3-series MQXFA07 | bar: 2019 2 to 2020 3; 2020 7 to 2021 1; 2021 8 to 2021 9; 2023 1 to 2023 2; 2023 7 to 2023 8
Q1/3-series MQXFA08 | bar: 2020 7 to 2020 2; 2021 4 to 2021 6; 2021 0 to 2022 1; 2022 4 to 2022 5; 2022 1 to 2022 2
|  | Q1/3-series MQXFA09 - LQXFA09 | 2025 0: F; 2026 2: D; 2026 5: V
|  | Q1/3-series MQXFA10 - LQXFA03 | 2022 6: B; 2023 1: F; 2024 2: D; 2024 5: V
Q1/3-series MQXFA11 | bar: 2021 1 to 2021 6; 2022 4 to 2022 6; 2022 9 to 2022 0
|  | Q1/3-series MQXFA12 - LQXFA04 | 2023 1: B; 2024 2: F; 2024 5: D; 2024 7: C; 2024 1: V
Q1/3-series MQXFA13 | bar: 2021 5 to 2021 9; 2022 8 to 2022 9; 2023 3 to 2023 4
|  | Q1/3-series MQXFA14 - LQXFA05 | 2023 5: B; 2024 4: F; 2024 8: D; 2025 6: V
Q1/3-series MQXFA15 | bar: 2021 9 to 2022 3; 2022 1 to 2022 2; 2023 7 to 2023 8
|  | Q1/3-series MQXFA16 - LQXFA06 | 2023 2: B; 2024 9: F; 2024 2: D; 2025 0: V
Q1/3-series MQXFA17 | bar: 2022 3 to 2022 7; 2023 4 to 2023 5; 2024 2 to 2024 3
|  | Q1/3-series MQXFA18 - LQXFA07 | 2024 3: B; 2024 1: F; 2025 2: D; 2025 2: V
Q1/3-series MQXFA19 | bar: 2022 8 to 2022 2; 2023 6 to 2023 7; 2024 5 to 2024 6
|  | Q1/3-series MQXFA20 - LQXFA08 | 2024 7: B; 2025 2: F; 2025 5: D; 2026 3: V
Q1/3-series MQXFA21 | bar: 2023 1 to 2023 5; 2023 1 to 2023 2
|  | Q1/3-series MQXFA22 - LQXFA10 | 2025 6: F; 2025 0: D; 2026 7: V
Q1/3-series MQXFA23 | bar: 2023 6 to 2023 0
Q2 cold mass | Q2 | MQXFBMT4 | bar: 2022 0 to 2023 6
MQXFBMT5 | bar: 2023 1 to 2023 4; 2023 6 to 2023 8
Q2-proto 1 MQXFBP1 | bar: 2016 4 to 2020 2; 2020 7 to 2020 8
Q2-proto 2 MQXFBP2 (Q2b) | bar: 2019 4 to 2020 3; 2020 7 to 2021 5; 2021 0 to 2021 2; 2022 7 to 2023 1; 2023 5 to 2023 1
Q2-proto 3 MQXFBP3 (Q2a) | bar: 2020 3; 2020 7 to 2021 4; 2021 1 to 2021 2; 2022 4 to 2023 5; 2023 8 to 2023 2
Q2-series 2 MQXFB02 | bar: 2020 8 to 2021 4; 2022 6 to 2023 8; 2023 0 to 2023 1; 2024 2 to 2025 3
Q2-series 3 MQXFB03 | bar: 2022 6 to 2024 6; 2024 8 to 2024 9; 2025 3 to 2025 6
Q2-series 4 MQXFB04 | bar: 2023 4 to 2024 7; 2025 7 to 2025 0
Q2-series 5 MQXFB05 | bar: 2023 9 to 2024 2; 2025 1 to 2026 2
Q2-series 6 MQXFB06 | bar: 2024 2 to 2025 5; 2026 2 to 2026 4
Q2-series 7 MQXFB07 | bar: 2024 7 to 2025 0; 2026 4 to 2026 6
Q2-series 8 MQXFB08 | bar: 2024 2 to 2026 3; 2026 7 to 2026 9
Q2-spare 1 MQXFB09 | bar: 2025 5 to 2026 1
Q2-spare 2 MQXFB10 | bar: 2025 0 to 2027 2
| MCBXFB | MCBXFBP1 - proto 1 (CIEMAT/CERN) | 2017 4: S; 2018 2: C; 2019 2: D; 2019 3: C; 2019 6: C; 2019 9: C
MCBXFBP2 - proto 2 (CIEMAT/CERN) | bar: 2019 3 to 2020 2; 2020 7 to 2020 9; 2022 1 to 2022 5
MCBXFB01 - series 1 (CIEMAT/CERN) | bar: 2020 3; 2020 7 to 2021 6
|  | MCBXFB02 - series 2 | 2021 3: T; 2022 8: D; 2022 9: C
MCBXFB03 - series 3 | bar: 2022 5 to 2022 1; 2023 2 to 2023 3
MCBXFB04 - series 4 | bar: 2022 1 to 2023 5
MCBXFB05 - series 5 | bar: 2023 2 to 2023 8
MCBXFB06 - series 6 | bar: 2023 5 to 2023 1
MCBXFB07 - series 7 | bar: 2023 8 to 2024 2
MCBXFB08 - series 8 | bar: 2023 1 to 2024 5
MCBXFB09 - spare 1 | bar: 2024 2 to 2024 8
|  | MCBXFB10 - spare 2 | 2024 0: D; 2024 1: C; 2024 2: Z
|  | MCBXFB11 - spare 3 | 2025 1: D; 2025 2: C; 2025 3: Z
|  | MCBXFB12 - spare 4 | 2025 4: D; 2025 5: C; 2025 6: Z
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
Corrector package | MCBXFA | MCBXFAP1 - string | bar: 2021 1 to 2023 2
|  | MCBXFA1 - series 1 | 2021 3: T; 2023 4: D; 2023 5: C; 2024 4: C; 2024 6: V
|  | MCBXFA2 - series 2 | 2023 8: D; 2023 9: C; 2024 2: C; 2025 2: V
|  | MCBXFA3 - series 3 | 2023 2: D; 2024 2: C; 2025 7: C; 2025 9: V
|  | MCBXFA4 - series 4 | 2024 4: D; 2024 5: C; 2026 2: C; 2026 4: V
|  | MCBXFA5 - spare 1 | 2024 8: D; 2024 9: C; 2026 1: C; 2026 2: Z
|  | MCBXFA6 - spare 2 | 2024 2: D; 2025 2: C; 2025 3: Z
| HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 8 to 2019 6; 2020 2; 2020 6 to 2020 7
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 0
MgB2 corrector - proto | bar: 2017 8 to 2018 1; 2019 4 to 2019 8
|  | Batch 1a (9 magnets) | 2019 1: T; 2020 9: L; 2020 1: L; 2020 2: L; 2021 1: D
Batch 1b (9 magnets) | bar: 2020 9 to 2021 5
Batch 2 (18 magnets) | bar: 2021 1 to 2022 3
|  | Batch 3 (18 magnets) | 2022 3: L; 2022 5: L; 2022 7: L; 2022 8: L; 2022 9: D; 2022 0: Z
D1 |  | MBXFS1 - short model 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
MBXFS2 - short model 2 | bar: 2017 1 to 2018 7; 2018 9
MBXFS3 - short model 3 | bar: 2018 6 to 2019 6; 2019 8 to 2019 9
|  | MBXFP1 - prototype | 2019 4: T; 2021 6: K; 2021 9: K; 2022 2: D; 2023 4: C
|  | MBXF1 - series 1 | 2023 3: K; 2024 2: D; 2024 7: C; 2025 7: V
|  | MBXF2 - series 2 | 2023 6: K; 2024 6: D; 2024 0: C; 2025 1: V
|  | MBXF3 - series 3 | 2024 3: K; 2025 2: D; 2025 6: C; 2026 5: V
|  | MBXF4 - series 4 | 2024 7: K; 2025 8: D; 2025 2: C; 2026 3: Z
|  | MBXF5 - spare 1 | 2023 0: K; 2024 0: D; 2025 2: C; 2026 2: V
|  | MBXF6 - spare 2 | 2025 3: K; 2026 2: D; 2026 6: C; 2026 8: Z
DCM |  | DCM - prototype | bar: 2022 1 to 2023 5
DCM - series 1 | bar: 2023 6 to 2023 0
DCM - series 2 | bar: 2023 1 to 2024 3
DCM - series 3 | bar: 2024 4 to 2024 8
DCM - series 4 | bar: 2024 9 to 2025 1
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
D2 cold mass | D2 | MBRDS1 - short model | bar: 2016 9; 2017 2 to 2019 2; 2019 5 to 2020 2; 2020 8
|  | MBRDP1 - prototype | 2018 0: T; 2021 0: D; 2022 7: C
|  | MBRD1 - series 1 | 2021 2: T*; 2023 4: D; 2024 1: C; 2024 4: V
|  | MBRD2 - series 2 | 2023 8: D; 2024 4: C; 2025 2: V
|  | MBRD3 - series 3 | 2024 1: D; 2024 0: C; 2025 7: V
|  | MBRD4 - series 4 | 2024 5: D; 2025 1: C; 2026 5: V
|  | MBRD5 - spare 1 | 2024 9: D; 2025 5: C; 2025 6: Z; 2026 9: Z
|  | MBRD6 - spare 2 | 2025 1: D; 2025 9: C; 2026 2: Z
| D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDS2 - short model double aperture | bar: 2017 9 to 2018 5
MCBRDP1 - prototype | bar: 2018 6 to 2018 1; 2019 7 to 2019 9
|  | MCBRDP2 - prototype IHEP | 2020 6: I; 2020 9: D; 2020 0: C
MCBRDP3 - third prototype | bar: 2020 0 to 2021 3; 2021 5
MCBRDP4 - fourth prototype | bar: 2022 1 to 2022 6
|  | MCBRD01 - series 1 | 2020 8: T; 2021 8: I; 2021 2: D; 2022 3: U
|  | MCBRD02 - series 2 | 2022 3: I; 2022 5: D; 2022 6: C
MCBRD03 - series 3 | bar: 2022 8 to 2022 2; 2023 3
|  | MCBRD04 - series 4 | 2023 2: I; 2023 3: D; 2023 4: C
MCBRD05 - series 5 | bar: 2023 2 to 2023 4; 2023 9
MCBRD06 - series 6 | bar: 2023 4 to 2023 6; 2023 9
|  | MCBRD07 - series 7 | 2023 8: I; 2023 9: D; 2023 0: C
MCBRD08 - series 8 | bar: 2023 8 to 2023 0; 2024 5
MCBRD09 - spare 1 | bar: 2023 0 to 2023 2; 2024 5
MCBRD10 - spare 2 | bar: 2023 2 to 2024 2; 2024 5
MCBRD11 - spare 3 | bar: 2022 2 to 2023 4
MCBRD12 - spare 4 | bar: 2022 9 to 2023 1
MQYY |  | Q4 - short model | bar: 2016 9 to 2019 0; 2020 1 to 2020 2
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 2; 2020 7 to 2020 9; 2020 2 to 2021 1
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 2; 2020 7 to 2020 9; 2020 2 to 2021 1
|  |  | Magnet construction | [30 empty] | M |  | Mirror or single coil test | [24 empty] | C | Test at CERN
|  |  | Vertical test | [30 empty] | S |  | Slice (mechanical model) | [24 empty] | B | Test at BNL
|  |  | Cold mass assembly | [30 empty] | T |  | Contract signed | [24 empty] | F | Test at FNAL
|  |  | Cryostating | [30 empty] | D |  | Delivery at CERN | [24 empty] | S | Test at Saclay
|  |  | Horizontal test | [30 empty] | V |  | Delivery to vacuum | [24 empty] | L | Test at LASA
|  |  | Available for STRING | [30 empty] | Z |  | Delivery to storage | [24 empty] | K | Test at KEK
[61 empty] | U | Test at FREIA
[61 empty] | I | Test at IMP
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
| Q4 stdalone | 1 | bar: 2026 5 to 2026 0
2 | bar: 2026 1 to 2027 3
3 | bar: 2027 4 to 2027 7
4 | bar: 2027 8 to 2027 1
| MS Q10 | 1 | bar: 2026 5 to 2026 0
2 | bar: 2026 8 to 2027 1
3 | bar: 2026 1 to 2027 5
4 | bar: 2027 3 to 2027 8
21
59
40
Note on B136: Délio Ramos: Convert to stand-alone
Note on B140: Délio Ramos: Convert to stand-alone

## schedule October 2021
WP3 schedule October 2021 |  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
MQXF SHORT |  | MQXFS1 (RRP LARP) | 2015 4: S; 2015 5: M; 2016 3: F; 2016 9: F; 2017 5: F
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5; 2018 0; 2019 7 to 2019 0; 2021 5 to 2021 6; 2021 0 to 2021 2
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0; 2019 5 to 2019 8; 2019 0; 2020 2 to 2020 3; 2020 7 to 2020 0
MQXFSM2 (Mirror AUP) | bar: 2019 5 to 2019 2
MQXFS7 (2 RRP 2 PIT CERN) | bar: 2019 1 to 2020 2; 2020 7 to 2020 8; 2020 1 to 2020 2; 2021 2; 2021 6; 2021 8 to 2021 1
MQXFS8 (mini-swap) | bar: 2021 1 to 2022 5
Q1/3 |  | Q1/3 4.0 m proto 1 MQXFAP1 | bar: 2015 5 to 2017 2; 2019 1 to 2019 7
Q1/3 4.2 m proto 2 MQXFAP2 - LXQFP | bar: 2016 7 to 2018 1
Q1/3 4.2 m proto 3 MQXFA03 | bar: 2018 3 to 2020 1
|  | Q1/3-series MQXFA04 - LQXFA01 (Q1) | 2020 8: B; 2022 4: F; 2022 8: D; 2022 1: C
Q1/3-series MQXFA05 | bar: 2019 2 to 2020 3; 2020 7; 2021 4 to 2021 5
|  | Q1/3-series MQXFA06 - LQXFA02 (Q3) | 2021 6: B; 2022 7: F; 2022 2: D
Q1/3-series MQXFA07 | bar: 2019 2 to 2020 3; 2020 7 to 2021 1; 2021 8 to 2021 9
|  | Q1/3-series MQXFA08 - LQXFA03 | 2021 0: B; 2023 1: F; 2023 5: D; 2023 8: V
Q1/3-series MQXFA09 | bar: 2020 8 to 2021 2; 2021 7 to 2021 9; 2021 2 to 2022 1
|  | Q1/3-series MQXFA10 - LQXFA04 | 2022 2: B; 2023 4: F; 2023 8: D; 2023 1: V
Q1/3-series MQXFA11 | bar: 2021 1 to 2021 6; 2021 2 to 2022 1; 2022 4 to 2022 5
|  | Q1/3-series MQXFA12 - LQXFA05 | 2022 6: B; 2023 7: F; 2023 1: D; 2023 2: C; 2024 4: V
Q1/3-series MQXFA13 | bar: 2021 5 to 2021 9; 2022 3 to 2022 4; 2022 8 to 2022 9
|  | Q1/3-series MQXFA14 - LQXFA06 | 2022 0: B; 2023 0: F; 2024 2: D; 2024 5: V
Q1/3-series MQXFA15 | bar: 2021 0 to 2022 2; 2022 5 to 2022 7; 2022 2 to 2023 1
|  | Q1/3-series MQXFA16 - LQXFA07 | 2023 2: B; 2024 1: F; 2024 5: D; 2024 8: V
Q1/3-series MQXFA17 | bar: 2022 1 to 2022 5; 2022 8 to 2022 0; 2023 4 to 2023 5
|  | Q1/3-series MQXFA18 - LQXFA08 | 2023 6: B; 2024 4: F; 2024 8: D; 2024 1: V
Q1/3-series MQXFA19 | bar: 2022 4 to 2022 9; 2022 2 to 2023 2; 2023 8 to 2023 9
|  | Q1/3-series MQXFA20 - LQXFA09 | 2023 0: B; 2024 7: F; 2024 1: D; 2025 2: V
Q1/3-series MQXFA21 | bar: 2022 8 to 2023 1; 2023 4 to 2023 6; 2023 2 to 2024 1
|  | Q1/3-series MQXFA22 - LQXFA10 | 2024 2: B; 2024 0: F; 2025 2: D; 2025 5: V
Q1/3-series MQXFA23 | bar: 2022 2 to 2023 5; 2023 7 to 2023 9
Q2 cold mass | Q2 | Q2-proto 1 MQXFBP1 | bar: 2016 4 to 2020 2; 2020 7 to 2020 8
Q2-proto 2 MQXFBP2 | bar: 2019 4 to 2020 3; 2020 7 to 2021 5; 2021 0 to 2023 3
Q2-proto 3 MQXFBP3 | bar: 2020 3; 2020 7 to 2021 4; 2021 1 to 2023 4
Q2-series 2 MQXFB02 | bar: 2020 8 to 2021 4; 2021 2 to 2023 7
Q2-series 3 MQXFB03 | bar: 2021 2 to 2023 9
Q2-series 4 MQXFB04 | bar: 2022 5 to 2024 1
Q2-series 5 MQXFB05 | bar: 2022 0 to 2024 5
Q2-series 6 MQXFB06 | bar: 2023 3 to 2024 0
Q2-series 7 MQXFB07 | bar: 2023 8 to 2025 3
Q2-series 8 MQXFB08 | bar: 2024 1 to 2025 8
Q2-spare 1 MQXFB09 | bar: 2024 6 to 2025 2
Q2-spare 2 MQXFB10 | bar: 2024 1 to 2025 2
| MCBXFB | MCBXFBP1 - proto 1 (CIEMAT/CERN) | 2017 4: S; 2018 2: C; 2019 2: D; 2019 3: C; 2019 6: C; 2019 9: C
MCBXFBP2 - proto 2 (CIEMAT/CERN) | bar: 2019 3 to 2020 2; 2020 7 to 2020 9
MCBXFB01 - series 1 (CIEMAT/CERN) | bar: 2020 3; 2020 7 to 2021 6
|  | MCBXFB02 - series 2 | 2021 3: T; 2021 2: D; 2022 1: C
MCBXFB03 - series 3 | bar: 2021 9 to 2022 3
MCBXFB04 - series 4 | bar: 2021 2 to 2022 5
MCBXFB05 - series 5 | bar: 2022 2 to 2022 7
MCBXFB06 - series 6 | bar: 2022 4 to 2022 9
MCBXFB07 - series 7 | bar: 2022 6 to 2022 1
MCBXFB08 - series 8 | bar: 2022 8 to 2023 1
MCBXFB09 - spare 1 | bar: 2022 0 to 2023 3
MCBXFB10 - spare 2 | bar: 2022 2 to 2023 5
MCBXFB11 - spare 3 | bar: 2023 2 to 2023 7
MCBXFB12 - spare 4 | bar: 2023 4 to 2023 9
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
Corrector package | MCBXFA | MCBXFAP1 - proto | bar: 2021 1 to 2023 5
|  | MCBXFA1 - series 1 | 2021 3: T; 2022 7: U; 2022 8: D; 2023 6: C; 2023 8: V
|  | MCBXFA2 - series 2 | 2022 1: U; 2022 2: D; 2023 2: C; 2024 2: V
|  | MCBXFA3 - series 3 | 2023 1: U; 2023 2: D; 2024 2: C; 2024 4: V
|  | MCBXFA4 - series 4 | 2023 3: U; 2023 4: D; 2024 5: C; 2024 7: V
|  | MCBXFA5 - spare 1 | 2023 6: U; 2023 7: D; 2024 8: C; 2024 9: V
|  | MCBXFA6 - spare 2 | 2023 9: U; 2023 0: D; 2023 1: Z
| HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 8 to 2019 6; 2020 2; 2020 6 to 2020 7
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 0
MgB2 corrector - proto | bar: 2017 8 to 2018 1; 2019 4 to 2019 8
|  | Batch 1a (9 magnets) | 2019 1: T; 2020 9: L; 2020 1: L; 2020 2: L; 2021 1: D
Batch 1b (9 magnets) | bar: 2020 9 to 2021 5
|  | Batch 2 (18 magnets) | [132 empty] | MQXFXS | 6 | 5 | 1 | bar: 2021 1 to 2022 3
|  | Batch 3 (18 magnets, spares) | 2022 3: L; 2022 5: L; 2022 7: L; 2022 8: L; 2022 9: D; 2022 0: Z | MQXFA | 23 | 4 | 2
D1 |  | MBXFS1 - short model 1 | [132 empty] | MQXFB | 12 | 1 | 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
|  | MBXFS2 - short model 2 | [132 empty] | MCBXF | 21 | 1 | bar: 2017 1 to 2018 7; 2018 9
|  | MBXFS3 - short model 3 | [132 empty] | HO | 59 | 6 | bar: 2018 6 to 2019 6; 2019 8 to 2019 9
|  | MBXFP1 - prototype | 2019 4: T; 2021 6: K; 2021 9: K; 2022 3: D; 2022 8: C | D1 | 10 | 3
|  | MBXF1 - series 1 | 2022 6: K; 2022 0: D; 2023 2: C; 2023 7: V | D2 | 8 | 1
|  | MBXF2 - series 2 | 2022 9: K; 2023 2: D; 2023 6: C; 2023 1: V | D2 c | 14 | 2
|  | MBXF3 - series 3 | 2023 1: K; 2023 8: D; 2023 2: C; 2024 5: V |  | 153 | 23
|  | MBXF4 - series 4 | 2023 5: K; 2024 2: D; 2024 6: C; 2024 1: V
|  | MBXF5 - spare 1 | 2023 1: K; 2024 4: D; 2024 8: C; 2024 0: Z
|  | MBXF6 - spare 2 | 2024 5: K; 2024 0: D; 2024 1: Z
DCM |  | DCM - prototype | bar: 2022 1 to 2022 0
DCM - series 1 | bar: 2023 6 to 2023 0
DCM - series 2 | bar: 2023 1 to 2024 3
DCM - series 3 | bar: 2024 4 to 2024 8
DCM - series 4 | bar: 2024 9 to 2025 1
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
D2 cold mass | D2 | MBRDS1 - short model | bar: 2016 9; 2017 2 to 2019 2; 2019 5 to 2020 2; 2020 8
|  | MBRDP1 - prototype | 2018 0: T; 2021 0: D; 2022 6: C
|  | MBRD1 - series 1 | 2021 2: T*; 2023 1: D; 2023 0: C; 2024 2: V
|  | MBRD2 - series 2 | 2023 4: D; 2023 2: C; 2024 5: V
|  | MBRD3 - series 3 | 2023 7: D; 2024 4: C; 2024 8: V
|  | MBRD4 - series 4 | 2023 0: D; 2024 6: C; 2024 0: V
|  | MBRD5 - spare 1 | 2024 1: D; 2024 9: C; 2024 0: Z
|  | MBRD6 - spare 2 | 2024 4: D; 2024 0: 2; 2024 2: C; 2025 1: Z
| D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDS2 - short model double aperture | bar: 2017 9 to 2018 5
MCBRDP1 - prototype | bar: 2018 6 to 2018 1; 2019 7 to 2019 9
|  | MCBRDP2 - prototype IHEP | 2020 6: I; 2020 9: D; 2020 0: C
MCBRDP3 - third prototype | bar: 2020 0 to 2021 3; 2021 5
MCBRDP4 - fourth prototype | bar: 2022 1 to 2022 6
|  | MCBRD01 - series 1 | 2021 8: I; 2021 1: D; 2021 2: U
|  | MCBRD02 - series 2 | 2021 2: I; 2022 2: D; 2022 3: U
MCBRD03 - series 3 | bar: 2021 0 to 2022 2; 2022 5
|  | MCBRD04 - series 4 | 2022 4: I; 2022 5: D; 2022 6: C
MCBRD05 - series 5 | bar: 2022 4 to 2022 6; 2022 1
MCBRD06 - series 6 | bar: 2022 6 to 2022 8; 2022 1
|  | MCBRD07 - series 7 | 2022 0: I; 2022 1: D; 2022 2: C
MCBRD08 - series 8 | bar: 2022 0 to 2022 2; 2023 7
MCBRD09 - spare 1 | bar: 2022 2 to 2023 2; 2023 7
MCBRD10 - spare 2 | bar: 2023 2 to 2023 4; 2023 7
MCBRD11 - spare 3 | bar: 2023 4 to 2023 6; 2023 0
MCBRD12 - spare 4 | bar: 2023 6 to 2023 8; 2023 0
MQYY |  | Q4 - short model | bar: 2016 9 to 2019 0; 2020 1 to 2020 2
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 2; 2020 7 to 2020 9; 2020 2 to 2021 1
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 2; 2020 7 to 2020 9; 2020 2 to 2021 1
|  |  | Magnet construction | [30 empty] | M |  | Mirror or single coil test | [24 empty] | C | Test at CERN
|  |  | Vertical test | [30 empty] | S |  | Slice (mechanical model) | [24 empty] | B | Test at BNL
|  |  | Cold mass assembly | [30 empty] | T |  | Contract signed | [24 empty] | F | Test at FNAL
|  |  | Cryostating | [30 empty] | D |  | Delivery at CERN | [24 empty] | S | Test at Saclay
|  |  | Horizontal test | [30 empty] | V |  | Delivery to vacuum | [24 empty] | L | Test at LASA
|  |  | Available for STRING | [30 empty] | Z |  | Delivery to storage | [24 empty] | K | Test at KEK
[61 empty] | U | Test at FREIA
[61 empty] | I | Test at IMP
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
| Q4 stdalone | Q4 | 2024 1: 2
|  | Q4 | 2024 7: 2
|  | Q4 | 2024 2: 2
|  | Q4 | 2025 4: 2
Note on B134: Délio Ramos: Convert to stand-alone

## schedule October 2020
WP3 schedule October 2020 |  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
MQXF SHORT |  | MQXFS1 (RRP LARP) | 2015 4: S; 2015 5: M; 2016 3: F; 2016 9: F; 2017 5: F
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5; 2018 0; 2019 7 to 2019 0; 2021 3 to 2021 4
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0; 2019 5 to 2019 8; 2019 0; 2020 2 to 2020 3; 2020 7 to 2020 0
MQXFSM2 (Mirror AUP) | bar: 2019 5 to 2019 2
MQXFS7 (2 RRP 2 PIT CERN) | bar: 2019 1 to 2020 2; 2020 7 to 2020 8; 2020 1 to 2020 2; 2021 2
Q1/3 |  | Q1/3 4.0 m proto 1 MQXFAP1 | bar: 2015 5 to 2017 2; 2019 1 to 2019 7
Q1/3 4.2 m proto 2 MQXFAP2 - LXQFP | bar: 2016 7 to 2018 1
Q1/3 4.2 m proto 3 MQXFA03 | bar: 2018 3 to 2020 1
|  | Q1/3-series MQXFA04 - LQXFA01 (Q1) | 2020 8: B; 2021 9: F; 2022 3: D
Q1/3-series MQXFA05 | bar: 2019 2 to 2020 3; 2020 7; 2020 2 to 2021 2
|  | Q1/3-series MQXFA06 - LQXFA02 (Q3) | 2021 2: B; 2021 2: F; 2022 6: D
Q1/3-series MQXFA07 | bar: 2019 2 to 2020 3; 2020 7 to 2021 1; 2021 4 to 2021 5
|  | Q1/3-series MQXFA08 - LQXFA03 | 2021 6: B; 2022 3: F; 2023 9: D; 2023 0: 2; 2024 3: 3
Q1/3-series MQXFA09 | bar: 2020 8 to 2021 2; 2021 4 to 2021 6; 2021 8 to 2021 9
|  | Q1/3-series MQXFA10 - LQXFA04 | 2021 0: B; 2022 7: F; 2023 1: D; 2023 2: 2; 2024 3: 2
Q1/3-series MQXFA11 | bar: 2021 1 to 2021 9; 2021 2 to 2022 1
|  | Q1/3-series MQXFA12 - LQXFA05 | 2022 2: B; 2022 1: F; 2023 4: C; 2024 3: D; 2024 4: 2; 2024 7: 3; 2024 0: 3
Q1/3-series MQXFA13 | bar: 2021 5 to 2021 9; 2021 1 to 2022 1; 2022 4 to 2022 5
|  | Q1/3-series MQXFA14 - LQXFA06 | 2022 6: B; 2023 3: F; 2024 5: D; 2024 6: 2
Q1/3-series MQXFA15 | bar: 2021 9 to 2022 4; 2022 8 to 2022 9
|  | Q1/3-series MQXFA16 - LQXFA07 | 2022 0: B; 2023 7: F; 2024 7: D; 2024 8: 2; 2024 1: 3
Q1/3-series MQXFA17 | bar: 2021 2 to 2022 8; 2022 2 to 2023 1
|  | Q1/3-series MQXFA18 - LQXFA08 | 2023 2: B; 2023 1: F; 2024 9: D; 2024 0: 2
Q1/3-series MQXFA19 | bar: 2022 4 to 2022 2; 2023 4 to 2023 5
|  | Q1/3-series MQXFA20 - LQXFA09 | 2023 6: B; 2024 3: F; 2025 3: D; 2025 4: 2; 2025 7: 3
Q1/3-series MQXFA21 | bar: 2022 8 to 2023 4; 2023 8 to 2023 9
|  | Q1/3-series MQXFA22 - LQXFA10 | 2023 0: B; 2024 7: F; 2025 6: D; 2025 7: 2
Q1/3-series MQXFA23 | bar: 2022 2 to 2023 8
Q2 cold mass | Q2 | Q2-proto 1 MQXFBP1 | bar: 2016 4 to 2020 2; 2020 7 to 2020 8
Q2-proto 2 MQXFBP2 | bar: 2019 4 to 2020 3; 2020 7 to 2022 3
|  | Q2-series 1 MQXFB01 | 2021 7: C; 2023 2: 2
|  | Q2-series 2 MQXFB02 | 2021 2: C; 2023 7: 2
|  | Q2-series 3 MQXFB03 | 2022 4: C; 2023 9: 2
|  | Q2-series 4 MQXFB04 | 2022 9: C; 2023 2: 2
|  | Q2-series 5 MQXFB05 | 2023 2: C; 2024 2: 2
|  | Q2-series 6 MQXFB06 | 2023 7: C; 2024 5: 2
|  | Q2-series 7 MQXFB07 | 2023 2: C; 2024 7: 2
|  | Q2-series 8 MQXFB08 | 2024 5: C; 2024 0: 2
Q2-spare 1 MQXFB09 | bar: 2023 8 to 2024 1
Q2-spare 2 MQXFB10 | bar: 2024 1 to 2025 5
| MCBXFB | MCBXFBP1 - proto 1 (CIEMAT/CERN) | 2017 4: S; 2018 2: C; 2019 2: D; 2019 3: C; 2019 6: C; 2019 9: C
MCBXFBP2 - proto 2 (CIEMAT/CERN) | bar: 2019 3 to 2020 2; 2020 7 to 2020 9
MCBXFB01 - series 1 (CIEMAT/CERN) | bar: 2020 3; 2020 7 to 2021 3
|  | MCBXFB02 - series 2 | 2021 3: T; 2021 0: D; 2021 1: C
MCBXFB03 - series 3 | bar: 2021 7 to 2022 1
MCBXFB04 - series 4 | bar: 2021 0 to 2022 3
MCBXFB05 - series 5 | bar: 2021 2 to 2022 5
MCBXFB06 - series 6 | bar: 2022 2 to 2022 7
MCBXFB07 - series 7 | bar: 2022 4 to 2022 9
MCBXFB08 - series 8 | bar: 2022 6 to 2022 1
MCBXFB09 - spare 1 | bar: 2022 8 to 2023 1
MCBXFB10 - spare 2 | bar: 2022 0 to 2023 3
MCBXFB11 - spare 3 | bar: 2022 2 to 2023 5
MCBXFB12 - spare 4 | bar: 2023 2 to 2023 7
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
Corrector package | MCBXFA | MCBXFAP1 - proto | bar: 2020 1 to 2022 7; 2023 7
|  | MCBXFA1 - series 1 | 2021 3: T; 2022 3: U; 2022 4: D; 2022 0: C
|  | MCBXFA2 - series 2 | 2022 5: U; 2022 6: D; 2022 2: C
|  | MCBXFA3 - series 3 | 2022 7: U; 2022 8: D; 2023 3: C
|  | MCBXFA4 - series 4 | 2022 9: U; 2022 0: D; 2023 6: C
|  | MCBXFA5 - spare 1 | 2022 1: U; 2022 2: D; 2023 9: C
MCBXFA6 - spare 2 | bar: 2022 8 to 2022 1; 2023 1 to 2023 2
| HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 8 to 2019 6; 2020 2; 2020 6 to 2020 7
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 0
MgB2 corrector - proto | bar: 2017 8 to 2018 1; 2019 4 to 2019 8
|  | Batch 1a (9 magnets) | 2019 1: T; 2020 9: L; 2020 1: L; 2020 2: L; 2021 1: D
Batch 1b (9 magnets) | bar: 2020 9 to 2021 5
|  | Batch 2 (18 magnets) | [132 empty] | MQXFXS | 6 | 5 | 1 | bar: 2021 1 to 2021 1
|  | Batch 3 (18 magnets, spares) | [132 empty] | MQXFA | 23 | 4 | 2 | bar: 2021 7 to 2022 5
D1 |  | MBXFS1 - short model 1 | [132 empty] | MQXFB | 12 | 1 | 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
|  | MBXFS2 - short model 2 | [132 empty] | MCBXF | 21 | 1 | bar: 2017 1 to 2018 7; 2018 9
|  | MBXFS3 - short model 3 | [132 empty] | HO | 59 | 6 | bar: 2018 6 to 2019 6; 2019 8 to 2019 9
|  | MBXFP1 - prototype | 2019 4: T; 2021 5: K; 2021 0: D; 2022 2: C; 2024 4: -1 | D1 | 10 | 3
|  | MBXF1 - series 1 | 2022 3: K; 2022 8: D; 2022 0: C; 2022 2: 2; 2023 5: 3 | D2 | 8 | 1
|  | MBXF2 - series 2 | 2022 5: K; 2023 2: D; 2023 4: C; 2023 6: 2; 2023 0: 3 | D2 c | 14 | 2
|  | MBXF3 - series 3 | 2022 1: K; 2023 8: D; 2023 0: C; 2023 2: 2; 2024 4: 3 |  | 153 | 23
|  | MBXF4 - series 4 | 2023 5: K; 2024 2: D; 2024 4: C; 2024 6: 2; 2024 0: 3
|  | MBXF5 - spare 1 | 2023 1: K; 2024 4: D; 2024 6: C
MBXF6 - spare 2 | bar: 2023 1 to 2024 8; 2024 0
DCM |  | DCM - prototype | bar: 2021 0 to 2022 1; 2022 4
DCM - series 1 | bar: 2022 2 to 2022 6
DCM - series 2 | bar: 2022 7 to 2022 2
DCM - series 3 | bar: 2023 1 to 2023 5
DCM - series 4 | bar: 2023 6 to 2023 8
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
D2 cold mass | D2 | MBRDS1 - short model | bar: 2016 9; 2017 2 to 2019 2; 2019 5 to 2020 2; 2020 8
|  | MBRDP1 - prototype | 2018 0: T; 2021 5: D; 2022 3: C
|  | MBRD1 - series 1 | 2021 2: T*; 2022 1: D; 2022 9: C; 2022 2: 3
|  | MBRD2 - series 2 | 2022 4: D; 2022 2: C; 2023 2: 3
|  | MBRD3 - series 3 | 2022 7: D; 2023 3: C; 2023 5: 3
|  | MBRD4 - series 4 | 2022 0: D; 2023 6: C; 2023 8: 3
MBRD5 - spare 1 | bar: 2022 5 to 2023 9
|  | MBRD6 - spare 2 | 2023 4: D; 2023 0: 2; 2023 2: C
| D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDS2 - short model double aperture | bar: 2017 9 to 2018 5
MCBRDP1 - prototype | bar: 2018 6 to 2018 1; 2019 7 to 2019 9
|  | MCBRDP2 - prototype IHEP | 2020 6: I; 2020 9: D; 2020 0: C
MCBRDP3 - third prototype | bar: 2020 0 to 2021 2
|  | MCBRD01 - series 1 | 2021 2: I; 2021 4: D; 2021 5: C
|  | MCBRD02 - series 2 | 2021 5: I; 2021 7: D; 2021 8: C
MCBRD03 - series 3 | bar: 2021 5 to 2021 7; 2022 1
|  | MCBRD04 - series 4 | 2021 9: I; 2022 1: D; 2022 2: C
MCBRD05 - series 5 | bar: 2021 9 to 2021 1; 2022 1
MCBRD06 - series 6 | bar: 2021 1 to 2022 1; 2022 7
|  | MCBRD07 - series 7 | 2022 3: I; 2022 7: D; 2022 8: C
MCBRD08 - series 8 | bar: 2022 3 to 2022 5; 2022 7
MCBRD09 - spare 1 | bar: 2022 5 to 2022 7; 2023 3
MCBRD10 - spare 2 | bar: 2022 7 to 2022 9; 2023 3
MCBRD11 - spare 3 | bar: 2022 9 to 2022 1; 2023 3
MCBRD12 - spare 4 | bar: 2022 1 to 2023 1; 2023 3
MQYY |  | Q4 - short model | bar: 2016 9 to 2019 0; 2020 1 to 2020 2
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 2; 2020 7 to 2020 9; 2020 2 to 2021 1
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 2; 2020 7 to 2020 9; 2020 2 to 2021 1
|  |  | Magnet construction | [30 empty] | M |  | Mirror or single coil test | [24 empty] | C | Test at CERN
|  |  | Vertical test | [30 empty] | S |  | Slice (mechanical model) | [24 empty] | B | Test at BNL
|  |  | Cold mass assembly | [30 empty] | T |  | Contract signed | [24 empty] | F | Test at FNAL
|  |  | Cryostating | [30 empty] | D |  | Delivery at CERN | [24 empty] | S | Test at Saclay
|  |  | Horizontal test | [57 empty] | L | Test at LASA
|  |  | Available for STRING | [57 empty] | K | Test at KEK
[61 empty] | U | Test at FREIA
[61 empty] | I | Test at IMP
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
| MS Q10 | Q10 - series 1 | 2024 1: -1; 2024 7: 1+2
|  | Q10 - series 2 | 2024 6: -1; 2024 1: 1+2
|  | Q10 - series 3 | 2024 0: -1; 2025 3: 1+2
|  | Q10 - series 4 | 2025 2: -1; 2025 7: 1+2
| Q4 stdalone | Q4 | 2024 1: 2
|  | Q4 | 2024 7: 2
|  | Q4 | 2024 2: 2
|  | Q4 | 2025 4: 2
Note on B136: Délio Ramos: Convert to stand-alone
Note on DB35: Délio Ramos: Beamscreen + BPM (just a guess - actual duration to be provided by VSC)
Note on DF17: Délio Ramos: Cryostating phase 2: Service module assembly
Note on DI17: Délio Ramos: Beamscreen + BPM (just a guess - actual duration to be provided by VSC)
Note on DJ17: Délio Ramos: Cryostatting phase 3: End closure assembly
Note on DK17: Délio Ramos: Cryostatting phase 3: End closure assembly

## schedule March 2020
WP3 schedule March 2020 |  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
MQXF SHORT |  | MQXFS1 (RRP LARP) | 2015 4: S; 2015 5: M; 2016 3: F; 2016 9: F; 2017 5: F
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5; 2018 0; 2019 7 to 2019 0
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0; 2019 5 to 2019 8; 2019 0; 2020 2 to 2020 3
MQXFSM2 (Mirror AUP) | bar: 2019 5 to 2019 2
MQXFS7 (2 RRP 2 PIT CERN) | bar: 2019 1 to 2020 7
Q1/3 |  | Q1/3 4.0 m proto 1 MQXFAP1 | bar: 2015 5 to 2017 2; 2019 1 to 2019 7
Q1/3 4.2 m proto 2 MQXFAP2 - LXQFP | bar: 2016 7 to 2018 1
Q1/3 4.2 m proto 3 MQXFA03 | bar: 2018 8 to 2019 2
|  | Q1/3-series MQXFA04 - LQXFA01 | 2020 3: B; 2021 3: F; 2022 3: D; 2022 4: 2+3
Q1/3-series MQXFA05 | bar: 2019 3 to 2020 7
|  | Q1/3-series MQXFA06 - LQXFA02 | 2020 8: B; 2021 8: F; 2022 6: D; 2022 8: 2
Q1/3-series MQXFA07 | bar: 2019 8 to 2020 7; 2020 0 to 2020 1
|  | Q1/3-series MQXFA08 - LQXFA03 | 2020 2: B; 2022 5: F; 2023 1: D; 2023 2: 2; 2023 7: 3
Q1/3-series MQXFA09 | bar: 2020 3 to 2020 0; 2021 2 to 2021 3
|  | Q1/3-series MQXFA10 - LQXFA04 | 2021 4: B; 2022 6: F; 2023 3: D; 2023 4: 2
Q1/3-series MQXFA11 | bar: 2020 7 to 2021 3; 2021 6 to 2021 7
|  | Q1/3-series MQXFA12 - LQXFA05 | 2021 8: B; 2022 0: F; 2023 7: D; 2023 8: 2; 2023 1: 3
Q1/3-series MQXFA13 | bar: 2020 2 to 2021 8; 2021 0 to 2021 1
|  | Q1/3-series MQXFA14 - LQXFA06 | 2021 2: B; 2023 1: F; 2023 9: D; 2023 0: 2
Q1/3-series MQXFA15 | bar: 2021 4 to 2022 3
|  | Q1/3-series MQXFA16 - LQXFA07 | 2022 4: B; 2023 5: F; 2023 2: D; 2024 1: 2; 2024 4: 3
Q1/3-series MQXFA17 | bar: 2021 8 to 2022 7
|  | Q1/3-series MQXFA18 - LQXFA08 | 2022 8: B; 2023 9: F; 2024 2: D; 2024 3: 2
Q1/3-series MQXFA19 | bar: 2021 2 to 2022 8; 2022 0 to 2022 1
|  | Q1/3-series MQXFA20 - LQXFA09 | 2022 2: B; 2024 1: F; 2024 7: D; 2024 8: 2; 2024 1: 3
Q1/3-series MQXFA21 | bar: 2022 3 to 2023 3
|  | Q1/3-series MQXFA22 - LQXFA10 | 2023 4: B; 2024 4: F; 2024 1: D; 2024 2: 2
Q1/3-series MQXFA23 | bar: 2022 7 to 2023 4; 2023 6 to 2023 7
Q2 cold mass | Q2 | Q2-proto 1 MQXFBP1 (CERN) Q2b | 2020 1: Short; 2020 4: C; 2021 2: C; 2021 4: 2
|  | Q2-proto 2 MQXFBP2 (CERN) Q2a | 2021 2: C; 2021 7: 2; 2024 7: -1
|  | Q2-series 1 MQXFB01 (CERN) Q2b | 2021 5: 1; 2021 6: C; 2023 2: 2
|  | Q2-series 2 MQXFB02 (CERN) Q2a | 2020 3: T; 2021 1: 1; 2021 2: C; 2023 7: 2
|  | Q2-series 3 MQXFB03 (ind at CERN) Q2b | 2022 4: 1; 2022 5: C; 2023 9: 2
|  | Q2-series 4 MQXFB04 (ind at CERN) Q2a | 2022 8: 1; 2022 9: C; 2023 2: 2
|  | Q2-series 5 MQXFB05 (ind at CERN) Q2b | 2022 2: 1; 2023 1: C; 2024 2: 2
|  | Q2-series 6 MQXFB06 (ind at CERN) Q2a | 2023 4: 1; 2023 5: C; 2024 5: 2
|  | Q2-series 7 MQXFB07 (ind at CERN) Q2b | 2023 8: 1; 2023 9: C; 2024 7: 2
|  | Q2-series 8 MQXFB08 (ind at CERN) Q2a | 2023 2: 1; 2024 1: C; 2024 0: 2
Q2-spare 1 MQXFB09 (ind at CERN) Q2b | bar: 2023 3 to 2024 6
Q2-spare 2 MQXFB10 (ind at CERN) Q2a | bar: 2023 6 to 2024 0
| MCBXFB | MCBXFBP1 - proto 1 | 2017 4: S; 2018 2: C; 2019 2: D; 2019 3: C; 2019 6: C; 2019 9: C
MCBXFBP2 - proto 2 | bar: 2019 3 to 2020 4
MCBXFB01 - series 1 | bar: 2020 4 to 2020 1
|  | MCBXFB02 - series 2 | 2020 6: T; 2021 5: D; 2021 6: C
MCBXFB03 - series 3 | bar: 2021 2 to 2021 8
MCBXFB04 - series 4 | bar: 2021 5 to 2021 0
MCBXFB05 - series 5 | bar: 2021 7 to 2021 2
MCBXFB06 - series 6 | bar: 2021 9 to 2022 2
MCBXFB07 - series 7 | bar: 2021 1 to 2022 4
MCBXFB08 - series 8 | bar: 2022 1 to 2022 6
MCBXFB09 - spare 1 | bar: 2022 3 to 2022 8
MCBXFB10 - spare 2 | bar: 2022 5 to 2022 0
MCBXFB11 - spare 3 | bar: 2022 7 to 2022 2
MCBXFB12 - spare 4 | bar: 2022 9 to 2023 2
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
Corrector package | MCBXFA | MCBXFAP1 - proto 1 | 2021 6: D; 2021 7: C; 2021 1: 1+2; 2022 4: C; 2023 8: -1
|  | MCBXFA1 - series 1 | 2020 6: T; 2022 3: U; 2022 4: D; 2022 8: 1+2; 2022 2: C
|  | MCBXFA2 - series 2 | 2022 5: U; 2022 6: D; 2022 2: 1+2; 2023 3: C
|  | MCBXFA3 - series 3 | 2022 7: U; 2022 8: D; 2023 3: 1+2; 2023 6: C
|  | MCBXFA4 - series 4 | 2022 9: U; 2022 0: D; 2023 6: 1+2; 2023 9: C
|  | MCBXFA5 - spare 1 | 2022 1: U; 2022 2: D; 2023 9: 1+2; 2023 2: C
MCBXFA6 - spare 2 | bar: 2022 8 to 2022 1; 2023 1 to 2023 2
| HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 8 to 2019 6; 2020 3 to 2020 4
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 0
MgB2 corrector - proto | bar: 2017 8 to 2018 1; 2019 4 to 2019 8
|  | Batch 1a (9 magnets) | 2019 1: T; 2020 6: L; 2020 9: D
Batch 1b (9 magnets) | bar: 2020 6 to 2021 1
Batch 2 (18 magnets) | bar: 2020 0 to 2021 6
Batch 3 (18 magnets, spares) | bar: 2021 4 to 2021 2
D1 |  | MBXFS1 - short model 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
MBXFS2 - short model 2 | bar: 2017 1 to 2018 7; 2018 9
MBXFS3 - short model 3 | bar: 2018 6 to 2019 6; 2019 8 to 2019 9
|  | MBXFP1 - prototype | 2019 4: T; 2020 0: K; 2021 2: D; 2021 3: 1; 2021 5: C; 2021 7: 2+3; 2023 2: -1
|  | MBXF1 - series 1 | 2021 5: K; 2021 2: D; 2022 1: 1; 2022 2: C; 2022 4: 2; 2022 9: 3
|  | MBXF2 - series 2 | 2021 9: K; 2022 3: D; 2022 4: 1; 2022 5: C; 2022 0: 2; 2023 2: 3
|  | MBXF3 - series 3 | 2022 1: K; 2022 2: D; 2023 1: 1; 2023 2: C; 2023 4: 2; 2023 8: 3
|  | MBXF4 - series 4 | 2022 9: K; 2023 3: D; 2023 4: 1; 2023 5: C; 2023 7: 2; 2023 1: 3
|  | MBXF5 - spare 1 | 2023 1: K; 2023 2: D; 2024 1: 1; 2024 2: C
MBXF6 - spare 2 | bar: 2023 8 to 2024 5
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
D2 cold mass | D2 | MBRDS1 - short model | bar: 2016 9; 2017 2 to 2019 2; 2019 5 to 2020 4
|  | MBRDP1 - prototype | 2018 0: T; 2020 1: D; 2021 4: 1+2; 2021 9: C; 2023 4: -1
|  | MBRD1 - series 1 | 2020 9: T; 2021 9: D; 2022 1: 1+2; 2022 5: C; 2022 9: 3
|  | MBRD2 - series 2 | 2022 2: D; 2022 6: 1+2; 2022 9: C; 2022 2: 3
|  | MBRD3 - series 3 | 2022 5: D; 2022 9: 1+2; 2022 2: C; 2023 3: 3
|  | MBRD4 - series 4 | 2022 8: D; 2022 2: 1+2; 2023 3: C; 2023 6: 3
|  | MBRD5 - spare 1 | 2022 1: D; 2023 3: 1+2; 2023 6: C
|  | MBRD6 - spare 2 | 2023 2: D; 2023 6: 1+2; 2023 9: C
| D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDS2 - short model double aperture | bar: 2017 9 to 2018 5
MCBRDP1 - prototype | bar: 2018 6 to 2018 1; 2019 7 to 2019 9
|  | MCBRDP2 - prototype IHEP | 2020 4: I; 2020 6: D; 2020 7: C
|  | MCBRD01 - series 1 | 2020 8: I; 2020 9: D; 2020 0: C
|  | MCBRD02 - series 2 | 2020 0: I; 2020 1: D; 2020 2: C
MCBRD03 - series 3 | bar: 2020 0 to 2020 2; 2021 5
|  | MCBRD04 - series 4 | 2021 2: I; 2021 5: D; 2021 6: C
MCBRD05 - series 5 | bar: 2021 2 to 2021 5
MCBRD06 - series 6 | bar: 2021 4 to 2021 6; 2021 1
|  | MCBRD07 - series 7 | 2021 8: I; 2021 1: D; 2021 2: C
MCBRD08 - series 8 | bar: 2021 8 to 2021 1
MCBRD09 - spare 1 | bar: 2021 0 to 2021 2; 2022 7
MCBRD10 - spare 2 | bar: 2021 2 to 2022 2; 2022 7
MCBRD11 - spare 3 | bar: 2022 2 to 2022 4; 2022 7
MCBRD12 - spare 4 | bar: 2022 4 to 2022 7
MQYY |  | Q4 - short model | bar: 2016 9 to 2019 0; 2020 1 to 2020 2
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 9; 2020 2 to 2021 1
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 9; 2020 2 to 2021 1
|  |  | Magnet construction | [30 empty] | M |  | Mirror or single coil test | [24 empty] | C | Test at CERN
|  |  | Vertical test | [30 empty] | S |  | Slice (mechanical model) | [24 empty] | B | Test at BNL
|  |  | Cold mass assembly | [30 empty] | T |  | Contract signed | [24 empty] | F | Test at FNAL
|  |  | Cryostating (phases 1/2/3) | [30 empty] | D |  | Delivery at CERN | [24 empty] | S | Test at Saclay
|  | -1 | 2015 1: Decryostating; 2019 1: L; 2019 2: Test at LASA
|  |  | Horizontal test | [57 empty] | K | Test at KEK
|  |  | Beamscreen+BPM | [57 empty] | U | Test at FREIA
|  |  | Available for STRING | [57 empty] | I | Test at IMP
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
| MS Q10 | Q10 - series 1 | 2024 1: -1; 2024 7: 1+2
|  | Q10 - series 2 | 2024 6: -1; 2024 1: 1+2
|  | Q10 - series 3 | 2024 0: -1; 2025 3: 1+2
|  | Q10 - series 4 | 2025 2: -1; 2025 7: 1+2
| Q4 stdalone | Q4 | 2024 1: 2; 2024 8: 3
|  | Q4 | 2024 7: 2; 2025 1: 3
|  | Q4 | 2024 2: 2; 2025 5: 3
|  | Q4 | 2025 4: 2; 2025 9: 3
Note on B130: Délio Ramos: Convert to stand-alone
Note on CD33: Délio Ramos: For the string: no Beamsreen. No BPM
Note on CE34: Délio Ramos: For the string: No beamscreen. No BPM
Note on CG80: Délio Ramos: For the string: no beamscreen. No BPM
Note on CL60: Délio Ramos: Includes standard section+service module+current leads. For the string: No BS. No BPM
Note on CO13: Délio Ramos: For the string: No beamscreen. No BPM. Includes service module+end closure
Note on CQ15: Délio Ramos: For the string: No beamscreen. No BPM
Note on CT61: Délio Ramos: Standard section+service module+current leads
Note on CX17: Délio Ramos: Cryostating phase 2: Service module assembly
Note on DA17: Délio Ramos: Beamscreen + BPM (just a guess - actual duration to be provided by VSC)
Note on DB17: Délio Ramos: Cryostatting phase 3: End closure assembly
Note on DB35: Délio Ramos: Beamscreen + BPM (just a guess - actual duration to be provided by VSC)
Note on DN34: Délio Ramos: Decryostating for testing of spare

## schedule September 2019
WP3 schedule October 2019 |  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
MQXF SHORT |  | MQXFS1 (RRP LARP) | 2015 4: S; 2015 5: M; 2016 3: F; 2016 9: F; 2017 5: F
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5; 2018 0; 2019 7 to 2019 0
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0; 2019 5 to 2019 8; 2019 0
Q1/3 |  | Q1/3 4.0 m proto 1 MQXFAP1 | bar: 2015 5 to 2017 2; 2019 1 to 2019 7
Q1/3 4.2 m proto 2 MQXFAP2 - LXQFP | bar: 2016 7 to 2018 1; 2019 0 to 2020 8
Q1/3 4.2 m proto 3 MQXFA03 | bar: 2018 8 to 2019 6; 2019 8 to 2019 9
|  | Q1/3-series MQXFA04 - LQXFA01 | 2019 0: B; 2021 1: F; 2021 3: F; 2022 3: D; 2022 4: 2+3
Q1/3-series MQXFA05 | bar: 2019 1 to 2020 3
|  | Q1/3-series MQXFA06 - LQXFA02 | 2020 5: B; 2021 5: F; 2021 7: F; 2022 6: D; 2022 8: 2
Q1/3-series MQXFA07 | bar: 2019 9 to 2020 0
|  | Q1/3-series MQXFA08 - LQXFA03 | 2020 1: B; 2021 9: F; 2021 1: F; 2023 1: D; 2023 2: 2; 2023 7: 3
Q1/3-series MQXFA09 | bar: 2020 3 to 2021 3
|  | Q1/3-series MQXFA10 - LQXFA04 | 2021 4: B; 2022 1: F; 2022 3: F; 2023 3: D; 2023 4: 2
Q1/3-series MQXFA11 | bar: 2020 7 to 2021 4; 2021 6 to 2021 7
|  | Q1/3-series MQXFA12 - LQXFA05 | 2021 8: B; 2022 5: F; 2022 7: F; 2023 7: D; 2023 8: 2; 2023 1: 3
Q1/3-series MQXFA13 | bar: 2020 1 to 2021 8; 2021 0 to 2021 1
|  | Q1/3-series MQXFA14 - LQXFA06 | 2021 2: B; 2022 1: F; 2023 1: F; 2023 9: D; 2023 0: 2
Q1/3-series MQXFA15 | bar: 2021 3 to 2021 2; 2022 2 to 2022 3
|  | Q1/3-series MQXFA16 - LQXFA07 | 2022 4: B; 2023 3: F; 2023 5: F; 2023 2: D; 2024 1: 2; 2024 4: 3
Q1/3-series MQXFA17 | bar: 2021 7 to 2022 4; 2022 6 to 2022 7
|  | Q1/3-series MQXFA18 - LQXFA08 | 2022 8: B; 2023 7: F; 2023 9: F; 2024 2: D; 2024 3: 2
Q1/3-series MQXFA19 | bar: 2021 0 to 2022 7; 2022 0 to 2022 1
|  | Q1/3-series MQXFA20 - LQXFA09 | 2022 2: B; 2023 0: F; 2024 1: F; 2024 7: D; 2024 8: 2; 2024 1: 3
Q1/3-series MQXFA21 | bar: 2022 2 to 2022 2; 2023 2 to 2023 3
|  | Q1/3-series MQXFA22 - LQXFA10 | 2023 4: B; 2024 1: F; 2024 4: F; 2024 1: D; 2024 2: 2
Q1/3-series MQXFA23 | bar: 2022 6 to 2023 3; 2023 6 to 2023 7
Q2 cold mass | Q2 | Q2-proto 1 MQXFBP1 (CERN) Q2b | 2019 1: Short; 2020 1: C; 2020 1: C; 2021 1: 2
|  | Q2-proto 2 MQXFBP2 (CERN) Q2a | 2021 1: C; 2021 6: 2; 2024 7: -1
|  | Q2-series 1 MQXFB01 (CERN) Q2b | 2021 5: 1; 2021 6: C; 2023 2: 2
|  | Q2-series 2 MQXFB02 (ind at CERN) Q2a | 2020 3: T; 2022 1: 1; 2022 2: C; 2023 7: 2
|  | Q2-series 3 MQXFB03 (ind at CERN) Q2b | 2022 4: 1; 2022 5: C; 2023 9: 2
|  | Q2-series 4 MQXFB04 (ind at CERN) Q2a | 2022 8: 1; 2022 9: C; 2023 2: 2
|  | Q2-series 5 MQXFB05 (ind at CERN) Q2b | 2022 2: 1; 2023 1: C; 2024 2: 2
|  | Q2-series 6 MQXFB06 (ind at CERN) Q2a | 2023 4: 1; 2023 5: C; 2024 5: 2
|  | Q2-series 7 MQXFB07 (ind at CERN) Q2b | 2023 8: 1; 2023 9: C; 2024 7: 2
|  | Q2-series 8 MQXFB08 (ind at CERN) Q2a | 2023 2: 1; 2024 1: C; 2024 0: 2
Q2-spare 1 MQXFB09 (ind at CERN) Q2b | bar: 2023 3 to 2024 6
Q2-spare 2 MQXFB10 (ind at CERN) Q2a | bar: 2023 6 to 2024 0
| MCBXFB | MCBXFBP1 - proto 1 | 2017 4: S; 2018 2: C; 2019 2: D; 2019 3: C; 2019 6: C; 2019 9: C
MCBXFBP2 - proto 2 | bar: 2019 3 to 2020 1
|  | MCBXFB01 - series 1 | 2020 2: T; 2021 1: D; 2021 2: C
MCBXFB02 - series 2 | bar: 2020 9 to 2021 4
MCBXFB03 - series 3 | bar: 2020 2 to 2021 6
MCBXFB04 - series 4 | bar: 2021 3 to 2021 8
MCBXFB05 - series 5 | bar: 2021 5 to 2021 0
MCBXFB06 - series 6 | bar: 2021 7 to 2021 2
MCBXFB07 - series 7 | bar: 2021 9 to 2022 2
MCBXFB08 - series 8 | bar: 2021 1 to 2022 4
MCBXFB09 - spare 1 | bar: 2022 1 to 2022 6
MCBXFB10 - spare 2 | bar: 2022 3 to 2022 8
MCBXFB11 - spare 3 | bar: 2022 5 to 2022 0
MCBXFB12 - spare 4 | bar: 2022 7 to 2022 2
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
Corrector package | MCBXFA | MCBXFAP1 - proto 1 | 2020 6: D; 2020 7: C; 2020 1: 1+2; 2021 4: C; 2022 8: -1
|  | MCBXFA1 - series 1 | 2020 2: T; 2021 3: U; 2021 4: D; 2021 8: 1+2; 2021 2: C
|  | MCBXFA2 - series 2 | 2021 5: U; 2021 6: D; 2021 2: 1+2; 2022 3: C
|  | MCBXFA3 - series 3 | 2021 7: U; 2021 8: D; 2022 3: 1+2; 2022 6: C
|  | MCBXFA4 - series 4 | 2021 9: U; 2021 0: D; 2022 6: 1+2; 2022 9: C
|  | MCBXFA5 - spare 1 | 2021 1: U; 2021 2: D; 2022 9: 1+2; 2022 2: C
MCBXFA6 - spare 2 | bar: 2021 8 to 2021 1; 2022 1 to 2022 2
| HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 8 to 2019 6
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 0
MgB2 corrector - proto | bar: 2017 8 to 2018 1; 2019 4 to 2019 8
|  | Batch 1a (9 magnets) | 2019 1: T; 2020 3: L; 2020 6: D
Batch 1b (9 magnets) | bar: 2020 3 to 2020 0
Batch 2 (18 magnets) | bar: 2020 7 to 2021 3
Batch 3 (18 magnets, spares) | bar: 2021 1 to 2021 9
D1 |  | MBXFS1 - short model 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
MBXFS2 - short model 2 | bar: 2017 1 to 2018 7; 2018 9
MBXFS3 - short model 3 | bar: 2018 6 to 2019 6; 2019 8 to 2019 9
|  | MBXFP1 - prototype | 2019 4: T; 2020 8: K; 2020 2: D; 2021 1: 1; 2021 3: C; 2021 5: 2+3; 2023 2: -1
|  | MBXF1 - series 1 | 2021 5: K; 2021 2: D; 2022 1: 1; 2022 2: C; 2022 4: 2; 2022 9: 3
|  | MBXF2 - series 2 | 2021 9: K; 2022 3: D; 2022 4: 1; 2022 5: C; 2022 0: 2; 2023 2: 3
|  | MBXF3 - series 3 | 2022 1: K; 2022 2: D; 2023 1: 1; 2023 2: C; 2023 4: 2; 2023 8: 3
|  | MBXF4 - series 4 | 2022 9: K; 2023 3: D; 2023 4: 1; 2023 5: C; 2023 7: 2; 2023 1: 3
|  | MBXF5 - spare 1 | 2023 1: K; 2023 2: D; 2024 1: 1; 2024 2: C
MBXF6 - spare 2 | bar: 2023 8 to 2024 5
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
D2 cold mass | D2 | MBRDS1 - short model | bar: 2016 9; 2017 2 to 2019 2; 2019 5 to 2019 0
|  | MBRDP1 - prototype | 2018 0: T; 2020 8: D; 2020 2: 1+2; 2021 5: C; 2023 4: -1
|  | MBRD1 - series 1 | 2021 9: D; 2022 1: 1+2; 2022 5: C; 2022 9: 3
|  | MBRD2 - series 2 | 2022 2: D; 2022 6: 1+2; 2022 9: C; 2022 2: 3
|  | MBRD3 - series 3 | 2022 5: D; 2022 9: 1+2; 2022 2: C; 2023 3: 3
|  | MBRD4 - series 4 | 2022 8: D; 2022 2: 1+2; 2023 3: C; 2023 6: 3
|  | MBRD5 - spare 1 | 2022 1: D; 2023 3: 1+2; 2023 6: C
|  | MBRD6 - spare 2 | 2023 2: D; 2023 6: 1+2; 2023 9: C
| D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDS2 - short model double aperture | bar: 2017 9 to 2018 5
MCBRDP1 - prototype | bar: 2018 6 to 2018 1; 2019 7 to 2019 9
MCBRDP2 - prototype IHEP | bar: 2019 7 to 2019 2; 2020 2
|  | MCBRD01 - series 1 | 2020 6: I; 2020 9: D; 2020 0: C
|  | MCBRD02 - series 2 | 2020 8: I; 2020 1: D; 2020 2: C
MCBRD03 - series 3 | bar: 2020 8 to 2020 0; 2021 5
|  | MCBRD04 - series 4 | 2020 2: I; 2021 5: D; 2021 6: C
MCBRD05 - series 5 | bar: 2020 2 to 2021 2; 2021 5
MCBRD06 - series 6 | bar: 2021 2 to 2021 4; 2021 1
|  | MCBRD07 - series 7 | 2021 6: I; 2021 1: D; 2021 2: C
MCBRD08 - series 8 | bar: 2021 6 to 2021 8; 2021 1
MCBRD09 - spare 1 | bar: 2021 8 to 2021 0; 2022 7
MCBRD10 - spare 2 | bar: 2021 0 to 2021 2; 2022 7
MCBRD11 - spare 3 | bar: 2021 2 to 2022 2; 2022 7
MCBRD12 - spare 4 | bar: 2022 2 to 2022 4; 2022 7
MQYY |  | Q4 - short model | bar: 2016 9 to 2019 0; 2020 1 to 2020 2
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 9; 2020 2 to 2021 1
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 9; 2020 2 to 2021 1
|  |  | Magnet construction | [30 empty] | M |  | Mirror or single coil test | [24 empty] | C | Test at CERN
|  |  | Vertical test | [30 empty] | S |  | Slice (mechanical model) | [24 empty] | B | Test at BNL
|  |  | Cold mass assembly | [30 empty] | T |  | Contract signed | [24 empty] | F | Test at FNAL
|  |  | Cryostating (phases 1/2/3) | [30 empty] | D |  | Delivery at CERN | [24 empty] | S | Test at Saclay
|  | -1 | 2015 1: Decryostating; 2019 1: L; 2019 2: Test at LASA
|  |  | Horizontal test | [57 empty] | K | Test at KEK
|  |  | Beamscreen+BPM | [57 empty] | U | Test at FREIA
|  |  | Available for STRING | [57 empty] | I | Test at IMP
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
| MS Q10 | Q10 - series 1 | 2024 1: -1; 2024 7: 1+2
|  | Q10 - series 2 | 2024 6: -1; 2024 1: 1+2
|  | Q10 - series 3 | 2024 0: -1; 2025 3: 1+2
|  | Q10 - series 4 | 2025 2: -1; 2025 7: 1+2
| Q4 stdalone | Q4 | 2024 1: 2; 2024 8: 3
|  | Q4 | 2024 7: 2; 2025 1: 3
|  | Q4 | 2024 2: 2; 2025 5: 3
|  | Q4 | 2025 4: 2; 2025 9: 3
Note on B128: Délio Ramos: Convert to stand-alone
Note on BZ58: Délio Ramos: Includes standard section+service module+current leads. For the string: No BS. No BPM
Note on CA31: Délio Ramos: For the string: no Beamsreen. No BPM
Note on CD32: Délio Ramos: For the string: No beamscreen. No BPM
Note on CE78: Délio Ramos: For the string: no beamscreen. No BPM
Note on CH59: Délio Ramos: Standard section+service module+current leads
Note on CO11: Délio Ramos: For the string: No beamscreen. No BPM. Includes service module+end closure
Note on CQ13: Délio Ramos: For the string: No beamscreen. No BPM
Note on CX15: Délio Ramos: Cryostating phase 2: Service module assembly
Note on DA15: Délio Ramos: Beamscreen + BPM (just a guess - actual duration to be provided by VSC)
Note on DB15: Délio Ramos: Cryostatting phase 3: End closure assembly
Note on DB33: Délio Ramos: Beamscreen + BPM (just a guess - actual duration to be provided by VSC)
Note on DN32: Délio Ramos: Decryostating for testing of spare

## schedule December 2018
WP3 schedule December 2018 |  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
MQXF SHORT |  | MQXFS1 (RRP LARP) | 2015 4: S; 2015 5: M; 2016 3: F; 2016 9: F; 2017 5: F
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0
Q1/3 |  | Q1/3 4.0 m proto 1 MQXFAP1 | bar: 2015 5 to 2017 2
Q1/3 4.2 m proto 2 MQXFAP2 | bar: 2016 7 to 2018 1
Q1/3 4.2 m proto 3 MQXFA03 | bar: 2018 8 to 2019 6; 2019 8 to 2019 9
|  | Q1/3-series MQXFA04 - LQXFA01 | 2019 0: B; 2021 3: F; 2021 7: D
Q1/3-series MQXFA05 | bar: 2019 1 to 2020 3
|  | Q1/3-series MQXFA06 - LQXFA02 | 2020 5: B; 2021 8: F; 2021 2: D
Q1/3-series MQXFA07 | bar: 2019 9 to 2020 0
|  | Q1/3-series MQXFA08 - LQXFA03 | 2020 1: B; 2021 1: F; 2022 6: D
Q1/3-series MQXFA09 | bar: 2020 3 to 2021 3
|  | Q1/3-series MQXFA10 - LQXFA04 | 2021 4: B; 2022 3: F; 2022 0: D
Q1/3-series MQXFA11 | bar: 2020 7 to 2021 4; 2021 6 to 2021 7
|  | Q1/3-series MQXFA12 - LQXFA05 | 2021 8: B; 2022 7: F; 2023 2: D
Q1/3-series MQXFA13 | bar: 2020 1 to 2021 8; 2021 0 to 2021 1
|  | Q1/3-series MQXFA14 - LQXFA06 | 2021 2: B; 2023 1: F; 2023 6: D
Q1/3-series MQXFA15 | bar: 2021 3 to 2021 2; 2022 2 to 2022 3
|  | Q1/3-series MQXFA16 - LQXFA07 | 2022 4: B; 2023 5: F; 2023 0: D
Q1/3-series MQXFA17 | bar: 2021 7 to 2022 4; 2022 6 to 2022 7
|  | Q1/3-series MQXFA18 - LQXFA08 | 2022 8: B; 2023 8: F; 2023 2: D
Q1/3-series MQXFA19 | bar: 2021 0 to 2022 7; 2022 0 to 2022 1
|  | Q1/3-series MQXFA20 - LQXFA09 | 2022 2: B; 2024 1: F; 2024 5: D
Q1/3-series MQXFA21 | bar: 2022 2 to 2022 2; 2023 2 to 2023 3
|  | Q1/3-series MQXFA22 - LQXFA10 | 2023 4: B; 2024 4: F; 2024 0: D
Q1/3-series MQXFA23 | bar: 2022 6 to 2023 3; 2023 6 to 2023 7
Q2 cold mass | Q2 | Q2-proto 1 MQXFBP1 (CERN) | bar: 2016 4 to 2019 6; 2019 1 to 2020 7
Q2-proto 2 MQXFBP2 (CERN) | bar: 2018 5 to 2020 3
Q2-series 1 MQXFB01 (CERN) | bar: 2019 4 to 2020 0
Q2-series 2 MQXFB02 (CERN) | bar: 2019 8 to 2021 2
Q2-series 3 MQXFB03 (CERN) | bar: 2019 2 to 2021 6
Q2-series 4 MQXFB04 (CERN) | bar: 2020 4 to 2021 0
Q2-series 5 MQXFB05 (CERN) | bar: 2020 8 to 2022 2
Q2-series 6 MQXFB06 (CERN) | bar: 2020 2 to 2022 6
Q2-series 7 MQXFB07 (CERN) | bar: 2021 4 to 2022 0
Q2-series 8 MQXFB08 (CERN) | bar: 2021 8 to 2023 2
Q2-spare 1 MQXFB09 (CERN) | bar: 2021 2 to 2023 6
Q2-spare 2 MQXFB10 (CERN) | bar: 2022 4 to 2023 0
| MCBXFB | MCBXFBP1 - proto 1 | 2017 4: S; 2018 2: C; 2019 2: D; 2019 3: C
MCBXFBP2 - proto 2 | bar: 2019 3 to 2019 0
|  | MCBXFB01 - series 1 | 2019 3: T; 2020 3: D; 2020 4: C
MCBXFB02 - series 2 | bar: 2019 0 to 2020 6
MCBXFB03 - series 3 | bar: 2020 1 to 2020 5; 2020 2
MCBXFB04 - series 4 | bar: 2020 3 to 2020 7; 2020 2
MCBXFB05 - series 5 | bar: 2020 5 to 2020 9; 2020 2
MCBXFB06 - series 6 | bar: 2020 7 to 2020 2
MCBXFB07 - series 7 | bar: 2020 9 to 2021 1
MCBXFB08 - series 8 | bar: 2020 1 to 2021 3; 2021 2
MCBXFB09 - spare 1 | bar: 2021 1 to 2021 5; 2021 2
MCBXFB10 - spare 2 | bar: 2021 3 to 2021 7; 2021 2
MCBXFB11 - spare 3 | bar: 2021 5 to 2021 9; 2021 2
MCBXFB12 - spare 4 | bar: 2021 7 to 2021 2
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
Corrector package | MCBXFA | MCBXFAP1 - proto 1 | 2018 1: T; 2020 6: D; 2020 7: C; 2021 3: C
MCBXFA1 - series 1 | bar: 2020 3 to 2020 8; 2020 1 to 2021 7
MCBXFA2 - series 2 | bar: 2020 6 to 2020 0; 2021 2 to 2021 9
MCBXFA3 - series 3 | bar: 2020 8 to 2020 2; 2021 4 to 2021 1
MCBXFA4 - series 4 | bar: 2020 0 to 2021 2; 2021 6 to 2022 1
MCBXFA5 - spare 1 | bar: 2020 2 to 2021 4; 2021 8 to 2022 3
MCBXFA6 - spare 2 | bar: 2021 2 to 2021 6
| HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 6 to 2018 0
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 6
MgB2 corrector - proto | bar: 2017 0 to 2018 6
|  | N&S Sextupole - series (8+4) | 2019 1: T; 2020 1: L; 2020 3: D; 2020 9: L; 2020 1: D; 2021 4: L; 2021 6: D
N&S Octupole - series (8+4) | bar: 2019 9 to 2021 6
N&S Decapole - series (8+4) | bar: 2019 9 to 2021 6
N&S Dodecapole - series (8+4) | bar: 2019 9 to 2021 6
Skew quadrupole - series (4+2) | bar: 2019 9 to 2021 6
D1 |  | MBXFS1 - short model 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
MBXFS2 - short model 2 | bar: 2017 1 to 2018 7; 2018 9
MBXFS3 - short model 3 | bar: 2018 6 to 2019 2
|  | MBXFP1 - prototype | 2019 4: T; 2020 2: K; 2020 2: D; 2021 4: C
|  | MBXF1 - series 1 | 2021 1: K; 2021 2: D; 2022 4: C
|  | MBXF2 - series 1 | 2021 3: K; 2022 3: D; 2022 7: C
|  | MBXF3 - series 1 | 2021 1: K; 2022 2: D; 2023 4: C
|  | MBXF4 - series 1 | 2022 1: K; 2023 3: D; 2023 7: C
|  | MBXF5 - spare 1 | 2022 1: K; 2023 2: D; 2024 4: C
MBXF6 - spare 2 | bar: 2022 8 to 2023 5; 2024 3
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
D2 cold mass | D2 | MBRDS1 - short model | bar: 2016 9; 2017 2 to 2018 0
MBRDP1 - prototype | bar: 2018 0; 2019 1 to 2020 2
MBRD1 - series 1 | bar: 2020 1 to 2022 2
MBRD2 - series 2 | bar: 2021 4 to 2022 8
MBRD3 - series 3 | bar: 2021 7 to 2022 1
MBRD4 - series 4 | bar: 2021 0 to 2023 2
MBRD5 - spare 1 | bar: 2022 1 to 2023 5
MBRD6 - spare 2 | bar: 2022 4 to 2023 9
| D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDS2 - short model double aperture | bar: 2017 9 to 2018 1
MCBRDP1 - prototype | bar: 2018 1 to 2018 5
MCBRDP2 - prototype IHEP | bar: 2019 1 to 2019 6; 2019 8
|  | MCBRD01 - series 1 | 2020 1: I; 2020 3: D; 2020 4: C
|  | MCBRD02 - series 2 | 2020 3: I; 2020 5: D; 2020 6: C
MCBRD03 - series 3 | bar: 2020 3 to 2020 5; 2020 1
|  | MCBRD04 - series 4 | 2020 7: I; 2020 1: D; 2020 2: C
MCBRD05 - series 5 | bar: 2020 7 to 2020 9; 2020 1
MCBRD06 - series 6 | bar: 2020 9 to 2020 1; 2021 5
|  | MCBRD07 - series 7 | 2021 1: I; 2021 5: D; 2021 6: C
MCBRD08 - series 8 | bar: 2021 1 to 2021 3; 2021 5
MCBRD09 - spare 1 | bar: 2021 3 to 2021 5; 2022 1
MCBRD10 - spare 2 | bar: 2021 5 to 2021 7; 2022 1
MCBRD11 - spare 3 | bar: 2021 7 to 2021 9; 2022 1
MCBRD12 - spare 4 | bar: 2021 9 to 2021 1; 2022 1
MQYY |  | Q4 - short model | bar: 2016 9 to 2018 9
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 4
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 4
|  |  | Magnet construction | [30 empty] | M |  | Mirror or single coil test | [24 empty] | C | Test at CERN
|  |  | Vertical test | [30 empty] | S |  | Slice (mechanical model) | [24 empty] | B | Test at BNL
|  |  | Cold mass assembly | [30 empty] | T |  | Contract signed | [24 empty] | F | Test at FNAL
|  |  | Cryostating | [30 empty] | D |  | Delivery at CERN | [24 empty] | S | Test at Saclay
|  |  | Horizontal test | [57 empty] | L | Test at LASA
[61 empty] | K | Test at KEK
[61 empty] | N | Test at FREIA
[61 empty] | I | Test at IMP
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
| Q4 | Q4 - series 1 | bar: 2019 1 to 2019 8
Q4 - series 2 | bar: 2020 3 to 2020 0
Q4 - series 3 | bar: 2020 5 to 2020 2
Q4 - series 4 | bar: 2020 7 to 2021 2
| Q5 | Q5 - series 1 | bar: 2024 0 to 2025 1
Q5 - series 2 | bar: 2024 2 to 2025 3
Q5 - series 3 | bar: 2025 2 to 2025 5
Q5 - series 4 | bar: 2025 4 to 2025 7
| MS Q10 | Q10 - series 1 | bar: 2019 1 to 2019 8
Q10 - series 2 | bar: 2019 5 to 2019 2
Q10 - series 3 | bar: 2019 9 to 2020 4
Q10 - series 4 | bar: 2020 1 to 2020 8
| IR6 Q5 | IR6 Q5 - series 1 | bar: 2025 7 to 2025 0
IR6 Q5 - series 2 | bar: 2025 9 to 2025 2
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| Q2 at CERN | Q2-proto 1 MQXFBP1 (CERN) | bar: 2016 4 to 2019 6; 2019 1 to 2020 7
Q2-proto 2 MQXFBP2 (CERN) | bar: 2018 5 to 2020 3
Q2-series 1 MQXFB01 (CERN) | bar: 2019 4 to 2020 0
Q2-series 2 MQXFB02 (CERN) | bar: 2019 8 to 2021 2
Q2-series 3 MQXFB03 (CERN) | bar: 2019 2 to 2021 6
Q2-series 4 MQXFB04 (CERN) | bar: 2020 4 to 2021 0
Q2-series 5 MQXFB05 (CERN) | bar: 2020 8 to 2022 2
Q2-series 6 MQXFB06 (CERN) | bar: 2020 2 to 2022 6
Q2-series 7 MQXFB07 (CERN) | bar: 2021 4 to 2022 0
Q2-series 8 MQXFB08 (CERN) | bar: 2021 8 to 2023 2
Q2-spare 1 MQXFB09 (CERN) | bar: 2021 2 to 2023 6
Q2-spare 2 MQXFB10 (CERN) | bar: 2022 4 to 2023 0
1
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| Q2 at CERN with external contract | Q2-proto 1 MQXFBP1 (CERN) | bar: 2016 4 to 2019 6; 2019 1 to 2020 7
Q2-proto 2 MQXFBP2 (CERN) | bar: 2018 5 to 2020 3
Q2-series 1 MQXFB01 (CERN) | bar: 2019 4 to 2020 0
Q2-series 2 MQXFB02 (CERN) | bar: 2019 8 to 2021 2
Q2-series 3 MQXFB03 (CERN) | bar: 2019 2 to 2021 6
Q2-series 4 MQXFB04 (CERN) | bar: 2020 4 to 2021 0
Q2-series 5 MQXFB05 (CERN) | bar: 2019 2; 2020 8 to 2022 5
Q2-series 6 MQXFB06 (CERN) | bar: 2021 4 to 2022 0
Q2-series 7 MQXFB07 (CERN) | bar: 2021 8 to 2023 2
Q2-series 8 MQXFB08 (CERN) | bar: 2021 2 to 2023 6
Q2-spare 1 MQXFB09 (CERN) | bar: 2022 4 to 2023 0
Q2-spare 2 MQXFB10 (CERN) | bar: 2022 8 to 2024 2
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| Q2 industry | Q2-proto 1 MQXFBP1 (CERN) | bar: 2016 4 to 2019 6; 2019 1 to 2020 7
Q2-proto 2 MQXFBP2 (CERN) | bar: 2018 5 to 2020 3
Q2-series 1 MQXFB01 (CERN) | bar: 2019 4 to 2020 0
Q2-series 2 MQXFB02 (CERN) | bar: 2019 8 to 2021 2
Q2-series 3 MQXFB03 (CERN) | bar: 2019 2 to 2021 6
Q2-series 4 MQXFB04 | bar: 2018 9; 2019 1 to 2021 0
Q2-series 5 MQXFB05 | bar: 2020 6 to 2022 4
Q2-series 6 MQXFB06 | bar: 2021 1 to 2022 9
Q2-series 7 MQXFB07 | bar: 2021 6 to 2023 1
Q2-series 8 MQXFB08 | bar: 2021 1 to 2023 5
Q2-spare 1 MQXFB09 | bar: 2022 3 to 2023 9
Q2-spare 2 MQXFB10 | bar: 2022 7 to 2024 1

## schedule march 2018
WP3 schedule March 2018 |  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
MQXF SHORT |  | MQXFS1 (RRP LARP) | 2015 4: S; 2015 5: M; 2016 3: F; 2016 9: F; 2017 5: F
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0
Q1/3 |  | Q1/3 4.0 m proto 1 MQXFAP1 | bar: 2015 5 to 2017 2
|  | Q1/3 4.2 m proto 2 MQXFAP2 | 2018 5: B; 2018 2: B; 2020 1: F; 2020 5: C
Q1/3 4.2 m proto 3 MQXFA03 | bar: 2017 2 to 2019 8
|  | Q1/3-series MQXFA04 - LQXFA01 | 2019 0: B; 2020 0: F; 2021 2: C
Q1/3-series MQXFA05 | bar: 2019 2 to 2020 3
|  | Q1/3-series MQXFA06 - LQXFA02 | 2020 6: B; 2021 3: F; 2021 7: C
Q1/3-series MQXFA07 | bar: 2019 1 to 2020 8; 2020 1 to 2020 2
Q1/3-series MQXFA08 - LQXFA03 | bar: 2020 3 to 2020 1; 2021 1 to 2021 8
Q1/3-series MQXFA09 | bar: 2020 5 to 2021 1; 2021 3 to 2021 4
|  | Q1/3-series MQXFA10 - LQXFA04 | 2021 4: B; 2022 1: F; 2022 5: C
Q1/3-series MQXFA11 | bar: 2020 9 to 2021 7
Q1/3-series MQXFA12 - LQXFA05 | bar: 2020 1 to 2021 9; 2022 1 to 2022 6
Q1/3-series MQXFA13 | bar: 2021 1 to 2021 1
Q1/3-series MQXFA14 - LQXFA06 | bar: 2021 3 to 2022 1; 2022 7 to 2022 2
Q1/3-series MQXFA15 | bar: 2021 5 to 2022 3
Q1/3-series MQXFA16 - LQXFA07 | bar: 2021 7 to 2022 5; 2022 1 to 2023 4
Q1/3-series MQXFA17 | bar: 2021 9 to 2022 7
Q1/3-series MQXFA18 - LQXFA08 | bar: 2021 1 to 2022 9; 2023 3 to 2023 8
Q1/3-series MQXFA19 | bar: 2022 1 to 2022 1
Q1/3-series MQXFA20 - LQXFA09 | bar: 2022 3 to 2023 1; 2023 9 to 2024 2
Q1/3-series MQXFA21 | bar: 2022 5 to 2023 3
Q1/3-series MQXFA22 - LQXFA10 | bar: 2022 7 to 2023 5; 2024 3 to 2024 8
Q1/3-series MQXFA23 | bar: 2022 9 to 2023 8
Q2 cold mass | Q2 | Q2-proto 1 MQXFBP1 (CERN) | bar: 2016 4 to 2019 6; 2019 1 to 2020 7
Q2-proto 2 MQXFBP2 (CERN) | bar: 2018 5 to 2020 3
Q2-series 1 MQXFB01 (CERN) | bar: 2019 4 to 2020 0
Q2-series 2 MQXFB02 (CERN) | bar: 2019 8 to 2021 2
Q2-series 3 MQXFB03 (CERN) | bar: 2019 2 to 2021 6
Q2-series 4 MQXFB04 | bar: 2018 9; 2019 1 to 2021 0
Q2-series 5 MQXFB05 | bar: 2020 6 to 2022 4
Q2-series 6 MQXFB06 | bar: 2021 1 to 2022 9
Q2-series 7 MQXFB07 | bar: 2021 6 to 2023 1
Q2-series 8 MQXFB08 | bar: 2021 1 to 2023 5
Q2-spare 1 MQXFB09 | bar: 2022 3 to 2023 9
Q2-spare 2 MQXFB10 | bar: 2022 7 to 2024 1
| MCBXFB | MCBXFBP1 - proto 1 | bar: 2017 4; 2017 0 to 2018 8
MCBXFBP2 - proto 2 | bar: 2018 5 to 2018 2
MCBXFB01 - series 1 | bar: 2018 1; 2019 5 to 2019 2
MCBXFB02 - series 2 | bar: 2019 1 to 2020 3
MCBXFB03 - series 3 | bar: 2020 1 to 2020 5
MCBXFB04 - series 4 | bar: 2020 3 to 2020 7
MCBXFB05 - series 5 | bar: 2020 5 to 2020 9
MCBXFB06 - series 6 | bar: 2020 7 to 2020 1
MCBXFB07 - series 7 | bar: 2020 9 to 2021 1
MCBXFB08 - series 8 | bar: 2020 1 to 2021 3
MCBXFB09 - spare 1 | bar: 2021 1 to 2021 5
MCBXFB10 - spare 2 | bar: 2021 3 to 2021 7
MCBXFB11 - spare 3 | bar: 2021 5 to 2021 9
MCBXFB12 - spare 4 | bar: 2021 7 to 2021 1
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
Corrector package | MCBXFA | MCBXFAP1 - proto 1 | bar: 2018 1; 2019 1 to 2021 4
MCBXFA1 - series 1 | bar: 2020 3 to 2020 8; 2020 1 to 2021 7
MCBXFA2 - series 2 | bar: 2020 6 to 2020 0; 2021 2 to 2021 9
MCBXFA3 - series 3 | bar: 2020 8 to 2020 2; 2021 4 to 2021 1
MCBXFA4 - series 4 | bar: 2020 0 to 2021 2; 2021 6 to 2022 1
MCBXFA5 - spare 1 | bar: 2020 2 to 2021 4; 2021 8 to 2022 3
MCBXFA6 - spare 2 | bar: 2021 2 to 2021 6
| HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 6 to 2018 0
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 6
MgB2 corrector - proto | bar: 2017 0 to 2018 6
N&S Sextupole - series (8+4) | bar: 2019 1; 2019 9 to 2021 7
N&S Octupole - series (8+4) | bar: 2019 9 to 2021 7
N&S Decapole - series (8+4) | bar: 2019 9 to 2021 7
N&S Dodecapole - series (8+4) | bar: 2019 9 to 2021 7
Skew quadrupole - series (4+2) | bar: 2019 9 to 2021 7
D1 |  | MBXFS1 - short model 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
MBXFS2 - short model 2 | bar: 2017 1 to 2018 7; 2018 9
MBXFS3 - short model 3 | bar: 2018 6 to 2019 2
|  | MBXFP1 - prototype | 2019 4: T; 2020 2: K; 2020 2: C
MBXF1 - series 1 | bar: 2020 4 to 2021 3; 2021 6 to 2021 0
MBXF2 - series 1 | bar: 2021 1 to 2021 9; 2021 2 to 2022 4
MBXF3 - series 1 | bar: 2021 6 to 2022 3; 2022 6 to 2022 0
MBXF4 - series 1 | bar: 2021 2 to 2022 9; 2022 2 to 2023 4
MBXF5 - spare 1 | bar: 2022 6 to 2023 2; 2023 5 to 2023 9
MBXF6 - spare 2 | bar: 2022 2 to 2023 9; 2023 2 to 2024 4
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
D2 cold mass | D2 | MBRDS1 - short model | bar: 2016 9; 2017 2 to 2018 0
MBRDP1 - prototype | bar: 2018 0; 2019 1 to 2020 0
MBRD1 - series 1 | bar: 2020 3; 2020 1 to 2022 2
MBRD2 - series 1 | bar: 2021 4 to 2022 7
MBRD3 - series 1 | bar: 2021 7 to 2022 0
MBRD4 - series 1 | bar: 2021 0 to 2023 1
MBRD5 - spare 1 | bar: 2022 1 to 2023 4
MBRD6 - spare 2 | bar: 2022 4 to 2023 7
| D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDS2 - short model double aperture | bar: 2017 9 to 2018 1
MCBRDP1 - prototype | bar: 2018 1 to 2018 5
MCBRD01 - series 1 | bar: 2018 2; 2019 7 to 2019 0
MCBRD02 - series 1 | bar: 2019 0 to 2019 2
MCBRD03 - series 1 | bar: 2019 2 to 2020 2
MCBRD04 - series 1 | bar: 2020 2 to 2020 4
MCBRD05 - series 1 | bar: 2020 4 to 2020 6
MCBRD06 - series 1 | bar: 2020 6 to 2020 8
MCBRD07 - series 1 | bar: 2020 8 to 2020 0
MCBRD08 - series 1 | bar: 2020 0 to 2020 2
MCBRD09 - spare 1 | bar: 2020 2 to 2021 2
MCBRD10 - spare 2 | bar: 2021 2 to 2021 4
MCBRD11 - spare 3 | bar: 2021 4 to 2021 6
MCBRD12 - spare 4 | bar: 2021 6 to 2021 8
MQYY |  | Q4 - short model | bar: 2016 9 to 2018 9
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 4
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 4
|  |  | Magnet construction | [30 empty] | M |  | Mirror or single coil test | [24 empty] | C | Test at CERN
|  |  | Vertical test | [30 empty] | S |  | Slice (mechanical model) | [24 empty] | B | Test at BNL
|  |  | Cold mass assembly | [30 empty] | T |  | Contract signed (ext. Contr.) | [24 empty] | F | Test at FNAL
|  |  | Cryostating | [30 empty] | F |  | Finance committee | [24 empty] | S | Test at Saclay
|  |  | Horizontal test | [57 empty] | L | Test at LASA
[61 empty] | K | Test at KEK
[61 empty] | N | Test at FREIA
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
| Q4 | Q4 - series 1 | bar: 2019 1 to 2019 8
Q4 - series 2 | bar: 2020 3 to 2020 0
Q4 - series 3 | bar: 2020 5 to 2020 2
Q4 - series 4 | bar: 2020 7 to 2021 2
| Q5 | Q5 - series 1 | bar: 2024 0 to 2025 1
Q5 - series 2 | bar: 2024 2 to 2025 3
Q5 - series 3 | bar: 2025 2 to 2025 5
Q5 - series 4 | bar: 2025 4 to 2025 7
| MS Q10 | Q10 - series 1 | bar: 2019 1 to 2019 8
Q10 - series 2 | bar: 2019 5 to 2019 2
Q10 - series 3 | bar: 2019 9 to 2020 4
Q10 - series 4 | bar: 2020 1 to 2020 8
| IR6 Q5 | IR6 Q5 - series 1 | bar: 2025 7 to 2025 0
IR6 Q5 - series 2 | bar: 2025 9 to 2025 2
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| Q2 at CERN | Q2-proto 1 MQXFBP1 (CERN) | bar: 2016 4 to 2019 6; 2019 1 to 2020 7
Q2-proto 2 MQXFBP2 (CERN) | bar: 2018 5 to 2020 3
Q2-series 1 MQXFB01 (CERN) | bar: 2019 4 to 2020 0
Q2-series 2 MQXFB02 (CERN) | bar: 2019 8 to 2021 2
Q2-series 3 MQXFB03 (CERN) | bar: 2019 2 to 2021 6
Q2-series 4 MQXFB04 (CERN) | bar: 2020 4 to 2021 0
Q2-series 5 MQXFB05 (CERN) | bar: 2020 8 to 2022 2
Q2-series 6 MQXFB06 (CERN) | bar: 2020 2 to 2022 6
Q2-series 7 MQXFB07 (CERN) | bar: 2021 4 to 2022 0
Q2-series 8 MQXFB08 (CERN) | bar: 2021 8 to 2023 2
Q2-spare 1 MQXFB09 (CERN) | bar: 2021 2 to 2023 6
Q2-spare 2 MQXFB10 (CERN) | bar: 2022 4 to 2023 0
1
|  |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| Q2 | Q2-proto 1 MQXFBP1 (CERN) | bar: 2016 4 to 2019 6; 2019 1 to 2020 7
Q2-proto 2 MQXFBP2 (CERN) | bar: 2018 5 to 2020 3
Q2-series 1 MQXFB01 (CERN) | bar: 2019 4 to 2020 0
Q2-series 2 MQXFB02 (CERN) | bar: 2019 8 to 2021 2
Q2-series 3 MQXFB03 (CERN) | bar: 2019 2 to 2021 6
Q2-series 4 MQXFB04 | bar: 2018 9; 2019 1 to 2021 0
Q2-series 5 MQXFB05 | bar: 2020 6 to 2022 4
Q2-series 6 MQXFB06 | bar: 2021 1 to 2022 9
Q2-series 7 MQXFB07 | bar: 2021 6 to 2023 1
Q2-series 8 MQXFB08 | bar: 2021 1 to 2023 5
Q2-spare 1 MQXFB09 | bar: 2022 3 to 2023 9
Q2-spare 2 MQXFB10 | bar: 2022 7 to 2024 1

## schedule 2017
WP3 schedule September 2017 |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
QXF SHORT | MQXFS1 (RRP LARP) | 2015 1: §; 2015 4: S; 2015 5: M
MQXFS3 (RRP CERN) | bar: 2015 1 to 2016 1; 2017 3 to 2017 9; 2017 1 to 2018 1
MQXFS5 (PIT CERN) | bar: 2016 0 to 2017 7; 2017 1
MQXFS4 (RRP CERN) | bar: 2017 3 to 2018 5
MQXFS6 (PIT CERN) | bar: 2016 1 to 2017 4; 2018 2 to 2018 0
Q1/3 | Q1/3 4 m proto 1 | bar: 2015 5 to 2017 8
Q1/3 4.2 m proto 2 | bar: 2016 7 to 2018 2
Q1/3 4.2 m proto 3 | bar: 2017 5 to 2020 4
Q1/3-series 1 | bar: 2018 2 to 2021 3
Q1/3-series 2 | bar: 2019 2 to 2021 2
Q1/3-series 3 | bar: 2020 6 to 2022 5
Q1/3-series 4 | bar: 2020 9 to 2022 8
Q1/3-series 5 | bar: 2021 6 to 2023 4
Q1/3-series 6 | bar: 2021 9 to 2023 7
Q1/3-series 7 | bar: 2022 4 to 2024 1
Q1/3-series 8 | bar: 2022 6 to 2024 5
Q1/3-spare 1 | bar: 2022 9 to 2024 7
Q1/3-spare 2 | bar: 2022 1 to 2024 0
Q2 | Q2-proto 1 MQXFBP1 (CERN) | bar: 2016 4 to 2019 2
Q2-proto 2 MQXFBP2 (CERN) | bar: 2017 0 to 2019 8
Q2-series 1 MQXFB01 (CERN) | bar: 2018 7 to 2020 2
Q2-series 2 MQXFB02 (CERN) | bar: 2019 2 to 2020 7
Q2-series 3 MQXFB03 (CERN) | bar: 2019 9 to 2021 2
Q2-series 4 MQXFB04 (CERN) | bar: 2020 3 to 2021 8
Q2-series 5 MQXFB05 | bar: 2018 5; 2019 2 to 2021 6; 2022 4
Q2-series 6 MQXFB06 | bar: 2020 6 to 2021 2
Q2-series 7 MQXFB07 | bar: 2020 0 to 2022 4
Q2-series 8 MQXFB08 | bar: 2021 2 to 2022 8
Q2-spare 1 MQXFB09 | bar: 2021 6 to 2022 2
Q2-spare 2 MQXFB10 | bar: 2021 0 to 2023 4
MCBXFB | MCBXFBP1 - proto 1 | bar: 2017 4; 2017 7 to 2018 5
MCBXFBP2 - proto 2 | bar: 2018 5 to 2018 2
MCBXFB01 - series 1 | bar: 2018 1; 2019 5 to 2019 2
MCBXFB02 - series 2 | bar: 2019 1 to 2020 3
MCBXFB03 - series 3 | bar: 2020 1 to 2020 5
MCBXFB04 - series 4 | bar: 2020 3 to 2020 7
MCBXFB05 - series 5 | bar: 2020 5 to 2020 9
MCBXFB06 - series 6 | bar: 2020 6 to 2020 0
MCBXFB07 - series 7 | bar: 2020 8 to 2020 2
MCBXFB08 - series 8 | bar: 2020 0 to 2021 2
MCBXFB09 - spare 1 | bar: 2020 2 to 2021 4
MCBXFB10 - spare 2 | bar: 2021 2 to 2021 6
MCBXFB11 - spare 3 | bar: 2021 4 to 2021 8
MCBXFB12 - spare 4 | bar: 2021 6 to 2021 0
|  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
MCBXFA | MCBXFAP1 - proto 1 | bar: 2019 1 to 2021 4
MCBXFA1 - series 1 | bar: 2018 1; 2020 3 to 2021 4
MCBXFA2 - series 2 | bar: 2020 6 to 2021 6
MCBXFA3 - series 3 | bar: 2020 8 to 2021 7
MCBXFA4 - series 4 | bar: 2020 0 to 2021 9
MCBXFA5 - spare 1 | bar: 2020 2 to 2021 2
MCBXFA6 - spare 2 | bar: 2021 2 to 2021 6
HO correctors | Sextupole - proto MCSXFP1 | bar: 2015 3 to 2016 2
Octupole - proto MCOXFP1 | bar: 2016 7 to 2017 3
Decapole - proto MCDXFP1 | bar: 2017 3 to 2017 6
Skew quadrupole - proto MCQSXFP1 | bar: 2017 9; 2018 6 to 2018 0
Dodecapole - proto MCTXFP1 | bar: 2018 3 to 2018 6
MgB2 corrector - proto | bar: 2017 0 to 2018 6
N&S Sextupole - series (8+4) | bar: 2019 1; 2019 9 to 2021 7
N&S Octupole - series (8+4) | bar: 2019 9 to 2021 7
N&S Decapole - series (8+4) | bar: 2019 9 to 2021 7
N&S Dodecapole - series (8+4) | bar: 2019 9 to 2021 7
Skew quadrupole - series (4+2) | bar: 2019 9 to 2021 7
D1 | MBXFS1 - short model 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
MBXFS2 - short model 2 | bar: 2017 2 to 2018 6
MBXFS3 - short model3 | bar: 2018 7 to 2019 1
MBXFP1 - prototype | bar: 2018 8; 2019 7 to 2021 2
MBXF1 - series 1 | bar: 2021 7 to 2023 1
MBXF2 - series 1 | bar: 2021 2 to 2023 4
MBXF3 - series 1 | bar: 2022 5 to 2023 7
MBXF4 - series 1 | bar: 2022 8 to 2023 0
MBXF5 - spare 1 | bar: 2022 0 to 2023 2
MBXF6 - spare 2 | bar: 2022 2 to 2024 2
|  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
D2 | MBRDS1 - short model | bar: 2016 9; 2017 6 to 2018 6
MBRDP1 - prototype | bar: 2018 4; 2018 8 to 2020 4
MBRD1 - series 1 | bar: 2019 6; 2019 0; 2020 8 to 2021 1
MBRD2 - series 1 | bar: 2021 1 to 2022 4
MBRD3 - series 1 | bar: 2021 4 to 2022 7
MBRD4 - series 1 | bar: 2021 7 to 2022 0
MBRD5 - spare 1 | bar: 2021 9 to 2022 2
MBRD6 - spare 2 | bar: 2021 2 to 2023 3
D2 correctors | MCBRDS1 - short model | bar: 2017 2 to 2017 6
MCBRDP1 - prototype | bar: 2017 8 to 2018 2
MCBRD01 - series 1 | bar: 2018 5; 2019 1 to 2019 4
MCBRD02 - series 1 | bar: 2019 4 to 2019 6
MCBRD03 - series 1 | bar: 2019 6 to 2019 8
MCBRD04 - series 1 | bar: 2019 8 to 2019 0
MCBRD05 - series 1 | bar: 2019 0 to 2019 2
MCBRD06 - series 1 | bar: 2019 2 to 2020 2
MCBRD07 - series 1 | bar: 2020 2 to 2020 4
MCBRD08 - series 1 | bar: 2020 4 to 2020 6
MCBRD09 - spare 1 | bar: 2020 6 to 2020 8
MCBRD10 - spare 2 | bar: 2020 8 to 2020 0
MCBRD11 - spare 3 | bar: 2020 0 to 2020 2
MCBRD12 - spare 4 | bar: 2020 2 to 2021 2
(MQYY) | Q4 - short model | bar: 2016 9 to 2018 9
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 4
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 4
|  | Magnet construction | [30 empty] | M |  | Mirror or single coil test
|  | Vertical test | [30 empty] | S |  | Slice (mechanical model)
|  | Cold mass assembly | [30 empty] | C |  | Contract signed
|  | Cryostating | [30 empty] | FC |  | Finance committee
Horizontal test
|  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
Q4 | Q4 - series 1 | bar: 2018 1 to 2018 8
Q4 - series 2 | bar: 2019 3 to 2019 0
Q4 - series 3 | bar: 2019 5 to 2019 2
Q4 - series 4 | bar: 2019 7 to 2020 2
Q5 | Q5 - series 1 | bar: 2024 0 to 2025 1
Q5 - series 2 | bar: 2024 2 to 2025 3
Q5 - series 3 | bar: 2025 2 to 2025 5
Q5 - series 4 | bar: 2025 4 to 2025 7
MS Q10 | Q10 - series 1 | bar: 2018 1 to 2018 8
Q10 - series 2 | bar: 2018 5 to 2018 2
Q10 - series 3 | bar: 2018 9 to 2019 4
Q10 - series 4 | bar: 2019 1 to 2019 8
IR6 Q5 | IR6 Q5 - series 1 | bar: 2025 7 to 2025 0
IR6 Q5 - series 2 | bar: 2025 9 to 2025 2
MBW | MBW - coil set 1 | bar: 2018 1 to 2019 1
MBW -coil set 2 | bar: 2019 2 to 2019 4
MBW -coil set 3 | bar: 2019 5 to 2019 7
MBW -coil set 4 | bar: 2019 8 to 2019 0
MQW | MQW - series 1 | bar: 2019 1 to 2020 1
MQW - series 2 | bar: 2020 2 to 2020 4
MQW - series 3 | bar: 2020 5 to 2020 7
MQW - series 4 | bar: 2020 8 to 2020 0
MQW - spare 1 | bar: 2020 1 to 2021 1
|  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
Q2 in industry | Q2-proto 1 | bar: 2016 4 to 2019 2
Q2-proto 2 | bar: 2017 0 to 2019 8
Q2 - proto industry | bar: 2017 6; 2017 9; 2018 8 to 2019 2
Q2-series 1 | bar: 2020 4 to 2021 0
Q2-series 2 | bar: 2020 8 to 2022 1
Q2-series 3 | bar: 2020 2 to 2022 3
Q2-series 4 | bar: 2021 4 to 2022 0
Q2-series 5 | bar: 2021 8 to 2023 1
Q2-series 6 | bar: 2021 2 to 2023 5
Q2-series 7 | bar: 2022 4 to 2023 9
Q2-series 8 | bar: 2022 8 to 2024 1
Q2-spare 1 | bar: 2018 0 to 2020 5
Q2-spare 2 | bar: 2019 4 to 2020 0
Q2 at CERN | Q2-proto 1 | bar: 2016 4 to 2019 2
Q2-proto 2 | bar: 2017 2 to 2019 8
Q2-series 1 | bar: 2018 0 to 2020 5
Q2-series 2 | bar: 2019 5 to 2021 1
Q2-series 3 | bar: 2019 1 to 2021 6
Q2-series 4 | bar: 2020 5 to 2021 1
Q2-series 5 | bar: 2020 0 to 2022 3
Q2-series 6 | bar: 2021 2 to 2022 7
Q2-series 7 | bar: 2021 5 to 2023 1
Q2-series 8 | bar: 2021 0 to 2023 3
Q2-spare 1 | bar: 2022 2 to 2023 7
Q2-spare 2 | bar: 2022 5 to 2023 1

## schedule 2016
WP3 schedule September 2016 |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
QXF SHORT | MQXFS-1 (RRP LARP) | bar: 2015 1 to 2017 2
MQXFS-2 (RRP CERN) | bar: 2015 1 to 2017 9
MQXFS-3 (RRP CERN) | bar: 2015 2 to 2016 1
MQXFS-4 (RRP LARP) | bar: 2016 3 to 2018 2
MQXFS-5 (PIT CERN) | bar: 2016 2 to 2017 4
Q1/3 | Q1/3 4 m proto 1 | bar: 2015 5 to 2017 8
Q1/3 4.2 m proto 2 | bar: 2016 7 to 2018 2
Q1/3 4.2 m proto 3 | bar: 2017 5 to 2020 4
Q1/3-series 1 | bar: 2018 2 to 2021 3
Q1/3-series 2 | bar: 2019 2 to 2021 2
Q1/3-series 3 | bar: 2020 6 to 2022 5
Q1/3-series 4 | bar: 2020 9 to 2022 8
Q1/3-series 5 | bar: 2021 6 to 2023 4
Q1/3-series 6 | bar: 2021 9 to 2023 7
Q1/3-series 7 | bar: 2022 4 to 2024 1
Q1/3-series 8 | bar: 2022 6 to 2024 5
Q1/3-spare 1 | bar: 2022 9 to 2024 7
Q1/3-spare 2 | bar: 2022 1 to 2024 0
Q2 | Q2-proto 1 | bar: 2016 4 to 2019 2
Q2-proto 2 | bar: 2017 2 to 2019 8
Q2-series 1 | bar: 2018 0 to 2020 5
Q2-series 2 | bar: 2019 5 to 2021 1
Q2-series 3 | bar: 2019 1 to 2021 6
Q2-series 4 | bar: 2020 5 to 2021 1
Q2-series 5 | bar: 2020 0 to 2022 3
Q2-series 6 | bar: 2021 2 to 2022 7
Q2-series 7 | bar: 2021 5 to 2023 1
Q2-series 8 | bar: 2021 0 to 2023 3
Q2-spare 1 | bar: 2022 2 to 2023 7
Q2-spare 2 | bar: 2022 5 to 2023 1
MCBXFB | MCBXFB - proto | bar: 2016 6; 2016 0 to 2017 2
MCBXFB - series 1 | bar: 2018 3; 2018 0 to 2019 5
MCBXFB - series 2 | bar: 2019 2 to 2019 7
MCBXFB - series 3 | bar: 2019 5 to 2019 9
MCBXFB - series 4 | bar: 2019 7 to 2019 1
MCBXFB - series 5 | bar: 2019 0 to 2020 2
MCBXFB - series 6 | bar: 2019 2 to 2020 4
MCBXFB - series 7 | bar: 2020 2 to 2020 6
MCBXFB - series 8 | bar: 2020 4 to 2020 8
MCBXFB - spare 1 | bar: 2020 6 to 2020 0
MCBXFB - spare 2 | bar: 2020 8 to 2020 2
MCBXFB - spare 3 | bar: 2020 0 to 2021 2
MCBXFB - spare 4 | bar: 2020 2 to 2021 4
|  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
MCBXFA | MCBXFA - prototype | bar: 2019 1 to 2020 7
MCBXFA - series 1 | bar: 2018 3; 2019 0 to 2020 1
MCBXFA - series 2 | bar: 2020 1 to 2021 1
MCBXFA - series 3 | bar: 2020 3 to 2021 3
MCBXFA - series 4 | bar: 2020 5 to 2021 5
MCBXFA - spare 1 | bar: 2020 7 to 2021 7
MCBXFA - spare 2 | bar: 2020 9 to 2021 1
HO correctors | Sextupole - proto | bar: 2015 3 to 2016 2
Octupole - proto | bar: 2016 4 to 2016 2
Decapole - proto | bar: 2016 7 to 2017 1
Skew quadrupole - proto | bar: 2017 1 to 2017 7
Dodecapole - proto | bar: 2017 7 to 2017 2
N&S Sextupole - series (8+4) | bar: 2018 0; 2019 4 to 2020 1
N&S Octupole - series (8+4) | bar: 2019 4 to 2020 1
N&S Decapole - series (8+4) | bar: 2019 4 to 2020 1
N&S Dodecapole - series (8+4) | bar: 2019 4 to 2020 1
Skew quadrupole - series (4+2) | bar: 2019 4 to 2020 1
D1 | D1 - short model 1 | bar: 2015 1 to 2016 3; 2016 5; 2016 8 to 2017 1
D1 - short model 2 | bar: 2017 1 to 2017 0
D1-prototype | bar: 2018 8; 2019 7 to 2021 2
D1-series 1 | bar: 2021 7 to 2023 1
D1-series 2 | bar: 2021 2 to 2023 4
D1-series 3 | bar: 2022 5 to 2023 7
D1-series 4 | bar: 2022 8 to 2023 0
D1-spare 1 | bar: 2022 0 to 2023 2
D1-spare 2 | bar: 2022 2 to 2024 2
|  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
D2 | D2-short model | bar: 2016 9; 2017 1 to 2018 2
D2-prototype | bar: 2018 4; 2018 8 to 2020 4
D2-series 1 | bar: 2019 6; 2019 0; 2020 8 to 2021 1
D2-series 2 | bar: 2021 1 to 2022 4
D2-series 3 | bar: 2021 4 to 2022 7
D2-series 4 | bar: 2021 7 to 2022 0
D2-spare 1 | bar: 2021 9 to 2022 2
D2-spare 2 | bar: 2021 2 to 2023 3
D2 correctors | CCT single ap. 1 m long | bar: 2016 3 to 2016 2
D2 orbit - proto | bar: 2017 1 to 2017 9
D2 orbit-series 1 | bar: 2018 5; 2019 1 to 2019 4
D2 orbit-series 2 | bar: 2019 4 to 2019 6
D2 orbit-series 3 | bar: 2019 6 to 2019 8
D2 orbit-series 4 | bar: 2019 8 to 2019 0
D2 orbit-series 5 | bar: 2019 0 to 2019 2
D2 orbit-series 6 | bar: 2019 2 to 2020 2
D2 orbit-series 7 | bar: 2020 2 to 2020 4
D2 orbit-series 8 | bar: 2020 4 to 2020 6
D2 orbit-spare 1 | bar: 2020 6 to 2020 8
D2 orbit-spare 2 | bar: 2020 8 to 2020 0
D2 orbit-spare 3 | bar: 2020 0 to 2020 2
D2 orbit-spare 4 | bar: 2020 2 to 2021 2
(MQYY) | Q4 - short model | bar: 2016 9 to 2017 9
Q4-prototype 1 (QUACO) | bar: 2016 0; 2018 1 to 2020 4
Q4-prototype 2 (QUACO) | bar: 2018 1 to 2020 4
|  | Magnet construction | [30 empty] | M |  | Mirror or single coil test
|  | Vertical test | [30 empty] | S |  | Slice (mechanical model)
|  | Cold mass assembly | [30 empty] | C |  | Contract signed
|  | Cryostating | [30 empty] | FC |  | Finance committee
Horizontal test
|  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
Q4 | Q4 - series 1 | bar: 2018 1 to 2018 8
Q4 - series 2 | bar: 2019 3 to 2019 0
Q4 - series 3 | bar: 2019 5 to 2019 2
Q4 - series 4 | bar: 2019 7 to 2020 2
Q5 | Q5 - series 1 | bar: 2024 0 to 2025 1
Q5 - series 2 | bar: 2024 2 to 2025 3
Q5 - series 3 | bar: 2025 2 to 2025 5
Q5 - series 4 | bar: 2025 4 to 2025 7
MS Q10 | Q10 - series 1 | bar: 2018 1 to 2018 8
Q10 - series 2 | bar: 2018 5 to 2018 2
Q10 - series 3 | bar: 2018 9 to 2019 4
Q10 - series 4 | bar: 2019 1 to 2019 8
IR6 Q5 | IR6 Q5 - series 1 | bar: 2025 7 to 2025 0
IR6 Q5 - series 2 | bar: 2025 9 to 2025 2
MBW | MBW - series 1 | bar: 2018 1 to 2019 1
MBW -series 2 | bar: 2019 2 to 2019 4
MBW -series 3 | bar: 2019 5 to 2019 7
MBW -series 4 | bar: 2019 8 to 2019 0
MBW - spare 1 | bar: 2019 1 to 2020 1
MBW - spare 2 | bar: 2020 2 to 2020 4
MBW - spare 3 | bar: 2020 5 to 2020 7
MBW - spare 4 | bar: 2020 8 to 2020 0
MQW | MQW - series 1 | bar: 2019 1 to 2020 1
MQW - series 2 | bar: 2020 2 to 2020 4
MQW - series 3 | bar: 2020 5 to 2020 7
MQW - series 4 | bar: 2020 8 to 2020 0
MQW - spare 1 | bar: 2020 1 to 2021 1
MQW - spare 2 | bar: 2021 2 to 2021 4
MQW - spare 3 | bar: 2021 5 to 2021 7
MQW - spare 4 | bar: 2021 8 to 2021 0
|  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
Q2 in industry | Q2-proto 1 | bar: 2016 4 to 2019 2
Q2-proto 2 | bar: 2017 0 to 2019 8
Q2 - proto industry | bar: 2017 6; 2017 9; 2018 8 to 2019 2
Q2-series 1 | bar: 2020 4 to 2021 0
Q2-series 2 | bar: 2020 8 to 2022 1
Q2-series 3 | bar: 2020 2 to 2022 3
Q2-series 4 | bar: 2021 4 to 2022 0
Q2-series 5 | bar: 2021 8 to 2023 1
Q2-series 6 | bar: 2021 2 to 2023 5
Q2-series 7 | bar: 2022 4 to 2023 9
Q2-series 8 | bar: 2022 8 to 2024 1
Q2-spare 1 | bar: 2018 0 to 2020 5
Q2-spare 2 | bar: 2019 4 to 2020 0
Q2 at CERN | Q2-proto 1 | bar: 2016 4 to 2019 2
Q2-proto 2 | bar: 2017 2 to 2019 8
Q2-series 1 | bar: 2018 0 to 2020 5
Q2-series 2 | bar: 2019 5 to 2021 1
Q2-series 3 | bar: 2019 1 to 2021 6
Q2-series 4 | bar: 2020 5 to 2021 1
Q2-series 5 | bar: 2020 0 to 2022 3
Q2-series 6 | bar: 2021 2 to 2022 7
Q2-series 7 | bar: 2021 5 to 2023 1
Q2-series 8 | bar: 2021 0 to 2023 3
Q2-spare 1 | bar: 2022 2 to 2023 7
Q2-spare 2 | bar: 2022 5 to 2023 1

## schedule 2015
WP3 schedule March 2015 |  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2
QXF SHORT | MQXFS-1 (RRP LARP) | bar: 2015 1 to 2015 1
MQXFS-2 (RRP LARP) | bar: 2015 1 to 2016 0
MQXFS-3 (RRP CERN) | bar: 2015 1 to 2016 7
MQXFS-4 (RRP LARP) | bar: 2015 0 to 2017 3
MQXFS-5 (PIT CERN) | bar: 2015 0 to 2017 3
Q1/3 | Q1/3 half proto 1 | bar: 2015 5 to 2017 2
Q1/3 half proto 2 | bar: 2016 6 to 2017 2
Q1/3 half proto 3 | bar: 2017 4 to 2018 6
Q1/3-series 1 | bar: 2018 1 to 2021 1
Q1/3-series 2 | bar: 2019 3 to 2021 5
Q1/3-series 3 | bar: 2019 8 to 2021 9
Q1/3-series 4 | bar: 2020 1 to 2022 1
Q1/3-series 5 | bar: 2020 5 to 2022 5
Q1/3-series 6 | bar: 2020 9 to 2022 9
Q1/3-series 7 | bar: 2021 1 to 2023 1
Q1/3-series 8 | bar: 2021 5 to 2023 5
Q1/3-spare 1 | bar: 2021 9 to 2023 9
Q1/3-spare 2 | bar: 2022 1 to 2023 2
Q2 | Q2-proto 1 | bar: 2015 1 to 2018 6
Q2-proto 2 | bar: 2017 6 to 2018 2
Q2-series 1 | bar: 2018 7 to 2020 3
Q2-series 2 | bar: 2019 2 to 2020 7
Q2-series 3 | bar: 2019 6 to 2020 1
Q2-series 4 | bar: 2019 0 to 2021 3
Q2-series 5 | bar: 2020 1 to 2021 6
Q2-series 6 | bar: 2020 4 to 2021 9
Q2-series 7 | bar: 2020 7 to 2021 2
Q2-series 8 | bar: 2020 0 to 2022 3
Q2-spare 1 | bar: 2021 2 to 2022 7
Q2-spare 2 | bar: 2021 6 to 2022 1
|  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
MCBXFB | MCBXFB - proto | bar: 2015 1 to 2016 2
MCBXFB - series 1 | bar: 2019 1 to 2019 6
MCBXFB - series 2 | bar: 2019 4 to 2019 9
MCBXFB - series 3 | bar: 2019 7 to 2019 2
MCBXFB - series 4 | bar: 2019 0 to 2020 3
MCBXFB - series 5 | bar: 2019 2 to 2020 5
MCBXFB - series 6 | bar: 2020 3 to 2020 8
MCBXFB - series 7 | bar: 2020 6 to 2020 1
MCBXFB - series 8 | bar: 2020 8 to 2021 1
MCBXFB - spare 1 | bar: 2020 1 to 2021 4
MCBXFB - spare 2 | bar: 2021 2 to 2021 7
MCBXFA | MCBXFA - series 1 | bar: 2018 1 to 2019 2
MCBXFA - series 2 | bar: 2018 4 to 2019 5
MCBXFA - series 3 | bar: 2018 6 to 2019 7
MCBXFA - series 4 | bar: 2018 9 to 2019 0
MCBXFA - spare 1 | bar: 2018 1 to 2019 2
MCBXFA - spare 2 | bar: 2019 2 to 2020 3
HO correctors | HO corrector - series 1 | bar: 2018 1 to 2018 8
HO corrector - series 2 | bar: 2018 3 to 2018 0
HO corrector - series 3 | bar: 2018 5 to 2018 2
HO corrector - series 4 | bar: 2018 7 to 2019 2
HO corrector - spare 1 | bar: 2018 0 to 2019 4
HO corrector - spare 2 | bar: 2018 2 to 2019 6
D1 | D1 - short model 1 | bar: 2015 1 to 2015 1
D1 - short model 2 | bar: 2015 1 to 2016 5
D1-prototype | bar: 2018 4 to 2019 0
D1-series 1 | bar: 2019 1 to 2021 2
D1-series 2 | bar: 2020 2 to 2021 4
D1-series 3 | bar: 2020 5 to 2021 7
D1-series 4 | bar: 2020 8 to 2021 0
D1-spare 1 | bar: 2020 0 to 2021 2
D1-spare 2 | bar: 2020 2 to 2022 2
|  | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
D2 | D2-short model | bar: 2016 1 to 2017 1
D2-prototype | bar: 2018 3 to 2019 8
D2-series 1 | bar: 2020 1 to 2021 4
D2-series 2 | bar: 2020 4 to 2021 7
D2-series 3 | bar: 2020 6 to 2021 9
D2-series 4 | bar: 2020 9 to 2021 2
D2-spare 1 | bar: 2020 1 to 2022 2
D2-spare 2 | bar: 2021 2 to 2022 5
D2 correctors | D2 - orbit - proto | bar: 2017 1 to 2017 2
D2 orbit-series 1 | bar: 2018 9 to 2019 3
D2 orbit-series 2 | bar: 2018 2 to 2019 5
D2 orbit-series 3 | bar: 2019 3 to 2019 7
D2 orbit-series 4 | bar: 2019 6 to 2019 0
D2 orbit-series 5 | bar: 2019 9 to 2020 1
D2 orbit-series 6 | bar: 2019 1 to 2020 3
D2 orbit-series 7 | bar: 2020 1 to 2020 5
D2 orbit-series 8 | bar: 2020 3 to 2020 7
D2 orbit-spare 1 | bar: 2020 5 to 2020 9
D2 orbit-spare 2 | bar: 2020 7 to 2020 1
Q4 | Q4 - short model | bar: 2015 0 to 2017 5
Q4-prototype | bar: 2018 2 to 2019 7
Q4-series 1 | bar: 2019 6 to 2020 8
Q4-series 2 | bar: 2019 0 to 2020 2
Q4-series 3 | bar: 2020 3 to 2021 5
Q4-series 4 | bar: 2020 7 to 2021 9
Q4-series spare 1 | bar: 2020 0 to 2021 2
Q4 correctors | Q4 orbit-series 1 | bar: 2018 9 to 2019 3
Q4 orbit-series 2 | bar: 2018 2 to 2019 5
Q4 orbit-series 3 | bar: 2019 3 to 2019 7
Q4 orbit-series 4 | bar: 2019 6 to 2019 0
Q4 orbit-series 5 | bar: 2019 9 to 2020 1
Q4 orbit-series 6 | bar: 2019 1 to 2020 3
Q4 orbit-series 7 | bar: 2020 1 to 2020 5
Q4 orbit-series 8 | bar: 2020 3 to 2020 7
Q4 orbit-spare 1 | bar: 2020 5 to 2020 9
Q4 orbit-spare 2 | bar: 2020 7 to 2020 1
Magnet construction
Vertical test
Cold mass assembly
Cryostating
Horizontal test